## Cumulative Totals
| Original Estimated Project Budget | Current Estimated Project Budget | FY 2016-17 Encumbered | Percent Encumbered | FY 2016-17 Expended | Percent Expended | Remaining Project Balance | Percent Remaining
SEPTEMBER, 2016 QUARTERLY REPORT
DPS 9/16 | 38778877 | 38778877 | 2162778.32 | 5.577% | 1793696.42 | 4.625% | 34822402.26 | 89.8%
TMD 9/16 | 19562500 | 19562500 | 8931737 | 45.66% | 943263 | 4.822% | 9687500 | 49.52%
TPWD 9/16 | 91000000 | 91000000 | 10624197 | 11.67% | 2370519 | 2.605% | 78005284 | 85.72%
TDCJ 9/16 | 56393901 | 58765393 | 32020908 | 54.49% | 14055123 | 23.92% | 12689362 | 21.59%
TFC 9/16 | 217156348 | 217156348 | 97731599 | 45.01% | 5413721 | 2.493% | 114011028 | 52.5%
TXDOT 9/16 | 200000000 | 62400000 | 18103047 | 29.01% | 2247514 | 3.602% | 42049439 | 67.39%
Totals | 622891626 | 487663118 | 169574266.32 | 34.77% | 26823836.42 | 5.5% | 291265015.26 | 59.73%
JUNE, 2016 QUARTERLY REPORT
DPS 6/16 | 38778877 | 38778877 | 903724.93 | 2.33% | 1793696.42 | 4.625% | 36081455 | 93.04%
TMD 6/16 | 19562500 | 19562500 | 6464547 | 33.05% | 108872 | 0.5565% | 12989081 | 66.4%
TPWD 6/16 | 91000000 | 91000000 | 7089127 | 7.79% | 1191692 | 1.31% | 82719181 | 90.9%
TDCJ 6/16 | 56393901 | 57638273 | 29712683 | 51.55% | 6544679 | 11.35% | 21380911 | 37.09%
TFC 6/16 | 217156348 | 217156348 | 17508535 | 8.063% | 2419828 | 1.114% | 197227985 | 90.82%
TXDOT 6/16 | 200000000 | 200000000 | 5139554 | 2.57% | 481243 | 0.2406% | 194379203 | 97.19%
Totals | 622891626 | 624135998 | 66818170.93 | 10.71% | 12540010.42 | 2.009% | 544777816 | 87.29%
MARCH, 2016 QUARTERLY REPORT
DPS 3/16 | 38778877 | 38778877 | 0 | 0% | 0 | 0% | 38778877 | 100%
TMD 3/16 | 19562500 | 19562500 | 644301 | 3.294% | 22694 | 0.116% | 18895505 | 96.59%
TPWD 3/16 | 91000000 | 91000000 | 5978999 | 6.57% | 371487 | 0.4082% | 84649514 | 93.02%
TDCJ 3/16 | 56393901 | 56685613 | 32900866 | 58.04% | 1985964 | 3.503% | 21798783 | 38.46%
TFC 3/16 | 217156348 | 217156348 | 12176876 | 5.607% | 511856 | 0.2357% | 204467616 | 94.16%
TXDOT 3/16 | 200000000 | 200000000 | 1535625 | 0.7678% | 98690 | 0.04934% | 198959830 | 99.48%
Totals | 622891626 | 623183338 | 53236667 | 8.543% | 2990691 | 0.4799% | 567550125 | 91.07%
DECEMBER, 2015 QUARTERLY REPORT
DPS 12/15 | 38778877 | 38778877 | 0 | 0% | 0 | 0% | 38778877 | 100%
TMD 12/15 | 19562500 | 19562500 | 711000 | 3.635% | 0 | 0% | 18851500 | 96.37%
TPWD 12/15 | 91000000 | 91000000 | 4057560 | 4.459% | 6187 | 0.006799% | 86936253 | 95.53%
TDCJ 12/15 | 56393901 | 57644001 | 20632937 | 35.79% | 423472 | 0.7346% | 36587592 | 63.47%
TFC 12/15 | 217156348 | 217156348 | 0 | 0% | 0 | 0% | 217156348 | 100%
TxDOT 12/15 | 200000000 | 200000000 | 313105 | 0.1566% | - |  | 200000000 | 100%
Totals | 622891626 | 624141726 | 25714602 | 4.12% | 429659 | 0.06884% | 598310570 | 95.86%
.

## DPS 9.16
| Agency: | [5 empty] | Texas Department of Public Safety - 0405
| Date: | [5 empty] | Updated 9-15-16
| Prepared by: | [5 empty] | Tavia Wendlandt
Project Priority | Agency ID | Agency ID with XXXXX | Agency ID - with out index | Index | Concatenate | Agency ID - Absolute | Project Name & Location | Project Description | Type - Original | Type - Adjusted | Source of Funding (MOF) | TFC/Facilities PM | Project Notes | Req # | PO # | Original Estimated Project Budget | Current Estimated Project Budget (for FY 16 1st Qtr.) | Current Estimated Project Budget (for FY 16 2nd Qtr.) | Current Estimated Project Budget (for FY 16 3rd Qtr.) | Current Estimated Project Budget (for FY 16 4th Qtr.) | Current Estimated Project Budget (for FY 17 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-2017 Committed | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | ST-TEMP-62601 | ST-TEMP-XXXXX | ST-TEMP- | 62601 | ST-TEMP-62601 | ST-TEMP-62601 | Statewide Temporary DM Staff | Temporary staff needed to administer DM projects. (estimate two years) | Rider 40 | Rider 40 | General Revenue (Fund 0001) |  |  |  |  | 215000 | 215000 | 215000 | 215000 | 215000 |  | Duration of projects |  |  |  |  | 9167.92 | 205832.08 | No
2 | 3-COR-17-62737 | 3-COR-16-XXXXX | 3-COR-16- | 62737 | 3-COR-16-62737 | 3-COR-16-62737 | Corpus Christi District Office (Reg 3) DM Multi-system project 1922 S. Padre Island Drive Corpus Christi, Texas 78416 | Complete ongoing DM projects (HVAC, Sanitary Sewer, Etc.) | 21M | Rider 40 | General Revenue (Fund 0001) | TFC | GMP I - 100%; GMP II 50%; GMP III NTP given 5/20/16; Bids 5/18/16; Hanger |  |  | 780000 | 780000 | 780000 | 780000 | 780000 |  | 24 months - Negotiating IAC with TFC. | [5 empty] | 780000 | No
3 | 6-ANW-17-62738 | 6-ANW-16-XXXXX | 6-ANW-16- | 62738 | 6-ANW-16-62738 | 6-ANW-16-62738 | Austin Northwest Area Office (Reg 6) Roof Replacement 13730 Research Boulevard Austin, Texas 78750 | Partial roof replacement (Built up portion only) | 21M | Rider 40 | General Revenue (Fund 0001) | TFC | 5-26-16 DD; Received cost estimate from CMR on 2-11-16. Reviewing budget with TFC and negociating IAC for construction portion. |  |  | 250000 | 250000 | 625000 | 625000 | 625000 |  | 12 months - Received cost estimate from CMR on 2-11-16. Reviewing budget with TFC and negociating IAC for construction portion. | 100% |  |  |  |  | 625000 | No
4 | 2-LUF-17-62603 | 2-LUF-17-XXXXX | 2-LUF-17- | 62603 | 2-LUF-17-62603 | 2-LUF-17-62603 | Lufkin Lease Refresh - Lufkin CID Lease (Reg 2) 2815 John Redditt Dr. Lufkin, Texas 75904 | Refurbishment and equipping of a certain leased facility in Lufkin for use by CID as per Rider 63. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker | ACM Surveying 6-2016; DD Issued 7/13/2016; 9-1-16 ACM gone to bid | 17-R077471 - Asbestos Abate ($12K) |  | 200000 | 200000 | 200000 | 200000 | 200000 |  | 2017-05-01 | 100% |  | 12000 |  |  | 200000 | No
5 | HQ-C-16-62905 | HQ-C-16-XXXXX | HQ-C-16- | 62905 | HQ-C-16-62905 | HQ-C-16-62905 | Austin HQ (Building C) Dormitory Renovations Floor 2&3 5805 North Lamar Blvd Austin, Texas 78752 | Dormitory floors 2 and 3 are vacant since 2009 due to fire marshal code violations. Renovations will bring these floors into current building code compliance to allow for additional recruit classes to be held. | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth | 5/2/16-Asbestos ($15K) 90% CD; HVAC bid was $382,042 over budget. | 16-R063150 CO16-R077873 to add$382,042 for HVAC; |  | 0 | 0 |  | 1300000 | 1300000 |  | 2017-01-01 | 100% | 10% | 1600000 | 289605.57 |  | 1010394.43 | No
6 | HQ-CAM-16-62906 | HQ-CAM-16-XXXXX | HQ-CAM-16- | 62906 | HQ-CAM-16-62906 | HQ-CAM-16-62906 | Austin HQ (Campus) Dual Power Feed 5805 North Lamar Blvd Austin, Texas 78752 | Upgrade existing single power source to the complex. Austin Energy will provide two separate power grids to provide redundant power back up for the crime lab, data centers and other critical DPS functions. | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | TFC - Jessica Warren | 6/2016 Study completed 12/2015; 7/16 - A/E design contract in progress; TFC fees $127,500 | 16-R071341; 17-R074183TFC IAC; |  | 0 | 0 |  | 2182097 | 2182097 |  | 18 months -TFC seeking A/E firm | 10% |  |  | 142500 |  | 2039597 | No
7 | HQ-A-16-62895 |  |  | 62895 | 62895 | HQ-A-16-62895 | Austin HQ (Building A) Data Center Upgrades 5805 North Lamar Blvd Austin, Texas 78752 | Replace existing HVAC, electrical, and fire suppression system, provide redundancy for HVAC/Electrical in the Data Center. | 21 M | Agency Savings | General Revenue (Fund 0001) | TFC - Jessica Warren | Backgrounds in progress. GC not given construction schedule yet. |  |  | 0 | 0 | 1750000 | 1750000 | 1750000 |  | 2017-02-01 | 100% | 25% |  |  | 1750000 | 0 | No
8 | 7-CAP-16-62322 |  |  | 62322 | 62322 | 7-CAP-16-62322 | Austin Capital Services (Reg 7) 1500 N. Congress Austin, Texas 78701 Generator Replacement | Replace existing ATS and package Generator unit at the Capital Services Building. (Additional funding needed according to TFC estimates) | 21 M | Agency Savings | General Revenue (Fund 0001) | TFC - Clay Bosworth |  |  |  | 0 | 0 |  | 150000 | 150000 |  | 2017-08-31 | 100% |  |  | 150000 |  | 0 | No
9 | 1-GAR-17-62606 | 1-GAR-16-XXXXX | 1-GAR-16- | 62606 | 1-GAR-16-62606 | 1-GAR-16-62606 | Garland Regional Headquarters (Reg 1) HVAC Replacement 350 West IH-30 Garland, Texas 75043 | Heating Ventilation Air Conditioning (HVAC) System replacement in the Annex Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | 6-2016 In design phase |  |  | 400000 | 400000 | 400000 | 400000 | 400000 |  | 2017-08-31 | 50% |  |  |  |  | 400000 | No
10 | 1-HUR-17-62607 | 1-HUR-16-XXXXX | 1-HUR-16- | 62607 | 1-HUR-16-62607 | 1-HUR-16-62607 | Hurst District Office (Reg 1) HVAC Replacement 624 NE Loop 820 Hurst, Texas 76053 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren / Steve Haney | 6-2016 In design phase |  |  | 302623 | 302623 | 302623 | 302623 | 302623 |  | 2017-12-31 | 50% |  |  |  |  | 302623 | No
11 | 5-WIC-17-62608 | 5-WIC-17-XXXXX | 5-WIC-17- | 62608 | 5-WIC-17-62608 | 5-WIC-17-62608 | Wichita Falls Sub-District Office (Reg 5) Roof Replacement 5505 N. Central Expressway Wichita Falls, Texas 79306 | Replace Roof - construction phase. (TFC is engineering roof replacement from Rider 45 DM funds) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Yen Nguyen | 17-R071368 submitted 7-2016 in ePro |  |  | 200000 | 200000 | 200000 | 200000 | 200000 |  | 2016-11-30 | 100% |  |  |  |  | 200000 | No
12 | 2-BEU-17-62609 | 2-BEU-16-XXXXX | 2-BEU-16- | 62609 | 2-BEU-16-62609 | 2-BEU-16-62609 | Beaumont District Office (Reg 2) HVAC Replacement 7200 Eastex Freeway Beaumont, Texas 77708 | Replacement of Heating Ventilation Air Conditioning (HVAC) Distribution System. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 315000 | 315000 | 315000 | 315000 | 315000 |  | 2017-06-30 | 95% |  |  |  |  | 315000 | No
13 | 3-LAR-17-62610 | 3-LAR-16-XXXXX | 3-LAR-16- | 62610 | 3-LAR-16-62610 | 3-LAR-16-62610 | Laredo District Office (Reg 3) Vacant area refresh 1901 Bob Bullock Loop Laredo, Texas 78043 | Vacant lab area - Refresh all deteriorated finishes and systems, lighting, roof, HVAC, and other infrastructure serving that area. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Nat Oechsner |  |  |  | 150000 | 150000 | 150000 | 150000 | 150000 |  | 2017-08-31 | 25% |  |  |  |  | 150000 | No
14 | 5-ABI-17-62611 | 5-ABI-16-XXXXX | 5-ABI-16- | 62611 | 5-ABI-16-62611 | 5-ABI-16-62611 | Abilene District Office (Reg 5) HVAC Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | TFC - Yen Nguyen |  |  |  | 260000 | 260000 | 260000 | 260000 | 260000 |  | 24 months - In assessment phase. Negotiating IAC with TFC. | [5 empty] | 260000 | No
15 | 1-CLE-17-62612 | 1-CLE-16-XXXXX | 1-CLE-16- | 62612 | 1-CLE-16-62612 | 1-CLE-16-62612 | Cleburne Area Office (Reg 1) HVAC Replacement 600 W. Kilpatrick St. Cleburne, Texas 76031 | Heating Ventilation Air Conditioning (HVAC) System replacement | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | 6-2016 Steve is assessing the project |  |  | 325000 | 325000 | 325000 | 325000 | 325000 |  | 2016-12-31 | 90% |  |  |  |  | 325000 | No
16 | 5-CHI-17-62613 | 5-CHI-16-XXXXX | 5-CHI-16- | 62613 | 5-CHI-16-62613 | 5-CHI-16-62613 | Childress Area Office (Reg 5) HVAC Replacement 1700 Ave. F Northwest Childress, Texas 79201 | Replacement of Heating Ventilation Air Conditioning (HVAC) System. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | TFC - Yen Nguyen |  |  |  | 500000 | 500000 | 500000 | 500000 | 500000 |  | 18 months - In assessment phase. Negotiating IAC with TFC. | 60% |  |  |  |  | 500000 | No
17 | 2-HGR-17-62614 | 2-HGR-16-XXXXX | 2-HGR-16- | 62614 | 2-HGR-16-62614 | 2-HGR-16-62614 | Houston Grant Road Driver License Office (Reg 2) Drainage Repairs - 10503 Grant Road Houston, Texas 77070 | DL parking lot repairs and drainage deficiencies | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 250000 | 250000 | 250000 | 250000 | 250000 |  | On hold - DL vacated office | [5 empty] | 250000 | No
18 | 4-ODE-17-62615 | 4-ODE-17-XXXXX | 4-ODE-17- | 62615 | 4-ODE-17-62615 | 4-ODE-17-62615 | Odessa Area Office (Reg 4) HVAC Replacement 1910 IH-20 West Odessa, Texas 79762 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) (Combined with project 4-ODE-17-62847) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 6/3/16 Initial site visit made and photos of the spaces. HVAC information has been given to Steve Haney |  |  | 150714 | 150714 | 150714 | 150714 | 150714 |  | Rolled into priority project 38. Estimated completion | 100% |  |  |  |  | 150714 | No
19 | 4-GAT-17-62616 | 4-GAT-17-XXXXX | 4-GAT-17- | 62616 | 4-GAT-17-62616 | 4-GAT-17-62616 | El Paso Gateway East Driver License Office (Reg 4) HVAC Replacement 7300 Gateway East El Paso, Texas 79915 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 6-10-16 16-R061559 Bid closes; 7-2016 - Award to vendor in process (Needed to add hailguards - no change in price or services, but Procurement made us rebid this project. | 17-R076596 |  | 200000 | 200000 | 200000 | 80000 | 80000 |  | 2016-12-31 | 100% |  |  | 80000 |  | 0 | No
20 | HQ-L-16-62617 | HQ-L-16-XXXXX | HQ-L-16- | 62617 | HQ-L-16-62617 | HQ-L-16-62617 | Austin HQ (Building L) HVAC Replacement 5710 Guadalupe Austin, Texas 78752 | Partial RTU replacements - Building L - Fleet Operations | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 6-13-16 - 17.5 Ton 14 IEER Gas Heat Rooftop Unit $21K (Phase 1) | 16-R068586 |  | 78000 | 78000 | 78000 | 78000 | 78000 |  | 2017-03-15 | 100% | 50% |  | 0 |  | 78000 | No
21 | HQ-GA-17-62618 | HQ-GA-16-XXXXX | HQ-GA-16- | 62618 | HQ-GA-16-62618 | HQ-GA-16-62618 | Austin HQ (Building G Annex) Chiller/Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace chillers/boilers in Building G Annex - Multi-Service Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 6-2016 - In design phase |  |  | 769600 | 769600 | 769600 | 769600 | 769600 |  | 2017-06-30 | 100% |  |  |  |  | 769600 | No
22 | HQ-E-17-62619 | HQ-E-16-XXXXX | HQ-E-16- | 62619 | HQ-E-16-62619 | HQ-E-16-62619 | Austin HQ (Building E) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace boiler in Building E - Law Enforcement Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 6-2016 - In design phase |  |  | 78000 | 78000 | 78000 | 78000 | 78000 |  | 2017-06-30 | 100% |  |  |  |  | 78000 | No
23 | HQ-C-17-62620 | HQ-C-16-XXXXX | HQ-C-16- | 62620 | HQ-C-16-62620 | HQ-C-16-62620 | Austin HQ (Building C) HVAC Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial HVAC replacement for Building C Training Academy | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Clay Bosworth |  |  |  | 520000 | 520000 | 520000 | 520000 | 520000 |  | 2017-08-31 | 30% |  |  |  |  | 520000 | No
24 | HQ-A-17-62621 | HQ-A-16-XXXXX | HQ-A-16- | 62621 | HQ-A-16-62621 | HQ-A-16-62621 | Austin HQ (Building A) Roof Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial roof replacement for Building A | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker | 8/10/16 sub req | 17-R072554 |  | 1040000 | 1040000 | 1040000 | 1040000 | 1040000 |  | 2017-08-31 | 100% |  |  | 1040000 |  | 0 | No
25 | HQ-E-17-62622 | HQ-E-16-XXXXX | HQ-E-16- | 62622 | HQ-E-16-62622 | HQ-E-16-62622 | Austin HQ (Building E) Roof Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial roof replacement for Building E - Law Enforcement Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  | 16-R072883 |  | 1787058 | 1787058 | 1787058 | 1787058 | 1787058 |  | 2017-08-31 | 100% |  | 500000 |  |  | 1787058 | No
26 | HQ-O-17-62623 | HQ-O-16-XXXXX | HQ-O-16- | 62623 | HQ-O-16-62623 | HQ-O-16-62623 | Austin HQ (Building O) Sprinkler System 5601 Guadalupe Austin, Texas 78752 | Add Sprinklers (Fire Marshal recommendation) - Building O Fleet Operations | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | 9/1/16In assessment phase |  |  | 26000 | 26000 | 26000 | 26000 | 26000 |  | 2017-08-31 | [5 empty] | 26000 | No
27 | 2-CON-17-62624 | 2-CON-16-XXXXX | 2-CON-16- | 62624 | 2-CON-16-62624 | 2-CON-16-62624 | Conroe District Office (Reg 2) Ductwork Replacement 2 Hilbig St. Conroe, Texas 77301 | Ductwork replacement-system reviewed and found contaminants and poor IAQ in facility due to condition of ductwork. Funding request to replace all flex duct and have the hard duct cleaned and sealed. (Includes office and Motor Vehicle Theft (MVT) Garage | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 603870 | 603870 | 603870 | 603870 | 603870 |  | 2017-08-31 | 40% |  |  |  |  | 603870 | No
28 | 1-GAR-17-62625 | 1-GAR-16-XXXXX | 1-GAR-16- | 62625 | 1-GAR-16-62625 | 1-GAR-16-62625 | Garland Regional Headquarters (Reg 1) Site Lighting Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged site lighting. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | 7/2016 Developing RFQ for Design Firm |  |  | 134006 | 134006 | 134006 | 134006 | 134006 |  | 2017-08-31 | [5 empty] | 134006 | No
29 | 1-GAR-17-62626 | 1-GAR-16-XXXXX | 1-GAR-16- | 62626 | 1-GAR-16-62626 | 1-GAR-16-62626 | Garland Regional Headquarters (Reg 1) Electrical Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged electrical system | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | 7/2016 Developing RFQ for Design Firm |  |  | 574870 | 574870 | 574870 | 574870 | 574870 |  | 2017-08-31 | [5 empty] | 574870 | No
30 | 1-GAR-17-62627 | 1-GAR-16-XXXXX | 1-GAR-16- | 62627 | 1-GAR-16-62627 | 1-GAR-16-62627 | Garland Regional Headquarters (Reg 1) Plumbing Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged plumbing (i.e.: Natural Gas system, domestic water system and fixtures, etc.) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | 7/2016 Developing RFQ for Design Firm |  |  | 517577 | 517577 | 517577 | 517577 | 517577 |  | 2017-08-31 | [5 empty] | 517577 | No
31 | 1-GAR-17-62628 | 1-GAR-16-XXXXX | 1-GAR-16- | 62628 | 1-GAR-16-62628 | 1-GAR-16-62628 | Garland Regional Headquarters (Reg 1) Foundation Study 350 West IH-30 Garland, Texas 75043 | Several signs of stress and settlement is seen throughout the facility, specifically on the Westside of the building. Recommend a professional structural engineering study be conducted for resolution. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | 7/2016 Developing RFQ for Design Firm |  |  | 150000 | 150000 | 150000 | 150000 | 150000 |  | 2017-08-31 | [5 empty] | 150000 | No
32 | 2-PIE-17-62629 | 2-PIE-16-XXXXX | 2-PIE-16- | 62629 | 2-PIE-16-62629 | 2-PIE-16-62629 | Pierce Sub-District Office (Reg 2) Foundation Study 19692 US Hwy 59 El Campo, Texas 77437 | Northwest wall and a part of Northeast wall are showings signs of structural degradation. Recommend professional study. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | TFC - Eddie King |  |  |  | 150000 | 150000 | 150000 | 150000 | 150000 |  | 16 months - Negotiating IAC with TFC. Assessment phase. | [5 empty] | 150000 | No
33 | 2-BAY-17-62630 | 2-BAY-16-XXXXX | 2-BAY-16- | 62630 | 2-BAY-16-62630 | 2-BAY-16-62630 | Baytown Area Office (Reg 2) Foundation Repairs 5420 Decker Drive Baytown, Texas 77520 | Repair foundation / interior finishes | Rider 40 | Rider 40 | General Revenue (Fund 0001) | TFC - Eddie King |  |  |  | 150000 | 150000 | 150000 | 150000 | 150000 |  | 16 months - Negotiating IAC with TFC. Assessment phase. | [5 empty] | 150000 | No
34 | 5-CHI-17-62631 | 5-CHI-16-XXXXX | 5-CHI-16- | 62631 | 5-CHI-16-62631 | 5-CHI-16-62631 | Childress Area Office (Reg 5) Foundation Study 1700 Ave. F Northwest Childress, Texas 79201 | The retaining walls are cracking and showing signs of structural problems. Recommend professional study. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | TFC - Eddie King |  |  |  | 150000 | 150000 | 150000 | 150000 | 150000 |  | 16 months - Negotiating IAC with TFC. Assessment phase. | [5 empty] | 150000 | No
35 | 1-SUL-17-62632 | 1-SUL-16-XXXXX | 1-SUL-16- | 62632 | 1-SUL-16-62632 | 1-SUL-16-62632 | Sulphur Springs Area Office (Reg 1) Foundation Study 1528 E. Shannon Road Sulphur Springs, Texas 75482 | Settlement cracks in foundation, exterior walls, and interior wall systems. Recommend a professional structural engineering study be conducted for resolution. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren |  |  |  | 150000 | 150000 | 150000 | 150000 | 150000 |  | 2017-08-31 | [5 empty] | 150000 | No
36 | 2-CON-17-62633 | 2-CON-16-XXXXX | 2-CON-16- | 62633 | 2-CON-16-62633 | 2-CON-16-62633 | Conroe District Office (Reg 2) Foundation Study 804 Interstate 45 South Conroe, Texas 77304 | Exterior walls are showing stress and damage at the MVT Garage. Recommend professional structure analysis to determine condition and repair of exterior wall and implement repairs. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 185000 | 185000 | 185000 | 185000 | 185000 |  | 9/15/16 On hold pending further assessment. | [5 empty] | 185000 | No
37 | HQ-L-17-62634 | HQ-L-16-XXXXX | HQ-L-16- | 62634 | HQ-L-16-62634 | HQ-L-16-62634 | Austin HQ (Building L) Car Wash Replacement 5710 Guadalupe Austin, Texas 78752 | Replace car wash at Fleet Operations - Building L | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Clay Bosworth | 9-1-16 in assessment phase. |  |  | 100000 | 100000 | 100000 | 100000 | 100000 |  | 2017-08-31 | [5 empty] | 100000 | No
38 | 4-ODE-17-62847 | 4-ODE-17-XXXXX | 4-ODE-17- | 62847 | 4-ODE-17-62847 | 4-ODE-17-62847 | Odessa Area Office (Reg 4) HVAC Replacement 1910 IH-20 West Odessa, Texas 79762 | Terminal & Package Units (Building Automation System) (Combined with project 4-ODE-17-62615) | 21 M | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 6/3/16 Initial site visit made and photos of the spaces. HVAC information has been given to Steve Haney |  |  | 234000 | 234000 | 234000 | 234000 | 234000 |  | 2017-08-31 | 100% |  |  |  |  | 234000 | No
39 | 4-ODE-17-62754 | 4-ODE-17-XXXXX | 4-ODE-17- | 62754 | 4-ODE-17-62754 | 4-ODE-17-62754 | Odessa Area Office (Reg 4) Roof Replacement 1910 IH-20 West Odessa, Texas 79762 | Roof Coverings/openings-built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 6/3/16 Site Assessment |  |  | 249600 | 249600 | 249600 | 249600 | 249600 |  | 2017-08-31 | 5% |  |  |  |  | 249600 | No
40 | ST-FUEL-16-62739 | ST-FUEL-16-XXXXX | ST-FUEL-16- | 62739 | ST-FUEL-16-62739 | ST-FUEL-16-62739 | Statewide Fuel System Maintenance/Removal | UST/AST fueling systems repairs/maintenance/removal | 21 M | Rider 40 | General Revenue (Fund 0001) | Philip Johnson | 2/13/16 Plainview - Removed fuel (Riley Industrial Services) and Stat Inv Reconciliation for Temp removed from service (Total SIR LLC); SA, Seguin, New Braunfels; | Feb 2016 Pcard $1857, Amarillo 3453.25, Seguin/New Braunfels $3870; MTI Services Pcard - Houston tank $1,750; R&R Petro pcard-Corpus $623.14 |  | 250000 | 250000 | 250000 | 250000 | 250000 |  | 2/28/18 - Performing TCEQ compliance audit; performing repairs as identified |  |  |  | 11553.39 | 0 | 238446.61 | No
41 | 5-AMA-17-62740 | 5-AMA-16-XXXXX | 5-AMA-16- | 62740 | 5-AMA-16-62740 | 5-AMA-16-62740 | Amarillo District Office (Reg 5) Exterior Door/Window Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Exterior doors replacement/Window replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | Yen Nguyen | 9-1-16 in assessment phase |  |  | 167666.72 | 167666.72 | 167666.72 | 167666.72 | 167666.72 |  | 2017-08-31 | [5 empty] | 167666.72 | No
42 | 6-ADO-17-62741 | 6-ADO-16-XXXXX | 6-ADO-16- | 62741 | 6-ADO-16-62741 | 6-ADO-16-62741 | Austin District Office (Reg 6) HVAC Replacement 9000 IH-35 North Austin, Texas 78753 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 6-2016 Not started |  |  | 192294.48 | 192294.48 | 192294.48 | 192294.48 | 192294.48 |  | 2017-08-31 | 5% |  |  |  |  | 192294.48 | No
43 | 6-ADO-17-62742 | 6-ADO-16-XXXXX | 6-ADO-16- | 62742 | 6-ADO-16-62742 | 6-ADO-16-62742 | Austin District Office (Reg 6) Roof Replacement 9000 IH-35 North Austin, Texas 78753 | Roof Coverings built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker | Est is over budget. Req sub 8/5/17 | 17-R074769 |  | 338000 | 338000 | 338000 | 338000 | 338000 |  | 2017-08-31 | 100% |  | 375000 |  |  | 338000 | No
44 | 2-HHQ-17-62743 | 2-HHQ-16-XXXXX | 2-HHQ-16- | 62743 | 2-HHQ-16-62743 | 2-HHQ-16-62743 | Houston Regional Headquarters (West Road) Crime Lab (Reg 2) Chiller Replacement 12230 West Road Jersey Village, Texas 77065 | Chiller replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | Steve Haney |  |  |  | 312000 | 312000 | 312000 | 312000 | 312000 |  | 2017-06-30 | 100% |  |  |  |  | 312000 | No
45 | 4-SAN-17-62744 | 4-SAN-16-XXXXX | 4-SAN-16- | 62744 | 4-SAN-16-62744 | 4-SAN-16-62744 | San Angelo Sub-District Office (Reg 4) HVAC Replacement 1600 W. Loop 306 San Angelo, Texas 76903 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 6/3/16 Initial site visit made and photos of the spaces. HVAC information has been given to Steve Haney |  |  | 633900.8 | 633900.8 | 633900.8 | 633900.8 | 633900.8 |  | 2017-08-31 | 75% |  |  |  |  | 633900.8 | No
46 | 4-SAN-17-62745 | 4-SAN-16-XXXXX | 4-SAN-16- | 62745 | 4-SAN-16-62745 | 4-SAN-16-62745 | San Angelo Sub-District Office (Reg 4) Roof Replacement 1600 W. Loop 306 San Angelo, Texas 76903 | Roof Coverings built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 9/1/16 in assessment |  |  | 325000 | 325000 | 325000 | 325000 | 325000 |  | 2017-08-31 | 5% |  |  |  |  | 325000 | No
47 | 1-HUR-17-62746 | 1-HUR-16-XXXXX | 1-HUR-16- | 62746 | 1-HUR-16-62746 | 1-HUR-16-62746 | Hurst Sub-District Office (Reg 1) Roof Replacement 624 NE Loop 820 Hurst, Texas 76053 | Roof Coverings built-up roofing replacement (Including roof openings) | 21 M | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | 9-1-16 in assessment |  |  | 430981.2 | 430981.2 | 430981.2 | 430981.2 | 430981.2 |  | 2017-12-31 | [5 empty] | 430981.2 | No
48 | 3-EAG-17-62747 | 3-EAG-16-XXXXX | 3-EAG-16- | 62747 | 3-EAG-16-62747 | 3-EAG-16-62747 | Eagle Pass Area Office (Reg 3) HVAC Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Terminal & package units replacement/upgrade (Add BAS as needed) | 21 M | Rider 40 | General Revenue (Fund 0001) | Nat Oechsner | 9/1/16 in assessment |  |  | 10000 | 10000 | 10000 | 10000 | 10000 |  | 2017-08-31 | 10% |  |  |  |  | 10000 | No
49 | 3-HAR-17-62748 | 3-HAR-16-XXXXX | 3-HAR-16- | 62748 | 3-HAR-16-62748 | 3-HAR-16-62748 | Harlingen Area Office (Reg 3) Roof Repairs 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Roof repairs | 21 M | Rider 40 | General Revenue (Fund 0001) | Nat Oechsner | During evaluation - determined roof does not need to be replaced - only needs PM | 17-R075684 |  | 325000 | 325000 | 325000 | 325000 | 325000 |  | 2017-02-28 | 100% |  | 3500 |  |  | 325000 | Yes
50 | 3-BEE-17-62749 | 3-BEE-16-XXXXX | 3-BEE-16- | 62749 | 3-BEE-16-62749 | 3-BEE-16-62749 | Beeville Area Office (Reg 3) HVAC Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Terminal & package units replacement/upgrade (Add BAS as needed) | 21 M | Rider 40 | General Revenue (Fund 0001) | Nat Oechsner Steve Haney |  | 17-R076672 |  | 10000 | 10000 | 10000 | 10000 | 10000 |  | 2017-08-31 | 100% |  | 20000 |  |  | 10000 | No
51 | 3-BEE-17-62750 | 3-BEE-16-XXXXX | 3-BEE-16- | 62750 | 3-BEE-16-62750 | 3-BEE-16-62750 | Beeville Area Office (Reg 3) Roof Repairs 400 S. Hillside Drive Beeville, Texas 78102 | Roof repairs | 21 M | Rider 40 | General Revenue (Fund 0001) | Nat Oechsner | During evaluation - determined roof does not need to be replaced - only needs PM | 17-R074917 |  | 150000 | 150000 | 150000 | 150000 | 150000 |  | 2017-08-31 | 100% |  | 3500 |  |  | 150000 | Yes
52 | 4-BIG-17-62751 | 4-BIG-16-XXXXX | 4-BIG-16- | 62751 | 4-BIG-16-62751 | 4-BIG-16-62751 | Big Spring Area Office (Reg 4) HVAC Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Terminal & package units replacement/upgrade - including split DX (Add BAS as needed) | 21 M | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 6/3/16 Initial site visit made and photos of the spaces. HVAC information has been given to Steve Haney |  |  | 2954.64 | 2954.64 | 2954.64 | 2954.64 | 2954.64 |  | 2017-08-31 | 5% |  |  |  |  | 2954.64 | No
53 | ST-PM-17-62635 | ST-PM-16-XXXXX | ST-PM-16- | 62635 | ST-PM-16-62635 | ST-PM-16-62635 | Statewide TFC Project Mgmt. Fees | TFC Project Management fees. | Rider 40 | Rider 40 | General Revenue (Fund 0001) |  |  |  |  | 616800 | 616800 | 300000 | 300000 | 300000 |  | Duration of projects Negotiating IAC with TFC. | [5 empty] | 300000 | No
54 | HQ-C-16-62904 | HQ-C-16-62904 | HQ-C-16- | 62904 | HQ-C-16- 62904 | HQ-C-16- 62904 | Austin HQ (Building C) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Boiler replacement (two boilers supporting original building) | 21 M - GO Bond Funded | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Steve Haney | 3-25-16 sent EPS to Vivian. Approved - will use bond; in the bid process; Bid Opening 6-16-16 Contractor on site installing as of 9/1/2017 | 405-16-R058997 |  | 0 | 0 | 100000 | 100000 | 100000 |  | 2016-10-01 | 100% | 25% |  | 100000 |  | 0 | No
55 | 2-BRE-17-62752 | 2-BRE-16-XXXXX | 2-BRE-16- | 62752 | 2-BRE-16-62752 | 2-BRE-16-62752 | Brenham Area Office (Reg 2) HVAC Controls Replacement 975 Hwy 290 West. Brenham, Texas 77834 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker |  |  |  | 168720.24 | 168720.24 | 168720.24 | 168720.24 | 168720.24 |  | 2017-08-31 | 50% |  |  |  |  | 168720.24 | No
56 | 2-BRE-17-62753 | 2-BRE-16-XXXXX | 2-BRE-16- | 62753 | 2-BRE-16-62753 | 2-BRE-16-62753 | Brenham Area Office (Reg 2) Roof Replacement 975 Hwy 290 West. Brenham, Texas 77834 | Roof Coverings built-up roofing replacement and access ladder | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker | sub req 8/10/16 for $40K | 17-R074981 |  | 130000 | 130000 | 130000 | 130000 | 130000 |  | 2017-08-31 | 100% |  |  | 40000 |  | 90000 | No
57 | 2-ORA-17-62755 | 2-ORA-16-XXXXX | 2-ORA-16- | 62755 | 2-ORA-16-62755 | 2-ORA-16-62755 | Orange Area Office (Reg 2) Roof Replacement 711 South Hwy 87 Orange, Texas 77630 | Roof Coverings built-up roofing replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker |  | 16-R072896 |  | 182000 | 182000 | 182000 | 182000 | 182000 |  | 2017-08-31 | 100% |  | 50000 |  |  | 182000 | No
58 | 4-OZO-16-62756 | 4-OZO-16-XXXXX | 4-OZO-16- | 62756 | 4-OZO-16-62756 | 4-OZO-16-62756 | Ozona Area Office (Reg 4) HVAC Replacement 1503 Monterey St Ozona, Texas 76943 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance (Project was completed from other funding) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | AnnMarie Davis | Steve will assess unit replaced a in prior FYand add DDC. Determined full DDC is not needed and used a Tstat to control. | Replaced in prior FY |  | 132242.24 | 132242.24 | 132242.24 | 132242.24 | 132242.24 | -132242 | Project completed in prior fiscal year using other funding. | 100% | 100% |  | 0 | 0 | 132242.24 | Yes
59 | 4-Pec-17-62757 | 4-Pec-16-XXXXX | 4-Pec-16- | 62757 | 4-Pec-16-62757 | 4-Pec-16-62757 | Pecos Area Office (Reg 4) HVAC Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Terminal & package units replacement/upgrade (Add BAS as needed), Distribution systems, controls and instrumentation replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | AnnMarie Davis | 9/1/16 in assessment |  |  | 117413.92 | 117413.92 | 117413.92 | 117413.92 | 117413.92 |  | 2017-08-31 | [5 empty] | 117413.92 | No
60 | 4-Pec-17-62758 | 4-Pec-16-XXXXX | 4-Pec-16- | 62758 | 4-Pec-16-62758 | 4-Pec-16-62758 | Pecos Area Office (Reg 4) Roof Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Roof Coverings built-up roofing replacement/roof openings | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | AnnMarie Davis | 9/1/16 in assessment |  |  | 133023.28 | 133023.28 | 133023.28 | 133023.28 | 133023.28 |  | 2017-08-31 | [5 empty] | 133023.28 | No
61 | 3-UVA-17-62759 | 3-UVA-16-XXXXX | 3-UVA-16- | 62759 | 3-UVA-16-62759 | 3-UVA-16-62759 | Uvalde Area Office (Reg 3) Roof Replacement 2901 E. Main Uvalde, Texas 78801 | Roof Coverings built-up roofing replacement/roof openings | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner | 9-2016 Req Submitted for 3,850 SF | 17-R079238 |  | 102397.2 | 102397.2 | 102397.2 | 102397.2 | 102397.2 |  | 2017-08-31 | 100% |  | 75075 |  |  | 102397.2 | No
62 | 1-GAR-17-62760 | 1-GAR-16-XXXXX | 1-GAR-16- | 62760 | 1-GAR-16-62760 | 1-GAR-16-62760 | Garland Regional Headquarters Site (Reg 1) Communication & Security 350 West IH-30 Garland, Texas 75043 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren | 7/2016 Developing RFQ for Design Firm |  |  | 49042.24 | 49042.24 | 49042.24 | 49042.24 | 49042.24 |  | TBD after A/E Contract is executed | [5 empty] | 49042.24 | No
63 | 1-GAR-17-62761 | 1-GAR-16-XXXXX | 1-GAR-16- | 62761 | 1-GAR-16-62761 | 1-GAR-16-62761 | Garland Regional Headquarters Site (Reg 1) Landscaping Upgrade 350 West IH-30 Garland, Texas 75043 | Landscaping (xeriscape) upgrade | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren | 7/2016 Developing RFQ for Design Firm |  |  | 98962.24 | 98962.24 | 98962.24 | 98962.24 | 98962.24 |  | TBD after A/E Contract is executed | [5 empty] | 98962.24 | No
64 | 1-GAR-17-62762 | 1-GAR-16-XXXXX | 1-GAR-16- | 62762 | 1-GAR-16-62762 | 1-GAR-16-62762 | Garland Regional Headquarters Site (Reg 1) Parking Lot Replacement 350 West IH-30 Garland, Texas 75043 | Parking lot/pedestrian paving/driveways replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren | 7/2016 Developing RFQ for Design Firm |  |  | 789058.4 | 789058.4 | 789058.4 | 789058.4 | 789058.4 |  | TBD after A/E Contract is executed | [5 empty] | 789058.4 | No
65 | 1-GAR-17-62763 | 1-GAR-16-XXXXX | 1-GAR-16- | 62763 | 1-GAR-16-62763 | 1-GAR-16-62763 | Garland Regional Headquarters Site (Reg 1) Sanitary Sewer Replacement 350 West IH-30 Garland, Texas 75043 | Sanitary sewer replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren | 7/2016 Developing RFQ for Design Firm |  |  | 24553.36 | 24553.36 | 24553.36 | 24553.36 | 24553.36 |  | TBD after A/E Contract is executed | [5 empty] | 24553.36 | No
66 | 1-GAR-17-62764 | 1-GAR-16-XXXXX | 1-GAR-16- | 62764 | 1-GAR-16-62764 | 1-GAR-16-62764 | Garland Regional Headquarters Site (Reg 1) Site Development 350 West IH-30 Garland, Texas 75043 | Site Development (i.e.: Storm water system, etc.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren | 7/2016 Developing RFQ for Design Firm |  |  | 287119.04 | 287119.04 | 287119.04 | 287119.04 | 287119.04 |  | TBD after A/E Contract is executed | [5 empty] | 287119.04 | No
67 | 1-GAR-17-62765 | 1-GAR-16-XXXXX | 1-GAR-16- | 62765 | 1-GAR-16-62765 | 1-GAR-16-62765 | Garland Regional Headquarters Site (Reg 1) Water Supply Upgrade 350 West IH-30 Garland, Texas 75043 | Water Supply upgrade/replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren | 7/2016 Developing RFQ for Design Firm |  |  | 67370.16 | 67370.16 | 67370.16 | 67370.16 | 67370.16 |  | TBD after A/E Contract is executed | [5 empty] | 67370.16 | No
68 | 2-PIE-17-62766 | 2-PIE-16-XXXXX | 2-PIE-16- | 62766 | 2-PIE-16-62766 | 2-PIE-16-62766 | Pierce Sub-District Office (Reg 2) Ductwork Replacement 19692 US Hwy 59 El Campo, Texas 77437 | Duct work and insulation replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker | 9/1/16 in assessment |  |  | 62400 | 62400 | 62400 | 62400 | 62400 |  | 2017-08-31 | [5 empty] | 62400 | No
69 | 2-BRE-17-62767 | 2-BRE-16-XXXXX | 2-BRE-16- | 62767 | 2-BRE-16-62767 | 2-BRE-16-62767 | Brenham Area Office (Reg 2) Exterior Wall Repair 975 Hwy 290 West. Brenham, Texas 77834 | Exterior walls repair | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker |  |  |  | 10773.36 | 10773.36 | 10773.36 | 10773.36 | 10773.36 |  | 2017-08-31 | 50% |  |  |  |  | 10773.36 | No
70 | 2-HHQ-17-62768 | 2-HHQ-16-XXXXX | 2-HHQ-16- | 62768 | 2-HHQ-16-62768 | 2-HHQ-16-62768 | Houston Regional Headquarters (West Road) (Reg 2) Security System Replacement 12230 West Road Jersey Village, Texas 77065 | Security system replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker |  |  |  | 208000 | 208000 | 208000 | 208000 | 208000 |  | 2017-07-01 | 100% |  |  |  |  | 208000 | No
71 | 4-MID-17-62769 | 4-MID-16-XXXXX | 4-MID-16- | 62769 | 4-MID-16-62769 | 4-MID-16-62769 | Midland Sub District Office (Reg 4) Vacant DL Remodel/Refresh 2405 S. Loop 250 West Midland, Texas 79703 | Remodel vacant DL area including to replacing deteriorated finishes and MEP systems | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | AnnMarie Davis | 6-2-16 Site Assessment; 9-1-16 Planning with Regional Staff |  |  | 442000 | 442000 | 442000 | 442000 | 442000 |  | 2018-02-28 | 5% |  |  |  |  | 442000 | No
72 | 5-AMA-176-62770 | 5-AMA-16-XXXXX | 5-AMA-16- | 62770 | 5-AMA-16-62770 | 5-AMA-16-62770 | Amarillo District Office (Reg 5) Security System Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Security system replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen | 9-1-16 in assessment phase |  |  | 343698.16 | 343698.16 | 343698.16 | 343698.16 | 343698.16 |  | 2018-02-28 | [5 empty] | 343698.16 | No
73 | 5-AMA-17-62771 | 5-AMA-16-XXXXX | 5-AMA-16- | 62771 | 5-AMA-16-62771 | 5-AMA-16-62771 | Amarillo District Office (Reg 5) Sprinkler System 4200 Canyon Dr. Amarillo, Texas 79109 | Sprinkler System | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen | 9-1-16 in assessment phase |  |  | 153180.56 | 153180.56 | 153180.56 | 153180.56 | 153180.56 |  | 2018-02-28 | [5 empty] | 153180.56 | No
74 | 5-AMA-17-62772 | 5-AMA-16-XXXXX | 5-AMA-16- | 62772 | 5-AMA-16-62772 | 5-AMA-16-62772 | Amarillo District Office (Reg 5) Foundation Study/Repair 4200 Canyon Dr. Amarillo, Texas 79109 | Standard Foundations | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen | 9/1/16 in assessment |  |  | 40278.16 | 40278.16 | 40278.16 | 40278.16 | 40278.16 |  | 2017-08-31 | [5 empty] | 40278.16 | No
75 | 5-AMA-17-62773 | 5-AMA-16-XXXXX | 5-AMA-16- | 62773 | 5-AMA-16-62773 | 5-AMA-16-62773 | Amarillo District Office (Reg 5) Interior Finishes Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen | 6-2016 - this is a phased project and will begin in spring of 2017 when DL is expected to relocate to a leased facility. |  |  | 575051.36 | 575051.36 | 575051.36 | 575051.36 | 575051.36 |  | 8-31-18 - Phased project | [5 empty] | 575051.36 | No
76 | 5-AMA-17-62774 | 5-AMA-16-XXXXX | 5-AMA-16- | 62774 | 5-AMA-16-62774 | 5-AMA-16-62774 | Amarillo District Office (Reg 5) Fittings Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Fittings (Specialties) replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen | 9/1/16 in assessment |  |  | 17077.84 | 17077.84 | 17077.84 | 17077.84 | 17077.84 |  | 2017-08-31 | [5 empty] | 17077.84 | No
77 | 6-ADO-17-62775 | 6-ADO-16-XXXXX | 6-ADO-16- | 62775 | 6-ADO-16-62775 | 6-ADO-16-62775 | Austin District Office Site (Reg 6) Parking Lot Replacement 9000 IH-35 North Austin, Texas 78753 | Parking lot replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth | 9-1-16 in assessment phase |  |  | 260000 | 260000 | 260000 | 260000 | 260000 |  | 2017-08-31 | [5 empty] | 260000 | No
78 | 6-ADO-17-62776 | 6-ADO-16-XXXXX | 6-ADO-16- | 62776 | 6-ADO-16-62776 | 6-ADO-16-62776 | Austin District Office Site (Reg 6) Site Lighting Replacement/Upgrade 9000 IH-35 North Austin, Texas 78753 | Site Lighting | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth | 9-1-16 in assessment phase |  |  | 57117.84 | 57117.84 | 57117.84 | 57117.84 | 57117.84 |  | 2017-08-31 | [5 empty] | 57117.84 | No
79 | 6-ADO-17-62777 | 6-ADO-16-XXXXX | 6-ADO-16- | 62777 | 6-ADO-16-62777 | 6-ADO-16-62777 | Austin District Office Site (Reg 6) Communication & Security 9000 IH-35 North Austin, Texas 78753 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth | 9-1-16 in assessment phase |  |  | 22046.96 | 22046.96 | 22046.96 | 22046.96 | 22046.96 |  | 2017-08-31 | [5 empty] | 22046.96 | No
80 | 6-ADO-17-62778 | 6-ADO-16-XXXXX | 6-ADO-16- | 62778 | 6-ADO-16-62778 | 6-ADO-16-62778 | Austin District Office Storage Hwy Patrol (Reg 6) Special Structures 9000 IH-35 North Austin, Texas 78753 | Special Structures - Storage Bldg. < 1000sf | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth | 9-1-16 in assessment phase |  |  | 12728.56 | 12728.56 | 12728.56 | 12728.56 | 12728.56 |  | 2017-08-31 | [5 empty] | 12728.56 | No
81 | 5-ABI-17-62779 | 5-ABI-16-XXXXX | 5-ABI-16- | 62779 | 5-ABI-16-62779 | 5-ABI-16-62779 | Abilene District Office (Reg 5) Security/Site System Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Security system replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth | 9-1-16 in assessment phase |  |  | 220581.92 | 220581.92 | 220581.92 | 220581.92 | 220581.92 |  | 2017-08-31 | [5 empty] | 220581.92 | No
82 | 3-LAR-17-62780 | 3-LAR-16-XXXXX | 3-LAR-16- | 62780 | 3-LAR-16-62780 | 3-LAR-16-62780 | Laredo District Office (Reg 3) Ceiling Replacement 1901 Bob Bullock Loop Laredo, Texas 78043 | Ceiling/wall finishes replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 389896.32 | 389896.32 | 389896.32 | 389896.32 | 389896.32 |  | 2017-08-31 | 10% |  |  |  |  | 389896.32 | No
83 | 3-LAR-17-62781 | 3-LAR-16-XXXXX | 3-LAR-16- | 62781 | 3-LAR-16-62781 | 3-LAR-16-62781 | Laredo District Office (Reg 3) Security System Replacement 1901 Bob Bullock Loop Laredo, Texas 78043 | Security system replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 373251.84 | 373251.84 | 373251.84 | 373251.84 | 373251.84 |  | 2017-08-31 | 10% |  |  |  |  | 373251.84 | No
84 | 6-WAC-17-62782 | 6-WAC-16-XXXXX | 6-WAC-16- | 62782 | 6-WAC-16-62782 | 6-WAC-16-62782 | Waco District Office (Reg 6) Interior Finishes Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth |  |  |  | 567938.8 | 567938.8 | 567938.8 | 567938.8 | 567938.8 |  | 2017-08-31 | 5% |  |  |  |  | 567938.8 | Yes
85 | 6-WAC-17-62783 | 6-WAC-16-XXXXX | 6-WAC-16- | 62783 | 6-WAC-16-62783 | 6-WAC-16-62783 | Waco District Office (Reg 6) Fixed Furnishings Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Fixed furnishings replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth | 9-1-16 in assessment phase |  |  | 137846.8 | 137846.8 | 137846.8 | 137846.8 | 137846.8 |  | 2017-08-31 | [5 empty] | 137846.8 | No
86 | 3-EAG-17-62784 | 3-EAG-16-XXXXX | 3-EAG-16- | 62784 | 3-EAG-16-62784 | 3-EAG-16-62784 | Eagle Pass Area Office (Reg 3) Interior Finishes Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 186283.86 | 186283.86 | 186283.86 | 186283.86 | 186283.86 |  | 2017-08-31 | 10% |  |  |  |  | 186283.86 | No
87 | 3-EAG-17-62785 | 3-EAG-16-XXXXX | 3-EAG-16- | 62785 | 3-EAG-16-62785 | 3-EAG-16-62785 | Eagle Pass Area Office (Reg 3) Electrical Systems 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Other Electrical Systems (Repair illuminated exit signs throughout the facility and add emergency lighting where needed.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 150000 | 150000 | 150000 | 150000 | 150000 |  | 2017-08-31 | 10% |  |  |  |  | 150000 | No
88 | 3-EAG-17-62786 | 3-EAG-16-XXXXX | 3-EAG-16- | 62786 | 3-EAG-16-62786 | 3-EAG-16-62786 | Eagle Pass Area Office (Reg 3) Security System Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Security system replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 125000 | 125000 | 125000 | 125000 | 125000 |  | 2017-08-31 | 10% |  |  |  |  | 125000 | No
89 | 3-EAG-17-62787 | 3-EAG-16-XXXXX | 3-EAG-16- | 62787 | 3-EAG-16-62787 | 3-EAG-16-62787 | Eagle Pass Area Office (Reg 3) Sprinkler System 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Sprinkler System | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 49622.56 | 49622.56 | 49622.56 | 49622.56 | 49622.56 |  | 2017-08-31 | 10% |  |  |  |  | 49622.56 | No
90 | 3-EAG-17-62788 | 3-EAG-16-XXXXX | 3-EAG-16- | 62788 | 3-EAG-16-62788 | 3-EAG-16-62788 | Eagle Pass Site (Reg 3) Communication & Security 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 9984 | 9984 | 9984 | 9984 | 9984 |  | 2017-08-31 | 10% |  |  |  |  | 9984 | No
91 | 3-EAG-17-62789 | 3-EAG-16-XXXXX | 3-EAG-16- | 62789 | 3-EAG-16-62789 | 3-EAG-16-62789 | Eagle Pass Site (Reg 3) Landscaping Upgrade 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Landscaping (xeriscape) upgrade | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 4285.84 | 4285.84 | 4285.84 | 4285.84 | 4285.84 |  | 2017-08-31 | 10% |  |  |  |  | 4285.84 | No
92 | 3-EAG-17-62790 | 3-EAG-16-XXXXX | 3-EAG-16- | 62790 | 3-EAG-16-62790 | 3-EAG-16-62790 | Eagle Pass Site (Reg 3) Site Lighting Replacement/Upgrade 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Site Lighting | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 20368.4 | 20368.4 | 20368.4 | 20368.4 | 20368.4 |  | 2017-08-31 | 10% |  |  |  |  | 20368.4 | No
93 | 5-AMA-17-62791 | 5-AMA-16-XXXXX | 5-AMA-16- | 62791 | 5-AMA-16-62791 | 5-AMA-16-62791 | Amarillo MVT Building (Reg 5) Electrical Systems 4200 Canyon Dr. Amarillo, Texas 79109 | Other Electrical Systems (Add illuminated exit signs throughout the facility and add emergency lighting where needed.) | 21 M | Rider 40 | General Revenue (Fund 0001) | Yen Nguyen | Life Safety Issue - completed with Regional Index 29011 - pCard. Was informed this project was completed by the field staff on 6/14/16. |  |  | 260 | 260 | 260 | 260 | 260 |  | 2015-08-26 |  |  |  | 0 | 0 | 260 | No
94 | 5-AMA-17-62792 | 5-AMA-16-XXXXX | 5-AMA-16- | 62792 | 5-AMA-16-62792 | 5-AMA-16-62792 | Amarillo Site (Reg 5) Communication & Security 4200 Canyon Dr. Amarillo, Texas 79109 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen | 9/1/16 in assessment |  |  | 25084.8 | 25084.8 | 25084.8 | 25084.8 | 25084.8 |  | 2017-08-31 | [5 empty] | 25084.8 | No
95 | 5-AMA-17-62793 | 5-AMA-16-XXXXX | 5-AMA-16- | 62793 | 5-AMA-16-62793 | 5-AMA-16-62793 | Amarillo Site (Reg 5) Fuel Distribution Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Fuel distribution replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen | 9-1-16 in assessment phase |  |  | 46800 | 46800 | 46800 | 46800 | 46800 |  | 2018-02-28 | [5 empty] | 46800 | No
96 | 5-AMA-17-62794 | 5-AMA-16-XXXXX | 5-AMA-16- | 62794 | 5-AMA-16-62794 | 5-AMA-16-62794 | Amarillo Site (Reg 5) Parking Lot/Pedestrian Paving 4200 Canyon Dr. Amarillo, Texas 79109 | Parking lot/pedestrian paving replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen | 9/1/16 in assessment |  |  | 291766.8 | 291766.8 | 291766.8 | 291766.8 | 291766.8 |  | 2017-08-31 | [5 empty] | 291766.8 | No
97 | 5-AMA-17-62795 | 5-AMA-16-XXXXX | 5-AMA-16- | 62795 | 5-AMA-16-62795 | 5-AMA-16-62795 | Amarillo Site (Reg 5) Site Lighting Replacement/Upgrade 4200 Canyon Dr. Amarillo, Texas 79109 | Site Lighting | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen | 9-1-16 in assessment phase |  |  | 65007.28 | 65007.28 | 65007.28 | 65007.28 | 65007.28 |  | 2018-02-28 | [5 empty] | 65007.28 | No
98 | HQ-A-17-62796 | HQ-A-16-XXXXX | HQ-A-16- | 62796 | HQ-A-16-62796 | HQ-A-16-62796 | Austin HQ (Building A) AHU/FCU Replacement 5805 North Lamar Blvd Austin, Texas 78752 | HVAC - replace all AHU and FCUs not already in process/completed | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Steve Haney | 6-2016 - In design phase |  |  | 520000 | 520000 | 520000 | 520000 | 520000 |  | 2017-12-31 | 45% |  |  |  |  | 520000 | No
99 | HQ-A-17-62797 | HQ-A-16-XXXXX | HQ-A-16- | 62797 | HQ-A-16-62797 | HQ-A-16-62797 | Austin HQ (Building A) DDC Retrofit 5805 North Lamar Blvd Austin, Texas 78752 | HVAC - retrofit existing pneumatic controls to DDC | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Steve Haney | 6-2016 - In design phase |  |  | 62400 | 62400 | 62400 | 62400 | 62400 |  | 2017-12-31 | 10% |  |  |  |  | 62400 | No
100 | 2-BRY-17-XXXXX | 2-BRY-16-XXXXX | 2-BRY-16- | 62896 | 2-BRY-16- 62896 | 2-BRY-16- 62896 | Bryan District Office (Reg 2) Foundation/Drainage Modifications 2571 North Earl Rudder Freeway Bryan, Texas 77805 | Foundation/site drainage modifications | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker | DPS had no changes to drawings. Still waiting for IAC from TFC. |  |  | 0 | 0 | 650000 | 650000 | 650000 |  | 12 months - waiting for IAC from TFC to proceed to contstruction phase. | 100% | 0% |  |  |  | 650000 | No
101 | 6-WTR-17-XXXX | 6-WTR-16-XXXX | 6-WTR-16- | 62897 | 6-WTR-16- 62897 | 6-WTR-16- 62897 | Waco Texas Rangers Headquarters and Education Center (Reg 6) HVAC Replacement 102 Texas Ranger Trail Waco, Texas 76705 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Steve Haney | 6-2016 - In design phase |  |  | 0 | 0 | 350000 | 350000 | 350000 |  | 2017-12-31 | [5 empty] | 350000 | No
102 | 1-TER-17-XXXXX | 1-TER-16-XXXXX | 1-TER-16- | 62899 | 1-TER-16- 62899 | 1-TER-16- 62899 | Terrell Area Office (Reg 1) Drainage Repairs 111 Tejas Drive Terrell, Texas 75160 | Site drainage repairs | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Eddie King | 9/1/16 in assessment |  |  | 0 | 0 | 100000 | 100000 | 100000 |  | 2017-08-31 | [5 empty] | 100000 | No
103 | 3-EAG-17-62900 | 3-EAG-16-XXXXX | 3-EAG-16- | 62900 | 3-EAG-16- 62900 | 3-EAG-16- 62900 | Eagle Pass Area Office (Reg 3) Foundation/Drainage Modifications 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Foundation/site drainage modifications | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner | Awarded to Grassroots Construction & Maintenance on 3/24/16 (PO7175 for $4275) | 16-R052096 | 16-P007175 | 0 | 0 | 100000 | 100000 | 100000 |  | 2017-08-31 | 10% |  |  | 4275 |  | 95725 | No
104 | 6-ANW-17-XXXXX | 6-ANW-16-XXXXX | 6-ANW-16- | 62901 | 6-ANW-16- 62901 | 6-ANW-16- 62901 | Austin Northwest Area Office (Reg 6) Interior Finish Replacement 13730 Research Boulevard Austin, Texas 78750 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren | 6-13-16 Design has been completed. Cost est expected in 2 wks. | 6-15-16 waiting for cost estimate. |  | 0 | 0 | 50000 | 50000 | 50000 |  | 2017-08-31 | 95% |  |  |  |  | 50000 | No
105 | HQ-L-17-XXXXX | HQ-L-16-XXXXX | HQ-L-16- | 62903 | HQ-L-16- 62903 | HQ-L-16- 62903 | Austin HQ (Building L) Car Lift Replacement 5710 Guadalupe Austin, Texas 78752 | Replace 18 original car lifts that are no longer functioning, leaking hydraulic oil, or not operating effectively. | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth |  |  |  | 0 | 0 | 100000 | 100000 | 100000 |  | 2017-08-31 | [5 empty] | 100000 | No
106 | ST-CON-16-62636 | ST-CON-16-XXXXX | ST-CON-16- | 62636 | ST-CON-16-62636 | ST-CON-16-62636 | Statewide Unexpected DM repairs/Project Contingency | Statewide Unexpected DM repairs/Project Contingency: Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. | Rider 40 | Rider 40 | General Revenue (Fund 0001) |  |  |  |  | 1529759 | 1529759 | 1760161 | 1625113.19 | 1576113.19 |  | Duration of projects. Negotiating IAC with TFC. | [5 empty] | 1576113.19 | No
107 | ST-CONB-17-62894 | ST-CON-17-XXXXX | ST-CON-17- | 62894 | ST-CON-17-62894 | ST-CON-17-62894 | Statewide Unexpected DM repairs/Project Contingency | Statewide Unexpected DM repairs/Project Contingency: Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. May also include any addition project expenses such as TFC fees | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. |  |  |  |  | 0 | 0 | 1457366 | 1335528.66 | 1335528.66 |  | Duration of projects | [5 empty] | 1335528.66 | No
108 | ST-CON-16-62461 | ST-CON-16-XXXXX | ST-CON-16- | 62461 | ST-CON-16-62461 | ST-CON-16-62461 | Childress Area Office (Reg 5) Roof Replacement 1700 Ave. F Northwest Childress, Texas 79201 | Statewide Unexpected DM repairs/Project Contingency: Replace Childress radio shop roof (Roof is leaking and contains asbestos) 3/24/16 - entered req. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Yen Nguyen | 6-11-16 Award has been made. Currently in backgroumd checks | Req 16-R058830 |  | 0 | 0 | 50000 | 50000 | 50000 |  | 2016-08-31 |  |  |  | 50000 |  | 0 | Yes
109 | 4-ALP-16-62461 | 4-ALP-16-XXXXX | 4-ALP-16- | 62902 | 4-ALP-16- 62902 | 4-ALP-16-62461 | Alpine Area Office (Reg 4) Energy Efficiency Project 3500 North Highway 118 Alpine, Texas 79830 | Statewide Unexpected DM repairs/Project Contingency: Add ceiling insulation to increase energy efficiency to assist HVAC system to better control temperature in open ceiling area. | 21 M - GO Bond Funded | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | Vivian uploaded in EPS 5-4-16. | 16-R063449 |  | 0 | 0 | 60000 | 60000 | 60000 |  | 2017-02-28 | 100% |  |  | 60000 |  | 0 | No
110 | 2-Gal-16-62441 | 2-Gal-16-XXXXX | 2-Gal-16- | 62441 | 2-Gal-16-62441 | 2-Gal-16-62441 | Galveston Driver License Office (Reg 2) Replace Failed RTU 6802 Broadway Galveston, Texas 77554 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 10-ton RTU |  | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker / Steve Haney | Awarded to Rincon Air & Heat Company (Org $15,888 - CO1 - $425) | 16-R041711 | 16-P005343 |  |  |  | 16313 | 16313 |  | 2016-04-04 |  | 100% |  | 15240 | 1073 | 0 | No
111 | 4-EHQ-16-62441 | 4-EHQ-16-XXXXX | 4-EHQ-16- | 62441 | 4-EHQ-16-62441 | 4-EHQ-16-62441 | El Paso Regional Headquarters (Reg 4) RTU Replacement 11612 Scott Simpson El Paso, Texas 79936 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 2.5 Ton RTU (Commander's area) |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded toPC Automated Controls on 4/19/16. Unit is being manufactured. Will be installed in the winter months. Current unit was repaired. | 16-R056011 | PO07532 |  |  |  | 6982.51 | 6982.51 |  | 2016-12-01 |  | 100% |  | 6982.51 | 0 | 0 | No
112 | 1-Min-16-62441 | 1-Min-16-XXXXX | 1-Min-16- | 62441 | 1-Min-16-62441 | 1-Min-16-62441 | Mineral Wells Area Office (Reg 1) RTU Replacement 600 FM 1821 North Mineral Wells, Texas 76067 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 5 ton RTU. |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to LOVIC HVAC on 11/18/15 | 16-R041768 | P005521 |  |  |  | 9100 | 9100 |  | 2015-11-27 |  | 100% |  | 0 | 9100 | 0 | No
113 | 2-BAY-16-62441 | 2-BAY-16-XXXXX | 2-BAY-16- | 62441 | 2-BAY-16-62441 | 2-BAY-16-62441 | Baytown Area Office (Reg 2) RTU Replacement 5420 Decker Drive Baytown, Texas 77520 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 3 ton RTU |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to ABM Building Services | 16-R039687 | 16-P005593 |  |  |  | 10534 | 10534 |  | 2016-03-10 |  | 100% |  | 0 | 10534 | 0 | No
114 | HQ-TTC-16-62441 | HQ-TTC-16-XXXXX | HQ-TTC-16- | 62441 | HQ-TTC-16-62441 | HQ-TTC-16-62441 | Tactical Training Center (HQ) RTU Replacement 820 CR 240 Florence, Texas 76527 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 2 ton RTU |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to K-Air Corp | 16-R039876 | 16-P005605 |  |  |  | 9850.5 | 9850.5 |  | 2016-02-22 |  | 100% |  | 0 | 9850.5 | 0 | No
115 | 3-DEL-16-62431 | 3-DEL-16-XXXXX | 3-DEL-16- | 62431 | 3-DEL-16-62431 | 3-DEL-16-62431 | Del Rio Sub District Office (Reg 3) Water Heater Replacement 2012 Veteran Boulevard Del Rio, Texas 78840 | Statewide Unexpected DM repairs/Project Contingency: Replace failed water heater |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Rudy Robles Plumbing | 16-R44844 | 16-P005628 |  |  |  | 3310 | 3310 |  | 2015-12-16 |  | 100% |  | 0 | 0 | 3310 | No
116 | HQ-L-16-62441 | HQ-L-16-XXXXX | HQ-L-16 | 62441 | HQ-L-1662441 | HQ-L-16-62441 | Austin HQ (Building L) Shop Heaters Replacement 5710 Guadalupe Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Replace 6 outdated gas fired shop heaters (Labor only) and install 5 natural gas shop heaters. |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Clinton McFerrin | 16-R041205 | 16-P005733 |  |  |  | 3971 | 3971 |  | 2015-12-08 |  | 100% |  | 0 | 3971 | 0 | No
117 | 2-ROS-16-62481 | 2-ROS-16-XXXXX | 2-ROS-16- | 62481 | 2-ROS-16-62481 | 2-ROS-16-62481 | Rosenberg Area Office (Reg 2) Water Line Replacement 5505 Avenue N. Rosenberg, TX 77471-5640 | Statewide Unexpected DM repairs/Project Contingency: Water Line Replacement due to line breakage |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Gregory Edwards | 16-R046793 | 16-P005785 |  |  |  | 20362 | 20362 |  | 2016-01-06 |  | 100% |  | 20362 | 0 | 0 | No
118 | 2-ANG-16-62441 | 2-ANG-16-XXXXX | 2-ANG-16- | 62441 | 2-ANG-16-62441 | 2-ANG-16-62441 | Angleton Driver License Office (Reg 2) RTU Replacement 501 South Velasco Angleton, Texas 77515 | Statewide Unexpected DM repairs/Project Contingency: Replace failed 5 ton RTU. |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Rincon Air and Heat Company on 12/14/15 | 16-R043084 | 16-P005922 |  |  |  | 14833 | 14833 |  | 2016-02-12 |  | 100% |  | 14833 |  | 0 | No
119 | 1-GCL-16-62441 | 1-GCL-16-XXXXX | 1-GCL-16- | 62441 | 1-GCL-16-62441 | 1-GCL-16-62441 | Garland Crime Laboratory (Reg 1) BTU Boiler Replacement 402 West IH-30 Garland, Texas 75043 | Statewide Unexpected DM repairs/Project Contingency: Replace 2 failed BTU boilers and appurtenances |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Acument Enterprises, Inc 1/12/16 | 16-R046364 | 16-P006245 |  |  |  | 22950 | 22950 |  | 2016-03-18 |  | 100% |  | 22950 |  | 0 | No
120 | 3-WES-16-62441 | 3-WES-16-XXXXX | 3-WES-16- | 62441 | 3-WES-16-62441 | 3-WES-16-62441 | Weslaco Regional Headquarters (Reg 3) VFD Replacement 2525 N. International Blvd Weslaco, TX 78596 | Statewide Unexpected DM repairs/Project Contingency: Replace failed VFD |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to five star Electric Motors on 1/26/16 | R042709 | 16-P006336 |  |  |  | 4550.85 | 4550.85 |  | 2016-03-08 |  | 0% |  | 4550.85 |  | 0 | No
121 | 2-LUF-16-62441 | 2-LUF-16-XXXXX | 2-LUF-16- | 62441 | 2-LUF-16-62441 | 2-LUF-16-62441 | Lufkin Sub-District Office (Reg 2) Replace cooling system 2809 South John Redditt Drive Lufkin, TX 75904 | Statewide Unexpected DM repairs/Project Contingency: Replace split cooling system with a gas furnace |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Concord Commercial Services on 3/10/16 | 16-R043499 | 16-P006973 |  |  |  | 11676 | 11676 |  | 2016-04-21 |  | 100% |  | 11676 |  | 0 | No
122 | 2-BCA-16-62431 | 2-BCA-16-XXXXX | 2-BCA-16- | 62431 | 2-BCA-16-62431 | 2-BCA-16-62431 | Bay City Area Office (Reg 2) 510 Avenue F Bay City, TX 77414 | Statewide Unexpected DM repairs/Project Contingency: Replace failed gas water heater |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Big State Plumbing | 16-R040862 | RPA 1390 |  |  |  | 2104.95 | 2104.95 |  | 2015-11-18 |  | 100% |  |  | 0 | 2104.95 | No
123 | HQ-C-16-62431 | HQ-C-16-XXXXX | HQ-C-16- | 62431 | HQ-C-16-62431 | HQ-C-16-62431 | Austin HQ (Building C&E) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Replace deteriorated Bldg. C-Annex/ Building E Waterproofing Elev#16. & Bldg. E-Rm. E001. |  | Rider 40 | General Revenue (Fund 0001) | Steve Harper | Awarded to Jeans Water proofing of Texas on 3/17/16; 4-27-Experiencing weather delay Bldg E | 16-R048154 | 16-P006950 |  |  |  | 33750 | 33750 |  | 2016-05-10 |  | 100% |  | 33750 | 0 | 0 | No
124 | 6-VIC-16-62431 | 6-VIC-16-XXXXX | 6-VIC-16- | 62431 | 6-VIC-16-62431 | 6-VIC-16-62431 | Victoria Site (Reg 6) HVAC - CID Replacement 8802 N. Navarro Victoria, Texas 77904 | Statewide Unexpected DM repairs/Project Contingency: HVAC unit (1.5 ton split system and 3.5 ton split system) serving CID and conference room failed. |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 5-26-16 Req Created; June 2016 in bid phase | [5 empty] | 24500 | 24500 |  | 2016-07-15 |  |  |  | 24500 |  | 0 | No
125 | HQ-CA-16-62451 | HQ-CA-16-XXXXX | HQ-CA-16- | 62451 | HQ-CA-16-62451 | ST-CON-16-62894 | Austin HQ (Building C Annex) Floor Finish Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Replace deteriorated Bldg. C-Annex/ Corridor C (basement) Annex Flooring. |  | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | Req R070710 created 7-5-16 - did not add DM40 Cont in short description - need to be sure this is updated for tracking purposes. | 405-16-R070710 | 16-P008841 |  |  |  |  | 4500 |  | 2016-08-20 | [5 empty] | 4500 | No
126 | HQ-CA-16-62451 | HQ-CA-16-XXXXX | HQ-CA-16- | 62451 | HQ-CA-16-62451 | ST-CON-16-62894 | Austin HQ (Building C Annex) Wall Finish Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Statewide Unexpected DM repairs/Project Contingency: Replace deteriorated Bldg. C-Annex/ Corridor C (basement) Annex wall covering. |  | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | Req R070699 created 7-5-16 - did not add DM40 Cont in short description - need to be sure this is updated for tracking purposes. | 405-16-R070699 | 16-P008858 |  |  |  |  | 4500 |  | 2016-08-20 | [5 empty] | 4500 | No
127 | 6-SAN-17-62441 | 6-SAN-17-XXXXX | 6-SAN-17 | 62441 | 6-SAN-1762441 | 6-SAN-17-62441 | San Antonio Regiona HQ (Reg 6) RTU Replacement 6502 South New Braunfels Ave San Antonio, Texas 78223 | Statewide Unexpected DM repairs/Project Contingency: Replace two failed RTU. (17.5 ton and 5 ton) |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney |  | 17-R076654 | [5 empty] | 40000 |  | 2016-12-31 |  |  |  | 40000 |  | 0 | No
128 | HQ-CONB-17-62908 | ST-CON-17-XXXXX | ST-CONB-17- | 62908 | ST-CONB-17-62908 | HQ-CONB-17-62908 | Tactical Training Center (HQ) Security Replacement 820 CR 240 Florence, Texas 76527 | Statewide Unexpected DM repairs/Project Contingency-Bond: Security system needs to be replaced and expanded to protect the firing range and other adjacent areas | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner | 9/6/16 approval given to proceed with Req |  |  | 0 | 0 | 1457366 | 1612331.56 |  | 100000 | 2017-08-31 |  |  | 100000 |  |  | 0 | Yes
129 | 3-CONB-17-62907 | ST-CON-17-XXXXX | ST-CONB-17- | 62907 | ST-CONB-17-62907 | 3-CONB-17-62907 | Alice Area Office (Reg 3) Roof Replacement 300 South Johnson Alice, Texas 78332 | Statewide Unexpected DM repairs/Project Contingency-Bond: Inspected roof due to reported leaks, replace deteriorated roof system. | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner | 9/6/16 approval given to proceed with Req |  |  | 0 | 0 | 1457366 | 2187382.92 |  | 65400 | 2017-08-31 |  |  | 65400 |  |  | 0 | Yes
130 | HQ-B-17-XXXXX | HQ-B-16-XXXXX | HQ-L-16- |  | HQ-L-16- | HQ-L-16- | Austin HQ (Building B) Building B Renovation 5805 North Lamar Blvd Austin, Texas 78752 | Complete renovations to vacated crime laboratory area and DM upgrades. | 21 M | 21 M - GO Bond Funded | Submitting request to LBB - G.O. Bond savings from 80th Legislative $200M bond package. | Eddie King |  |  |  | 0 | 0 |  | 5100000 | 5100000 |  | Waiting LBB approval | [5 empty] | 5100000 | Yes
| Consolidated | [5 empty] | Projects not funded | Summary of projects not funded that were originally submitted 9-15-15 to the JOC | [7 empty] | 13605967.82 | 13605967.82 | 8549999.81 | 0 | [8 empty] | 0
[11 empty] | Totals: |  |  |  |  | 38778877 | 38778877 | 41693608.99 | 42578591.32 | 38778876.84 | [5 empty] | 2162778.32 | 1793696.42 | 34822402.1
[26 empty] | 2162778.32 | 1793696.42 | 34822402

## DPS Notes 9.16
| Agency: | Texas Department of Public Safety - 0405
| Date: | 2016-09-15
| Prepared by: | Tavia Wendlandt
Project Priority | Supplemental Information
49, 51 | Beeville/Harlingen Roofs were on the replacement list, but recent inspection determined that the overall roof does not need to be replaced but repaired to assure integrity of overall roof system
58 | Ozona HVAC has one unit serving the building and was completed in prior fiscal year before funding was approved.
84 | Added note in project scope to complete on going DM projects from prior DM funding (Phase I) with this phase II of the project.
108 | Abatement was needed to replace the Childress roof resulting in a change order request. Upon evaluation, DPS rebid this project to realize savings.
128 | Alice roof replacement: Upon inspection of reported leaks, it was determined that the entire roof system should be replaced.
129 | Tactical Training Center Security Replacement/Upgrade: Recent camera outages resulted in a determination that the entire system needed to be replaced and coverage of certain additional areas.
130 | New priority DM project proposed utilizing the $200M bond funding to upgrade vacated crime laboratory space to help relieve overcrowding at the Headquarters complex. This is an approved bond project with TPFA - seeking approval to proceed from the LBB. Original proposed DM projects have been moved to a separate tab within the spreadsheet as they have become a lower agency priority compared to Building B. If there are any savings from the approved DM projects, then we will begin to work on these currently unfunded DM projects.
Waiting for LBB approval of funding to begin project; Excerpt from letter to LBB: “Per Article IX Sec. 14.03 (h) (3) Limitation on Expenditures – Capital Budget, the Department of Public Safety requests to transfer appropriations from a capital budget item to a non-capital budget item. Capital budget authority of $21, 000,000 is included in Article V, Rider 2 b. (2) Deferred Maintenance for deferred maintenance projects at the Department of Public Safety, however additional appropriations of $21,000,000 were not provided. This situation results in a $21,000,000 reduction to our Agency’s operations which cause undue hardship on the Agency’s programs. The Department requests a transfer of $11,139,565 in fiscal year 2016 and $9,860,435 in fiscal year 2017 from a capital budget item to a non-capital budget item.”

## DPS Projs. Not Funded
| Agency: | [5 empty] | Texas Department of Public Safety - 0405
| Date: | [5 empty] | 2016-09-15
| Prepared by: | [5 empty] | Tavia Wendlandt
Project Priority | Agency ID | Agency ID with XXXXX | Agency ID - with out index | Index | Concatenate | Agency ID - Absolute | Project Name & Location | Project Description | Type - Original | Type - Adjusted | Source of Funding (MOF) | TFC/Facilities PM | Project Notes | Req # | PO # | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Current Estimated Project Budget (for 2nd Qtr.) | Current Estimated Project Budget (for 3rd Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
Proposed DM Projects Not Currently Funded
131 | HQ-A-16-62798 | HQ-A-16-XXXXX | HQ-A-16- | 62798 | HQ-A-16-62798 | HQ-A-16-62798 | Austin HQ (Building A) Plumbing Fixtures Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Plumbing fixtures replacement (i.e.: toilets/lavatories) | 21 M | 21 M | Unknown |  |  |  |  | 41600 | 41600 | 41600 | 41600 | Unknown |  |  |  |  | 41600 | Yes
132 | 3-DEL-16-62799 | 3-DEL-16-XXXXX | 3-DEL-16- | 62799 | 3-DEL-16-62799 | 3-DEL-16-62799 | Del Rio Sub District Office (Reg 3) Security System Replacement 2012 Veteran Boulevard Del Rio, Texas 78840 | Security system replacement | 21 M | 21 M | Unknown |  |  |  |  | 228853.04 | 228853.04 | 228853.04 | 228853.04 | Unknown |  |  |  |  | 228853.04 | Yes
133 | 3-HAR-16-62800 | 3-HAR-16-XXXXX | 3-HAR-16- | 62800 | 3-HAR-16-62800 | 3-HAR-16-62800 | Harlingen Area Office (Reg 3) Ceiling Replacement 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Ceiling finishes replacement | 21 M | 21 M | Unknown |  |  |  |  | 84252.48 | 84252.48 | 84252.48 | 84252.48 | Unknown |  |  |  |  | 84252.48 | Yes
134 | 3-HAR-16-62801 | 3-HAR-16-XXXXX | 3-HAR-16- | 62801 | 3-HAR-16-62801 | 3-HAR-16-62801 | Harlingen Area Office (Reg 3) ADA Parking Spaces 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Correct American Disabilities Act (ADA) Parking Spaces. | 21 M | 21 M | Unknown |  |  |  |  | 62400 | 62400 | 62400 | 62400 | Unknown |  |  |  |  | 62400 | Yes
135 | 3-HAR-16-62802 | 3-HAR-16-XXXXX | 3-HAR-16- | 62802 | 3-HAR-16-62802 | 3-HAR-16-62802 | Harlingen Area Office (Reg 3) Security System Replacement 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Security system replacement | 21 M | 21 M | Unknown |  |  |  |  | 157109.68 | 157109.68 | 157109.68 | 157109.68 | Unknown |  |  |  |  | 157109.68 | Yes
136 | 4-SAN-16-62803 | 4-SAN-16-XXXXX | 4-SAN-16- | 62803 | 4-SAN-16-62803 | 4-SAN-16-62803 | San Angelo Site (Reg 4) Site Lighting Replacement/Upgrade 1600 W. Loop 306 San Angelo, Texas 76903 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 43630.08 | 43630.08 | 43630.08 | 43630.08 | Unknown |  |  |  |  | 43630.08 | Yes
137 | 5-ABI-16-62804 | 5-ABI-16-XXXXX | 5-ABI-16- | 62804 | 5-ABI-16-62804 | 5-ABI-16-62804 | Abilene Site (Reg 5) Security Lighting Upgrade/Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Security lighting/site lighting replacement/upgrade | 21 M | 21 M | Unknown |  |  |  |  | 77654.72 | 77654.72 | 77654.72 | 77654.72 | Unknown |  |  |  |  | 77654.72 | Yes
138 | 3-BEE-16-62805 | 3-BEE-16-XXXXX | 3-BEE-16- | 62805 | 3-BEE-16-62805 | 3-BEE-16-62805 | Beeville Area Office (Reg 3) Security System Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Security system replacement | 21 M | 21 M | Unknown |  |  |  |  | 125000 | 125000 | 125000 | 125000 | Unknown |  |  |  |  | 125000 | Yes
139 | 3-BEE-16-62806 | 3-BEE-16-XXXXX | 3-BEE-16- | 62806 | 3-BEE-16-62806 | 3-BEE-16-62806 | Beeville Site (Reg 3) Communication & Security 400 S. Hillside Drive Beeville, Texas 78102 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown |  |  |  |  | 3602.56 | 3602.56 | 3602.56 | 3602.56 | Unknown |  |  |  |  | 3602.56 | Yes
140 | 3-BEE-16-62807 | 3-BEE-16-XXXXX | 3-BEE-16- | 62807 | 3-BEE-16-62807 | 3-BEE-16-62807 | Beeville Site (Reg 3) Driveway Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Roadways (DPS driveway) pavement replacement | 21 M | 21 M | Unknown |  |  |  |  | 20000 | 20000 | 20000 | 20000 | Unknown |  |  |  |  | 20000 | Yes
141 | 3-BEE-16-62808 | 3-BEE-16-XXXXX | 3-BEE-16- | 62808 | 3-BEE-16-62808 | 3-BEE-16-62808 | Beeville Site (Reg 3) Parking Lot Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Parking Lots/roadway replacement | 21 M | 21 M | Unknown |  |  |  |  | 75000 | 75000 | 75000 | 75000 | Unknown |  |  |  |  | 75000 | Yes
142 | 3-BEE-16-62809 | 3-BEE-16-XXXXX | 3-BEE-16- | 62809 | 3-BEE-16-62809 | 3-BEE-16-62809 | Beeville Site (Reg 3) Site Lighting Replacement/Upgrade 400 S. Hillside Drive Beeville, Texas 78102 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 9337.12 | 9337.12 | 9337.12 | 9337.12 | Unknown |  |  |  |  | 9337.12 | Yes
143 | 4-BIG-16-62810 | 4-BIG-16-XXXXX | 4-BIG-16- | 62810 | 4-BIG-16-62810 | 4-BIG-16-62810 | Big Spring Area Office (Reg 4) Interior Finishes Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Ceiling, wall, floor finishes replacement | 21 M | 21 M | Unknown |  |  |  |  | 227175.52 | 227175.52 | 227175.52 | 227175.52 | Unknown |  |  |  |  | 227175.52 | Yes
144 | 4-BIG-16-62811 | 4-BIG-16-XXXXX | 4-BIG-16- | 62811 | 4-BIG-16-62811 | 4-BIG-16-62811 | Big Spring Area Office (Reg 4) Exterior Door Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Exterior doors replacement | 21 M | 21 M | Unknown |  |  |  |  | 2006.16 | 2006.16 | 2006.16 | 2006.16 | Unknown |  |  |  |  | 2006.16 | Yes
145 | 4-BIG-16-62812 | 4-BIG-16-XXXXX | 4-BIG-16- | 62812 | 4-BIG-16-62812 | 4-BIG-16-62812 | Big Spring Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 5725 W. IH-20 Big Spring, Texas 79720 | Lighting and Branch Wiring | 21 M | 21 M | Unknown |  |  |  |  | 4767.36 | 4767.36 | 4767.36 | 4767.36 | Unknown |  |  |  |  | 4767.36 | Yes
146 | 4-BIG-16-62813 | 4-BIG-16-XXXXX | 4-BIG-16- | 62813 | 4-BIG-16-62813 | 4-BIG-16-62813 | Big Spring Area Office (Reg 4) Security System Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Security system replacement | 21 M | 21 M | Unknown |  |  |  |  | 135779.28 | 135779.28 | 135779.28 | 135779.28 | Unknown |  |  |  |  | 135779.28 | Yes
147 | 4-BIG-16-62814 | 4-BIG-16-XXXXX | 4-BIG-16- | 62814 | 4-BIG-16-62814 | 4-BIG-16-62814 | Big Spring Area Office (Reg 4) Sprinkler System 5725 W. IH-20 Big Spring, Texas 79720 | Sprinkler System | 21 M | 21 M | Unknown |  |  |  |  | 60514.48 | 60514.48 | 60514.48 | 60514.48 | Unknown |  |  |  |  | 60514.48 | Yes
148 | 4-BIG-16-62815 | 4-BIG-16-XXXXX | 4-BIG-16- | 62815 | 4-BIG-16-62815 | 4-BIG-16-62815 | Big Spring Site (Reg 4) Communication & Security 5725 W. IH-20 Big Spring, Texas 79720 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown |  |  |  |  | 12940.72 | 12940.72 | 12940.72 | 12940.72 | Unknown |  |  |  |  | 12940.72 | Yes
149 | 4-BIG-16-62816 | 4-BIG-16-XXXXX | 4-BIG-16- | 62816 | 4-BIG-16-62816 | 4-BIG-16-62816 | Big Spring Site (Reg 4) Parking Lot/Driveway Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Parking lot replacement, roadways (DPS driveway) pavement replacement | 21 M | 21 M | Unknown |  |  |  |  | 74893.52 | 74893.52 | 74893.52 | 74893.52 | Unknown |  |  |  |  | 74893.52 | Yes
150 | 4-BIG-16-62817 | 4-BIG-16-XXXXX | 4-BIG-16- | 62817 | 4-BIG-16-62817 | 4-BIG-16-62817 | Big Spring Site (Reg 4) Site Lighting Replacement/Upgrade 5725 W. IH-20 Big Spring, Texas 79720 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 33533.76 | 33533.76 | 33533.76 | 33533.76 | Unknown |  |  |  |  | 33533.76 | Yes
151 | 4-BIG-16-62818 | 4-BIG-16-XXXXX | 4-BIG-16- | 62818 | 4-BIG-16-62818 | 4-BIG-16-62818 | Big Spring Storage Building (Reg 4) Electrical Service Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Electrical service/distribution replacement | 21 M | 21 M | Unknown |  |  |  |  | 13395.2 | 13395.2 | 13395.2 | 13395.2 | Unknown |  |  |  |  | 13395.2 | Yes
152 | 5-WIC-16-62819 | 5-WIC-16-XXXXX | 5-WIC-16- | 62819 | 5-WIC-16-62819 | 5-WIC-16-62819 | Wichita Falls Site (Reg 5) Parking Lot Replacement 5505 N. Central Expressway Wichita Falls, Texas 79306 | Parking lot replacement | 21 M | 21 M | Unknown |  |  |  |  | 260000 | 260000 | 260000 | 260000 | Unknown |  |  |  |  | 260000 | Yes
153 | 5-WIC-16-62820 | 5-WIC-16-XXXXX | 5-WIC-16- | 62820 | 5-WIC-16-62820 | 5-WIC-16-62820 | Wichita Falls Site (Reg 5) Site Lighting Replacement/Upgrade 5505 N. Central Expressway Wichita Falls, Texas 79306 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 40254.24 | 40254.24 | 40254.24 | 40254.24 | Unknown |  |  |  |  | 40254.24 | Yes
154 | 6-WAC-16-62821 | 6-WAC-16-XXXXX | 6-WAC-16- | 62821 | 6-WAC-16-62821 | 6-WAC-16-62821 | Waco Site (Reg 6) Communication & Security 1617 E. Crest Dr. Waco, Texas 76705 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown |  |  |  |  | 40913.6 | 40913.6 | 40913.6 | 40913.6 | Unknown |  |  |  |  | 40913.6 | Yes
155 | 6-WAC-16-62822 | 6-WAC-16-XXXXX | 6-WAC-16- | 62822 | 6-WAC-16-62822 | 6-WAC-16-62822 | Waco Site (Reg 6) Parking Lot/Paving Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Parking lot/pedestrian paving replacement | 21 M | 21 M | Unknown |  |  |  |  | 363811.76 | 363811.76 | 363811.76 | 363811.76 | Unknown |  |  |  |  | 363811.76 | Yes
156 | 6-WAC-16-62823 | 6-WAC-16-XXXXX | 6-WAC-16- | 62823 | 6-WAC-16-62823 | 6-WAC-16-62823 | Waco Site (Reg 6) Site Lighting Replacement/Upgrade 1617 E. Crest Dr. Waco, Texas 76705 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 105996.8 | 105996.8 | 105996.8 | 105997 | Unknown |  |  |  |  | 105997 | Yes
157 | 6-WAC-16-62824 | 6-WAC-16-XXXXX | 6-WAC-16- | 62824 | 6-WAC-16-62824 | 6-WAC-16-62824 | Waco Site (Reg 6) Storm Sewer replacement/repair 1617 E. Crest Dr. Waco, Texas 76705 | Storm Sewer replacement/repair | 21 M | 21 M | Unknown |  |  |  |  | 211420.56 | 211420.56 | 211420.56 |  | Unknown |  |  |  |  | 0 | Yes
158 | 2-BRE-16-62825 | 2-BRE-16-XXXXX | 2-BRE-16- | 62825 | 2-BRE-16-62825 | 2-BRE-16-62825 | Brenham Site (Reg 2) Communication & Security 975 Hwy 290 West. Brenham, Texas 77834 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown |  |  |  |  | 3106.48 | 3106.48 | 3106.48 |  | Unknown |  |  |  |  | 0 | Yes
159 | 2-BRE-16-62826 | 2-BRE-16-XXXXX | 2-BRE-16- | 62826 | 2-BRE-16-62826 | 2-BRE-16-62826 | Brenham Site (Reg 2) Pedestrian paving replacement 975 Hwy 290 West. Brenham, Texas 77834 | Pedestrian paving replacement | 21 M | 21 M | Unknown |  |  |  |  | 3934.32 | 3934.32 | 3934.32 |  | Unknown |  |  |  |  | 0 | Yes
160 | 2-BRE-16-62827 | 2-BRE-16-XXXXX | 2-BRE-16- | 62827 | 2-BRE-16-62827 | 2-BRE-16-62827 | Brenham Site (Reg 2) Site Lighting Replacement/Upgrade 975 Hwy 290 West. Brenham, Texas 77834 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 8049.6 | 8049.6 | 8049.6 |  | Unknown |  |  |  |  | 0 | Yes
161 | 2-BRE-16-62828 | 2-BRE-16-XXXXX | 2-BRE-16- | 62828 | 2-BRE-16-62828 | 2-BRE-16-62828 | Brenham Site Reg 2) Storm Sewer replacement/repair 975 Hwy 290 West. Brenham, Texas 77834 | Storm Sewer replacement/repair | 21 M | 21 M | Unknown |  |  |  |  | 16107.52 | 16107.52 | 16107.52 |  | Unknown |  |  |  |  | 0 | Yes
162 | 3-BRO-16-62829 | 3-BRO-16-XXXXX | 3-BRO-16- | 62829 | 3-BRO-16-62829 | 3-BRO-16-62829 | Brownsville Area Office (Reg 3) Sprinkler System 2901 E. Paredes Line Road Brownsville, Texas 78521 | Sprinkler System | 21 M | 21 M | Unknown |  |  |  |  | 74402.64 | 74402.64 | 74402.64 |  | Unknown |  |  |  |  | 0 | Yes
163 | 3-BRO-16-62830 | 3-BRO-16-XXXXX | 3-BRO-16- | 62830 | 3-BRO-16-62830 | 3-BRO-16-62830 | Brownsville Area Office (Reg 3) Electrical Systems 2901 E. Paredes Line Road Brownsville, Texas 78521 | Other Electrical Systems (Add emergency lighting where needed.) | 21 M | 21 M | Unknown |  |  |  |  | 400000 | 400000 | 400000 |  | Unknown |  |  |  |  | 0 | Yes
164 | 3-BRO-16-62831 | 3-BRO-16-XXXXX | 3-BRO-16- | 62831 | 3-BRO-16-62831 | 3-BRO-16-62831 | Brownsville Site (Reg 3) Driveway Replacement 2901 E. Paredes Line Road Brownsville, Texas 78521 | Roadways (DPS driveway) pavement replacement | 21 M | 21 M | Unknown |  |  |  |  | 24739.52 | 24739.52 | 24739.52 |  | Unknown |  |  |  |  | 0 | Yes
165 | 3-BRO-16-62832 | 3-BRO-16-XXXXX | 3-BRO-16- | 62832 | 3-BRO-16-62832 | 3-BRO-16-62832 | Brownsville Site (Reg 3) Storm Sewer replacement/repair 2901 E. Paredes Line Road Brownsville, Texas 78521 | Storm Sewer replacement/repair | 21 M | 21 M | Unknown |  |  |  |  | 39411.84 | 39411.84 | 39411.84 |  | Unknown |  |  |  |  | 0 | Yes
166 | 4-FOR-16-62833 | 4-FOR-16-XXXXX | 4-FOR-16- | 62833 | 4-FOR-16-62833 | 4-FOR-16-62833 | Fort Stockton Area Office (Reg 4) Security System Replacement 2302 W. Dickinson Boulevard Fort Stockton, Texas 79735 | Security system replacement | 21 M | 21 M | Unknown |  |  |  |  | 89671.92 | 89671.92 | 89671.92 |  | Unknown |  |  |  |  | 0 | Yes
167 | 4-LAM-16-62834 | 4-LAM-16-XXXXX | 4-LAM-16- | 62834 | 4-LAM-16-62834 | 4-LAM-16-62834 | Lamesa Area Office (Reg 4) Interior Finishes Replacement 2901 E. Main Lamesa, Texas 79331 | Ceiling, wall finishes replacement | 21 M | 21 M | Unknown |  |  |  |  | 24428.56 | 24428.56 | 24428.56 |  | Unknown |  |  |  |  | 0 | Yes
168 | 4-LAM-16-62835 | 4-LAM-16-XXXXX | 4-LAM-16- | 62835 | 4-LAM-16-62835 | 4-LAM-16-62835 | Lamesa Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 2901 E. Main Lamesa, Texas 79331 | Lighting and Branch Wiring | 21 M | 21 M | Unknown |  |  |  |  | 53836.64 | 53836.64 | 53836.64 |  | Unknown |  |  |  |  | 0 | Yes
169 | 4-LAM-16-62836 | 4-LAM-16-XXXXX | 4-LAM-16- | 62836 | 4-LAM-16-62836 | 4-LAM-16-62836 | Lamesa Area Office (Reg 4) Equipment (Other) 2901 E. Main Lamesa, Texas 79331 | Other Equipment (Replace manufactured kitchen unit.) | 21 M | 21 M | Unknown |  |  |  |  | 2618.72 | 2618.72 | 2618.72 |  | Unknown |  |  |  |  | 0 | Yes
170 | 4-LAM-16-62837 | 4-LAM-16-XXXXX | 4-LAM-16- | 62837 | 4-LAM-16-62837 | 4-LAM-16-62837 | Lamesa Area Office (Reg 4) Exterior Door Replacement 2901 E. Main Lamesa, Texas 79331 | Exterior doors replacement | 21 M | 21 M | Unknown |  |  |  |  | 2674.88 | 2674.88 | 2674.88 |  | Unknown |  |  |  |  | 0 | Yes
171 | 4-LAM-16-62838 | 4-LAM-16-XXXXX | 4-LAM-16- | 62838 | 4-LAM-16-62838 | 4-LAM-16-62838 | Lamesa Area Office (Reg 4) Fittings Replacement 2901 E. Main Lamesa, Texas 79331 | Fittings (Specialties) replacement (i.e.: metal toilet partitions and other rest room fittings.) | 21 M | 21 M | Unknown |  |  |  |  | 2978.56 | 2978.56 | 2978.56 |  | Unknown |  |  |  |  | 0 | Yes
172 | 4-LAM-16-62839 | 4-LAM-16-XXXXX | 4-LAM-16- | 62839 | 4-LAM-16-62839 | 4-LAM-16-62839 | Lamesa Area Office (Reg 4) Fixed Furnishings Replacement 2901 E. Main Lamesa, Texas 79331 | Fixed furnishings replacement (i.e.: DL Service Counter) | 21 M | 21 M | Unknown |  |  |  |  | 13785.2 | 13785.2 | 13785.2 |  | Unknown |  |  |  |  | 0 | Yes
173 | 4-LAM-16-62840 | 4-LAM-16-XXXXX | 4-LAM-16- | 62840 | 4-LAM-16-62840 | 4-LAM-16-62840 | Lamesa Area Office (Reg 4) HVAC Replacement 2901 E. Main Lamesa, Texas 79331 | Terminal & package units replacement/upgrade (Add BAS as needed) | 21 M | 21 M | Unknown |  |  |  |  | 10400 | 10400 | 10400 |  | Unknown |  |  |  |  | 0 | Yes
174 | 4-LAM-16-62841 | 4-LAM-16-XXXXX | 4-LAM-16- | 62841 | 4-LAM-16-62841 | 4-LAM-16-62841 | Lamesa Area Office (Reg 4) Plumbing Fixtures Replacement 2901 E. Main Lamesa, Texas 79331 | Plumbing fixtures replacement (i.e.: toilets/lavatories) | 21 M | 21 M | Unknown |  |  |  |  | 26312 | 26312 | 26312 |  | Unknown |  |  |  |  | 0 | Yes
175 | 4-LAM-16-62842 | 4-LAM-16-XXXXX | 4-LAM-16- | 62842 | 4-LAM-16-62842 | 4-LAM-16-62842 | Lamesa Area Office (Reg 4) Security System Replacement 2901 E. Main Lamesa, Texas 79331 | Security system replacement | 21 M | 21 M | Unknown |  |  |  |  | 33945.6 | 33945.6 | 33945.6 |  | Unknown |  |  |  |  | 0 | Yes
176 | 4-LAM-16-62843 | 4-LAM-16-XXXXX | 4-LAM-16- | 62843 | 4-LAM-16-62843 | 4-LAM-16-62843 | Lamesa Area Office (Reg 4) Sprinkler System 2901 E. Main Lamesa, Texas 79331 | Sprinkler System | 21 M | 21 M | Unknown |  |  |  |  | 15128.88 | 15128.88 | 15128.88 |  | Unknown |  |  |  |  | 0 | Yes
177 | 4-LAM-16-62844 | 4-LAM-16-XXXXX | 4-LAM-16- | 62844 | 4-LAM-16-62844 | 4-LAM-16-62844 | Lamesa Site (Reg 4) Communication & Security 2901 E. Main Lamesa, Texas 79331 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown |  |  |  |  | 5200 | 5200 | 5200 |  | Unknown |  |  |  |  | 0 | Yes
178 | 4-LAM-16-62845 | 4-LAM-16-XXXXX | 4-LAM-16- | 62845 | 4-LAM-16-62845 | 4-LAM-16-62845 | Lamesa Site (Reg 4) Parking Lot Replacement 2901 E. Main Lamesa, Texas 79331 | Parking lot replacement | 21 M | 21 M | Unknown |  |  |  |  | 104000 | 104000 | 104000 |  | Unknown |  |  |  |  | 0 | Yes
179 | 4-LAM-16-62846 | 4-LAM-16-XXXXX | 4-LAM-16- | 62846 | 4-LAM-16-62846 | 4-LAM-16-62846 | Lamesa Site (Reg 4) Site Lighting Replacement/Upgrade 2901 E. Main Lamesa, Texas 79331 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 10400 | 10400 | 10400 |  | Unknown |  |  |  |  | 0 | Yes
180 | 4-ODE-16-62848 | 4-ODE-16-XXXXX | 4-ODE-16- | 62848 | 4-ODE-16-62848 | 4-ODE-16-62848 | Odessa Area Office (Reg 4) Interior Finishes Replacement 1910 IH-20 West Odessa, Texas 79762 | Ceiling, wall, floor finishes replacement | 21 M | 21 M | Unknown |  |  |  |  | 239200 | 239200 | 239200 |  | Unknown |  |  |  |  | 0 | Yes
181 | 4-ODE-16-62849 | 4-ODE-16-XXXXX | 4-ODE-16- | 62849 | 4-ODE-16-62849 | 4-ODE-16-62849 | Odessa Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 1910 IH-20 West Odessa, Texas 79762 | Lighting and Branch Wiring | 21 M | 21 M | Unknown |  |  |  |  | 98800 | 98800 | 98800 |  | Unknown |  |  |  |  | 0 | Yes
182 | 4-ODE-16-62850 | 4-ODE-16-XXXXX | 4-ODE-16- | 62850 | 4-ODE-16-62850 | 4-ODE-16-62850 | Odessa Area Office (Reg 4 Electrical Service Replacement 1910 IH-20 West Odessa, Texas 79762 | Electrical service/distribution replacement | 21 M | 21 M | Unknown |  |  |  |  | 34814 | 34814 | 34814 |  | Unknown |  |  |  |  | 0 | Yes
183 | 4-ODE-16-62851 | 4-ODE-16-XXXXX | 4-ODE-16- | 62851 | 4-ODE-16-62851 | 4-ODE-16-62851 | Odessa Area Office (Reg 4) DL Interior Wall Relocation 1910 IH-20 West Odessa, Texas 79762 | Relocate Interior walls (DL area) | 21 M | 21 M | Unknown |  |  |  |  | 52000 | 52000 | 52000 |  | Unknown |  |  |  |  | 0 | Yes
184 | 4-ODE-16-62852 | 4-ODE-16-XXXXX | 4-ODE-16- | 62852 | 4-ODE-16-62852 | 4-ODE-16-62852 | Odessa Area Office (Reg 4) Domestic Water Replacement 1910 IH-20 West Odessa, Texas 79762 | Domestic water distribution replacement | 21 M | 21 M | Unknown |  |  |  |  | 6674.72 | 6674.72 | 6674.72 |  | Unknown |  |  |  |  | 0 | Yes
185 | 4-ODE-16-62853 | 4-ODE-16-XXXXX | 4-ODE-16- | 62853 | 4-ODE-16-62853 | 4-ODE-16-62853 | Odessa Area Office (Reg 4) Equipment (Other) 1910 IH-20 West Odessa, Texas 79762 | Other Equipment (Replace manufactured refrigerator and remove existing dishwasher and cap plumbing.) | 21 M | 21 M | Unknown |  |  |  |  | 1738.88 | 1738.88 | 1738.88 |  | Unknown |  |  |  |  | 0 | Yes
186 | 4-ODE-16-62854 | 4-ODE-16-XXXXX | 4-ODE-16- | 62854 | 4-ODE-16-62854 | 4-ODE-16-62854 | Odessa Area Office (Reg 4) Exterior Window/Door Replacement 1910 IH-20 West Odessa, Texas 79762 | Exterior windows/doors replacement | 21 M | 21 M | Unknown |  |  |  |  | 43812.08 | 43812.08 | 43812.08 |  | Unknown |  |  |  |  | 0 | Yes
187 | 4-ODE-16-62855 | 4-ODE-16-XXXXX | 4-ODE-16- | 62855 | 4-ODE-16-62855 | 4-ODE-16-62855 | Odessa Area Office (Reg 4) Fixed Furnishings Replacement 1910 IH-20 West Odessa, Texas 79762 | Fixed furnishings replacement | 21 M | 21 M | Unknown |  |  |  |  | 18300.88 | 18300.88 | 18300.88 |  | Unknown |  |  |  |  | 0 | Yes
188 | 4-ODE-16-62856 | 4-ODE-16-XXXXX | 4-ODE-16- | 62856 | 4-ODE-16-62856 | 4-ODE-16-62856 | Odessa Area Office (Reg 4) Foundation Study/Repair 1910 IH-20 West Odessa, Texas 79762 | Standard Foundations | 21 M | 21 M | Unknown |  |  |  |  | 40278.16 | 40278.16 | 40278.16 |  | Unknown |  |  |  |  | 0 | Yes
189 | 4-ODE-16-62857 | 4-ODE-16-XXXXX | 4-ODE-16- | 62857 | 4-ODE-16-62857 | 4-ODE-16-62857 | Odessa Area Office (Reg 4) Interior Doors Replacement 1910 IH-20 West Odessa, Texas 79762 | Interior doors replacement | 21 M | 21 M | Unknown |  |  |  |  | 86320 | 86320 | 86320 |  | Unknown |  |  |  |  | 0 | Yes
190 | 4-ODE-16-62858 | 4-ODE-16-XXXXX | 4-ODE-16- | 62858 | 4-ODE-16-62858 | 4-ODE-16-62858 | Odessa Area Office (Reg 4) Plumbing Systems (Other) 1910 IH-20 West Odessa, Texas 79762 | Other Plumbing Systems - Natural gas system is quite old, beyond its expected useful life and should be replaced. | 21 M | 21 M | Unknown |  |  |  |  | 6383.52 | 6383.52 | 6383.52 |  | Unknown |  |  |  |  | 0 | Yes
191 | 4-ODE-16-62859 | 4-ODE-16-XXXXX | 4-ODE-16- | 62859 | 4-ODE-16-62859 | 4-ODE-16-62859 | Odessa Area Office (Reg 4) Security System Replacement 1910 IH-20 West Odessa, Texas 79762 | Security system replacement | 21 M | 21 M | Unknown |  |  |  |  | 156000 | 156000 | 156000 |  | Unknown |  |  |  |  | 0 | Yes
192 | 4-ODE-16-62860 | 4-ODE-16-XXXXX | 4-ODE-16- | 62860 | 4-ODE-16-62860 | 4-ODE-16-62860 | Odessa Area Office (Reg 4) Sprinkler System 1910 IH-20 West Odessa, Texas 79762 | Sprinkler System | 21 M | 21 M | Unknown |  |  |  |  | 78000 | 78000 | 78000 |  | Unknown |  |  |  |  | 0 | Yes
193 | 4-ODE-16-62861 | 4-ODE-16-XXXXX | 4-ODE-16- | 62861 | 4-ODE-16-62861 | 4-ODE-16-62861 | Odessa Site (Reg 4) Communication & Security 1910 IH-20 West Odessa, Texas 79762 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown |  |  |  |  | 55000 | 55000 | 55000 |  | Unknown |  |  |  |  | 0 | Yes
194 | 4-NEW-16-62862 | 4-NEW-16-XXXXX | 4-NEW-16- | 62862 | 4-NEW-16-62862 | 4-NEW-16-62862 | New Braunfels Site (Reg 6) Canopy Repair 3003 IH-35 South New Braunfels, Texas 78130 | Canopy repair | 21 M | 21 M | Unknown |  |  |  |  | 10400 | 10400 | 10400 |  | Unknown |  |  |  |  | 0 | Yes
195 | 4-NEW-16-62863 | 4-NEW-16-XXXXX | 4-NEW-16- | 62863 | 4-NEW-16-62863 | 4-NEW-16-62863 | New Braunfels Site (Reg 6) Parking Lot Replacement 3003 IH-35 South New Braunfels, Texas 78130 | Parking lot replacement | 21 M | 21 M | Unknown |  |  |  |  | 52000 | 52000 | 52000 |  | Unknown |  |  |  |  | 0 | Yes
196 | 4-NEW-16-62864 | 4-NEW-16-XXXXX | 4-NEW-16- | 62864 | 4-NEW-16-62864 | 4-NEW-16-62864 | New Braunfels Site (Reg 6) Site Lighting Replacement/Upgrade 3003 IH-35 South New Braunfels, Texas 78130 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 9729.2 | 9729.2 | 9729.2 |  | Unknown |  |  |  |  | 0 | Yes
197 | 4-NEW-16-62865 | 4-NEW-16-XXXXX | 4-NEW-16- | 62865 | 4-NEW-16-62865 | 4-NEW-16-62865 | New Braunfels Site (Reg 6) Fuel Distribution Replacement 3003 IH-35 South New Braunfels, Texas 78130 | Fuel distribution replacement | 21 M | 21 M | Unknown |  |  |  |  | 52000 | 52000 | 52000 |  | Unknown |  |  |  |  | 0 | Yes
198 | 4-OZO-16-62866 | 4-OZO-16-XXXXX | 4-OZO-16- | 62866 | 4-OZO-16-62866 | 4-OZO-16-62866 | Ozona Area Office (Reg 4) Interior Finishes Replacement 1503 Monterey St Ozona, Texas 76943 | Ceiling, wall, floor finishes replacement | 21 M | 21 M | Unknown |  |  |  |  | 45437.6 | 45437.6 | 45437.6 |  | Unknown |  |  |  |  | 0 | Yes
199 | 4-OZO-16-62867 | 4-OZO-16-XXXXX | 4-OZO-16- | 62867 | 4-OZO-16-62867 | 4-OZO-16-62867 | Ozona Area Office (Reg 4) Exterior Window/Door Replacement 1503 Monterey St Ozona, Texas 76943 | Exterior windows/doors replacement | 21 M | 21 M | Unknown |  |  |  |  | 23371.92 | 23371.92 | 23371.92 |  | Unknown |  |  |  |  | 0 | Yes
200 | 4-OZO-16-62868 | 4-OZO-16-XXXXX | 4-OZO-16- | 62868 | 4-OZO-16-62868 | 4-OZO-16-62868 | Ozona Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 1503 Monterey St Ozona, Texas 76943 | Lighting and Branch Wiring | 21 M | 21 M | Unknown |  |  |  |  | 43069.52 | 43069.52 | 43069.52 |  | Unknown |  |  |  |  | 0 | Yes
201 | 4-OZO-16-62869 | 4-OZO-16-XXXXX | 4-OZO-16- | 62869 | 4-OZO-16-62869 | 4-OZO-16-62869 | Ozona Area Office (Reg 4) Domestic Water Replacement 1503 Monterey St Ozona, Texas 76943 | Domestic water distribution replacement | 21 M | 21 M | Unknown |  |  |  |  | 4011.28 | 4011.28 | 4011.28 |  | Unknown |  |  |  |  | 0 | Yes
202 | 4-OZO-16-62870 | 4-OZO-16-XXXXX | 4-OZO-16- | 62870 | 4-OZO-16-62870 | 4-OZO-16-62870 | Ozona Area Office (Reg 4) Electrical Service Replacement 1503 Monterey St Ozona, Texas 76943 | Electrical service/distribution replacement | 21 M | 21 M | Unknown |  |  |  |  | 20960.16 | 20960.16 | 20960.16 |  | Unknown |  |  |  |  | 0 | Yes
203 | 4-OZO-16-62871 | 4-OZO-16-XXXXX | 4-OZO-16- | 62871 | 4-OZO-16-62871 | 4-OZO-16-62871 | Ozona Area Office (Reg 4) Fittings Replacement 1503 Monterey St Ozona, Texas 76943 | Fittings (Specialties) replacement | 21 M | 21 M | Unknown |  |  |  |  | 2399.28 | 2399.28 | 2399.28 |  | Unknown |  |  |  |  | 0 | Yes
204 | 4-OZO-16-62872 | 4-OZO-16-XXXXX | 4-OZO-16- | 62872 | 4-OZO-16-62872 | 4-OZO-16-62872 | Ozona Area Office (Reg 4) Interior Doors Replacement 1503 Monterey St Ozona, Texas 76943 | Interior doors replacement | 21 M | 21 M | Unknown |  |  |  |  | 17413.76 | 17413.76 | 17413.76 |  | Unknown |  |  |  |  | 0 | Yes
205 | 4-OZO-16-62873 | 4-OZO-16-XXXXX | 4-OZO-16- | 62873 | 4-OZO-16-62873 | 4-OZO-16-62873 | Ozona Area Office (Reg 4) Plumbing Systems 1503 Monterey St Ozona, Texas 76943 | Plumbing fixtures (i.e.: toilets/lavatories)/other plumbing systems replacement- Natural gas system is quite old, beyond its expected useful life and should be replaced. | 21 M | 21 M | Unknown |  |  |  |  | 24892.4 | 24892.4 | 24892.4 |  | Unknown |  |  |  |  | 0 | Yes
206 | 4-OZO-16-62874 | 4-OZO-16-XXXXX | 4-OZO-16- | 62874 | 4-OZO-16-62874 | 4-OZO-16-62874 | Ozona Area Office (Reg 4) Sanitary Waste Replacement 1503 Monterey St Ozona, Texas 76943 | Sanitary waste replacement | 21 M | 21 M | Unknown |  |  |  |  | 10699.52 | 10699.52 | 10699.52 |  | Unknown |  |  |  |  | 0 | Yes
207 | 4-OZO-16-62875 | 4-OZO-16-XXXXX | 4-OZO-16- | 62875 | 4-OZO-16-62875 | 4-OZO-16-62875 | Ozona Area Office (Reg 4) Security System Replacement 1503 Monterey St Ozona, Texas 76943 | Security system replacement | 21 M | 21 M | Unknown |  |  |  |  | 7001.28 | 7001.28 | 7001.28 |  | Unknown |  |  |  |  | 0 | Yes
208 | 4-OZO-16-62876 | 4-OZO-16-XXXXX | 4-OZO-16- | 62876 | 4-OZO-16-62876 | 4-OZO-16-62876 | Ozona Area Office (Reg 4) Sprinkler System 1503 Monterey St Ozona, Texas 76943 | Sprinkler System | 21 M | 21 M | Unknown |  |  |  |  | 11721.84 | 11721.84 | 11721.84 |  | Unknown |  |  |  |  | 0 | Yes
209 | 4-OZO-16-62877 | 4-OZO-16-XXXXX | 4-OZO-16- | 62877 | 4-OZO-16-62877 | 4-OZO-16-62877 | Ozona Area Office (Reg 4) Fixed Furnishings Replacement 1503 Monterey St Ozona, Texas 76943 | Fixed furnishings replacement | 21 M | 21 M | Unknown |  |  |  |  | 11021.92 | 11021.92 | 11021.92 |  | Unknown |  |  |  |  | 0 | Yes
210 | 4-OZO-16-62878 | 4-OZO-16-XXXXX | 4-OZO-16- | 62878 | 4-OZO-16-62878 | 4-OZO-16-62878 | Ozona Site (Reg 4) Landscaping Upgrade 1503 Monterey St Ozona, Texas 76943 | Landscaping (xeriscape) upgrade | 21 M | 21 M | Unknown |  |  |  |  | 4703.92 | 4703.92 | 4703.92 |  | Unknown |  |  |  |  | 0 | Yes
211 | 4-OZO-16-62879 | 4-OZO-16-XXXXX | 4-OZO-16- | 62879 | 4-OZO-16-62879 | 4-OZO-16-62879 | Ozona Site (Reg 4) Parking Lot Replacement 1503 Monterey St Ozona, Texas 76943 | Parking lot replacement | 21 M | 21 M | Unknown |  |  |  |  | 104000 | 104000 | 104000 |  | Unknown |  |  |  |  | 0 | Yes
212 | 4-OZO-16-62880 | 4-OZO-16-XXXXX | 4-OZO-16- | 62880 | 4-OZO-16-62880 | 4-OZO-16-62880 | Ozona Site (Reg 4) Site Lighting Replacement/Upgrade 1503 Monterey St Ozona, Texas 76943 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 6039.28 | 6039.28 | 6039.28 |  | Unknown |  |  |  |  | 0 | Yes
213 | 4-OZO-16-62881 | 4-OZO-16-XXXXX | 4-OZO-16- | 62881 | 4-OZO-16-62881 | 4-OZO-16-62881 | Ozona Storage (Reg 4) Special Structures 1503 Monterey St Ozona, Texas 76943 | Special Structures - Storage Bldg. < 1000sf | 21 M | 21 M | Unknown |  |  |  |  | 7271.68 | 7271.68 | 7271.68 |  | Unknown |  |  |  |  | 0 | Yes
214 | 4-Pec-16-62882 | 4-Pec-16-XXXXX | 4-Pec-16- | 62882 | 4-Pec-16-62882 | 4-Pec-16-62882 | Pecos Area Office (Reg 4) Security System Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Security system replacement | 21 M | 21 M | Unknown |  |  |  |  | 54772.64 | 54772.64 | 54772.64 |  | Unknown |  |  |  |  | 0 | Yes
215 | 6-GEN-16-62883 | 6-GEN-16-XXXXX | 6-GEN-16- | 62883 | 6-GEN-16-62883 | 6-GEN-16-62883 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) 1803 S. General McMullen San Antonio, Texas 78226 | Parking lot replacement | 21 M | 21 M | Unknown |  |  |  |  | 260000 | 260000 | 260000 |  | Unknown |  |  |  |  | 0 | Yes
216 | 6-GEN-16-62884 | 6-GEN-16-XXXXX | 6-GEN-16- | 62884 | 6-GEN-16-62884 | 6-GEN-16-62884 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) Sanitary Waste Replacement 1803 S. General McMullen San Antonio, Texas 78226 | Sanitary waste replacement | 21 M | 21 M | Unknown |  |  |  |  | 19922.24 | 19922.24 | 19922.24 |  | Unknown |  |  |  |  | 0 | Yes
217 | 6-GEN-16-62885 | 6-GEN-16-XXXXX | 6-GEN-16- | 62885 | 6-GEN-16-62885 | 6-GEN-16-62885 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) Rain Water Drainage Improvements 1803 S. General McMullen San Antonio, Texas 78226 | Rain Water Drainage | 21 M | 21 M | Unknown |  |  |  |  | 5254.08 | 5254.08 | 5254.08 |  | Unknown |  |  |  |  | 0 | Yes
218 | 6-GEN-16-62886 | 6-GEN-16-XXXXX | 6-GEN-16- | 62886 | 6-GEN-16-62886 | 6-GEN-16-62886 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) Site Lighting Replacement/Upgrade 1803 S. General McMullen San Antonio, Texas 78226 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 110258.72 | 110258.72 | 110258.72 |  | Unknown |  |  |  |  | 0 | Yes
219 | 6-VIC-16-62887 | 6-VIC-16-XXXXX | 6-VIC-16- | 62887 | 6-VIC-16-62887 | 6-VIC-16-62887 | Victoria Site (Reg 6) Communication & Security 8802 N. Navarro Victoria, Texas 77904 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown |  |  |  |  | 13783.12 | 13783.12 | 13783.12 |  | Unknown |  |  |  |  | 0 | Yes
220 | 6-VIC-16-62888 | 6-VIC-16-XXXXX | 6-VIC-16- | 62888 | 6-VIC-16-62888 | 6-VIC-16-62888 | Victoria Site (Reg 6) Driveway Replacement 8802 N. Navarro Victoria, Texas 77904 | Parking lot replacement, pedestrian paving, roadways (DPS driveway) pavement replacement | 21 M | 21 M | Unknown |  |  |  |  | 176389.2 | 176389.2 | 176389.2 |  | Unknown |  |  |  |  | 0 | Yes
221 | 6-SEG-16-62889 | 6-SEG-16-XXXXX | 6-SEG-16- | 62889 | 6-SEG-16-62889 | 6-SEG-16-62889 | Seguin Site (Reg 6) Communication & Security 1440 E. Kingsbury Seguin, Texas 78155 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown |  |  |  |  | 3895.84 | 3895.84 | 3895.84 |  | Unknown |  |  |  |  | 0 | Yes
222 | 6-SEG-16-62890 | 6-SEG-16-XXXXX | 6-SEG-16- | 62890 | 6-SEG-16-62890 | 6-SEG-16-62890 | Seguin Site (Reg 6) Parking Lot Replacement 1440 E. Kingsbury Seguin, Texas 78155 | Parking lot, pedestrian paving replacement | 21 M | 21 M | Unknown |  |  |  |  | 161000 | 161000 | 161000 |  | Unknown |  |  |  |  | 0 | Yes
223 | 6-SEG-16-62891 | 6-SEG-16-XXXXX | 6-SEG-16- | 62891 | 6-SEG-16-62891 | 6-SEG-16-62891 | Seguin Site (Reg 6) Site Lighting Replacement/Upgrade 1440 E. Kingsbury Seguin, Texas 78155 | Site Lighting | 21 M | 21 M | Unknown |  |  |  |  | 10095.28 | 10095.28 | 10095.28 |  | Unknown |  |  |  |  | 0 | Yes
224 | ST-TEST-16-62892 | ST-TEST-16-XXXXX | ST-TEST-16- | 62892 | ST-TEST-16-62892 | ST-TEST-16-62892 | Statewide Support Project Consultants | Funding for testing, consulting, commissioning, CMT, inspections type of expenditures associated with projects. | 21 M | 21 M | Unknown |  |  |  |  | 455199.82 | 455199.82 | 455199.82 | 455199.82 | Unknown |  |  |  |  | 455199.82 | Yes
225 | ST-PM-16-62893 | ST-PM-16-XXXXX | ST-PM-16- | 62893 | ST-PM-16-62893 | ST-PM-16-62893 | Statewide TFC Project Mgmt. Fees | TFC Project Management fees. | 21 M | 21 M | Unknown |  |  |  |  | 616800 | 616800 | 616800 | 616800 | Unknown |  |  |  |  | 616800 | Yes
226 | ST-CON-16-62894 | ST-CON-16-XXXXX | ST-CON-16- | 62894 | ST-CON-16-62894 | ST-CON-16-62894 | Statewide Unexpected DM repairs/Project Contingency | Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. | 21 M | 21 M | Unknown |  |  |  |  | 1852154.56 | 1852154.56 | 1796186.55 | 1723578 | Unknown |  |  |  |  | 1723578 | Yes
DM Projects Not Approved
Not Approved | ST-FCA-16-62604 | ST-FCA-16-XXXXX | ST-FCA-16- | 62604 | ST-FCA-16-62604 | ST-FCA-16-62604 | Statewide Facility Condition Assessment | Statewide Assessment: An updated professional statewide Facility Condition Assessment study is needed to identify current deferred maintenance and capital renewal projects and associated costs. 3-1-16 Not approved by governing authority | Dis-Approved Projects | Dis-Approved Projects | Not approved by governing authority |  |  |  |  | 1300000 | 1300000 | 0 | 0 | Not approved by governing authority |  |  |  |  | 0 | Yes
Not Approved | ST-IWMS-16-62605 | ST-IWMS-16-XXXXX | ST-IWMS-16- | 62605 | ST-IWMS-16-62605 | ST-IWMS-16-62605 | Statewide Integrated Workplace Management System | A computerized Integrated Workplace Management system (IWMS) that is web based and can be implemented statewide is needed to track and plan for maintenance of DPS facilities. As funding permits, this will include the implementation of space management, inventory management, lease management, and environmental sustainability integration. 3-1-16 Not approved by governing authority | Dis-Approved Projects | Dis-Approved Projects | Not approved by governing authority |  |  |  |  | 1700000 | 1700000 | 0 | 0 | Not approved by governing authority |  |  |  |  | 0 | Yes
Not Approved | HQ-CAM-16-62602 | HQ-CAM-16-XXXXX | HQ-CAM-16- | 62602 | HQ-CAM-16-62602 | HQ-CAM-16-62602 | Austin HQ Campus Campus Relocation Study 5805 North Lamar Blvd Austin, Texas 78752 | Campus relocation study (Rider 54). Includes campus conceptual design. 3-1-16 Not approved by governing authority | Dis-Approved Projects | Dis-Approved Projects | Not approved by governing authority |  |  |  |  | 2000000 | 2000000 | 0 | 0 | Not approved by governing authority |  |  |  |  | 0 | Yes
[11 empty] | Totals: |  |  |  |  | 13605967.82 | 13605967.82 | 8549999.81 | 5100000.1 |  |  |  | 0 | 0 | 5100000.1

## DPS 6.16
| Agency: | [5 empty] | Texas Department of Public Safety - 0405
| Date: | [5 empty] | 2016-06-15
| Prepared by: | [5 empty] | Tavia Wendlandt
Project Priority | Agency ID | Agency ID with XXXXX | Agency ID - with out index | Index | Concatenate | Agency ID - Absolute | Project Name & Location | Project Description | Type - Original | Type - Adjusted | Source of Funding (MOF) | TFC/Facilities PM | Project Notes | Req # | PO # | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Current Estimated Project Budget (for 2nd Qtr.) | Current Estimated Project Budget (for 3rd Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | ST-TEMP-62601 | ST-TEMP-XXXXX | ST-TEMP- | 62601 | ST-TEMP-62601 | ST-TEMP-62601 | Statewide Temporary DM Staff | Temporary staff needed to administer DM projects. (estimate two years) | Rider 40 | Rider 40 | General Revenue (Fund 0001) |  |  |  |  | 215000 | 215000 | 215000 | 215000 | Duration of projects |  |  |  | 9167.92 | 205832.08 | No
2 | 3-COR-16-62737 | 3-COR-16-XXXXX | 3-COR-16- | 62737 | 3-COR-16-62737 | 3-COR-16-62737 | Corpus Christi District Office (Reg 3) DM Multi-system project 1922 S. Padre Island Drive Corpus Christi, Texas 78416 | Complete ongoing DM projects (HVAC, Sanitary Sewer, Etc.) | 21M | Rider 40 | General Revenue (Fund 0001) | TFC | GMP I - 100%; GMP II 50%; GMP III NTP given 5/20/16; Bids 5/18/16; Hanger |  |  | 780000 | 780000 | 780000 | 780000 | 24 months - Negotiating IAC with TFC. |  |  |  |  | 780000 | No
3 | 6-ANW-16-62738 | 6-ANW-16-XXXXX | 6-ANW-16- | 62738 | 6-ANW-16-62738 | 6-ANW-16-62738 | Austin Northwest Area Office (Reg 6) Roof Replacement 13730 Research Boulevard Austin, Texas 78750 | Partial roof replacement (Built up portion only) | 21M | Rider 40 | General Revenue (Fund 0001) | TFC | 5-26-16 DD; |  |  | 250000 | 250000 | 625000 | 625000 | 12 months - Received cost estimate from CMR on 2-11-16. Reviewing budget with TFC and negociating IAC for construction portion. | 100% |  |  |  | 625000 | No
4 | 2-LUF-16-62603 | 2-LUF-16-XXXXX | 2-LUF-16- | 62603 | 2-LUF-16-62603 | 2-LUF-16-62603 | Lufkin Lease Refresh - Lufkin CID Lease (Reg 2) 2815 John Redditt Dr. Lufkin, Texas 75904 | Refurbishment and equipping of a certain leased facility in Lufkin for use by CID as per Rider 63. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker | ACM Surveying 6-2016 |  |  | 200000 | 200000 | 200000 | 200000 | 10 months - in schematic design | 10% |  |  |  | 200000 | No
5 | HQ-C-16-62905 | HQ-C-16-XXXXX | HQ-C-16- | 62905 | HQ-C-16-62905 | HQ-C-16-62905 | Austin HQ (Building C) Dormitory Renovations Floor 2&3 5805 North Lamar Blvd Austin, Texas 78752 | Dormitory floors 2 and 3 are vacant since 2009 due to fire marshal code violations. Renovations will bring these floors into current building code compliance to allow for additional recruit classes to be held. | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth | 5/2/16-Asbestos ($15K) | 16-R063150 |  | 0 | 0 |  | 1300000 | 2017-01-01 |  |  | 289605.57 |  | 1010394.43 | Yes
6 | HQ-CAM-16-XXXXX | [5 empty] | Austin HQ (Campus) Dual Power Feed 5805 North Lamar Blvd Austin, Texas 78752 | Upgrade existing single power source to the complex. Austin Energy will provide two separate power grids to provide redundant power back up for the crime lab, data centers and other critical DPS functions. | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren | 6/2016 Study completed 12/2015; seeking A/E firm |  |  | 0 | 0 |  | 2182097 | 18 months - seeking A/E firm |  |  | 15000 |  | 2167097 | Yes
7 | HQ-A-16-62895 |  |  | 62895 | 62895 | HQ-A-16-62895 | Austin HQ (Building A) Data Center Upgrades 5805 North Lamar Blvd Austin, Texas 78752 | Replace existing HVAC, electrical, and fire suppression system, provide redundancy for HVAC/Electrical in the Data Center. | 21 M | Agency Savings | General Revenue (Fund 0001) | TFC - Jessica Warren | Backgrounds in progress. GC not given construction schedule yet. |  |  | 0 | 0 | 1750000 | 1750000 | Construction schedule expected 7-1-16 | 100% |  |  | 1750000 | 0 | Yes
8 | 7-CAP-16-62322 |  |  | 62322 | 62322 | 7-CAP-16-62322 | Austin Capital Services (Reg 7) 1500 N. Congress Austin, Texas 78701 Generator Replacement | Replace existing ATS and package Generator unit at the Capital Services Building. (Additional funding needed according to TFC estimates) | 21 M | Agency Savings | General Revenue (Fund 0001) | TFC - Clay Bosworth |  |  |  | 0 | 0 |  | 150000 | 14 months - in assessment phase. |  |  | 150000 |  | 0 | Yes
9 | 1-GAR-16-62606 | 1-GAR-16-XXXXX | 1-GAR-16- | 62606 | 1-GAR-16-62606 | 1-GAR-16-62606 | Garland Regional Headquarters (Reg 1) HVAC Replacement 350 West IH-30 Garland, Texas 75043 | Heating Ventilation Air Conditioning (HVAC) System replacement in the Annex Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | 6-2016 In design phase |  |  | 400000 | 400000 | 400000 | 400000 | 14 months - in design phase. | 50% |  |  |  | 400000 | No
10 | 1-HUR-16-62607 | 1-HUR-16-XXXXX | 1-HUR-16- | 62607 | 1-HUR-16-62607 | 1-HUR-16-62607 | Hurst District Office (Reg 1) HVAC Replacement 624 NE Loop 820 Hurst, Texas 76053 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren / Steve Haney | 6-2016 In design phase |  |  | 302623 | 302623 | 302623 | 302623 | 16 months - in design phase. | 50% |  |  |  | 302623 | No
11 | 5-WIC-16-62608 | 5-WIC-16-XXXXX | 5-WIC-16- | 62608 | 5-WIC-16-62608 | 5-WIC-16-62608 | Wichita Falls Sub-District Office (Reg 5) Roof Replacement 5505 N. Central Expressway Wichita Falls, Texas 79306 | Replace Roof - construction phase. (TFC is engineering roof replacement from Rider 45 DM funds) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Yen Nguyen |  |  |  | 200000 | 200000 | 200000 | 200000 | 2016-11-30 | 90% |  |  |  | 200000 | No
12 | 2-BEU-16-62609 | 2-BEU-16-XXXXX | 2-BEU-16- | 62609 | 2-BEU-16-62609 | 2-BEU-16-62609 | Beaumont District Office (Reg 2) HVAC Replacement 7200 Eastex Freeway Beaumont, Texas 77708 | Replacement of Heating Ventilation Air Conditioning (HVAC) Distribution System. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 315000 | 315000 | 315000 | 315000 | 12 months - in assessment phase. |  |  |  |  | 315000 | No
13 | 3-LAR-16-62610 | 3-LAR-16-XXXXX | 3-LAR-16- | 62610 | 3-LAR-16-62610 | 3-LAR-16-62610 | Laredo District Office (Reg 3) Vacant area refresh 1901 Bob Bullock Loop Laredo, Texas 78043 | Vacant lab area - Refresh all deteriorated finishes and systems, lighting, roof, HVAC, and other infrastructure serving that area. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Nat Oechsner |  |  |  | 150000 | 150000 | 150000 | 150000 | 16 months - in assessment phase. |  |  |  |  | 150000 | No
14 | 5-ABI-16-62611 | 5-ABI-16-XXXXX | 5-ABI-16- | 62611 | 5-ABI-16-62611 | 5-ABI-16-62611 | Abilene District Office (Reg 5) HVAC Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | TFC - Yen Nguyen |  |  |  | 260000 | 260000 | 260000 | 260000 | 24 months - In assessment phase. Negotiating IAC with TFC. |  |  |  |  | 260000 | No
15 | 1-CLE-16-62612 | 1-CLE-16-XXXXX | 1-CLE-16- | 62612 | 1-CLE-16-62612 | 1-CLE-16-62612 | Cleburne Area Office (Reg 1) HVAC Replacement 600 W. Kilpatrick St. Cleburne, Texas 76031 | Heating Ventilation Air Conditioning (HVAC) System replacement | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren | 6-2016 Steve is assessing the project |  |  | 325000 | 325000 | 325000 | 325000 | 14 months - in assessment phase. |  |  |  |  | 325000 | No
16 | 5-CHI-16-62613 | 5-CHI-16-XXXXX | 5-CHI-16- | 62613 | 5-CHI-16-62613 | 5-CHI-16-62613 | Childress Area Office (Reg 5) HVAC Replacement 1700 Ave. F Northwest Childress, Texas 79201 | Replacement of Heating Ventilation Air Conditioning (HVAC) System. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | TFC - Yen Nguyen |  |  |  | 500000 | 500000 | 500000 | 500000 | 18 months - In assessment phase. Negotiating IAC with TFC. |  |  |  |  | 500000 | No
17 | 2-HGR-16-62614 | 2-HGR-16-XXXXX | 2-HGR-16- | 62614 | 2-HGR-16-62614 | 2-HGR-16-62614 | Houston Grant Road Driver License Office (Reg 2) Drainage Repairs - 10503 Grant Road Houston, Texas 77070 | DL parking lot repairs and drainage deficiencies | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 250000 | 250000 | 250000 | 250000 | 14 months - in assessment phase. |  |  |  |  | 250000 | No
18 | 4-ODE-16-62615 | 4-ODE-16-XXXXX | 4-ODE-16- | 62615 | 4-ODE-16-62615 | 4-ODE-16-62615 | Odessa Area Office (Reg 4) HVAC Replacement 1910 IH-20 West Odessa, Texas 79762 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 6/3/16 Initial site visit made and photos of the spaces. HVAC information has been given to Steve Haney |  |  | 150714 | 150714 | 150714 | 150714 | 12 months - in assessment phase. |  |  |  |  | 150714 | No
19 | 4-GAT-16-62616 | 4-GAT-16-XXXXX | 4-GAT-16- | 62616 | 4-GAT-16-62616 | 4-GAT-16-62616 | El Paso Gateway East Driver License Office (Reg 4) HVAC Replacement 7300 Gateway East El Paso, Texas 79915 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 6-10-16 Bid closes | 16-R061559 |  | 200000 | 200000 | 200000 | 80000 | 2016-09-01 |  |  | 80000 |  | 0 | No
20 | HQ-L-16-62617 | HQ-L-16-XXXXX | HQ-L-16- | 62617 | HQ-L-16-62617 | HQ-L-16-62617 | Austin HQ (Building L) HVAC Replacement 5710 Guadalupe Austin, Texas 78752 | Partial RTU replacements - Building L - Fleet Operations | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 6-13-16 - 17.5 Ton 14 IEER Gas Heat Rooftop Unit $21K (Phase 1) |  |  | 78000 | 78000 | 78000 | 78000 | 6 months - in assessment phase. |  |  | 0 |  | 78000 | No
21 | HQ-GA-16-62618 | HQ-GA-16-XXXXX | HQ-GA-16- | 62618 | HQ-GA-16-62618 | HQ-GA-16-62618 | Austin HQ (Building G Annex) Chiller/Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace chillers/boilers in Building G Annex - Multi-Service Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 6-2016 - In design phase |  |  | 769600 | 769600 | 769600 | 769600 | 14 months - in design phase. | 25% |  |  |  | 769600 | No
22 | HQ-E-16-62619 | HQ-E-16-XXXXX | HQ-E-16- | 62619 | HQ-E-16-62619 | HQ-E-16-62619 | Austin HQ (Building E) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace boiler in Building E - Law Enforcement Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 6-2016 - In design phase |  |  | 78000 | 78000 | 78000 | 78000 | 14 months - in design phase. | 25% |  |  |  | 78000 | No
23 | HQ-C-16-62620 | HQ-C-16-XXXXX | HQ-C-16- | 62620 | HQ-C-16-62620 | HQ-C-16-62620 | Austin HQ (Building C) HVAC Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial HVAC replacement for Building C Training Academy | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Clay Bosworth |  |  |  | 520000 | 520000 | 520000 | 520000 | 12 months - in assessment phase. |  |  |  |  | 520000 | No
24 | HQ-A-16-62621 | HQ-A-16-XXXXX | HQ-A-16- | 62621 | HQ-A-16-62621 | HQ-A-16-62621 | Austin HQ (Building A) Roof Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial roof replacement for Building A | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 1040000 | 1040000 | 1040000 | 1040000 | 12 months - in assessment phase. |  |  |  |  | 1040000 | No
25 | HQ-E-16-62622 | HQ-E-16-XXXXX | HQ-E-16- | 62622 | HQ-E-16-62622 | HQ-E-16-62622 | Austin HQ (Building E) Roof Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial roof replacement for Building E - Law Enforcement Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 1787058 | 1787058 | 1787058 | 1787058 | 12 months - in assessment phase. |  |  |  |  | 1787058 | No
26 | HQ-O-16-62623 | HQ-O-16-XXXXX | HQ-O-16- | 62623 | HQ-O-16-62623 | HQ-O-16-62623 | Austin HQ (Building O) Sprinkler System 5601 Guadalupe Austin, Texas 78752 | Add Sprinklers (Fire Marshal recommendation) - Building O Fleet Operations | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren |  |  |  | 26000 | 26000 | 26000 | 26000 | 12 months - in assessment phase. |  |  |  |  | 26000 | No
27 | 2-CON-16-62624 | 2-CON-16-XXXXX | 2-CON-16- | 62624 | 2-CON-16-62624 | 2-CON-16-62624 | Conroe District Office (Reg 2) Ductwork Replacement 2 Hilbig St. Conroe, Texas 77301 | Ductwork replacement-system reviewed and found contaminants and poor IAQ in facility due to condition of ductwork. Funding request to replace all flex duct and have the hard duct cleaned and sealed. (Includes office and Motor Vehicle Theft (MVT) Garage | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 603870 | 603870 | 603870 | 603870 | 14 months - in assessment phase. |  |  |  |  | 603870 | No
28 | 1-GAR-16-62625 | 1-GAR-16-XXXXX | 1-GAR-16- | 62625 | 1-GAR-16-62625 | 1-GAR-16-62625 | Garland Regional Headquarters (Reg 1) Site Lighting Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged site lighting. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren |  |  |  | 134006 | 134006 | 134006 | 134006 | 12 months - in assessment phase. |  |  |  |  | 134006 | No
29 | 1-GAR-16-62626 | 1-GAR-16-XXXXX | 1-GAR-16- | 62626 | 1-GAR-16-62626 | 1-GAR-16-62626 | Garland Regional Headquarters (Reg 1) Electrical Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged electrical system | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren |  |  |  | 574870 | 574870 | 574870 | 574870 | 12 months - in assessment phase. |  |  |  |  | 574870 | No
30 | 1-GAR-16-62627 | 1-GAR-16-XXXXX | 1-GAR-16- | 62627 | 1-GAR-16-62627 | 1-GAR-16-62627 | Garland Regional Headquarters (Reg 1) Plumbing Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged plumbing (i.e.: Natural Gas system, domestic water system and fixtures, etc.) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren |  |  |  | 517577 | 517577 | 517577 | 517577 | 12 months - in assessment phase. |  |  |  |  | 517577 | No
31 | 1-GAR-16-62628 | 1-GAR-16-XXXXX | 1-GAR-16- | 62628 | 1-GAR-16-62628 | 1-GAR-16-62628 | Garland Regional Headquarters (Reg 1) Foundation Study 350 West IH-30 Garland, Texas 75043 | Several signs of stress and settlement is seen throughout the facility, specifically on the Westside of the building. Recommend a professional structural engineering study be conducted for resolution. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren |  |  |  | 150000 | 150000 | 150000 | 150000 | 12 months - in assessment phase. |  |  |  |  | 150000 | No
32 | 2-PIE-16-62629 | 2-PIE-16-XXXXX | 2-PIE-16- | 62629 | 2-PIE-16-62629 | 2-PIE-16-62629 | Pierce Sub-District Office (Reg 2) Foundation Study 19692 US Hwy 59 El Campo, Texas 77437 | Northwest wall and a part of Northeast wall are showings signs of structural degradation. Recommend professional study. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | TFC - Eddie King |  |  |  | 150000 | 150000 | 150000 | 150000 | 16 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 150000 | No
33 | 2-BAY-16-62630 | 2-BAY-16-XXXXX | 2-BAY-16- | 62630 | 2-BAY-16-62630 | 2-BAY-16-62630 | Baytown Area Office (Reg 2) Foundation Repairs 5420 Decker Drive Baytown, Texas 77520 | Repair foundation / interior finishes | Rider 40 | Rider 40 | General Revenue (Fund 0001) | TFC - Eddie King |  |  |  | 150000 | 150000 | 150000 | 150000 | 16 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 150000 | No
34 | 5-CHI-16-62631 | 5-CHI-16-XXXXX | 5-CHI-16- | 62631 | 5-CHI-16-62631 | 5-CHI-16-62631 | Childress Area Office (Reg 5) Foundation Study 1700 Ave. F Northwest Childress, Texas 79201 | The retaining walls are cracking and showing signs of structural problems. Recommend professional study. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | TFC - Eddie King |  |  |  | 150000 | 150000 | 150000 | 150000 | 16 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 150000 | No
35 | 1-SUL-16-62632 | 1-SUL-16-XXXXX | 1-SUL-16- | 62632 | 1-SUL-16-62632 | 1-SUL-16-62632 | Sulphur Springs Area Office (Reg 1) Foundation Study 1528 E. Shannon Road Sulphur Springs, Texas 75482 | Settlement cracks in foundation, exterior walls, and interior wall systems. Recommend a professional structural engineering study be conducted for resolution. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Jessica Warren |  |  |  | 150000 | 150000 | 150000 | 150000 | 12 months - in assessment phase. |  |  |  |  | 150000 | No
36 | 2-CON-16-62633 | 2-CON-16-XXXXX | 2-CON-16- | 62633 | 2-CON-16-62633 | 2-CON-16-62633 | Conroe District Office (Reg 2) Foundation Study 804 Interstate 45 South Conroe, Texas 77304 | Exterior walls are showing stress and damage at the MVT Garage. Recommend professional structure analysis to determine condition and repair of exterior wall and implement repairs. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 185000 | 185000 | 185000 | 185000 | 12 months - in assessment phase. |  |  |  |  | 185000 | No
37 | HQ-L-16-62634 | HQ-L-16-XXXXX | HQ-L-16- | 62634 | HQ-L-16-62634 | HQ-L-16-62634 | Austin HQ (Building L) Car Wash Replacement 5710 Guadalupe Austin, Texas 78752 | Replace car wash at Fleet Operations - Building L | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Clay Bosworth |  |  |  | 100000 | 100000 | 100000 | 100000 | 8 months - in assessment phase. |  |  |  |  | 100000 | No
38 | 4-ODE-16-62847 | 4-ODE-16-XXXXX | 4-ODE-16- | 62847 | 4-ODE-16-62847 | 4-ODE-16-62847 | Odessa Area Office (Reg 4) HVAC Replacement 1910 IH-20 West Odessa, Texas 79762 | Terminal & Package Units (Building Automation System) | 21 M | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 6/3/16 Initial site visit made and photos of the spaces. HVAC information has been given to Steve Haney |  |  | 234000 | 234000 | 234000 | 234000 | 12 months - in design phase | 5% |  |  |  | 234000 | No
39 | 4-ODE-16-62754 | 4-ODE-16-XXXXX | 4-ODE-16- | 62754 | 4-ODE-16-62754 | 4-ODE-16-62754 | Odessa Area Office (Reg 4) Roof Replacement 1910 IH-20 West Odessa, Texas 79762 | Roof Coverings/openings-built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 6/3/16 Site Assessment |  |  | 249600 | 249600 | 249600 | 249600 | 12 months - in assessment phase. |  |  |  |  | 249600 | No
40 | ST-FUEL-16-62739 | ST-FUEL-16-XXXXX | ST-FUEL-16- | 62739 | ST-FUEL-16-62739 | ST-FUEL-16-62739 | Statewide Fuel System Maintenance/Removal | UST/AST fueling systems repairs/maintenance/removal | 21 M | Rider 40 | General Revenue (Fund 0001) | Philip Johnson | 2/13/16 Plainview - Removed fuel (Riley Industrial Services) and Stat Inv Reconciliation for Temp removed from service (Total SIR LLC). | Feb 2016 Pcard $1857, Amarillo 3453.25, Seguin/New Braunfels $3870 |  | 250000 | 250000 | 250000 | 250000 | 18 months - Performing TCEQ compliance audit |  |  |  | 0 | 250000 | No
41 | 5-AMA-16-62740 | 5-AMA-16-XXXXX | 5-AMA-16- | 62740 | 5-AMA-16-62740 | 5-AMA-16-62740 | Amarillo District Office (Reg 5) Exterior Door/Window Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Exterior doors replacement/Window replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | Yen Nguyen |  |  |  | 167666.72 | 167666.72 | 167666.72 | 167666.72 | 14 months - in assessment phase. |  |  |  |  | 167666.72 | No
42 | 6-ADO-16-62741 | 6-ADO-16-XXXXX | 6-ADO-16- | 62741 | 6-ADO-16-62741 | 6-ADO-16-62741 | Austin District Office (Reg 6) HVAC Replacement 9000 IH-35 North Austin, Texas 78753 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 6-2016 Not started |  |  | 192294.48 | 192294.48 | 192294.48 | 192294.48 | 12 months - in assessment phase. |  |  |  |  | 192294.48 | No
43 | 6-ADO-16-62742 | 6-ADO-16-XXXXX | 6-ADO-16- | 62742 | 6-ADO-16-62742 | 6-ADO-16-62742 | Austin District Office (Reg 6) Roof Replacement 9000 IH-35 North Austin, Texas 78753 | Roof Coverings built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker |  |  |  | 338000 | 338000 | 338000 | 338000 | 12 months - in assessment phase. |  |  |  |  | 338000 | No
44 | 2-HHQ-16-62743 | 2-HHQ-16-XXXXX | 2-HHQ-16- | 62743 | 2-HHQ-16-62743 | 2-HHQ-16-62743 | Houston Regional Headquarters (West Road) Crime Lab (Reg 2) Chiller Replacement 12230 West Road Jersey Village, Texas 77065 | Chiller replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | Steve Haney |  |  |  | 312000 | 312000 | 312000 | 312000 | 14 months - in design phase. | 25% |  |  |  | 312000 | No
45 | 4-SAN-16-62744 | 4-SAN-16-XXXXX | 4-SAN-16- | 62744 | 4-SAN-16-62744 | 4-SAN-16-62744 | San Angelo Sub-District Office (Reg 4) HVAC Replacement 1600 W. Loop 306 San Angelo, Texas 76903 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 6/3/16 Initial site visit made and photos of the spaces. HVAC information has been given to Steve Haney |  |  | 633900.8 | 633900.8 | 633900.8 | 633900.8 | 14 months - in design phase. | 5% |  |  |  | 633900.8 | No
46 | 4-SAN-16-62745 | 4-SAN-16-XXXXX | 4-SAN-16- | 62745 | 4-SAN-16-62745 | 4-SAN-16-62745 | San Angelo Sub-District Office (Reg 4) Roof Replacement 1600 W. Loop 306 San Angelo, Texas 76903 | Roof Coverings built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis |  |  |  | 325000 | 325000 | 325000 | 325000 | 12 months - in assessment phase. |  |  |  |  | 325000 | No
47 | 1-HUR-16-62746 | 1-HUR-16-XXXXX | 1-HUR-16- | 62746 | 1-HUR-16-62746 | 1-HUR-16-62746 | Hurst Sub-District Office (Reg 1) Roof Replacement 624 NE Loop 820 Hurst, Texas 76053 | Roof Coverings built-up roofing replacement (Including roof openings) | 21 M | Rider 40 | General Revenue (Fund 0001) | Jessica Warren |  |  |  | 430981.2 | 430981.2 | 430981.2 | 430981.2 | 16 months - in assessment phase. |  |  |  |  | 430981.2 | No
48 | 3-EAG-16-62747 | 3-EAG-16-XXXXX | 3-EAG-16- | 62747 | 3-EAG-16-62747 | 3-EAG-16-62747 | Eagle Pass Area Office (Reg 3) HVAC Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Terminal & package units replacement/upgrade (Add BAS as needed) | 21 M | Rider 40 | General Revenue (Fund 0001) | Nat Oechsner |  |  |  | 10000 | 10000 | 10000 | 10000 | 12 months - in assessment phase. |  |  |  |  | 10000 | No
49 | 3-HAR-16-62748 | 3-HAR-16-XXXXX | 3-HAR-16- | 62748 | 3-HAR-16-62748 | 3-HAR-16-62748 | Harlingen Area Office (Reg 3) Roof Replacement 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Roof Coverings built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | Nat Oechsner |  |  |  | 325000 | 325000 | 325000 | 325000 | 12 months - in assessment phase. |  |  |  |  | 325000 | No
50 | 3-BEE-16-62749 | 3-BEE-16-XXXXX | 3-BEE-16- | 62749 | 3-BEE-16-62749 | 3-BEE-16-62749 | Beeville Area Office (Reg 3) HVAC Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Terminal & package units replacement/upgrade (Add BAS as needed) | 21 M | Rider 40 | General Revenue (Fund 0001) | Nat Oechsner |  |  |  | 10000 | 10000 | 10000 | 10000 | 12 months - in assessment phase. |  |  |  |  | 10000 | No
51 | 3-BEE-16-62750 | 3-BEE-16-XXXXX | 3-BEE-16- | 62750 | 3-BEE-16-62750 | 3-BEE-16-62750 | Beeville Area Office (Reg 3) Roof Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Roof Coverings built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | Nat Oechsner |  |  |  | 150000 | 150000 | 150000 | 150000 | 12 months - in assessment phase. |  |  |  |  | 150000 | No
52 | 4-BIG-16-62751 | 4-BIG-16-XXXXX | 4-BIG-16- | 62751 | 4-BIG-16-62751 | 4-BIG-16-62751 | Big Spring Area Office (Reg 4) HVAC Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Terminal & package units replacement/upgrade - including split DX (Add BAS as needed) | 21 M | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | 6/3/16 Initial site visit made and photos of the spaces. HVAC information has been given to Steve Haney |  |  | 2954.64 | 2954.64 | 2954.64 | 2954.64 | 12 months - in design phase | 5% |  |  |  | 2954.64 | No
53 | ST-PM-16-62635 | ST-PM-16-XXXXX | ST-PM-16- | 62635 | ST-PM-16-62635 | ST-PM-16-62635 | Statewide TFC Project Mgmt. Fees | TFC Project Management fees. | Rider 40 | Rider 40 | General Revenue (Fund 0001) |  |  |  |  | 616800 | 616800 | 300000 | 300000 | Duration of projects Negotiating IAC with TFC. |  |  |  |  | 300000 | No
54 | HQ-C-16-62904 | HQ-C-16-62904 | HQ-C-16- | 62904 | HQ-C-16- 62904 | HQ-C-16- 62904 | Austin HQ (Building C) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Boiler replacement (two boilers supporting original building) | 21 M - GO Bond Funded | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Steve Haney | 3-25-16 sent EPS to Vivian. Approved - will use bond; in the bid process; Bid Opening 6-16-16 | 405-16-R058997 |  | 0 | 0 | 100000 | 100000 | 6 months - in bid phase | 100% |  | 100000 |  | 0 | No
55 | 2-BRE-16-62752 | 2-BRE-16-XXXXX | 2-BRE-16- | 62752 | 2-BRE-16-62752 | 2-BRE-16-62752 | Brenham Area Office (Reg 2) HVAC Controls Replacement 975 Hwy 290 West. Brenham, Texas 77834 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker |  |  |  | 168720.24 | 168720.24 | 168720.24 | 168720.24 | 12 months - in assessment phase. |  |  |  |  | 168720.24 | No
56 | 2-BRE-16-62753 | 2-BRE-16-XXXXX | 2-BRE-16- | 62753 | 2-BRE-16-62753 | 2-BRE-16-62753 | Brenham Area Office (Reg 2) Roof Replacement 975 Hwy 290 West. Brenham, Texas 77834 | Roof Coverings built-up roofing replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker |  |  |  | 130000 | 130000 | 130000 | 130000 | 12 months - in assessment phase. |  |  |  |  | 130000 | No
57 | 2-ORA-16-62755 | 2-ORA-16-XXXXX | 2-ORA-16- | 62755 | 2-ORA-16-62755 | 2-ORA-16-62755 | Orange Area Office (Reg 2) Roof Replacement 711 South Hwy 87 Orange, Texas 77630 | Roof Coverings built-up roofing replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker |  |  |  | 182000 | 182000 | 182000 | 182000 | 12 months - in assessment phase. |  |  |  |  | 182000 | No
58 | 4-OZO-16-62756 | 4-OZO-16-XXXXX | 4-OZO-16- | 62756 | 4-OZO-16-62756 | 4-OZO-16-62756 | Ozona Area Office (Reg 4) HVAC Replacement 1503 Monterey St Ozona, Texas 76943 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | AnnMarie Davis | Steve will assess remaining two units not replaced a couple of years ago and add DDC. |  |  | 132242.24 | 132242.24 | 132242.24 | 132242.24 | 12 months - in assessment phase. |  |  |  |  | 132242.24 | No
59 | 4-Pec-16-62757 | 4-Pec-16-XXXXX | 4-Pec-16- | 62757 | 4-Pec-16-62757 | 4-Pec-16-62757 | Pecos Area Office (Reg 4) HVAC Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Terminal & package units replacement/upgrade (Add BAS as needed), Distribution systems, controls and instrumentation replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | AnnMarie Davis |  |  |  | 117413.92 | 117413.92 | 117413.92 | 117413.92 | 12 months - in assessment phase. |  |  |  |  | 117413.92 | No
60 | 4-Pec-16-62758 | 4-Pec-16-XXXXX | 4-Pec-16- | 62758 | 4-Pec-16-62758 | 4-Pec-16-62758 | Pecos Area Office (Reg 4) Roof Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Roof Coverings built-up roofing replacement/roof openings | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | AnnMarie Davis |  |  |  | 133023.28 | 133023.28 | 133023.28 | 133023.28 | 12 months - in assessment phase. |  |  |  |  | 133023.28 | No
61 | 3-UVA-16-62759 | 3-UVA-16-XXXXX | 3-UVA-16- | 62759 | 3-UVA-16-62759 | 3-UVA-16-62759 | Uvalde Area Office (Reg 3) Roof Replacement 2901 E. Main Uvalde, Texas 78801 | Roof Coverings built-up roofing replacement/roof openings | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 102397.2 | 102397.2 | 102397.2 | 102397.2 | 14 months - in assessment phase. |  |  |  |  | 102397.2 | No
62 | 1-GAR-16-62760 | 1-GAR-16-XXXXX | 1-GAR-16- | 62760 | 1-GAR-16-62760 | 1-GAR-16-62760 | Garland Regional Headquarters Site (Reg 1) Communication & Security 350 West IH-30 Garland, Texas 75043 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren |  |  |  | 49042.24 | 49042.24 | 49042.24 | 49042.24 | 14 months - in assessment phase. |  |  |  |  | 49042.24 | No
63 | 1-GAR-16-62761 | 1-GAR-16-XXXXX | 1-GAR-16- | 62761 | 1-GAR-16-62761 | 1-GAR-16-62761 | Garland Regional Headquarters Site (Reg 1) Landscaping Upgrade 350 West IH-30 Garland, Texas 75043 | Landscaping (xeriscape) upgrade | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren |  |  |  | 98962.24 | 98962.24 | 98962.24 | 98962.24 | 14 months - in assessment phase. |  |  |  |  | 98962.24 | No
64 | 1-GAR-16-62762 | 1-GAR-16-XXXXX | 1-GAR-16- | 62762 | 1-GAR-16-62762 | 1-GAR-16-62762 | Garland Regional Headquarters Site (Reg 1) Parking Lot Replacement 350 West IH-30 Garland, Texas 75043 | Parking lot/pedestrian paving/driveways replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren |  |  |  | 789058.4 | 789058.4 | 789058.4 | 789058.4 | 14 months - in assessment phase. |  |  |  |  | 789058.4 | No
65 | 1-GAR-16-62763 | 1-GAR-16-XXXXX | 1-GAR-16- | 62763 | 1-GAR-16-62763 | 1-GAR-16-62763 | Garland Regional Headquarters Site (Reg 1) Sanitary Sewer Replacement 350 West IH-30 Garland, Texas 75043 | Sanitary sewer replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren |  |  |  | 24553.36 | 24553.36 | 24553.36 | 24553.36 | 14 months - in assessment phase. |  |  |  |  | 24553.36 | No
66 | 1-GAR-16-62764 | 1-GAR-16-XXXXX | 1-GAR-16- | 62764 | 1-GAR-16-62764 | 1-GAR-16-62764 | Garland Regional Headquarters Site (Reg 1) Site Development 350 West IH-30 Garland, Texas 75043 | Site Development (i.e.: Storm water system, etc.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren |  |  |  | 287119.04 | 287119.04 | 287119.04 | 287119.04 | 14 months - in assessment phase. |  |  |  |  | 287119.04 | No
67 | 1-GAR-16-62765 | 1-GAR-16-XXXXX | 1-GAR-16- | 62765 | 1-GAR-16-62765 | 1-GAR-16-62765 | Garland Regional Headquarters Site (Reg 1) Water Supply Upgrade 350 West IH-30 Garland, Texas 75043 | Water Supply upgrade/replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren |  |  |  | 67370.16 | 67370.16 | 67370.16 | 67370.16 | 14 months - in assessment phase. |  |  |  |  | 67370.16 | No
68 | 2-PIE-16-62766 | 2-PIE-16-XXXXX | 2-PIE-16- | 62766 | 2-PIE-16-62766 | 2-PIE-16-62766 | Pierce Sub-District Office (Reg 2) Ductwork Replacement 19692 US Hwy 59 El Campo, Texas 77437 | Duct work and insulation replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker |  |  |  | 62400 | 62400 | 62400 | 62400 | 12 months - in assessment phase. |  |  |  |  | 62400 | Yes
69 | 2-BRE-16-62767 | 2-BRE-16-XXXXX | 2-BRE-16- | 62767 | 2-BRE-16-62767 | 2-BRE-16-62767 | Brenham Area Office (Reg 2) Exterior Wall Repair 975 Hwy 290 West. Brenham, Texas 77834 | Exterior walls repair | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker |  |  |  | 10773.36 | 10773.36 | 10773.36 | 10773.36 | 6 months - in assessment phase. |  |  |  |  | 10773.36 | No
70 | 2-HHQ-16-62768 | 2-HHQ-16-XXXXX | 2-HHQ-16- | 62768 | 2-HHQ-16-62768 | 2-HHQ-16-62768 | Houston Regional Headquarters (West Road) (Reg 2) Security System Replacement 12230 West Road Jersey Village, Texas 77065 | Security system replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker |  |  |  | 208000 | 208000 | 208000 | 208000 | 14 months - in assessment phase. |  |  |  |  | 208000 | No
71 | 4-MID-16-62769 | 4-MID-16-XXXXX | 4-MID-16- | 62769 | 4-MID-16-62769 | 4-MID-16-62769 | Midland Sub District Office (Reg 4) Vacant DL Remodel/Refresh 2405 S. Loop 250 West Midland, Texas 79703 | Remodel vacant DL area including to replacing deteriorated finishes and MEP systems | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | AnnMarie Davis | 6-2-16 Site Assessment |  |  | 442000 | 442000 | 442000 | 442000 | 18 months - in assessment phase. |  |  |  |  | 442000 | No
72 | 5-AMA-16-62770 | 5-AMA-16-XXXXX | 5-AMA-16- | 62770 | 5-AMA-16-62770 | 5-AMA-16-62770 | Amarillo District Office (Reg 5) Security System Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Security system replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen |  |  |  | 343698.16 | 343698.16 | 343698.16 | 343698.16 | 18 months - in assessment phase. |  |  |  |  | 343698.16 | No
73 | 5-AMA-16-62771 | 5-AMA-16-XXXXX | 5-AMA-16- | 62771 | 5-AMA-16-62771 | 5-AMA-16-62771 | Amarillo District Office (Reg 5) Sprinkler System 4200 Canyon Dr. Amarillo, Texas 79109 | Sprinkler System | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen |  |  |  | 153180.56 | 153180.56 | 153180.56 | 153180.56 | 18 months - in assessment phase. |  |  |  |  | 153180.56 | No
74 | 5-AMA-16-62772 | 5-AMA-16-XXXXX | 5-AMA-16- | 62772 | 5-AMA-16-62772 | 5-AMA-16-62772 | Amarillo District Office (Reg 5) Foundation Study/Repair 4200 Canyon Dr. Amarillo, Texas 79109 | Standard Foundations | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen |  |  |  | 40278.16 | 40278.16 | 40278.16 | 40278.16 | 12 months - in assessment phase. |  |  |  |  | 40278.16 | No
75 | 5-AMA-16-62773 | 5-AMA-16-XXXXX | 5-AMA-16- | 62773 | 5-AMA-16-62773 | 5-AMA-16-62773 | Amarillo District Office (Reg 5) Interior Finishes Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen | 6-2016 - this is a phased project and will begin in spring of 2017 when DL is expected to relocate to a leased facility. |  |  | 575051.36 | 575051.36 | 575051.36 | 575051.36 | 24 months - in assessment phase. |  |  |  |  | 575051.36 | Yes
76 | 5-AMA-16-62774 | 5-AMA-16-XXXXX | 5-AMA-16- | 62774 | 5-AMA-16-62774 | 5-AMA-16-62774 | Amarillo District Office (Reg 5) Fittings Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Fittings (Specialties) replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen |  |  |  | 17077.84 | 17077.84 | 17077.84 | 17077.84 | 12 months - in assessment phase. |  |  |  |  | 17077.84 | No
77 | 6-ADO-16-62775 | 6-ADO-16-XXXXX | 6-ADO-16- | 62775 | 6-ADO-16-62775 | 6-ADO-16-62775 | Austin District Office Site (Reg 6) Parking Lot Replacement 9000 IH-35 North Austin, Texas 78753 | Parking lot replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth |  |  |  | 260000 | 260000 | 260000 | 260000 | 14 months - in assessment phase. |  |  |  |  | 260000 | No
78 | 6-ADO-16-62776 | 6-ADO-16-XXXXX | 6-ADO-16- | 62776 | 6-ADO-16-62776 | 6-ADO-16-62776 | Austin District Office Site (Reg 6) Site Lighting Replacement/Upgrade 9000 IH-35 North Austin, Texas 78753 | Site Lighting | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth |  |  |  | 57117.84 | 57117.84 | 57117.84 | 57117.84 | 14 months - in assessment phase. |  |  |  |  | 57117.84 | No
79 | 6-ADO-16-62777 | 6-ADO-16-XXXXX | 6-ADO-16- | 62777 | 6-ADO-16-62777 | 6-ADO-16-62777 | Austin District Office Site (Reg 6) Communication & Security 9000 IH-35 North Austin, Texas 78753 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth |  |  |  | 22046.96 | 22046.96 | 22046.96 | 22046.96 | 14 months - in assessment phase. |  |  |  |  | 22046.96 | No
80 | 6-ADO-16-62778 | 6-ADO-16-XXXXX | 6-ADO-16- | 62778 | 6-ADO-16-62778 | 6-ADO-16-62778 | Austin District Office Storage Hwy Patrol (Reg 6) Special Structures 9000 IH-35 North Austin, Texas 78753 | Special Structures - Storage Bldg. < 1000sf | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth |  |  |  | 12728.56 | 12728.56 | 12728.56 | 12728.56 | 14 months - in assessment phase. |  |  |  |  | 12728.56 | No
81 | 5-ABI-16-62779 | 5-ABI-16-XXXXX | 5-ABI-16- | 62779 | 5-ABI-16-62779 | 5-ABI-16-62779 | Abilene District Office (Reg 5) Security/Site System Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Security system replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth |  |  |  | 220581.92 | 220581.92 | 220581.92 | 220581.92 | 14 months - in assessment phase. |  |  |  |  | 220581.92 | No
82 | 3-LAR-16-62780 | 3-LAR-16-XXXXX | 3-LAR-16- | 62780 | 3-LAR-16-62780 | 3-LAR-16-62780 | Laredo District Office (Reg 3) Ceiling Replacement 1901 Bob Bullock Loop Laredo, Texas 78043 | Ceiling/wall finishes replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 389896.32 | 389896.32 | 389896.32 | 389896.32 | 14 months - in assessment phase. |  |  |  |  | 389896.32 | No
83 | 3-LAR-16-62781 | 3-LAR-16-XXXXX | 3-LAR-16- | 62781 | 3-LAR-16-62781 | 3-LAR-16-62781 | Laredo District Office (Reg 3) Security System Replacement 1901 Bob Bullock Loop Laredo, Texas 78043 | Security system replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 373251.84 | 373251.84 | 373251.84 | 373251.84 | 14 months - in assessment phase. |  |  |  |  | 373251.84 | No
84 | 6-WAC-16-62782 | 6-WAC-16-XXXXX | 6-WAC-16- | 62782 | 6-WAC-16-62782 | 6-WAC-16-62782 | Waco District Office (Reg 6) Interior Finishes Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth |  |  |  | 567938.8 | 567938.8 | 567938.8 | 567938.8 | 14 months - in assessment phase. |  |  |  |  | 567938.8 | No
85 | 6-WAC-16-62783 | 6-WAC-16-XXXXX | 6-WAC-16- | 62783 | 6-WAC-16-62783 | 6-WAC-16-62783 | Waco District Office (Reg 6) Fixed Furnishings Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Fixed furnishings replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth |  |  |  | 137846.8 | 137846.8 | 137846.8 | 137846.8 | 14 months - in assessment phase. |  |  |  |  | 137846.8 | No
86 | 3-EAG-16-62784 | 3-EAG-16-XXXXX | 3-EAG-16- | 62784 | 3-EAG-16-62784 | 3-EAG-16-62784 | Eagle Pass Area Office (Reg 3) Interior Finishes Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 186283.86 | 186283.86 | 186283.86 | 186283.86 | 14 months - in assessment phase. |  |  |  |  | 186283.86 | No
87 | 3-EAG-16-62785 | 3-EAG-16-XXXXX | 3-EAG-16- | 62785 | 3-EAG-16-62785 | 3-EAG-16-62785 | Eagle Pass Area Office (Reg 3) Electrical Systems 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Other Electrical Systems (Repair illuminated exit signs throughout the facility and add emergency lighting where needed.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 150000 | 150000 | 150000 | 150000 | 14 months - in assessment phase. |  |  |  |  | 150000 | No
88 | 3-EAG-16-62786 | 3-EAG-16-XXXXX | 3-EAG-16- | 62786 | 3-EAG-16-62786 | 3-EAG-16-62786 | Eagle Pass Area Office (Reg 3) Security System Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Security system replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 125000 | 125000 | 125000 | 125000 | 14 months - in assessment phase. |  |  |  |  | 125000 | No
89 | 3-EAG-16-62787 | 3-EAG-16-XXXXX | 3-EAG-16- | 62787 | 3-EAG-16-62787 | 3-EAG-16-62787 | Eagle Pass Area Office (Reg 3) Sprinkler System 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Sprinkler System | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 49622.56 | 49622.56 | 49622.56 | 49622.56 | 14 months - in assessment phase. |  |  |  |  | 49622.56 | No
90 | 3-EAG-16-62788 | 3-EAG-16-XXXXX | 3-EAG-16- | 62788 | 3-EAG-16-62788 | 3-EAG-16-62788 | Eagle Pass Site (Reg 3) Communication & Security 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 9984 | 9984 | 9984 | 9984 | 14 months - in assessment phase. |  |  |  |  | 9984 | No
91 | 3-EAG-16-62789 | 3-EAG-16-XXXXX | 3-EAG-16- | 62789 | 3-EAG-16-62789 | 3-EAG-16-62789 | Eagle Pass Site (Reg 3) Landscaping Upgrade 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Landscaping (xeriscape) upgrade | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 4285.84 | 4285.84 | 4285.84 | 4285.84 | 14 months - in assessment phase. |  |  |  |  | 4285.84 | No
92 | 3-EAG-16-62790 | 3-EAG-16-XXXXX | 3-EAG-16- | 62790 | 3-EAG-16-62790 | 3-EAG-16-62790 | Eagle Pass Site (Reg 3) Site Lighting Replacement/Upgrade 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Site Lighting | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner |  |  |  | 20368.4 | 20368.4 | 20368.4 | 20368.4 | 14 months - in assessment phase. |  |  |  |  | 20368.4 | No
93 | 5-AMA-16-62791 | 5-AMA-16-XXXXX | 5-AMA-16- | 62791 | 5-AMA-16-62791 | 5-AMA-16-62791 | Amarillo MVT Building (Reg 5) Electrical Systems 4200 Canyon Dr. Amarillo, Texas 79109 | Other Electrical Systems (Add illuminated exit signs throughout the facility and add emergency lighting where needed.) | 21 M | Rider 40 | General Revenue (Fund 0001) | Yen Nguyen | Life Safety Issue - completed with Regional Index 29011 - pCard. Was informed this project was completed by the field staff on 6/14/16. |  |  | 260 | 260 | 260 | 260 | 2015-08-26 |  |  | 0 | 0 | 260 | No
94 | 5-AMA-16-62792 | 5-AMA-16-XXXXX | 5-AMA-16- | 62792 | 5-AMA-16-62792 | 5-AMA-16-62792 | Amarillo Site (Reg 5) Communication & Security 4200 Canyon Dr. Amarillo, Texas 79109 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen |  |  |  | 25084.8 | 25084.8 | 25084.8 | 25084.8 | 12 months - in assessment phase. |  |  |  |  | 25084.8 | No
95 | 5-AMA-16-62793 | 5-AMA-16-XXXXX | 5-AMA-16- | 62793 | 5-AMA-16-62793 | 5-AMA-16-62793 | Amarillo Site (Reg 5) Fuel Distribution Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Fuel distribution replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen |  |  |  | 46800 | 46800 | 46800 | 46800 | 18 months - in assessment phase. |  |  |  |  | 46800 | No
96 | 5-AMA-16-62794 | 5-AMA-16-XXXXX | 5-AMA-16- | 62794 | 5-AMA-16-62794 | 5-AMA-16-62794 | Amarillo Site (Reg 5) Parking Lot/Pedestrian Paving 4200 Canyon Dr. Amarillo, Texas 79109 | Parking lot/pedestrian paving replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen |  |  |  | 291766.8 | 291766.8 | 291766.8 | 291766.8 | 12 months - in assessment phase. |  |  |  |  | 291766.8 | No
97 | 5-AMA-16-62795 | 5-AMA-16-XXXXX | 5-AMA-16- | 62795 | 5-AMA-16-62795 | 5-AMA-16-62795 | Amarillo Site (Reg 5) Site Lighting Replacement/Upgrade 4200 Canyon Dr. Amarillo, Texas 79109 | Site Lighting | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Yen Nguyen |  |  |  | 65007.28 | 65007.28 | 65007.28 | 65007.28 | 18 months - in assessment phase. |  |  |  |  | 65007.28 | No
98 | HQ-A-16-62796 | HQ-A-16-XXXXX | HQ-A-16- | 62796 | HQ-A-16-62796 | HQ-A-16-62796 | Austin HQ (Building A) AHU/FCU Replacement 5805 North Lamar Blvd Austin, Texas 78752 | HVAC - replace all AHU and FCUs not already in process/completed | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Steve Haney | 6-2016 - In design phase |  |  | 520000 | 520000 | 520000 | 520000 | 16 months - in design phase. | 25% |  |  |  | 520000 | No
99 | HQ-A-16-62797 | HQ-A-16-XXXXX | HQ-A-16- | 62797 | HQ-A-16-62797 | HQ-A-16-62797 | Austin HQ (Building A) DDC Retrofit 5805 North Lamar Blvd Austin, Texas 78752 | HVAC - retrofit existing pneumatic controls to DDC | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Steve Haney | 6-2016 - In design phase |  |  | 62400 | 62400 | 62400 | 62400 | 16 months - in design phase. | 3% |  |  |  | 62400 | No
100 | 2-BRY-16-XXXXX | 2-BRY-16-XXXXX | 2-BRY-16- | 62896 | 2-BRY-16- 62896 | 2-BRY-16- 62896 | Bryan District Office (Reg 2) Foundation/Drainage Modifications 2571 North Earl Rudder Freeway Bryan, Texas 77805 | Foundation/site drainage modifications | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Michael Studebaker | DPS had no changes to drawings. Still waiting for IAC from TFC. |  |  | 0 | 0 | 650000 | 650000 | 12 months - waiting for IAC from TFC to proceed to contstruction phase. | 100% | 0% |  |  | 650000 | No
101 | 6-WTR-16-XXXX | 6-WTR-16-XXXX | 6-WTR-16- | 62897 | 6-WTR-16- 62897 | 6-WTR-16- 62897 | Waco Texas Rangers Headquarters and Education Center (Reg 6) HVAC Replacement 102 Texas Ranger Trail Waco, Texas 76705 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Steve Haney | 6-2016 - In design phase |  |  | 0 | 0 | 350000 | 350000 | 16 months - in design phase. |  |  |  |  | 350000 | No
102 | 1-TER-16-XXXXX | 1-TER-16-XXXXX | 1-TER-16- | 62899 | 1-TER-16- 62899 | 1-TER-16- 62899 | Terrell Area Office (Reg 1) Drainage Repairs 111 Tejas Drive Terrell, Texas 75160 | Site drainage repairs | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Eddie King |  |  |  | 0 | 0 | 100000 | 100000 | 14 months - in assessment phase. |  |  |  |  | 100000 | No
103 | 3-EAG-16-62900 | 3-EAG-16-XXXXX | 3-EAG-16- | 62900 | 3-EAG-16- 62900 | 3-EAG-16- 62900 | Eagle Pass Area Office (Reg 3) Foundation/Drainage Modifications 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Foundation/site drainage modifications | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Nat Oechsner | Awarded to Grassroots Construction & Maintenance on 3/24/16 (PO7175 for $4275) | 16-R052096 | 16-P007175 | 0 | 0 | 100000 | 100000 | 14 months - Consultant in assessment phase. |  |  | 4275 |  | 95725 | No
104 | 6-ANW-16-XXXXX | 6-ANW-16-XXXXX | 6-ANW-16- | 62901 | 6-ANW-16- 62901 | 6-ANW-16- 62901 | Austin Northwest Area Office (Reg 6) Interior Finish Replacement 13730 Research Boulevard Austin, Texas 78750 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Jessica Warren | 6-13-16 Design has been completed. Cost est expected in 2 wks. |  |  | 0 | 0 | 50000 | 50000 | 12 months - waiting for cost estimate. | 100% |  |  |  | 50000 | No
105 | HQ-L-16-XXXXX | HQ-L-16-XXXXX | HQ-L-16- | 62903 | HQ-L-16- 62903 | HQ-L-16- 62903 | Austin HQ (Building L) Car Lift Replacement 5710 Guadalupe Austin, Texas 78752 | Replace 18 original car lifts that are no longer functioning, leaking hydraulic oil, or not operating effectively. | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. | Clay Bosworth |  |  |  | 0 | 0 | 100000 | 100000 | 12 months - in assessment phase. |  |  |  |  | 100000 | No
106 | ST-CON-16-62636 | ST-CON-16-XXXXX | ST-CON-16- | 62636 | ST-CON-16-62636 | ST-CON-16-62636 | Statewide Unexpected DM repairs/Project Contingency | Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. | Rider 40 | Rider 40 | General Revenue (Fund 0001) |  |  |  |  | 1529759 | 1529759 | 1760161 | 1625113.19 | Duration of projects. Negotiating IAC with TFC. |  |  |  |  | 1625113.19 | No
107 | ST-CON-16-62461 | ST-CON-16-XXXXX | ST-CON-16- | 62461 | ST-CON-16-62461 | ST-CON-16-62461 | Statewide Unexpected DM repairs/Project Contingency Childress Area Office (Reg 5) Roof Replacement 1700 Ave. F Northwest Childress, Texas 79201 | Replace Childress radio shop roof (Roof is leaking and contains asbestos) 3/24/16 - entered req. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | Yen Nguyen | 6-11-16 Award has been made. Currently in backgroumd checks | Req 16-R058830 |  | 0 | 0 | 50000 | 50000 | 2016-08-31 |  |  | 50000 |  | 0 | No
108 | 4-ALP-16-62461 | 4-ALP-16-XXXXX | 4-ALP-16- | 62902 | 4-ALP-16- 62902 | 4-ALP-16-62461 | Alpine Area Office (Reg 4) Energy Efficiency Project 3500 North Highway 118 Alpine, Texas 79830 | Add ceiling insulation to increase energy efficiency to assist HVAC system to better control temperature in open ceiling area. | 21 M - GO Bond Funded | Rider 40 | General Revenue (Fund 0001) | AnnMarie Davis | Vivian uploaded in EPS 5-4-16. | 16-R063449 |  | 0 | 0 | 60000 | 60000 | 6 months - in bid phase | 100% |  | 60000 |  | 0 | No
109 | 2-Gal-16-62441 | 2-Gal-16-XXXXX | 2-Gal-16- | 62441 | 2-Gal-16-62441 | 2-Gal-16-62441 | Galveston Driver License Office (Reg 2) Replace Failed RTU 6802 Broadway Galveston, Texas 77554 | Replace failed 10-ton RTU |  | Rider 40 | General Revenue (Fund 0001) | Michael Studebaker / Steve Haney | Awarded to Rincon Air & Heat Company (Org $15,888 - CO1 - $425) | 16-R041711 | 16-P005343 |  |  |  | 16313 | 2016-04-04 |  | 100% | 15240 | 1073 | 0 | No
110 | 4-EHQ-16-62441 | 4-EHQ-16-XXXXX | 4-EHQ-16- | 62441 | 4-EHQ-16-62441 | 4-EHQ-16-62441 | El Paso Regional Headquarters (Reg 4) RTU Replacement 11612 Scott Simpson El Paso, Texas 79936 | Replace failed 2.5 Ton RTU (Commander's area) |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded toPC Automated Controls on 4/19/16. Unit is being manufactured. Will be installed in the winter months. Current unit was repaired. | 16-R056011 | PO07532 |  |  |  | 6982.51 | 2016-12-01 |  | 100% | 6982.51 | 0 | 0 | No
111 | 1-Min-16-62441 | 1-Min-16-XXXXX | 1-Min-16- | 62441 | 1-Min-16-62441 | 1-Min-16-62441 | Mineral Wells Area Office (Reg 1) RTU Replacement 600 FM 1821 North Mineral Wells, Texas 76067 | Replace failed 5 ton RTU. |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to LOVIC HVAC on 11/18/15 | 16-R041768 | P005521 |  |  |  | 9100 | 2015-11-27 |  | 100% | 0 | 9100 | 0 | No
112 | 2-BAY-16-62441 | 2-BAY-16-XXXXX | 2-BAY-16- | 62441 | 2-BAY-16-62441 | 2-BAY-16-62441 | Baytown Area Office (Reg 2) RTU Replacement 5420 Decker Drive Baytown, Texas 77520 | Replace failed 3 ton RTU |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to ABM Building Services | 16-R039687 | 16-P005593 |  |  |  | 10534 | 2016-03-10 |  | 100% | 0 | 10534 | 0 | No
113 | HQ-TTC-16-62441 | HQ-TTC-16-XXXXX | HQ-TTC-16- | 62441 | HQ-TTC-16-62441 | HQ-TTC-16-62441 | Tactical Training Center (HQ) RTU Replacement 820 CR 240 Florence, Texas 76527 | Replace failed 2 ton RTU |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to K-Air Corp | 16-R039876 | 16-P005605 |  |  |  | 9850.5 | 2016-02-22 |  | 100% | 0 | 9850.5 | 0 | No
114 | 3-DEL-16-62431 | 3-DEL-16-XXXXX | 3-DEL-16- | 62431 | 3-DEL-16-62431 | 3-DEL-16-62431 | Del Rio Sub District Office (Reg 3) Water Heater Replacement 2012 Veteran Boulevard Del Rio, Texas 78840 | Replace failed water heater |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Rudy Robles Plumbing | 16-R44844 | 16-P005628 |  |  |  | 3310 | 2015-12-16 |  | 100% | 0 | 0 | 3310 | No
115 | HQ-L-16-62441 | HQ-L-16-XXXXX | HQ-L-16 | 62441 | HQ-L-1662441 | HQ-L-16-62441 | Austin HQ (Building L) Shop Heaters Replacement 5710 Guadalupe Austin, Texas 78752 | Replace 6 outdated gas fired shop heaters (Labor only) and install 5 natural gas shop heaters. |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Clinton McFerrin | 16-R041205 | 16-P005733 |  |  |  | 3971 | 2015-12-08 |  | 100% | 0 | 3971 | 0 | No
116 | 2-ROS-16-62481 | 2-ROS-16-XXXXX | 2-ROS-16- | 62481 | 2-ROS-16-62481 | 2-ROS-16-62481 | Rosenberg Area Office (Reg 2) Water Line Replacement 5505 Avenue N. Rosenberg, TX 77471-5640 | Water Line Replacement due to line breakage |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Gregory Edwards | 16-R046793 | 16-P005785 |  |  |  | 20362 | 2016-01-06 |  | 100% | 20362 | 0 | 0 | No
117 | 2-ANG-16-62441 | 2-ANG-16-XXXXX | 2-ANG-16- | 62441 | 2-ANG-16-62441 | 2-ANG-16-62441 | Angleton Driver License Office (Reg 2) RTU Replacement 501 South Velasco Angleton, Texas 77515 | Replace failed 5 ton RTU. |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Rincon Air and Heat Company on 12/14/15 | 16-R043084 | 16-P005922 |  |  |  | 14833 | 2016-02-12 |  | 100% | 14833 |  | 0 | No
118 | 1-GCL-16-62441 | 1-GCL-16-XXXXX | 1-GCL-16- | 62441 | 1-GCL-16-62441 | 1-GCL-16-62441 | Garland Crime Laboratory (Reg 1) BTU Boiler Replacement 402 West IH-30 Garland, Texas 75043 | Replace 2 failed BTU boilers and appurtenances |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Acument Enterprises, Inc 1/12/16 | 16-R046364 | 16-P006245 |  |  |  | 22950 | 2016-03-18 |  | 100% | 22950 |  | 0 | No
119 | 3-WES-16-62441 | 3-WES-16-XXXXX | 3-WES-16- | 62441 | 3-WES-16-62441 | 3-WES-16-62441 | Weslaco Regional Headquarters (Reg 3) VFD Replacement 2525 N. International Blvd Weslaco, TX 78596 | Replace failed VFD |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to five star Electric Motors on 1/26/16 | R042709 | 16-P006336 |  |  |  | 4550.85 | 2016-03-08 |  | 0% | 4550.85 |  | 0 | No
120 | 2-LUF-16-62441 | 2-LUF-16-XXXXX | 2-LUF-16- | 62441 | 2-LUF-16-62441 | 2-LUF-16-62441 | Lufkin Sub-District Office (Reg 2) Replace cooling system 2809 South John Redditt Drive Lufkin, TX 75904 | Replace split cooling system with a gas furnace |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Concord Commercial Services on 3/10/16 | 16-R043499 | 16-P006973 |  |  |  | 11676 | 2016-04-21 |  | 100% | 11676 |  | 0 | No
121 | 2-BCA-16-62431 | 2-BCA-16-XXXXX | 2-BCA-16- | 62431 | 2-BCA-16-62431 | 2-BCA-16-62431 | Bay City Area Office (Reg 2) 510 Avenue F Bay City, TX 77414 | Replace failed gas water heater |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | Awarded to Big State Plumbing | 16-R040862 | RPA 1390 |  |  |  | 2104.95 | 2015-11-18 |  | 100% |  | 0 | 2104.95 | No
122 | HQ-C-16-62431 | HQ-C-16-XXXXX | HQ-C-16- | 62431 | HQ-C-16-62431 | HQ-C-16-62431 | Austin HQ (Building C&E) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace deteriorated Bldg. C-Annex/ Building E Waterproofing Elev#16. & Bldg. E-Rm. E001. |  | Rider 40 | General Revenue (Fund 0001) | Steve Harper | Awarded to Jeans Water proofing of Texas on 3/17/16; 4-27-Experiencing weather delay Bldg E | 16-R048154 | 16-P006950 |  |  |  | 33750 | 2016-05-10 |  | 100% | 33750 | 0 | 0 | No
123 | 6-VIC-16-62431 | 6-VIC-16-XXXXX | 6-VIC-16- | 62431 | 6-VIC-16-62431 | 6-VIC-16-62431 | Victoria Site (Reg 6) HVAC - CID Replacement 8802 N. Navarro Victoria, Texas 77904 | HVAC unit (1.5 ton split system and 3.5 ton split system) serving CID and conference room failed. |  | Rider 40 | General Revenue (Fund 0001) | Steve Haney | 5-26-16 Req Created; June 2016 in bid phase | [5 empty] | 24500 | 2016-07-15 |  |  | 24500 |  | 0 | No
124 | ST-CON-16-62894 | ST-CON-16-XXXXX | ST-CON-16- | 62894 | ST-CON-16-62894 | ST-CON-16-62894 | Statewide Unexpected DM repairs/Project Contingency | Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. May also include any addition project expenses such as TFC fees | 21 M | 21 M - GO Bond Funded | G.O. Bond savings from 80th Legislative $200M bond package. |  |  |  |  | 0 | 0 | 1457366 | 1335528.66 | Duration of projects |  |  |  |  | 1335528.66 | No
125 | HQ-B-16-XXXXX | HQ-B-16-XXXXX | HQ-L-16- |  | HQ-L-16- | HQ-L-16- | Austin HQ (Building B) Building B Renovation 5805 North Lamar Blvd Austin, Texas 78752 | Complete renovations to vacated crime laboratory area and DM upgrades. | 21 M | 21 M - GO Bond Funded | Submitting request to LBB - G.O. Bond savings from 80th Legislative $200M bond package. | Eddie King |  |  |  | 0 | 0 |  | 5100000 | Waiting LBB approval |  |  |  |  | 5100000 | Yes
| Consolidated | [5 empty] | Projects not funded | Summary of projects not funded that were originally submitted 9-15-15 | [7 empty] | 13605967.82 | 13605967.82 | 8549999.81 | 0 | [5 empty] | 0
[11 empty] | Totals: |  |  |  |  | 38778877 | 38778877 | 38778876.99 | 38778876.84 |  |  |  | 903724.93 | 1793696.42 | 36081455.49

## DPS Notes 6.16
| Agency: | Texas Department of Public Safety - 0405
| Date: | 2016-06-15
| Prepared by: | Tavia Wendlandt
Project Priority | Supplemental Information
Various | Note: G.O. Bond savings from 80th Legislative $200M bond package. LBB Approved 4-18-16; TPFA approved 5-26-16. Projects may now move forward.
5, 6, 8 | These projects are critical to the agency and were approved by the LBB on 4-18-16. These new projects were identified as needing a high priority.
7 | Formally priority #52, moved to priority #7. This is a project through TFC and is critical to replace the outdated infrastructure supporting the primary data center for the agency.
75 | This is a long lead item and is associated with a phased project. Replacement of interior finishes will begin in spring of 2017 when DL is expected to relocate to a leased facility.
125 | New priority DM project proposed utilizing the $200M bond funding to upgrade vacated crime laboratory space to help relieve overcrowding at the Headquarters complex. This is an approved bond project with TPFA - seeking approval to proceed from the LBB. Original proposed DM projects have been moved to a separate tab within the spreadsheet as they have become a lower agency priority compared to Building B. If there are any savings from the approved DM projects, then we will begin to work on these currently unfunded DM projects.
Waiting for LBB approval of funding to begin project; Excerpt from letter to LBB: “Per Article IX Sec. 14.03 (h) (3) Limitation on Expenditures – Capital Budget, the Department of Public Safety requests to transfer appropriations from a capital budget item to a non-capital budget item. Capital budget authority of $21, 000,000 is included in Article V, Rider 2 b. (2) Deferred Maintenance for deferred maintenance projects at the Department of Public Safety, however additional appropriations of $21,000,000 were not provided. This situation results in a $21,000,000 reduction to our Agency’s operations which cause undue hardship on the Agency’s programs. The Department requests a transfer of $11,139,565 in fiscal year 2016 and $9,860,435 in fiscal year 2017 from a capital budget item to a non-capital budget item.”

## DPS 3.16
| Agency: | [5 empty] | Texas Department of Public Safety - 0405
| Date: | [5 empty] | 2016-03-15
| Prepared by: | [5 empty] | Tavia Wendlandt
Project Priority | Agency ID | Agency ID with XXXXX | Agency ID - with out index | Index | Concatenate | Agency ID - Absolute | Project Name & Location | Project Description | Type - Original | Type - Adjusted | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Current Estimated Project Budget (for 2nd Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | ST-TEMP-62601 | ST-TEMP-XXXXX | ST-TEMP- | 62601 | ST-TEMP-62601 | ST-TEMP-62601 | Statewide Temporary DM Staff | Temporary staff needed to administer DM projects. (estimate two years) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 215000 | 215000 | 215000 | Duration of projects |  |  |  |  | 215000 | No
2 | 3-COR-16-62737 | 3-COR-16-XXXXX | 3-COR-16- | 62737 | 3-COR-16-62737 | 3-COR-16-62737 | Corpus Christi District Office (Reg 3) DM Multi-system project 1922 S. Padre Island Drive Corpus Christi, Texas 78416 | Complete ongoing DM projects (HVAC, Sanitary Sewer, Etc.) | 21M | Rider 40 | General Revenue (Fund 0001) | 780000 | 780000 | 780000 | 24 months - Negotiating IAC with TFC. |  |  |  |  | 780000 | Yes
3 | 6-ANW-16-62738 | 6-ANW-16-XXXXX | 6-ANW-16- | 62738 | 6-ANW-16-62738 | 6-ANW-16-62738 | Austin Northwest Area Office (Reg 6) Roof Replacement 13730 Research Boulevard Austin, Texas 78750 | Partial roof replacement (Built up portion only) | 21M | Rider 40 | General Revenue (Fund 0001) | 250000 | 250000 | 625000 | 12 months - Received cost estimate from CMR on 2-11-16. Still in assessment phase. Reviewing budget with TFC. |  |  |  |  | 625000 | Yes
4 | 2-LUF-16-62603 | 2-LUF-16-XXXXX | 2-LUF-16- | 62603 | 2-LUF-16-62603 | 2-LUF-16-62603 | Lufkin Lease Refresh - Lufkin CID Lease (Reg 2) 2815 John Redditt Dr. Lufkin, Texas 75904 | Refurbishment and equipping of a certain leased facility in Lufkin for use by CID as per Rider 63. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 200000 | 200000 | 200000 | 10 months - Negotiating IAC with TFC. - In schematic design | 10% |  |  |  | 200000 | Yes
5 | 1-GAR-16-62606 | 1-GAR-16-XXXXX | 1-GAR-16- | 62606 | 1-GAR-16-62606 | 1-GAR-16-62606 | Garland Regional Headquarters (Reg 1) HVAC Replacement 350 West IH-30 Garland, Texas 75043 | Heating Ventilation Air Conditioning (HVAC) System replacement in the Annex Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 400000 | 400000 | 400000 | 14 months - Negotiating IAC with TFC. |  |  |  |  | 400000 | Yes
6 | 1-HUR-16-62607 | 1-HUR-16-XXXXX | 1-HUR-16- | 62607 | 1-HUR-16-62607 | 1-HUR-16-62607 | Hurst District Office (Reg 1) HVAC Replacement 624 NE Loop 820 Hurst, Texas 76053 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 302623 | 302623 | 302623 | 16 months - Negotiating IAC with TFC.se. |  |  |  |  | 302623 | Yes
7 | 5-WIC-16-62608 | 5-WIC-16-XXXXX | 5-WIC-16- | 62608 | 5-WIC-16-62608 | 5-WIC-16-62608 | Wichita Falls Sub-District Office (Reg 5) Roof Replacement 5505 N. Central Expressway Wichita Falls, Texas 79306 | Replace Roof - construction phase. (TFC is engineering roof replacement from Rider 45 DM funds) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 200000 | 200000 | 200000 | 8 months - Negotiating IAC with TFC. Schematic design. 11-1-16 is est completion | 10% |  |  |  | 200000 | Yes
8 | 2-BEU-16-62609 | 2-BEU-16-XXXXX | 2-BEU-16- | 62609 | 2-BEU-16-62609 | 2-BEU-16-62609 | Beaumont District Office (Reg 2) HVAC Replacement 7200 Eastex Freeway Beaumont, Texas 77708 | Replacement of Heating Ventilation Air Conditioning (HVAC) Distribution System. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 315000 | 315000 | 315000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 315000 | Yes
9 | 3-LAR-16-62610 | 3-LAR-16-XXXXX | 3-LAR-16- | 62610 | 3-LAR-16-62610 | 3-LAR-16-62610 | Laredo District Office (Reg 3) Vacant area refresh 1901 Bob Bullock Loop Laredo, Texas 78043 | Vacant lab area - Refresh all deteriorated finishes and systems, lighting, roof, HVAC, and other infrastructure serving that area. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 150000 | 150000 | 150000 | 16 months - Negotiating IAC with TFC.. Assessment phase. |  |  |  |  | 150000 | Yes
10 | 5-ABI-16-62611 | 5-ABI-16-XXXXX | 5-ABI-16- | 62611 | 5-ABI-16-62611 | 5-ABI-16-62611 | Abilene District Office (Reg 5) HVAC Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 260000 | 260000 | 260000 | 24 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 260000 | Yes
11 | 1-CLE-16-62612 | 1-CLE-16-XXXXX | 1-CLE-16- | 62612 | 1-CLE-16-62612 | 1-CLE-16-62612 | Cleburne Area Office (Reg 1) HVAC Replacement 600 W. Kilpatrick St. Cleburne, Texas 76031 | Heating Ventilation Air Conditioning (HVAC) System replacement | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 325000 | 325000 | 325000 | 14 months - Negotiating IAC with TFC.. Assessment phase. |  |  |  |  | 325000 | Yes
12 | 5-CHI-16-62613 | 5-CHI-16-XXXXX | 5-CHI-16- | 62613 | 5-CHI-16-62613 | 5-CHI-16-62613 | Childress Area Office (Reg 5) HVAC Replacement 1700 Ave. F Northwest Childress, Texas 79201 | Replacement of Heating Ventilation Air Conditioning (HVAC) System. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 500000 | 500000 | 500000 | 18 months - Negotiating IAC with TFC.. Assessment phase. |  |  |  |  | 500000 | Yes
13 | 2-HGR-16-62614 | 2-HGR-16-XXXXX | 2-HGR-16- | 62614 | 2-HGR-16-62614 | 2-HGR-16-62614 | Houston Grant Road Driver License Office (Reg 2) Drainage Repairs - 10503 Grant Road Houston, Texas 77070 | DL parking lot repairs and drainage deficiencies | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 250000 | 250000 | 250000 | 14 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 250000 | Yes
14 | 4-ODE-16-62615 | 4-ODE-16-XXXXX | 4-ODE-16- | 62615 | 4-ODE-16-62615 | 4-ODE-16-62615 | Odessa Area Office (Reg 4) HVAC Replacement 1910 IH-20 West Odessa, Texas 79762 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 150714 | 150714 | 150714 | 8 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 150714 | Yes
15 | 4-GAT-16-62616 | 4-GAT-16-XXXXX | 4-GAT-16- | 62616 | 4-GAT-16-62616 | 4-GAT-16-62616 | El Paso Gateway East Driver License Office (Reg 4) HVAC Replacement 7300 Gateway East El Paso, Texas 79915 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 200000 | 200000 | 200000 | 6 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 200000 | Yes
16 | HQ-L-16-62617 | HQ-L-16-XXXXX | HQ-L-16- | 62617 | HQ-L-16-62617 | HQ-L-16-62617 | Austin HQ (Building L) HVAC Replacement 5710 Guadalupe Austin, Texas 78752 | Partial RTU replacements - Building L - Fleet Operations | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 78000 | 78000 | 78000 | 6 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 78000 | Yes
17 | HQ-GA-16-62618 | HQ-GA-16-XXXXX | HQ-GA-16- | 62618 | HQ-GA-16-62618 | HQ-GA-16-62618 | Austin HQ (Building G Annex) Chiller/Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace chillers/boilers in Building G Annex - Multi-Service Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 769600 | 769600 | 769600 | 14 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 769600 | Yes
18 | HQ-E-16-62619 | HQ-E-16-XXXXX | HQ-E-16- | 62619 | HQ-E-16-62619 | HQ-E-16-62619 | Austin HQ (Building E) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace boiler in Building E - Law Enforcement Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 78000 | 78000 | 78000 | 14 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 78000 | Yes
19 | HQ-C-16-62620 | HQ-C-16-XXXXX | HQ-C-16- | 62620 | HQ-C-16-62620 | HQ-C-16-62620 | Austin HQ (Building C) HVAC Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial HVAC replacement for Building C Training Academy | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 520000 | 520000 | 520000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 520000 | Yes
20 | HQ-A-16-62621 | HQ-A-16-XXXXX | HQ-A-16- | 62621 | HQ-A-16-62621 | HQ-A-16-62621 | Austin HQ (Building A) Roof Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial roof replacement for Building A | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 1040000 | 1040000 | 1040000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 1040000 | Yes
21 | HQ-E-16-62622 | HQ-E-16-XXXXX | HQ-E-16- | 62622 | HQ-E-16-62622 | HQ-E-16-62622 | Austin HQ (Building E) Roof Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial roof replacement for Building E - Law Enforcement Facility | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 1787058 | 1787058 | 1787058 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 1787058 | Yes
22 | HQ-O-16-62623 | HQ-O-16-XXXXX | HQ-O-16- | 62623 | HQ-O-16-62623 | HQ-O-16-62623 | Austin HQ (Building O) Sprinkler System 5601 Guadalupe Austin, Texas 78752 | Add Sprinklers (Fire Marshal recommendation) - Building O Fleet Operations | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 26000 | 26000 | 26000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 26000 | Yes
23 | 2-CON-16-62624 | 2-CON-16-XXXXX | 2-CON-16- | 62624 | 2-CON-16-62624 | 2-CON-16-62624 | Conroe District Office (Reg 2) Ductwork Replacement 2 Hilbig St. Conroe, Texas 77301 | Ductwork replacement-system reviewed and found contaminants and poor IAQ in facility due to condition of ductwork. Funding request to replace all flex duct and have the hard duct cleaned and sealed. (Includes office and Motor Vehicle Theft (MVT) Garage | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 603870 | 603870 | 603870 | 14 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 603870 | Yes
24 | 1-GAR-16-62625 | 1-GAR-16-XXXXX | 1-GAR-16- | 62625 | 1-GAR-16-62625 | 1-GAR-16-62625 | Garland Regional Headquarters (Reg 1) Site Lighting Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged site lighting. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 134006 | 134006 | 134006 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 134006 | Yes
25 | 1-GAR-16-62626 | 1-GAR-16-XXXXX | 1-GAR-16- | 62626 | 1-GAR-16-62626 | 1-GAR-16-62626 | Garland Regional Headquarters (Reg 1) Electrical Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged electrical system | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 574870 | 574870 | 574870 | 16 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 574870 | Yes
26 | 1-GAR-16-62627 | 1-GAR-16-XXXXX | 1-GAR-16- | 62627 | 1-GAR-16-62627 | 1-GAR-16-62627 | Garland Regional Headquarters (Reg 1) Plumbing Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged plumbing (i.e.: Natural Gas system, domestic water system and fixtures, etc.) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 517577 | 517577 | 517577 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 517577 | Yes
27 | 1-GAR-16-62628 | 1-GAR-16-XXXXX | 1-GAR-16- | 62628 | 1-GAR-16-62628 | 1-GAR-16-62628 | Garland Regional Headquarters (Reg 1) Foundation Study 350 West IH-30 Garland, Texas 75043 | Several signs of stress and settlement is seen throughout the facility, specifically on the Westside of the building. Recommend a professional structural engineering study be conducted for resolution. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 150000 | 150000 | 150000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 150000 | Yes
28 | 2-PIE-16-62629 | 2-PIE-16-XXXXX | 2-PIE-16- | 62629 | 2-PIE-16-62629 | 2-PIE-16-62629 | Pierce Sub-District Office (Reg 2) Foundation Study 19692 US Hwy 59 El Campo, Texas 77437 | Northwest wall and a part of Northeast wall are showings signs of structural degradation. Recommend professional study. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 150000 | 150000 | 150000 | 16 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 150000 | Yes
29 | 2-BAY-16-62630 | 2-BAY-16-XXXXX | 2-BAY-16- | 62630 | 2-BAY-16-62630 | 2-BAY-16-62630 | Baytown Area Office (Reg 2) Foundation Repairs 5420 Decker Drive Baytown, Texas 77520 | Repair foundation / interior finishes | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 150000 | 150000 | 150000 | 16 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 150000 | Yes
30 | 5-CHI-16-62631 | 5-CHI-16-XXXXX | 5-CHI-16- | 62631 | 5-CHI-16-62631 | 5-CHI-16-62631 | Childress Area Office (Reg 5) Foundation Study 1700 Ave. F Northwest Childress, Texas 79201 | The retaining walls are cracking and showing signs of structural problems. Recommend professional study. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 150000 | 150000 | 150000 | 16 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 150000 | Yes
31 | 1-SUL-16-62632 | 1-SUL-16-XXXXX | 1-SUL-16- | 62632 | 1-SUL-16-62632 | 1-SUL-16-62632 | Sulphur Springs Area Office (Reg 1) Foundation Study 1528 E. Shannon Road Sulphur Springs, Texas 75482 | Settlement cracks in foundation, exterior walls, and interior wall systems. Recommend a professional structural engineering study be conducted for resolution. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 150000 | 150000 | 150000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 150000 | Yes
32 | 2-CON-16-62633 | 2-CON-16-XXXXX | 2-CON-16- | 62633 | 2-CON-16-62633 | 2-CON-16-62633 | Conroe District Office (Reg 2) Foundation Study 2 Hilbig St. Conroe, Texas 77301 | Exterior walls are showing stress and damage at the MVT Garage. Recommend professional structure analysis to determine condition and repair of exterior wall and implement repairs. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 185000 | 185000 | 185000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 185000 | Yes
33 | HQ-L-16-62634 | HQ-L-16-XXXXX | HQ-L-16- | 62634 | HQ-L-16-62634 | HQ-L-16-62634 | Austin HQ (Building L) Car Wash Replacement 5710 Guadalupe Austin, Texas 78752 | Replace car wash at Fleet Operations - Building L | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 100000 | 100000 | 100000 | 8 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 100000 | Yes
34 | 4-ODE-16-62847 | 4-ODE-16-XXXXX | 4-ODE-16- | 62847 | 4-ODE-16-62847 | 4-ODE-16-62847 | Odessa Area Office (Reg 4) HVAC Replacement 1910 IH-20 West Odessa, Texas 79762 | Terminal & Package Units (Building Automation System) | 21 M | Rider 40 | General Revenue (Fund 0001) | 234000 | 234000 | 234000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 234000 | Yes
35 | 4-ODE-16-62754 | 4-ODE-16-XXXXX | 4-ODE-16- | 62754 | 4-ODE-16-62754 | 4-ODE-16-62754 | Odessa Area Office (Reg 4) Roof Replacement 1910 IH-20 West Odessa, Texas 79762 | Roof Coverings/openings-built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | 249600 | 249600 | 249600 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 249600 | Yes
36 | ST-FUEL-16-62739 | ST-FUEL-16-XXXXX | ST-FUEL-16- | 62739 | ST-FUEL-16-62739 | ST-FUEL-16-62739 | Statewide Fuel System Maintenance/Removal | UST/AST fueling systems repairs/maintenance/removal | 21 M | Rider 40 | General Revenue (Fund 0001) | 250000 | 250000 | 250000 | 16 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 250000 | Yes
37 | 5-AMA-16-62740 | 5-AMA-16-XXXXX | 5-AMA-16- | 62740 | 5-AMA-16-62740 | 5-AMA-16-62740 | Amarillo District Office (Reg 5) Exterior Door/Window Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Exterior doors replacement/Window replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | 167666.72 | 167666.72 | 167666.72 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 167666.72 | Yes
38 | 6-ADO-16-62741 | 6-ADO-16-XXXXX | 6-ADO-16- | 62741 | 6-ADO-16-62741 | 6-ADO-16-62741 | Austin District Office (Reg 6) HVAC Replacement 9000 IH-35 North Austin, Texas 78753 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | Rider 40 | General Revenue (Fund 0001) | 192294.48 | 192294.48 | 192294.48 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 192294.48 | Yes
39 | 6-ADO-16-62742 | 6-ADO-16-XXXXX | 6-ADO-16- | 62742 | 6-ADO-16-62742 | 6-ADO-16-62742 | Austin District Office (Reg 6) Roof Replacement 9000 IH-35 North Austin, Texas 78753 | Roof Coverings built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | 338000 | 338000 | 338000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 338000 | Yes
40 | 2-HHQ-16-62743 | 2-HHQ-16-XXXXX | 2-HHQ-16- | 62743 | 2-HHQ-16-62743 | 2-HHQ-16-62743 | Houston Regional Headquarters (West Road) Crime Lab (Reg 2) Chiller Replacement 12230 West Road Jersey Village, Texas 77065 | Chiller replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | 312000 | 312000 | 312000 | 14 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 312000 | Yes
41 | 4-SAN-16-62744 | 4-SAN-16-XXXXX | 4-SAN-16- | 62744 | 4-SAN-16-62744 | 4-SAN-16-62744 | San Angelo Sub-District Office (Reg 4) HVAC Replacement 1600 W. Loop 306 San Angelo, Texas 76903 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | Rider 40 | General Revenue (Fund 0001) | 633900.8 | 633900.8 | 633900.8 | 14 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 633900.8 | Yes
42 | 4-SAN-16-62745 | 4-SAN-16-XXXXX | 4-SAN-16- | 62745 | 4-SAN-16-62745 | 4-SAN-16-62745 | San Angelo Sub-District Office (Reg 4) Roof Replacement 1600 W. Loop 306 San Angelo, Texas 76903 | Roof Coverings built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | 325000 | 325000 | 325000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 325000 | Yes
43 | 1-HUR-16-62746 | 1-HUR-16-XXXXX | 1-HUR-16- | 62746 | 1-HUR-16-62746 | 1-HUR-16-62746 | Hurst Sub-District Office (Reg 1) Roof Replacement 624 NE Loop 820 Hurst, Texas 76053 | Roof Coverings built-up roofing replacement (Including roof openings) | 21 M | Rider 40 | General Revenue (Fund 0001) | 430981.2 | 430981.2 | 430981.2 | 16 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 430981.2 | Yes
44 | 3-EAG-16-62747 | 3-EAG-16-XXXXX | 3-EAG-16- | 62747 | 3-EAG-16-62747 | 3-EAG-16-62747 | Eagle Pass Area Office (Reg 3) HVAC Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Terminal & package units replacement/upgrade (Add BAS as needed) | 21 M | Rider 40 | General Revenue (Fund 0001) | 10000 | 10000 | 10000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 10000 | Yes
45 | 3-HAR-16-62748 | 3-HAR-16-XXXXX | 3-HAR-16- | 62748 | 3-HAR-16-62748 | 3-HAR-16-62748 | Harlingen Area Office (Reg 3) Roof Replacement 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Roof Coverings built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | 325000 | 325000 | 325000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 325000 | Yes
46 | 3-BEE-16-62749 | 3-BEE-16-XXXXX | 3-BEE-16- | 62749 | 3-BEE-16-62749 | 3-BEE-16-62749 | Beeville Area Office (Reg 3) HVAC Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Terminal & package units replacement/upgrade (Add BAS as needed) | 21 M | Rider 40 | General Revenue (Fund 0001) | 10000 | 10000 | 10000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 10000 | Yes
47 | 3-BEE-16-62750 | 3-BEE-16-XXXXX | 3-BEE-16- | 62750 | 3-BEE-16-62750 | 3-BEE-16-62750 | Beeville Area Office (Reg 3) Roof Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Roof Coverings built-up roofing replacement | 21 M | Rider 40 | General Revenue (Fund 0001) | 150000 | 150000 | 150000 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 150000 | Yes
48 | 4-BIG-16-62751 | 4-BIG-16-XXXXX | 4-BIG-16- | 62751 | 4-BIG-16-62751 | 4-BIG-16-62751 | Big Spring Area Office (Reg 4) HVAC Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Terminal & package units replacement/upgrade - including split DX (Add BAS as needed) | 21 M | Rider 40 | General Revenue (Fund 0001) | 2954.64 | 2954.64 | 2954.64 | 12 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 2954.64 | Yes
49 | ST-PM-16-62635 | ST-PM-16-XXXXX | ST-PM-16- | 62635 | ST-PM-16-62635 | ST-PM-16-62635 | Statewide TFC Project Mgmt. Fees | TFC Project Management fees. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 616800 | 616800 | 300000 | Duration of projects Negotiating IAC with TFC. |  |  |  |  | 300000 | Yes
50 | ST-CON-16-62636 | ST-CON-16-XXXXX | ST-CON-16- | 62636 | ST-CON-16-62636 | ST-CON-16-62636 | Statewide Unexpected DM repairs/Project Contingency | Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 1529759 | 1529759 | 1760161 | Duration of projects. Negotiating IAC with TFC. |  |  |  |  | 1760161 | Yes | totals: $17,778,877
51 | ST-CON-16-62636 | ST-CON-16-XXXXX | ST-CON-16- | 62636 | ST-CON-16-62636 | ST-CON-16-62636 | Statewide Unexpected DM repairs/Project Contingency Childress Area Office (Reg 5) Roof Replacement 1700 Ave. F Northwest Childress, Texas 79201 | Replace Childress radio shop roof (Roof is leaking and contains asbestos) | Rider 40 | Rider 40 | General Revenue (Fund 0001) | 0 | 0 | 50000 | 16 months - Negotiating IAC with TFC. Assessment phase. |  |  |  |  | 50000 | Yes | totals: $17,778,877
DM Projects Not Approved
Not Approved | ST-FCA-16-62604 | ST-FCA-16-XXXXX | ST-FCA-16- | 62604 | ST-FCA-16-62604 | ST-FCA-16-62604 | Statewide Facility Condition Assessment | Statewide Assessment: An updated professional statewide Facility Condition Assessment study is needed to identify current deferred maintenance and capital renewal projects and associated costs. 3-1-16 Not approved by governing authority | Dis-Approved Projects | Dis-Approved Projects | Not approved by governing authority | 1300000 | 1300000 | 0 | Not approved by governing authority |  |  |  |  | 0 | Yes
Not Approved | ST-IWMS-16-62605 | ST-IWMS-16-XXXXX | ST-IWMS-16- | 62605 | ST-IWMS-16-62605 | ST-IWMS-16-62605 | Statewide Integrated Workplace Management System | A computerized Integrated Workplace Management system (IWMS) that is web based and can be implemented statewide is needed to track and plan for maintenance of DPS facilities. As funding permits, this will include the implementation of space management, inventory management, lease management, and environmental sustainability integration. 3-1-16 Not approved by governing authority | Dis-Approved Projects | Dis-Approved Projects | Not approved by governing authority | 1700000 | 1700000 | 0 | Not approved by governing authority |  |  |  |  | 0 | Yes
Not Approved | HQ-CAM-16-62602 | HQ-CAM-16-XXXXX | HQ-CAM-16- | 62602 | HQ-CAM-16-62602 | HQ-CAM-16-62602 | Austin HQ Campus Campus Relocation Study 5805 North Lamar Blvd Austin, Texas 78752 | Campus relocation study (Rider 54). Includes campus conceptual design. 3-1-16 Not approved by governing authority | Dis-Approved Projects | Dis-Approved Projects | Not approved by governing authority | 2000000 | 2000000 | 0 | Not approved by governing authority |  |  |  |  | 0 | Yes
$21M Unfunded Authority - Funding Identified | [13 empty] | 12450000.34
52 | HQ-A-16-62895 | [5 empty] | Austin HQ (Building A) Data Center Upgrades 5805 North Lamar Blvd Austin, Texas 78752 | Replace existing HVAC, electrical, and fire suppression system, provide redundancy for HVAC/Electrical in the Data Center. | 21 M | Agency Savings | General Revenue (Fund 0001) | 0 | 0 | 1750000 | 12 months - In process of negotiating IAC with TFC. | [5 empty] | Yes
53 | 2-BRE-16-62752 | 2-BRE-16-XXXXX | 2-BRE-16- | 62752 | 2-BRE-16-62752 | 2-BRE-16-62752 | Brenham Area Office (Reg 2) HVAC Controls Replacement 975 Hwy 290 West. Brenham, Texas 77834 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 168720.24 | 168720.24 | 168720.24 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 168720.24 | Yes
54 | 2-BRE-16-62753 | 2-BRE-16-XXXXX | 2-BRE-16- | 62753 | 2-BRE-16-62753 | 2-BRE-16-62753 | Brenham Area Office (Reg 2) Roof Replacement 975 Hwy 290 West. Brenham, Texas 77834 | Roof Coverings built-up roofing replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 130000 | 130000 | 130000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 130000 | Yes
55 | 2-ORA-16-62755 | 2-ORA-16-XXXXX | 2-ORA-16- | 62755 | 2-ORA-16-62755 | 2-ORA-16-62755 | Orange Area Office (Reg 2) Roof Replacement 711 South Hwy 87 Orange, Texas 77630 | Roof Coverings built-up roofing replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 182000 | 182000 | 182000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 182000 | Yes
56 | 4-OZO-16-62756 | 4-OZO-16-XXXXX | 4-OZO-16- | 62756 | 4-OZO-16-62756 | 4-OZO-16-62756 | Ozona Area Office (Reg 4) HVAC Replacement 1503 Monterey St Ozona, Texas 76943 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 132242.24 | 132242.24 | 132242.24 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 132242.24 | Yes
57 | 4-Pec-16-62757 | 4-Pec-16-XXXXX | 4-Pec-16- | 62757 | 4-Pec-16-62757 | 4-Pec-16-62757 | Pecos Area Office (Reg 4) HVAC Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Terminal & package units replacement/upgrade (Add BAS as needed), Distribution systems, controls and instrumentation replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 117413.92 | 117413.92 | 117413.92 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 117413.92 | Yes
58 | 4-Pec-16-62758 | 4-Pec-16-XXXXX | 4-Pec-16- | 62758 | 4-Pec-16-62758 | 4-Pec-16-62758 | Pecos Area Office (Reg 4) Roof Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Roof Coverings built-up roofing replacement/roof openings | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 133023.28 | 133023.28 | 133023.28 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 133023.28 | Yes
59 | 3-UVA-16-62759 | 3-UVA-16-XXXXX | 3-UVA-16- | 62759 | 3-UVA-16-62759 | 3-UVA-16-62759 | Uvalde Area Office (Reg 3) Roof Replacement 2901 E. Main Uvalde, Texas 78801 | Roof Coverings built-up roofing replacement/roof openings | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 102397.2 | 102397.2 | 102397.2 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 102397.2 | Yes
60 | 1-GAR-16-62760 | 1-GAR-16-XXXXX | 1-GAR-16- | 62760 | 1-GAR-16-62760 | 1-GAR-16-62760 | Garland Regional Headquarters Site (Reg 1) Communication & Security 350 West IH-30 Garland, Texas 75043 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 49042.24 | 49042.24 | 49042.24 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 49042.24 | Yes
61 | 1-GAR-16-62761 | 1-GAR-16-XXXXX | 1-GAR-16- | 62761 | 1-GAR-16-62761 | 1-GAR-16-62761 | Garland Regional Headquarters Site (Reg 1) Landscaping Upgrade 350 West IH-30 Garland, Texas 75043 | Landscaping (xeriscape) upgrade | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 98962.24 | 98962.24 | 98962.24 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 98962.24 | Yes
62 | 1-GAR-16-62762 | 1-GAR-16-XXXXX | 1-GAR-16- | 62762 | 1-GAR-16-62762 | 1-GAR-16-62762 | Garland Regional Headquarters Site (Reg 1) Parking Lot Replacement 350 West IH-30 Garland, Texas 75043 | Parking lot/pedestrian paving/driveways replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 789058.4 | 789058.4 | 789058.4 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 789058.4 | Yes
63 | 1-GAR-16-62763 | 1-GAR-16-XXXXX | 1-GAR-16- | 62763 | 1-GAR-16-62763 | 1-GAR-16-62763 | Garland Regional Headquarters Site (Reg 1) Sanitary Sewer Replacement 350 West IH-30 Garland, Texas 75043 | Sanitary sewer replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 24553.36 | 24553.36 | 24553.36 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 24553.36 | Yes
64 | 1-GAR-16-62764 | 1-GAR-16-XXXXX | 1-GAR-16- | 62764 | 1-GAR-16-62764 | 1-GAR-16-62764 | Garland Regional Headquarters Site (Reg 1) Site Development 350 West IH-30 Garland, Texas 75043 | Site Development (i.e.: Storm water system, etc.) | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 287119.04 | 287119.04 | 287119.04 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 287119.04 | Yes
65 | 1-GAR-16-62765 | 1-GAR-16-XXXXX | 1-GAR-16- | 62765 | 1-GAR-16-62765 | 1-GAR-16-62765 | Garland Regional Headquarters Site (Reg 1) Water Supply Upgrade 350 West IH-30 Garland, Texas 75043 | Water Supply upgrade/replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 67370.16 | 67370.16 | 67370.16 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 67370.16 | Yes
66 | 2-PIE-16-62766 | 2-PIE-16-XXXXX | 2-PIE-16- | 62766 | 2-PIE-16-62766 | 2-PIE-16-62766 | Pierce Sub-District Office (Reg 2) Ductwork Replacement 19692 US Hwy 59 El Campo, Texas 77437 | Duct work and insulation replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 62400 | 62400 | 62400 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 62400 | Yes
67 | 2-BRE-16-62767 | 2-BRE-16-XXXXX | 2-BRE-16- | 62767 | 2-BRE-16-62767 | 2-BRE-16-62767 | Brenham Area Office (Reg 2) Exterior Wall Repair 975 Hwy 290 West. Brenham, Texas 77834 | Exterior walls repair | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 10773.36 | 10773.36 | 10773.36 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 10773.36 | Yes
68 | 2-HHQ-16-62768 | 2-HHQ-16-XXXXX | 2-HHQ-16- | 62768 | 2-HHQ-16-62768 | 2-HHQ-16-62768 | Houston Regional Headquarters (West Road) (Reg 2) Security System Replacement 12230 West Road Jersey Village, Texas 77065 | Security system replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 208000 | 208000 | 208000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 208000 | Yes
69 | 4-MID-16-62769 | 4-MID-16-XXXXX | 4-MID-16- | 62769 | 4-MID-16-62769 | 4-MID-16-62769 | Midland Sub District Office (Reg 4) Vacant DL Remodel/Refresh 2405 S. Loop 250 West Midland, Texas 79703 | Remodel vacant DL area including to replacing deteriorated finishes and MEP systems | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 442000 | 442000 | 442000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 442000 | Yes
70 | 5-AMA-16-62770 | 5-AMA-16-XXXXX | 5-AMA-16- | 62770 | 5-AMA-16-62770 | 5-AMA-16-62770 | Amarillo District Office (Reg 5) Security System Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Security system replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 343698.16 | 343698.16 | 343698.16 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 343698.16 | Yes
71 | 5-AMA-16-62771 | 5-AMA-16-XXXXX | 5-AMA-16- | 62771 | 5-AMA-16-62771 | 5-AMA-16-62771 | Amarillo District Office (Reg 5) Sprinkler System 4200 Canyon Dr. Amarillo, Texas 79109 | Sprinkler System | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 153180.56 | 153180.56 | 153180.56 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 153180.56 | Yes
72 | 5-AMA-16-62772 | 5-AMA-16-XXXXX | 5-AMA-16- | 62772 | 5-AMA-16-62772 | 5-AMA-16-62772 | Amarillo District Office (Reg 5) Foundation Study/Repair 4200 Canyon Dr. Amarillo, Texas 79109 | Standard Foundations | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 40278.16 | 40278.16 | 40278.16 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 40278.16 | Yes
73 | 5-AMA-16-62773 | 5-AMA-16-XXXXX | 5-AMA-16- | 62773 | 5-AMA-16-62773 | 5-AMA-16-62773 | Amarillo District Office (Reg 5) Interior Finishes Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 575051.36 | 575051.36 | 575051.36 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 575051.36 | Yes
74 | 5-AMA-16-62774 | 5-AMA-16-XXXXX | 5-AMA-16- | 62774 | 5-AMA-16-62774 | 5-AMA-16-62774 | Amarillo District Office (Reg 5) Fittings Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Fittings (Specialties) replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 17077.84 | 17077.84 | 17077.84 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 17077.84 | Yes
75 | 6-ADO-16-62775 | 6-ADO-16-XXXXX | 6-ADO-16- | 62775 | 6-ADO-16-62775 | 6-ADO-16-62775 | Austin District Office Site (Reg 6) Parking Lot Replacement 9000 IH-35 North Austin, Texas 78753 | Parking lot replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 260000 | 260000 | 260000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 260000 | Yes
76 | 6-ADO-16-62776 | 6-ADO-16-XXXXX | 6-ADO-16- | 62776 | 6-ADO-16-62776 | 6-ADO-16-62776 | Austin District Office Site (Reg 6) Site Lighting Replacement/Upgrade 9000 IH-35 North Austin, Texas 78753 | Site Lighting | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 57117.84 | 57117.84 | 57117.84 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 57117.84 | Yes
77 | 6-ADO-16-62777 | 6-ADO-16-XXXXX | 6-ADO-16- | 62777 | 6-ADO-16-62777 | 6-ADO-16-62777 | Austin District Office Site (Reg 6) Communication & Security 9000 IH-35 North Austin, Texas 78753 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 22046.96 | 22046.96 | 22046.96 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 22046.96 | Yes
78 | 6-ADO-16-62778 | 6-ADO-16-XXXXX | 6-ADO-16- | 62778 | 6-ADO-16-62778 | 6-ADO-16-62778 | Austin District Office Storage Hwy Patrol (Reg 6) Special Structures 9000 IH-35 North Austin, Texas 78753 | Special Structures - Storage Bldg. < 1000sf | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 12728.56 | 12728.56 | 12728.56 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 12728.56 | Yes
79 | 5-ABI-16-62779 | 5-ABI-16-XXXXX | 5-ABI-16- | 62779 | 5-ABI-16-62779 | 5-ABI-16-62779 | Abilene District Office (Reg 5) Security/Site System Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Security system replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 220581.92 | 220581.92 | 220581.92 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 220581.92 | Yes
80 | 3-LAR-16-62780 | 3-LAR-16-XXXXX | 3-LAR-16- | 62780 | 3-LAR-16-62780 | 3-LAR-16-62780 | Laredo District Office (Reg 3) Ceiling Replacement 1901 Bob Bullock Loop Laredo, Texas 78043 | Ceiling/wall finishes replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 389896.32 | 389896.32 | 389896.32 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 389896.32 | Yes
81 | 3-LAR-16-62781 | 3-LAR-16-XXXXX | 3-LAR-16- | 62781 | 3-LAR-16-62781 | 3-LAR-16-62781 | Laredo District Office (Reg 3) Security System Replacement 1901 Bob Bullock Loop Laredo, Texas 78043 | Security system replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 373251.84 | 373251.84 | 373251.84 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 373251.84 | Yes
82 | 6-WAC-16-62782 | 6-WAC-16-XXXXX | 6-WAC-16- | 62782 | 6-WAC-16-62782 | 6-WAC-16-62782 | Waco District Office (Reg 6) Interior Finishes Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 567938.8 | 567938.8 | 567938.8 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 567938.8 | Yes
83 | 6-WAC-16-62783 | 6-WAC-16-XXXXX | 6-WAC-16- | 62783 | 6-WAC-16-62783 | 6-WAC-16-62783 | Waco District Office (Reg 6) Fixed Furnishings Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Fixed furnishings replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 137846.8 | 137846.8 | 137846.8 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 137846.8 | Yes
84 | 3-EAG-16-62784 | 3-EAG-16-XXXXX | 3-EAG-16- | 62784 | 3-EAG-16-62784 | 3-EAG-16-62784 | Eagle Pass Area Office (Reg 3) Interior Finishes Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 186283.86 | 186283.86 | 186283.86 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 186283.86 | Yes
85 | 3-EAG-16-62785 | 3-EAG-16-XXXXX | 3-EAG-16- | 62785 | 3-EAG-16-62785 | 3-EAG-16-62785 | Eagle Pass Area Office (Reg 3) Electrical Systems 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Other Electrical Systems (Repair illuminated exit signs throughout the facility and add emergency lighting where needed.) | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 150000 | 150000 | 150000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 150000 | Yes
86 | 3-EAG-16-62786 | 3-EAG-16-XXXXX | 3-EAG-16- | 62786 | 3-EAG-16-62786 | 3-EAG-16-62786 | Eagle Pass Area Office (Reg 3) Security System Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Security system replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 125000 | 125000 | 125000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 125000 | Yes
87 | 3-EAG-16-62787 | 3-EAG-16-XXXXX | 3-EAG-16- | 62787 | 3-EAG-16-62787 | 3-EAG-16-62787 | Eagle Pass Area Office (Reg 3) Sprinkler System 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Sprinkler System | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 49622.56 | 49622.56 | 49622.56 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 49622.56 | Yes
88 | 3-EAG-16-62788 | 3-EAG-16-XXXXX | 3-EAG-16- | 62788 | 3-EAG-16-62788 | 3-EAG-16-62788 | Eagle Pass Site (Reg 3) Communication & Security 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 9984 | 9984 | 9984 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 9984 | Yes
89 | 3-EAG-16-62789 | 3-EAG-16-XXXXX | 3-EAG-16- | 62789 | 3-EAG-16-62789 | 3-EAG-16-62789 | Eagle Pass Site (Reg 3) Landscaping Upgrade 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Landscaping (xeriscape) upgrade | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 4285.84 | 4285.84 | 4285.84 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 4285.84 | Yes
90 | 3-EAG-16-62790 | 3-EAG-16-XXXXX | 3-EAG-16- | 62790 | 3-EAG-16-62790 | 3-EAG-16-62790 | Eagle Pass Site (Reg 3) Site Lighting Replacement/Upgrade 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Site Lighting | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 20368.4 | 20368.4 | 20368.4 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 20368.4 | Yes
91 | 5-AMA-16-62791 | 5-AMA-16-XXXXX | 5-AMA-16- | 62791 | 5-AMA-16-62791 | 5-AMA-16-62791 | Amarillo MVT Building (Reg 5) Electrical Systems 4200 Canyon Dr. Amarillo, Texas 79109 | Other Electrical Systems (Add illuminated exit signs throughout the facility and add emergency lighting where needed.) | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 260 | 260 | 260 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 260 | Yes
92 | 5-AMA-16-62792 | 5-AMA-16-XXXXX | 5-AMA-16- | 62792 | 5-AMA-16-62792 | 5-AMA-16-62792 | Amarillo Site (Reg 5) Communication & Security 4200 Canyon Dr. Amarillo, Texas 79109 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 25084.8 | 25084.8 | 25084.8 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 25084.8 | Yes
93 | 5-AMA-16-62793 | 5-AMA-16-XXXXX | 5-AMA-16- | 62793 | 5-AMA-16-62793 | 5-AMA-16-62793 | Amarillo Site (Reg 5) Fuel Distribution Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Fuel distribution replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 46800 | 46800 | 46800 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 46800 | Yes
94 | 5-AMA-16-62794 | 5-AMA-16-XXXXX | 5-AMA-16- | 62794 | 5-AMA-16-62794 | 5-AMA-16-62794 | Amarillo Site (Reg 5) Parking Lot/Pedestrian Paving 4200 Canyon Dr. Amarillo, Texas 79109 | Parking lot/pedestrian paving replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 291766.8 | 291766.8 | 291766.8 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 291766.8 | Yes
95 | 5-AMA-16-62795 | 5-AMA-16-XXXXX | 5-AMA-16- | 62795 | 5-AMA-16-62795 | 5-AMA-16-62795 | Amarillo Site (Reg 5) Site Lighting Replacement/Upgrade 4200 Canyon Dr. Amarillo, Texas 79109 | Site Lighting | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 65007.28 | 65007.28 | 65007.28 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 65007.28 | Yes
96 | HQ-A-16-62796 | HQ-A-16-XXXXX | HQ-A-16- | 62796 | HQ-A-16-62796 | HQ-A-16-62796 | Austin HQ (Building A) AHU/FCU Replacement 5805 North Lamar Blvd Austin, Texas 78752 | HVAC - replace all AHU and FCUs not already in process/completed | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 520000 | 520000 | 520000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 520000 | Yes
97 | HQ-A-16-62797 | HQ-A-16-XXXXX | HQ-A-16- | 62797 | HQ-A-16-62797 | HQ-A-16-62797 | Austin HQ (Building A) DDC Retrofit 5805 North Lamar Blvd Austin, Texas 78752 | HVAC - retrofit existing pneumatic controls to DDC | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 62400 | 62400 | 62400 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 62400 | Yes
98 | 2-BRY-16-XXXXX | 2-BRY-16-XXXXX | 2-BRY-16- | 62896 | 2-BRY-16- 62896 | 2-BRY-16- 62896 | Bryan District Office (Reg 2) Foundation/Drainage Modifications 2571 North Earl Rudder Freeway Bryan, Texas 77805 | Foundation/site drainage modifications | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 0 | 0 | 650000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 650000 | Yes
99 | 6-WTR-16-XXXX | 6-WTR-16-XXXX | 6-WTR-16- | 62897 | 6-WTR-16- 62897 | 6-WTR-16- 62897 | Waco Texas Rangers Headquarters and Education Center (Reg 6) HVAC Replacement 102 Texas Ranger Trail Waco, Texas 76705 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 0 | 0 | 350000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 350000 | Yes
100 | HQ-C-16-XXXXX | HQ-C-16-XXXXX | HQ-C-16- | 62898 | HQ-C-16- 62898 | HQ-C-16- 62898 | Austin HQ (Building C) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Boiler replacement (two boilers supporting original building) | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 0 | 0 | 100000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 100000 | Yes
101 | 1-TER-16-XXXXX | 1-TER-16-XXXXX | 1-TER-16- | 62899 | 1-TER-16- 62899 | 1-TER-16- 62899 | Terrell Area Office (Reg 1) Drainage Repairs 111 Tejas Drive Terrell, Texas 75160 | Site drainage repairs | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 0 | 0 | 100000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 100000 | Yes
102 | 3-EAG-16-XXXXX | 3-EAG-16-XXXXX | 3-EAG-16- | 62900 | 3-EAG-16- 62900 | 3-EAG-16- 62900 | Eagle Pass Area Office (Reg 3) Foundation/Drainage Modifications 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Foundation/site drainage modifications | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 0 | 0 | 100000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 100000 | Yes
103 | 6-ANW-16-XXXXX | 6-ANW-16-XXXXX | 6-ANW-16- | 62901 | 6-ANW-16- 62901 | 6-ANW-16- 62901 | Austin Northwest Area Office (Reg 6) Interior Finish Replacement 13730 Research Boulevard Austin, Texas 78750 | Ceiling, wall, floor finishes replacement | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 0 | 0 | 50000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 50000 | Yes
104 | 4-ALP-16-XXXXX | 4-ALP-16-XXXXX | 4-ALP-16- | 62902 | 4-ALP-16- 62902 | 4-ALP-16- 62902 | Alpine Area Office (Reg 4) Energy Efficiency Project 3500 North Highway 118 Alpine, Texas 79830 | Add ceiling insulation to increase energy efficiency to assist HVAC system to better control temperature in open ceiling area. | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 0 | 0 | 60000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 60000 | Yes
105 | HQ-L-16-XXXXX | HQ-L-16-XXXXX | HQ-L-16- | 62903 | HQ-L-16- 62903 | HQ-L-16- 62903 | Austin HQ (Building L) Car Lift Replacement 5710 Guadalupe Austin, Texas 78752 | Replace 18 original car lifts that are no longer functioning, leaking hydraulic oil, or not operating effectively. | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 0 | 0 | 100000 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 100000 | Yes
106 | ST-CON-16-62894 | ST-CON-16-XXXXX | ST-CON-16- | 62894 | ST-CON-16-62894 | ST-CON-16-62894 | Statewide Unexpected DM repairs/Project Contingency | Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. May also include any addition project expenses such as TFC fees | 21 M | 21 M - GO Bond Funded | Pending LBB Approval (G.O. Bond savings from 80th Legislative $200M bond package.) | 0 | 0 | 1457366 | Unknown - Pending LBB approval GO Bond Funding |  |  |  |  | 1457366 | Yes
$21M Unfunded Authority - Funding Not Identified | [13 empty] | 8549999.81
107 | HQ-A-16-62798 | HQ-A-16-XXXXX | HQ-A-16- | 62798 | HQ-A-16-62798 | HQ-A-16-62798 | Austin HQ (Building A) Plumbing Fixtures Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Plumbing fixtures replacement (i.e.: toilets/lavatories) | 21 M | 21 M | Unknown | 41600 | 41600 | 41600 | Unknown |  |  |  |  | 41600 | Yes
108 | 3-DEL-16-62799 | 3-DEL-16-XXXXX | 3-DEL-16- | 62799 | 3-DEL-16-62799 | 3-DEL-16-62799 | Del Rio Sub District Office (Reg 3) Security System Replacement 2012 Veteran Boulevard Del Rio, Texas 78840 | Security system replacement | 21 M | 21 M | Unknown | 228853.04 | 228853.04 | 228853.04 | Unknown |  |  |  |  | 228853.04 | Yes
109 | 3-HAR-16-62800 | 3-HAR-16-XXXXX | 3-HAR-16- | 62800 | 3-HAR-16-62800 | 3-HAR-16-62800 | Harlingen Area Office (Reg 3) Ceiling Replacement 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Ceiling finishes replacement | 21 M | 21 M | Unknown | 84252.48 | 84252.48 | 84252.48 | Unknown |  |  |  |  | 84252.48 | Yes
110 | 3-HAR-16-62801 | 3-HAR-16-XXXXX | 3-HAR-16- | 62801 | 3-HAR-16-62801 | 3-HAR-16-62801 | Harlingen Area Office (Reg 3) ADA Parking Spaces 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Correct American Disabilities Act (ADA) Parking Spaces. | 21 M | 21 M | Unknown | 62400 | 62400 | 62400 | Unknown |  |  |  |  | 62400 | Yes
111 | 3-HAR-16-62802 | 3-HAR-16-XXXXX | 3-HAR-16- | 62802 | 3-HAR-16-62802 | 3-HAR-16-62802 | Harlingen Area Office (Reg 3) Security System Replacement 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Security system replacement | 21 M | 21 M | Unknown | 157109.68 | 157109.68 | 157109.68 | Unknown |  |  |  |  | 157109.68 | Yes
112 | 4-SAN-16-62803 | 4-SAN-16-XXXXX | 4-SAN-16- | 62803 | 4-SAN-16-62803 | 4-SAN-16-62803 | San Angelo Site (Reg 4) Site Lighting Replacement/Upgrade 1600 W. Loop 306 San Angelo, Texas 76903 | Site Lighting | 21 M | 21 M | Unknown | 43630.08 | 43630.08 | 43630.08 | Unknown |  |  |  |  | 43630.08 | Yes
113 | 5-ABI-16-62804 | 5-ABI-16-XXXXX | 5-ABI-16- | 62804 | 5-ABI-16-62804 | 5-ABI-16-62804 | Abilene Site (Reg 5) Security Lighting Upgrade/Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Security lighting/site lighting replacement/upgrade | 21 M | 21 M | Unknown | 77654.72 | 77654.72 | 77654.72 | Unknown |  |  |  |  | 77654.72 | Yes
114 | 3-BEE-16-62805 | 3-BEE-16-XXXXX | 3-BEE-16- | 62805 | 3-BEE-16-62805 | 3-BEE-16-62805 | Beeville Area Office (Reg 3) Security System Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Security system replacement | 21 M | 21 M | Unknown | 125000 | 125000 | 125000 | Unknown |  |  |  |  | 125000 | Yes
115 | 3-BEE-16-62806 | 3-BEE-16-XXXXX | 3-BEE-16- | 62806 | 3-BEE-16-62806 | 3-BEE-16-62806 | Beeville Site (Reg 3) Communication & Security 400 S. Hillside Drive Beeville, Texas 78102 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown | 3602.56 | 3602.56 | 3602.56 | Unknown |  |  |  |  | 3602.56 | Yes
116 | 3-BEE-16-62807 | 3-BEE-16-XXXXX | 3-BEE-16- | 62807 | 3-BEE-16-62807 | 3-BEE-16-62807 | Beeville Site (Reg 3) Driveway Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Roadways (DPS driveway) pavement replacement | 21 M | 21 M | Unknown | 20000 | 20000 | 20000 | Unknown |  |  |  |  | 20000 | Yes
117 | 3-BEE-16-62808 | 3-BEE-16-XXXXX | 3-BEE-16- | 62808 | 3-BEE-16-62808 | 3-BEE-16-62808 | Beeville Site (Reg 3) Parking Lot Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Parking Lots/roadway replacement | 21 M | 21 M | Unknown | 75000 | 75000 | 75000 | Unknown |  |  |  |  | 75000 | Yes
118 | 3-BEE-16-62809 | 3-BEE-16-XXXXX | 3-BEE-16- | 62809 | 3-BEE-16-62809 | 3-BEE-16-62809 | Beeville Site (Reg 3) Site Lighting Replacement/Upgrade 400 S. Hillside Drive Beeville, Texas 78102 | Site Lighting | 21 M | 21 M | Unknown | 9337.12 | 9337.12 | 9337.12 | Unknown |  |  |  |  | 9337.12 | Yes
119 | 4-BIG-16-62810 | 4-BIG-16-XXXXX | 4-BIG-16- | 62810 | 4-BIG-16-62810 | 4-BIG-16-62810 | Big Spring Area Office (Reg 4) Interior Finishes Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Ceiling, wall, floor finishes replacement | 21 M | 21 M | Unknown | 227175.52 | 227175.52 | 227175.52 | Unknown |  |  |  |  | 227175.52 | Yes
120 | 4-BIG-16-62811 | 4-BIG-16-XXXXX | 4-BIG-16- | 62811 | 4-BIG-16-62811 | 4-BIG-16-62811 | Big Spring Area Office (Reg 4) Exterior Door Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Exterior doors replacement | 21 M | 21 M | Unknown | 2006.16 | 2006.16 | 2006.16 | Unknown |  |  |  |  | 2006.16 | Yes
121 | 4-BIG-16-62812 | 4-BIG-16-XXXXX | 4-BIG-16- | 62812 | 4-BIG-16-62812 | 4-BIG-16-62812 | Big Spring Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 5725 W. IH-20 Big Spring, Texas 79720 | Lighting and Branch Wiring | 21 M | 21 M | Unknown | 4767.36 | 4767.36 | 4767.36 | Unknown |  |  |  |  | 4767.36 | Yes
122 | 4-BIG-16-62813 | 4-BIG-16-XXXXX | 4-BIG-16- | 62813 | 4-BIG-16-62813 | 4-BIG-16-62813 | Big Spring Area Office (Reg 4) Security System Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Security system replacement | 21 M | 21 M | Unknown | 135779.28 | 135779.28 | 135779.28 | Unknown |  |  |  |  | 135779.28 | Yes
123 | 4-BIG-16-62814 | 4-BIG-16-XXXXX | 4-BIG-16- | 62814 | 4-BIG-16-62814 | 4-BIG-16-62814 | Big Spring Area Office (Reg 4) Sprinkler System 5725 W. IH-20 Big Spring, Texas 79720 | Sprinkler System | 21 M | 21 M | Unknown | 60514.48 | 60514.48 | 60514.48 | Unknown |  |  |  |  | 60514.48 | Yes
124 | 4-BIG-16-62815 | 4-BIG-16-XXXXX | 4-BIG-16- | 62815 | 4-BIG-16-62815 | 4-BIG-16-62815 | Big Spring Site (Reg 4) Communication & Security 5725 W. IH-20 Big Spring, Texas 79720 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown | 12940.72 | 12940.72 | 12940.72 | Unknown |  |  |  |  | 12940.72 | Yes
125 | 4-BIG-16-62816 | 4-BIG-16-XXXXX | 4-BIG-16- | 62816 | 4-BIG-16-62816 | 4-BIG-16-62816 | Big Spring Site (Reg 4) Parking Lot/Driveway Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Parking lot replacement, roadways (DPS driveway) pavement replacement | 21 M | 21 M | Unknown | 74893.52 | 74893.52 | 74893.52 | Unknown |  |  |  |  | 74893.52 | Yes
126 | 4-BIG-16-62817 | 4-BIG-16-XXXXX | 4-BIG-16- | 62817 | 4-BIG-16-62817 | 4-BIG-16-62817 | Big Spring Site (Reg 4) Site Lighting Replacement/Upgrade 5725 W. IH-20 Big Spring, Texas 79720 | Site Lighting | 21 M | 21 M | Unknown | 33533.76 | 33533.76 | 33533.76 | Unknown |  |  |  |  | 33533.76 | Yes
127 | 4-BIG-16-62818 | 4-BIG-16-XXXXX | 4-BIG-16- | 62818 | 4-BIG-16-62818 | 4-BIG-16-62818 | Big Spring Storage Building (Reg 4) Electrical Service Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Electrical service/distribution replacement | 21 M | 21 M | Unknown | 13395.2 | 13395.2 | 13395.2 | Unknown |  |  |  |  | 13395.2 | Yes
128 | 5-WIC-16-62819 | 5-WIC-16-XXXXX | 5-WIC-16- | 62819 | 5-WIC-16-62819 | 5-WIC-16-62819 | Wichita Falls Site (Reg 5) Parking Lot Replacement 5505 N. Central Expressway Wichita Falls, Texas 79306 | Parking lot replacement | 21 M | 21 M | Unknown | 260000 | 260000 | 260000 | Unknown |  |  |  |  | 260000 | Yes
129 | 5-WIC-16-62820 | 5-WIC-16-XXXXX | 5-WIC-16- | 62820 | 5-WIC-16-62820 | 5-WIC-16-62820 | Wichita Falls Site (Reg 5) Site Lighting Replacement/Upgrade 5505 N. Central Expressway Wichita Falls, Texas 79306 | Site Lighting | 21 M | 21 M | Unknown | 40254.24 | 40254.24 | 40254.24 | Unknown |  |  |  |  | 40254.24 | Yes
130 | 6-WAC-16-62821 | 6-WAC-16-XXXXX | 6-WAC-16- | 62821 | 6-WAC-16-62821 | 6-WAC-16-62821 | Waco Site (Reg 6) Communication & Security 1617 E. Crest Dr. Waco, Texas 76705 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown | 40913.6 | 40913.6 | 40913.6 | Unknown |  |  |  |  | 40913.6 | Yes
131 | 6-WAC-16-62822 | 6-WAC-16-XXXXX | 6-WAC-16- | 62822 | 6-WAC-16-62822 | 6-WAC-16-62822 | Waco Site (Reg 6) Parking Lot/Paving Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Parking lot/pedestrian paving replacement | 21 M | 21 M | Unknown | 363811.76 | 363811.76 | 363811.76 | Unknown |  |  |  |  | 363811.76 | Yes
132 | 6-WAC-16-62823 | 6-WAC-16-XXXXX | 6-WAC-16- | 62823 | 6-WAC-16-62823 | 6-WAC-16-62823 | Waco Site (Reg 6) Site Lighting Replacement/Upgrade 1617 E. Crest Dr. Waco, Texas 76705 | Site Lighting | 21 M | 21 M | Unknown | 105996.8 | 105996.8 | 105996.8 | Unknown |  |  |  |  | 105996.8 | Yes
133 | 6-WAC-16-62824 | 6-WAC-16-XXXXX | 6-WAC-16- | 62824 | 6-WAC-16-62824 | 6-WAC-16-62824 | Waco Site (Reg 6) Storm Sewer replacement/repair 1617 E. Crest Dr. Waco, Texas 76705 | Storm Sewer replacement/repair | 21 M | 21 M | Unknown | 211420.56 | 211420.56 | 211420.56 | Unknown |  |  |  |  | 211420.56 | Yes
134 | 2-BRE-16-62825 | 2-BRE-16-XXXXX | 2-BRE-16- | 62825 | 2-BRE-16-62825 | 2-BRE-16-62825 | Brenham Site (Reg 2) Communication & Security 975 Hwy 290 West. Brenham, Texas 77834 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown | 3106.48 | 3106.48 | 3106.48 | Unknown |  |  |  |  | 3106.48 | Yes
135 | 2-BRE-16-62826 | 2-BRE-16-XXXXX | 2-BRE-16- | 62826 | 2-BRE-16-62826 | 2-BRE-16-62826 | Brenham Site (Reg 2) Pedestrian paving replacement 975 Hwy 290 West. Brenham, Texas 77834 | Pedestrian paving replacement | 21 M | 21 M | Unknown | 3934.32 | 3934.32 | 3934.32 | Unknown |  |  |  |  | 3934.32 | Yes
136 | 2-BRE-16-62827 | 2-BRE-16-XXXXX | 2-BRE-16- | 62827 | 2-BRE-16-62827 | 2-BRE-16-62827 | Brenham Site (Reg 2) Site Lighting Replacement/Upgrade 975 Hwy 290 West. Brenham, Texas 77834 | Site Lighting | 21 M | 21 M | Unknown | 8049.6 | 8049.6 | 8049.6 | Unknown |  |  |  |  | 8049.6 | Yes
137 | 2-BRE-16-62828 | 2-BRE-16-XXXXX | 2-BRE-16- | 62828 | 2-BRE-16-62828 | 2-BRE-16-62828 | Brenham Site Reg 2) Storm Sewer replacement/repair 975 Hwy 290 West. Brenham, Texas 77834 | Storm Sewer replacement/repair | 21 M | 21 M | Unknown | 16107.52 | 16107.52 | 16107.52 | Unknown |  |  |  |  | 16107.52 | Yes
138 | 3-BRO-16-62829 | 3-BRO-16-XXXXX | 3-BRO-16- | 62829 | 3-BRO-16-62829 | 3-BRO-16-62829 | Brownsville Area Office (Reg 3) Sprinkler System 2901 E. Paredes Line Road Brownsville, Texas 78521 | Sprinkler System | 21 M | 21 M | Unknown | 74402.64 | 74402.64 | 74402.64 | Unknown |  |  |  |  | 74402.64 | Yes
139 | 3-BRO-16-62830 | 3-BRO-16-XXXXX | 3-BRO-16- | 62830 | 3-BRO-16-62830 | 3-BRO-16-62830 | Brownsville Area Office (Reg 3) Electrical Systems 2901 E. Paredes Line Road Brownsville, Texas 78521 | Other Electrical Systems (Add emergency lighting where needed.) | 21 M | 21 M | Unknown | 400000 | 400000 | 400000 | Unknown |  |  |  |  | 400000 | Yes
140 | 3-BRO-16-62831 | 3-BRO-16-XXXXX | 3-BRO-16- | 62831 | 3-BRO-16-62831 | 3-BRO-16-62831 | Brownsville Site (Reg 3) Driveway Replacement 2901 E. Paredes Line Road Brownsville, Texas 78521 | Roadways (DPS driveway) pavement replacement | 21 M | 21 M | Unknown | 24739.52 | 24739.52 | 24739.52 | Unknown |  |  |  |  | 24739.52 | Yes
141 | 3-BRO-16-62832 | 3-BRO-16-XXXXX | 3-BRO-16- | 62832 | 3-BRO-16-62832 | 3-BRO-16-62832 | Brownsville Site (Reg 3) Storm Sewer replacement/repair 2901 E. Paredes Line Road Brownsville, Texas 78521 | Storm Sewer replacement/repair | 21 M | 21 M | Unknown | 39411.84 | 39411.84 | 39411.84 | Unknown |  |  |  |  | 39411.84 | Yes
142 | 4-FOR-16-62833 | 4-FOR-16-XXXXX | 4-FOR-16- | 62833 | 4-FOR-16-62833 | 4-FOR-16-62833 | Fort Stockton Area Office (Reg 4) Security System Replacement 2302 W. Dickinson Boulevard Fort Stockton, Texas 79735 | Security system replacement | 21 M | 21 M | Unknown | 89671.92 | 89671.92 | 89671.92 | Unknown |  |  |  |  | 89671.92 | Yes
143 | 4-LAM-16-62834 | 4-LAM-16-XXXXX | 4-LAM-16- | 62834 | 4-LAM-16-62834 | 4-LAM-16-62834 | Lamesa Area Office (Reg 4) Interior Finishes Replacement 2901 E. Main Lamesa, Texas 79331 | Ceiling, wall finishes replacement | 21 M | 21 M | Unknown | 24428.56 | 24428.56 | 24428.56 | Unknown |  |  |  |  | 24428.56 | Yes
144 | 4-LAM-16-62835 | 4-LAM-16-XXXXX | 4-LAM-16- | 62835 | 4-LAM-16-62835 | 4-LAM-16-62835 | Lamesa Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 2901 E. Main Lamesa, Texas 79331 | Lighting and Branch Wiring | 21 M | 21 M | Unknown | 53836.64 | 53836.64 | 53836.64 | Unknown |  |  |  |  | 53836.64 | Yes
145 | 4-LAM-16-62836 | 4-LAM-16-XXXXX | 4-LAM-16- | 62836 | 4-LAM-16-62836 | 4-LAM-16-62836 | Lamesa Area Office (Reg 4) Equipment (Other) 2901 E. Main Lamesa, Texas 79331 | Other Equipment (Replace manufactured kitchen unit.) | 21 M | 21 M | Unknown | 2618.72 | 2618.72 | 2618.72 | Unknown |  |  |  |  | 2618.72 | Yes
146 | 4-LAM-16-62837 | 4-LAM-16-XXXXX | 4-LAM-16- | 62837 | 4-LAM-16-62837 | 4-LAM-16-62837 | Lamesa Area Office (Reg 4) Exterior Door Replacement 2901 E. Main Lamesa, Texas 79331 | Exterior doors replacement | 21 M | 21 M | Unknown | 2674.88 | 2674.88 | 2674.88 | Unknown |  |  |  |  | 2674.88 | Yes
147 | 4-LAM-16-62838 | 4-LAM-16-XXXXX | 4-LAM-16- | 62838 | 4-LAM-16-62838 | 4-LAM-16-62838 | Lamesa Area Office (Reg 4) Fittings Replacement 2901 E. Main Lamesa, Texas 79331 | Fittings (Specialties) replacement (i.e.: metal toilet partitions and other rest room fittings.) | 21 M | 21 M | Unknown | 2978.56 | 2978.56 | 2978.56 | Unknown |  |  |  |  | 2978.56 | Yes
148 | 4-LAM-16-62839 | 4-LAM-16-XXXXX | 4-LAM-16- | 62839 | 4-LAM-16-62839 | 4-LAM-16-62839 | Lamesa Area Office (Reg 4) Fixed Furnishings Replacement 2901 E. Main Lamesa, Texas 79331 | Fixed furnishings replacement (i.e.: DL Service Counter) | 21 M | 21 M | Unknown | 13785.2 | 13785.2 | 13785.2 | Unknown |  |  |  |  | 13785.2 | Yes
149 | 4-LAM-16-62840 | 4-LAM-16-XXXXX | 4-LAM-16- | 62840 | 4-LAM-16-62840 | 4-LAM-16-62840 | Lamesa Area Office (Reg 4) HVAC Replacement 2901 E. Main Lamesa, Texas 79331 | Terminal & package units replacement/upgrade (Add BAS as needed) | 21 M | 21 M | Unknown | 10400 | 10400 | 10400 | Unknown |  |  |  |  | 10400 | Yes
150 | 4-LAM-16-62841 | 4-LAM-16-XXXXX | 4-LAM-16- | 62841 | 4-LAM-16-62841 | 4-LAM-16-62841 | Lamesa Area Office (Reg 4) Plumbing Fixtures Replacement 2901 E. Main Lamesa, Texas 79331 | Plumbing fixtures replacement (i.e.: toilets/lavatories) | 21 M | 21 M | Unknown | 26312 | 26312 | 26312 | Unknown |  |  |  |  | 26312 | Yes
151 | 4-LAM-16-62842 | 4-LAM-16-XXXXX | 4-LAM-16- | 62842 | 4-LAM-16-62842 | 4-LAM-16-62842 | Lamesa Area Office (Reg 4) Security System Replacement 2901 E. Main Lamesa, Texas 79331 | Security system replacement | 21 M | 21 M | Unknown | 33945.6 | 33945.6 | 33945.6 | Unknown |  |  |  |  | 33945.6 | Yes
152 | 4-LAM-16-62843 | 4-LAM-16-XXXXX | 4-LAM-16- | 62843 | 4-LAM-16-62843 | 4-LAM-16-62843 | Lamesa Area Office (Reg 4) Sprinkler System 2901 E. Main Lamesa, Texas 79331 | Sprinkler System | 21 M | 21 M | Unknown | 15128.88 | 15128.88 | 15128.88 | Unknown |  |  |  |  | 15128.88 | Yes
153 | 4-LAM-16-62844 | 4-LAM-16-XXXXX | 4-LAM-16- | 62844 | 4-LAM-16-62844 | 4-LAM-16-62844 | Lamesa Site (Reg 4) Communication & Security 2901 E. Main Lamesa, Texas 79331 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown | 5200 | 5200 | 5200 | Unknown |  |  |  |  | 5200 | Yes
154 | 4-LAM-16-62845 | 4-LAM-16-XXXXX | 4-LAM-16- | 62845 | 4-LAM-16-62845 | 4-LAM-16-62845 | Lamesa Site (Reg 4) Parking Lot Replacement 2901 E. Main Lamesa, Texas 79331 | Parking lot replacement | 21 M | 21 M | Unknown | 104000 | 104000 | 104000 | Unknown |  |  |  |  | 104000 | Yes
155 | 4-LAM-16-62846 | 4-LAM-16-XXXXX | 4-LAM-16- | 62846 | 4-LAM-16-62846 | 4-LAM-16-62846 | Lamesa Site (Reg 4) Site Lighting Replacement/Upgrade 2901 E. Main Lamesa, Texas 79331 | Site Lighting | 21 M | 21 M | Unknown | 10400 | 10400 | 10400 | Unknown |  |  |  |  | 10400 | Yes
156 | 4-ODE-16-62848 | 4-ODE-16-XXXXX | 4-ODE-16- | 62848 | 4-ODE-16-62848 | 4-ODE-16-62848 | Odessa Area Office (Reg 4) Interior Finishes Replacement 1910 IH-20 West Odessa, Texas 79762 | Ceiling, wall, floor finishes replacement | 21 M | 21 M | Unknown | 239200 | 239200 | 239200 | Unknown |  |  |  |  | 239200 | Yes
157 | 4-ODE-16-62849 | 4-ODE-16-XXXXX | 4-ODE-16- | 62849 | 4-ODE-16-62849 | 4-ODE-16-62849 | Odessa Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 1910 IH-20 West Odessa, Texas 79762 | Lighting and Branch Wiring | 21 M | 21 M | Unknown | 98800 | 98800 | 98800 | Unknown |  |  |  |  | 98800 | Yes
158 | 4-ODE-16-62850 | 4-ODE-16-XXXXX | 4-ODE-16- | 62850 | 4-ODE-16-62850 | 4-ODE-16-62850 | Odessa Area Office (Reg 4 Electrical Service Replacement 1910 IH-20 West Odessa, Texas 79762 | Electrical service/distribution replacement | 21 M | 21 M | Unknown | 34814 | 34814 | 34814 | Unknown |  |  |  |  | 34814 | Yes
159 | 4-ODE-16-62851 | 4-ODE-16-XXXXX | 4-ODE-16- | 62851 | 4-ODE-16-62851 | 4-ODE-16-62851 | Odessa Area Office (Reg 4) DL Interior Wall Relocation 1910 IH-20 West Odessa, Texas 79762 | Relocate Interior walls (DL area) | 21 M | 21 M | Unknown | 52000 | 52000 | 52000 | Unknown |  |  |  |  | 52000 | Yes
160 | 4-ODE-16-62852 | 4-ODE-16-XXXXX | 4-ODE-16- | 62852 | 4-ODE-16-62852 | 4-ODE-16-62852 | Odessa Area Office (Reg 4) Domestic Water Replacement 1910 IH-20 West Odessa, Texas 79762 | Domestic water distribution replacement | 21 M | 21 M | Unknown | 6674.72 | 6674.72 | 6674.72 | Unknown |  |  |  |  | 6674.72 | Yes
161 | 4-ODE-16-62853 | 4-ODE-16-XXXXX | 4-ODE-16- | 62853 | 4-ODE-16-62853 | 4-ODE-16-62853 | Odessa Area Office (Reg 4) Equipment (Other) 1910 IH-20 West Odessa, Texas 79762 | Other Equipment (Replace manufactured refrigerator and remove existing dishwasher and cap plumbing.) | 21 M | 21 M | Unknown | 1738.88 | 1738.88 | 1738.88 | Unknown |  |  |  |  | 1738.88 | Yes
162 | 4-ODE-16-62854 | 4-ODE-16-XXXXX | 4-ODE-16- | 62854 | 4-ODE-16-62854 | 4-ODE-16-62854 | Odessa Area Office (Reg 4) Exterior Window/Door Replacement 1910 IH-20 West Odessa, Texas 79762 | Exterior windows/doors replacement | 21 M | 21 M | Unknown | 43812.08 | 43812.08 | 43812.08 | Unknown |  |  |  |  | 43812.08 | Yes
163 | 4-ODE-16-62855 | 4-ODE-16-XXXXX | 4-ODE-16- | 62855 | 4-ODE-16-62855 | 4-ODE-16-62855 | Odessa Area Office (Reg 4) Fixed Furnishings Replacement 1910 IH-20 West Odessa, Texas 79762 | Fixed furnishings replacement | 21 M | 21 M | Unknown | 18300.88 | 18300.88 | 18300.88 | Unknown |  |  |  |  | 18300.88 | Yes
164 | 4-ODE-16-62856 | 4-ODE-16-XXXXX | 4-ODE-16- | 62856 | 4-ODE-16-62856 | 4-ODE-16-62856 | Odessa Area Office (Reg 4) Foundation Study/Repair 1910 IH-20 West Odessa, Texas 79762 | Standard Foundations | 21 M | 21 M | Unknown | 40278.16 | 40278.16 | 40278.16 | Unknown |  |  |  |  | 40278.16 | Yes
165 | 4-ODE-16-62857 | 4-ODE-16-XXXXX | 4-ODE-16- | 62857 | 4-ODE-16-62857 | 4-ODE-16-62857 | Odessa Area Office (Reg 4) Interior Doors Replacement 1910 IH-20 West Odessa, Texas 79762 | Interior doors replacement | 21 M | 21 M | Unknown | 86320 | 86320 | 86320 | Unknown |  |  |  |  | 86320 | Yes
166 | 4-ODE-16-62858 | 4-ODE-16-XXXXX | 4-ODE-16- | 62858 | 4-ODE-16-62858 | 4-ODE-16-62858 | Odessa Area Office (Reg 4) Plumbing Systems (Other) 1910 IH-20 West Odessa, Texas 79762 | Other Plumbing Systems - Natural gas system is quite old, beyond its expected useful life and should be replaced. | 21 M | 21 M | Unknown | 6383.52 | 6383.52 | 6383.52 | Unknown |  |  |  |  | 6383.52 | Yes
167 | 4-ODE-16-62859 | 4-ODE-16-XXXXX | 4-ODE-16- | 62859 | 4-ODE-16-62859 | 4-ODE-16-62859 | Odessa Area Office (Reg 4) Security System Replacement 1910 IH-20 West Odessa, Texas 79762 | Security system replacement | 21 M | 21 M | Unknown | 156000 | 156000 | 156000 | Unknown |  |  |  |  | 156000 | Yes
168 | 4-ODE-16-62860 | 4-ODE-16-XXXXX | 4-ODE-16- | 62860 | 4-ODE-16-62860 | 4-ODE-16-62860 | Odessa Area Office (Reg 4) Sprinkler System 1910 IH-20 West Odessa, Texas 79762 | Sprinkler System | 21 M | 21 M | Unknown | 78000 | 78000 | 78000 | Unknown |  |  |  |  | 78000 | Yes
169 | 4-ODE-16-62861 | 4-ODE-16-XXXXX | 4-ODE-16- | 62861 | 4-ODE-16-62861 | 4-ODE-16-62861 | Odessa Site (Reg 4) Communication & Security 1910 IH-20 West Odessa, Texas 79762 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown | 55000 | 55000 | 55000 | Unknown |  |  |  |  | 55000 | Yes
170 | 4-NEW-16-62862 | 4-NEW-16-XXXXX | 4-NEW-16- | 62862 | 4-NEW-16-62862 | 4-NEW-16-62862 | New Braunfels Site (Reg 6) Canopy Repair 3003 IH-35 South New Braunfels, Texas 78130 | Canopy repair | 21 M | 21 M | Unknown | 10400 | 10400 | 10400 | Unknown |  |  |  |  | 10400 | Yes
171 | 4-NEW-16-62863 | 4-NEW-16-XXXXX | 4-NEW-16- | 62863 | 4-NEW-16-62863 | 4-NEW-16-62863 | New Braunfels Site (Reg 6) Parking Lot Replacement 3003 IH-35 South New Braunfels, Texas 78130 | Parking lot replacement | 21 M | 21 M | Unknown | 52000 | 52000 | 52000 | Unknown |  |  |  |  | 52000 | Yes
172 | 4-NEW-16-62864 | 4-NEW-16-XXXXX | 4-NEW-16- | 62864 | 4-NEW-16-62864 | 4-NEW-16-62864 | New Braunfels Site (Reg 6) Site Lighting Replacement/Upgrade 3003 IH-35 South New Braunfels, Texas 78130 | Site Lighting | 21 M | 21 M | Unknown | 9729.2 | 9729.2 | 9729.2 | Unknown |  |  |  |  | 9729.2 | Yes
173 | 4-NEW-16-62865 | 4-NEW-16-XXXXX | 4-NEW-16- | 62865 | 4-NEW-16-62865 | 4-NEW-16-62865 | New Braunfels Site (Reg 6) Fuel Distribution Replacement 3003 IH-35 South New Braunfels, Texas 78130 | Fuel distribution replacement | 21 M | 21 M | Unknown | 52000 | 52000 | 52000 | Unknown |  |  |  |  | 52000 | Yes
174 | 4-OZO-16-62866 | 4-OZO-16-XXXXX | 4-OZO-16- | 62866 | 4-OZO-16-62866 | 4-OZO-16-62866 | Ozona Area Office (Reg 4) Interior Finishes Replacement 1503 Monterey St Ozona, Texas 76943 | Ceiling, wall, floor finishes replacement | 21 M | 21 M | Unknown | 45437.6 | 45437.6 | 45437.6 | Unknown |  |  |  |  | 45437.6 | Yes
175 | 4-OZO-16-62867 | 4-OZO-16-XXXXX | 4-OZO-16- | 62867 | 4-OZO-16-62867 | 4-OZO-16-62867 | Ozona Area Office (Reg 4) Exterior Window/Door Replacement 1503 Monterey St Ozona, Texas 76943 | Exterior windows/doors replacement | 21 M | 21 M | Unknown | 23371.92 | 23371.92 | 23371.92 | Unknown |  |  |  |  | 23371.92 | Yes
176 | 4-OZO-16-62868 | 4-OZO-16-XXXXX | 4-OZO-16- | 62868 | 4-OZO-16-62868 | 4-OZO-16-62868 | Ozona Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 1503 Monterey St Ozona, Texas 76943 | Lighting and Branch Wiring | 21 M | 21 M | Unknown | 43069.52 | 43069.52 | 43069.52 | Unknown |  |  |  |  | 43069.52 | Yes
177 | 4-OZO-16-62869 | 4-OZO-16-XXXXX | 4-OZO-16- | 62869 | 4-OZO-16-62869 | 4-OZO-16-62869 | Ozona Area Office (Reg 4) Domestic Water Replacement 1503 Monterey St Ozona, Texas 76943 | Domestic water distribution replacement | 21 M | 21 M | Unknown | 4011.28 | 4011.28 | 4011.28 | Unknown |  |  |  |  | 4011.28 | Yes
178 | 4-OZO-16-62870 | 4-OZO-16-XXXXX | 4-OZO-16- | 62870 | 4-OZO-16-62870 | 4-OZO-16-62870 | Ozona Area Office (Reg 4) Electrical Service Replacement 1503 Monterey St Ozona, Texas 76943 | Electrical service/distribution replacement | 21 M | 21 M | Unknown | 20960.16 | 20960.16 | 20960.16 | Unknown |  |  |  |  | 20960.16 | Yes
179 | 4-OZO-16-62871 | 4-OZO-16-XXXXX | 4-OZO-16- | 62871 | 4-OZO-16-62871 | 4-OZO-16-62871 | Ozona Area Office (Reg 4) Fittings Replacement 1503 Monterey St Ozona, Texas 76943 | Fittings (Specialties) replacement | 21 M | 21 M | Unknown | 2399.28 | 2399.28 | 2399.28 | Unknown |  |  |  |  | 2399.28 | Yes
180 | 4-OZO-16-62872 | 4-OZO-16-XXXXX | 4-OZO-16- | 62872 | 4-OZO-16-62872 | 4-OZO-16-62872 | Ozona Area Office (Reg 4) Interior Doors Replacement 1503 Monterey St Ozona, Texas 76943 | Interior doors replacement | 21 M | 21 M | Unknown | 17413.76 | 17413.76 | 17413.76 | Unknown |  |  |  |  | 17413.76 | Yes
181 | 4-OZO-16-62873 | 4-OZO-16-XXXXX | 4-OZO-16- | 62873 | 4-OZO-16-62873 | 4-OZO-16-62873 | Ozona Area Office (Reg 4) Plumbing Systems 1503 Monterey St Ozona, Texas 76943 | Plumbing fixtures (i.e.: toilets/lavatories)/other plumbing systems replacement- Natural gas system is quite old, beyond its expected useful life and should be replaced. | 21 M | 21 M | Unknown | 24892.4 | 24892.4 | 24892.4 | Unknown |  |  |  |  | 24892.4 | Yes
182 | 4-OZO-16-62874 | 4-OZO-16-XXXXX | 4-OZO-16- | 62874 | 4-OZO-16-62874 | 4-OZO-16-62874 | Ozona Area Office (Reg 4) Sanitary Waste Replacement 1503 Monterey St Ozona, Texas 76943 | Sanitary waste replacement | 21 M | 21 M | Unknown | 10699.52 | 10699.52 | 10699.52 | Unknown |  |  |  |  | 10699.52 | Yes
183 | 4-OZO-16-62875 | 4-OZO-16-XXXXX | 4-OZO-16- | 62875 | 4-OZO-16-62875 | 4-OZO-16-62875 | Ozona Area Office (Reg 4) Security System Replacement 1503 Monterey St Ozona, Texas 76943 | Security system replacement | 21 M | 21 M | Unknown | 7001.28 | 7001.28 | 7001.28 | Unknown |  |  |  |  | 7001.28 | Yes
184 | 4-OZO-16-62876 | 4-OZO-16-XXXXX | 4-OZO-16- | 62876 | 4-OZO-16-62876 | 4-OZO-16-62876 | Ozona Area Office (Reg 4) Sprinkler System 1503 Monterey St Ozona, Texas 76943 | Sprinkler System | 21 M | 21 M | Unknown | 11721.84 | 11721.84 | 11721.84 | Unknown |  |  |  |  | 11721.84 | Yes
185 | 4-OZO-16-62877 | 4-OZO-16-XXXXX | 4-OZO-16- | 62877 | 4-OZO-16-62877 | 4-OZO-16-62877 | Ozona Area Office (Reg 4) Fixed Furnishings Replacement 1503 Monterey St Ozona, Texas 76943 | Fixed furnishings replacement | 21 M | 21 M | Unknown | 11021.92 | 11021.92 | 11021.92 | Unknown |  |  |  |  | 11021.92 | Yes
186 | 4-OZO-16-62878 | 4-OZO-16-XXXXX | 4-OZO-16- | 62878 | 4-OZO-16-62878 | 4-OZO-16-62878 | Ozona Site (Reg 4) Landscaping Upgrade 1503 Monterey St Ozona, Texas 76943 | Landscaping (xeriscape) upgrade | 21 M | 21 M | Unknown | 4703.92 | 4703.92 | 4703.92 | Unknown |  |  |  |  | 4703.92 | Yes
187 | 4-OZO-16-62879 | 4-OZO-16-XXXXX | 4-OZO-16- | 62879 | 4-OZO-16-62879 | 4-OZO-16-62879 | Ozona Site (Reg 4) Parking Lot Replacement 1503 Monterey St Ozona, Texas 76943 | Parking lot replacement | 21 M | 21 M | Unknown | 104000 | 104000 | 104000 | Unknown |  |  |  |  | 104000 | Yes
188 | 4-OZO-16-62880 | 4-OZO-16-XXXXX | 4-OZO-16- | 62880 | 4-OZO-16-62880 | 4-OZO-16-62880 | Ozona Site (Reg 4) Site Lighting Replacement/Upgrade 1503 Monterey St Ozona, Texas 76943 | Site Lighting | 21 M | 21 M | Unknown | 6039.28 | 6039.28 | 6039.28 | Unknown |  |  |  |  | 6039.28 | Yes
189 | 4-OZO-16-62881 | 4-OZO-16-XXXXX | 4-OZO-16- | 62881 | 4-OZO-16-62881 | 4-OZO-16-62881 | Ozona Storage (Reg 4) Special Structures 1503 Monterey St Ozona, Texas 76943 | Special Structures - Storage Bldg. < 1000sf | 21 M | 21 M | Unknown | 7271.68 | 7271.68 | 7271.68 | Unknown |  |  |  |  | 7271.68 | Yes
190 | 4-Pec-16-62882 | 4-Pec-16-XXXXX | 4-Pec-16- | 62882 | 4-Pec-16-62882 | 4-Pec-16-62882 | Pecos Area Office (Reg 4) Security System Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Security system replacement | 21 M | 21 M | Unknown | 54772.64 | 54772.64 | 54772.64 | Unknown |  |  |  |  | 54772.64 | Yes
191 | 6-GEN-16-62883 | 6-GEN-16-XXXXX | 6-GEN-16- | 62883 | 6-GEN-16-62883 | 6-GEN-16-62883 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) 1803 S. General McMullen San Antonio, Texas 78226 | Parking lot replacement | 21 M | 21 M | Unknown | 260000 | 260000 | 260000 | Unknown |  |  |  |  | 260000 | Yes
192 | 6-GEN-16-62884 | 6-GEN-16-XXXXX | 6-GEN-16- | 62884 | 6-GEN-16-62884 | 6-GEN-16-62884 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) Sanitary Waste Replacement 1803 S. General McMullen San Antonio, Texas 78226 | Sanitary waste replacement | 21 M | 21 M | Unknown | 19922.24 | 19922.24 | 19922.24 | Unknown |  |  |  |  | 19922.24 | Yes
193 | 6-GEN-16-62885 | 6-GEN-16-XXXXX | 6-GEN-16- | 62885 | 6-GEN-16-62885 | 6-GEN-16-62885 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) Rain Water Drainage Improvements 1803 S. General McMullen San Antonio, Texas 78226 | Rain Water Drainage | 21 M | 21 M | Unknown | 5254.08 | 5254.08 | 5254.08 | Unknown |  |  |  |  | 5254.08 | Yes
194 | 6-GEN-16-62886 | 6-GEN-16-XXXXX | 6-GEN-16- | 62886 | 6-GEN-16-62886 | 6-GEN-16-62886 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) Site Lighting Replacement/Upgrade 1803 S. General McMullen San Antonio, Texas 78226 | Site Lighting | 21 M | 21 M | Unknown | 110258.72 | 110258.72 | 110258.72 | Unknown |  |  |  |  | 110258.72 | Yes
195 | 6-VIC-16-62887 | 6-VIC-16-XXXXX | 6-VIC-16- | 62887 | 6-VIC-16-62887 | 6-VIC-16-62887 | Victoria Site (Reg 6) Communication & Security 8802 N. Navarro Victoria, Texas 77904 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown | 13783.12 | 13783.12 | 13783.12 | Unknown |  |  |  |  | 13783.12 | Yes
196 | 6-VIC-16-62888 | 6-VIC-16-XXXXX | 6-VIC-16- | 62888 | 6-VIC-16-62888 | 6-VIC-16-62888 | Victoria Site (Reg 6) Driveway Replacement 8802 N. Navarro Victoria, Texas 77904 | Parking lot replacement, pedestrian paving, roadways (DPS driveway) pavement replacement | 21 M | 21 M | Unknown | 176389.2 | 176389.2 | 176389.2 | Unknown |  |  |  |  | 176389.2 | Yes
197 | 6-SEG-16-62889 | 6-SEG-16-XXXXX | 6-SEG-16- | 62889 | 6-SEG-16-62889 | 6-SEG-16-62889 | Seguin Site (Reg 6) Communication & Security 1440 E. Kingsbury Seguin, Texas 78155 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | 21 M | 21 M | Unknown | 3895.84 | 3895.84 | 3895.84 | Unknown |  |  |  |  | 3895.84 | Yes
198 | 6-SEG-16-62890 | 6-SEG-16-XXXXX | 6-SEG-16- | 62890 | 6-SEG-16-62890 | 6-SEG-16-62890 | Seguin Site (Reg 6) Parking Lot Replacement 1440 E. Kingsbury Seguin, Texas 78155 | Parking lot, pedestrian paving replacement | 21 M | 21 M | Unknown | 161000 | 161000 | 161000 | Unknown |  |  |  |  | 161000 | Yes
199 | 6-SEG-16-62891 | 6-SEG-16-XXXXX | 6-SEG-16- | 62891 | 6-SEG-16-62891 | 6-SEG-16-62891 | Seguin Site (Reg 6) Site Lighting Replacement/Upgrade 1440 E. Kingsbury Seguin, Texas 78155 | Site Lighting | 21 M | 21 M | Unknown | 10095.28 | 10095.28 | 10095.28 | Unknown |  |  |  |  | 10095.28 | Yes
200 | ST-TEST-16-62892 | ST-TEST-16-XXXXX | ST-TEST-16- | 62892 | ST-TEST-16-62892 | ST-TEST-16-62892 | Statewide Support Project Consultants | Funding for testing, consulting, commissioning, CMT, inspections type of expenditures associated with projects. | 21 M | 21 M | Unknown | 455199.82 | 455199.82 | 455199.82 | Unknown |  |  |  |  | 455199.82 | Yes
201 | ST-PM-16-62893 | ST-PM-16-XXXXX | ST-PM-16- | 62893 | ST-PM-16-62893 | ST-PM-16-62893 | Statewide TFC Project Mgmt. Fees | TFC Project Management fees. | 21 M | 21 M | Unknown | 616800 | 616800 | 616800 | Unknown |  |  |  |  | 616800 | Yes
202 | ST-CON-16-62894 | ST-CON-16-XXXXX | ST-CON-16- | 62894 | ST-CON-16-62894 | ST-CON-16-62894 | Statewide Unexpected DM repairs/Project Contingency | Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. | 21 M | 21 M | Unknown | 1852154.56 | 1852154.56 | 1796186.55 | Unknown |  |  |  |  | 1796186.55 | Yes
[11 empty] | Totals: | 38778877 | 38778877 | 38778876.99 |  |  |  | 0 | 0 | 38778876.99

## DPS Notes 3.16
| Agency: | Texas Department of Public Safety - 0405
| Date: | 2016-03-15
| Prepared by: | Tavia Wendlandt
Project Priority | Supplemental Information
1-51 | Received LBB approval February 2, 2016 to expend Rider 40 funding of $17.8M.
2-3 | Formally priorities #37 and #38, up to priorities #2 and #3; these are ongoing DM projects and additional funding is needed to complete these projects.
3 | Preliminary construction manager at risk (CMR) estimate received in February 2016 is $625,000. Report adjusted to reflect this current estimate.
49 | TFC informally notified DPS the number of projects that will administered by TFC. The estimated Project Management fee is reduced to $300,000.
50 | Contingency reflects for differences as a result of project estimate changes.
51 | Used contingency fund to replace Childress radio shop roof (leaking and contains asbestos) - $50,000 (Index 62461).
Former priorities #2, #4 and #5 were not approved. Removed from priority list and replaced with $5M additional DM projects.
52 | New DM project - agency savings identified from IT operating index; the savings are derived from the transitioning away from staff augmentation expenses to regular salary. Infrastructure is outdated and needed to be replaced to protect data center which includes Agency's mainframe and servers.
53-106 | Request sent March 2, 2016 to LBB seeking approval to use $10.7 of G.O. Bond savings from 80th Legislative Session $200M bond package for these projects.
53-54 | Formally priority 54 and 55 - projects moved to $21M unfunded portion to accommodate cost increase in the priority #3 - Austin NW roof estimate from the Construction manager at risk (CMR).
98-105 | New projects identified as needing higher priority.
107-202 | Agency is attempting to identify savings in order to fund the remaining $8.5M of the $21M in deferred maintenance projects.
202 | Contingency amount adjusted to accommodate changes in $21M listed projects.
Waiting for LBB approval of funding to begin project; Excerpt from letter to LBB: “Per Article IX Sec. 14.03 (h) (3) Limitation on Expenditures – Capital Budget, the Department of Public Safety requests to transfer appropriations from a capital budget item to a non-capital budget item. Capital budget authority of $21, 000,000 is included in Article V, Rider 2 b. (2) Deferred Maintenance for deferred maintenance projects at the Department of Public Safety, however additional appropriations of $21,000,000 were not provided. This situation results in a $21,000,000 reduction to our Agency’s operations which cause undue hardship on the Agency’s programs. The Department requests a transfer of $11,139,565 in fiscal year 2016 and $9,860,435 in fiscal year 2017 from a capital budget item to a non-capital budget item.”

## DPS 12.15
| Agency: | [5 empty] | Texas Department of Public Safety - 0405
| Date: | [5 empty] | 2015-12-15
| Prepared by: | [5 empty] | Tavia Wendlandt
Project Priority | Agency ID | Agency ID with XXXXX | Agency ID - with out index | Index | Concantenate | Agency ID - Absolute | Project Name & Location | Project Description | Type | Category | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | ST-TEMP-62601 | ST-TEMP-XXXXX | ST-TEMP- | 62601 | ST-TEMP-62601 | ST-TEMP-62601 | Statewide Temporary DM Staff | Temporary staff needed to administer DM projects. (estimate two years) | Rider 40 | Professional Fees | General Revenue (Fund 0001) - Pending LBB approval | 215000 | 215000 | Pending LBB approval. |  |  |  |  | 215000 | Yes
2 | HQ-CAM-16-62602 | HQ-CAM-16-XXXXX | HQ-CAM-16- | 62602 | HQ-CAM-16-62602 | HQ-CAM-16-62602 | Austin HQ Campus Campus Relocation Study 5805 North Lamar Blvd Austin, Texas 78752 | Campus relocation study (Rider 54). Includes campus conceptual design. | Rider 40 | Professional Fees | General Revenue (Fund 0001) - Pending LBB approval | 2000000 | 2000000 | Pending LBB approval. |  |  |  |  | 2000000 | Yes
3 | 2-LUF-16-62603 | 2-LUF-16-XXXXX | 2-LUF-16- | 62603 | 2-LUF-16-62603 | 2-LUF-16-62603 | Lufkin Lease Refresh - Lufkin CID Lease (Reg 2) 2815 John Redditt Dr. Lufkin, Texas 75904 | Refurbishment and equipping of a certain leased facility in Lufkin for use by CID as per Rider 63. | Rider 40 | Facility Repairs to Infrastructure/ foundation | General Revenue (Fund 0001) - Pending LBB approval | 200000 | 200000 | Pending LBB approval. |  |  |  |  | 200000 | Yes
4 | ST-FCA-16-62604 | ST-FCA-16-XXXXX | ST-FCA-16- | 62604 | ST-FCA-16-62604 | ST-FCA-16-62604 | Statewide Facility Condition Assessment | Statewide Assessment: An updated professional statewide Facility Condition Assessment study is needed to identify current deferred maintenance and capital renewal projects and associated costs. | Rider 40 | Professional Fees | General Revenue (Fund 0001) - Pending LBB approval | 1300000 | 1300000 | Pending LBB approval. |  |  |  |  | 1300000 | Yes
5 | ST-IWMS-16-62605 | ST-IWMS-16-XXXXX | ST-IWMS-16- | 62605 | ST-IWMS-16-62605 | ST-IWMS-16-62605 | Statewide Integrated Workplace Management System | A computerized Integrated Workplace Management system (IWMS) that is web based and can be implemented statewide is needed to track and plan for maintenance of DPS facilities. As funding permits, this will include the implementation of space management, inventory management, lease management, and environmental sustainability integration . | Rider 40 | Professional Fees | General Revenue (Fund 0001) - Pending LBB approval | 1700000 | 1700000 | Pending LBB approval. |  |  |  |  | 1700000 | Yes
6 | 1-GAR-16-62606 | 1-GAR-16-XXXXX | 1-GAR-16- | 62606 | 1-GAR-16-62606 | 1-GAR-16-62606 | Garland Regional Office (Reg 1) HVAC Replacement 350 West IH-30 Garland, Texas 75043 | Heating Ventilation Air Conditioning (HVAC) System replacement in the Annex Facility | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 400000 | 400000 | Pending LBB approval. |  |  |  |  | 400000 | Yes
7 | 1-HUR-16-62607 | 1-HUR-16-XXXXX | 1-HUR-16- | 62607 | 1-HUR-16-62607 | 1-HUR-16-62607 | Hurst District Office (Reg 1) HVAC Replacement 624 NE Loop 820 Hurst, Texas 76053 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 302623 | 302623 | Pending LBB approval. |  |  |  |  | 302623 | Yes
8 | 5-WIC-16-62608 | 5-WIC-16-XXXXX | 5-WIC-16- | 62608 | 5-WIC-16-62608 | 5-WIC-16-62608 | Wichita Falls Sub-District Office (Reg 5) Roof Replacement 5505 N. Central Expressway Wichita Falls, Texas 79306 | Replace Roof - construction phase. (TFC is engineering roof replacement from Rider 45 DM funds) | Rider 40 | Roofing and Exterior Repairs | General Revenue (Fund 0001) - Pending LBB approval | 200000 | 200000 | Pending LBB approval. |  |  |  |  | 200000 | Yes
9 | 2-BEU-16-62609 | 2-BEU-16-XXXXX | 2-BEU-16- | 62609 | 2-BEU-16-62609 | 2-BEU-16-62609 | Beaumont District Office (Reg 2) HVAC Replacement 7200 Eastex Freeway Beaumont, Texas 77708 | Replacement of Heating Ventilation Air Conditioning (HVAC) Distribution System. | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 315000 | 315000 | Pending LBB approval. |  |  |  |  | 315000 | Yes
10 | 3-LAR-16-62610 | 3-LAR-16-XXXXX | 3-LAR-16- | 62610 | 3-LAR-16-62610 | 3-LAR-16-62610 | Laredo District Office (Reg 3) Vacant area refresh 1901 Bob Bullock Loop Laredo, Texas 78043 | Vacant lab area - Refresh all deteriorated finishes and systems, lighting, roof, HVAC, and other infrastructure serving that area. | Rider 40 | Facility Repairs to Infrastructure/ Foundation | General Revenue (Fund 0001) - Pending LBB approval | 150000 | 150000 | Pending LBB approval. |  |  |  |  | 150000 | Yes
11 | 5-ABI-16-62611 | 5-ABI-16-XXXXX | 5-ABI-16- | 62611 | 5-ABI-16-62611 | 5-ABI-16-62611 | Abilene District Office (Reg 5) HVAC Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 260000 | 260000 | Pending LBB approval. |  |  |  |  | 260000 | Yes
12 | 1-CLE-16-62612 | 1-CLE-16-XXXXX | 1-CLE-16- | 62612 | 1-CLE-16-62612 | 1-CLE-16-62612 | Cleburne Area Office (Reg 1) HVAC Replacement 600 W. Kilpatrick St. Cleburne, Texas 76031 | Heating Ventilation Air Conditioning (HVAC) System replacement | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 325000 | 325000 | Pending LBB approval. |  |  |  |  | 325000 | Yes
13 | 5-CHI-16-62613 | 5-CHI-16-XXXXX | 5-CHI-16- | 62613 | 5-CHI-16-62613 | 5-CHI-16-62613 | Childress Area Office (Reg 5) HVAC Replacement 1700 Ave. F Northwest Childress, Texas 79201 | Replacement of Heating Ventilation Air Conditioning (HVAC) System. | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 500000 | 500000 | Pending LBB approval. |  |  |  |  | 500000 | Yes
14 | 2-HGR-16-62614 | 2-HGR-16-XXXXX | 2-HGR-16- | 62614 | 2-HGR-16-62614 | 2-HGR-16-62614 | Houston Grant Road Driver License Office (Reg 2) Drainage Repairs - 10503 Grant Road Houston, Texas 77070 | DL parking lot repairs and drainage deficiencies | Rider 40 | Site Work Paving | General Revenue (Fund 0001) - Pending LBB approval | 250000 | 250000 | Pending LBB approval. |  |  |  |  | 250000 | Yes
15 | 4-ODE-16-62615 | 4-ODE-16-XXXXX | 4-ODE-16- | 62615 | 4-ODE-16-62615 | 4-ODE-16-62615 | Odessa Area Office (Reg 4) HVAC Replacement 1910 IH-20 West Odessa, Texas 79762 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 150714 | 150714 | Pending LBB approval. |  |  |  |  | 150714 | Yes
16 | 4-GAT-16-62616 | 4-GAT-16-XXXXX | 4-GAT-16- | 62616 | 4-GAT-16-62616 | 4-GAT-16-62616 | El Paso Gateway East Driver License Office (Reg 4) HVAC Replacement 7300 Gateway East El Paso, Texas 79915 | Heating Ventilation Air Conditioning (HVAC) System replacement (includes controls) | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 200000 | 200000 | Pending LBB approval. |  |  |  |  | 200000 | Yes
17 | HQ-L-16-62617 | HQ-L-16-XXXXX | HQ-L-16- | 62617 | HQ-L-16-62617 | HQ-L-16-62617 | Austin HQ (Building L) HVAC Replacement 5710 Guadalupe Austin, Texas 78752 | Partial RTU replacements - Building L - Fleet Operations | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 78000 | 78000 | Pending LBB approval. |  |  |  |  | 78000 | Yes
18 | HQ-GA-16-62618 | HQ-GA-16-XXXXX | HQ-GA-16- | 62618 | HQ-GA-16-62618 | HQ-GA-16-62618 | Austin HQ (Building G Annex) Chiller/Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace chillers/boilers in Building G Annex - Multi-Service Facility | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 769600 | 769600 | Pending LBB approval. |  |  |  |  | 769600 | Yes
19 | HQ-E-16-62619 | HQ-E-16-XXXXX | HQ-E-16- | 62619 | HQ-E-16-62619 | HQ-E-16-62619 | Austin HQ (Building E) Boiler Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace boiler in Building E - Law Enforcement Facility | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 78000 | 78000 | Pending LBB approval. |  |  |  |  | 78000 | Yes
20 | HQ-C-16-62620 | HQ-C-16-XXXXX | HQ-C-16- | 62620 | HQ-C-16-62620 | HQ-C-16-62620 | Austin HQ (Building C) HVAC Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial HVAC replacement for Building C Training Academy | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 520000 | 520000 | Pending LBB approval. |  |  |  |  | 520000 | Yes
21 | HQ-A-16-62621 | HQ-A-16-XXXXX | HQ-A-16- | 62621 | HQ-A-16-62621 | HQ-A-16-62621 | Austin HQ (Building A) Roof Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial roof replacement for Building A | Rider 40 | Roofing and Exterior Repairs | General Revenue (Fund 0001) - Pending LBB approval | 1040000 | 1040000 | Pending LBB approval. |  |  |  |  | 1040000 | Yes
22 | HQ-E-16-62622 | HQ-E-16-XXXXX | HQ-E-16- | 62622 | HQ-E-16-62622 | HQ-E-16-62622 | Austin HQ (Building E) Roof Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Partial roof replacement for Building E - Law Enforcement Facility | Rider 40 | Roofing and Exterior Repairs | General Revenue (Fund 0001) - Pending LBB approval | 1787058 | 1787058 | Pending LBB approval. |  |  |  |  | 1787058 | Yes
23 | HQ-O-16-62623 | HQ-O-16-XXXXX | HQ-O-16- | 62623 | HQ-O-16-62623 | HQ-O-16-62623 | Austin HQ (Building O) Sprinkler System 5601 Guadalupe Austin, Texas 78752 | Add Sprinklers (Fire Marshal recommendation) - Building O Fleet Operations | Rider 40 | Safety | General Revenue (Fund 0001) - Pending LBB approval | 26000 | 26000 | Pending LBB approval. |  |  |  |  | 26000 | Yes
24 | 2-CON-16-62624 | 2-CON-16-XXXXX | 2-CON-16- | 62624 | 2-CON-16-62624 | 2-CON-16-62624 | Conroe District Office (Reg 2) Ductwork Replacement 2 Hilbig St. Conroe, Texas 77301 | Ductwork replacement-system reviewed and found contaminants and poor IAQ in facility due to condition of ductwork. Funding request to replace all flex duct and have the hard duct cleaned and sealed. (Includes office and Motor Vehicle Theft (MVT) Garage | Rider 40 | HVAC | General Revenue (Fund 0001) - Pending LBB approval | 603870 | 603870 | Pending LBB approval. |  |  |  |  | 603870 | Yes
25 | 1-GAR-16-62625 | 1-GAR-16-XXXXX | 1-GAR-16- | 62625 | 1-GAR-16-62625 | 1-GAR-16-62625 | Garland Regional Office (Reg 1) Site Lighting Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged site lighting. | Rider 40 | Site Work Paving | General Revenue (Fund 0001) - Pending LBB approval | 134006 | 134006 | Pending LBB approval. |  |  |  |  | 134006 | Yes
26 | 1-GAR-16-62626 | 1-GAR-16-XXXXX | 1-GAR-16- | 62626 | 1-GAR-16-62626 | 1-GAR-16-62626 | Garland Regional Office (Reg 1) Electrical Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged electrical system | Rider 40 | Facility Repairs to Infrastructure/ foundation | General Revenue (Fund 0001) - Pending LBB approval | 574870 | 574870 | Pending LBB approval. |  |  |  |  | 574870 | Yes
27 | 1-GAR-16-62627 | 1-GAR-16-XXXXX | 1-GAR-16- | 62627 | 1-GAR-16-62627 | 1-GAR-16-62627 | Garland Regional Office (Reg 1) Plumbing Replacement 350 West IH-30 Garland, Texas 75043 | Replace aged plumbing (ie: Natural Gas system, domestic water system and fixtures, etc) | Rider 40 | Facility Repairs to Infrastructure/ foundation | General Revenue (Fund 0001) - Pending LBB approval | 517577 | 517577 | Pending LBB approval. |  |  |  |  | 517577 | Yes
28 | 1-GAR-16-62628 | 1-GAR-16-XXXXX | 1-GAR-16- | 62628 | 1-GAR-16-62628 | 1-GAR-16-62628 | Garland Regional Office (Reg 1) Foundation Study 350 West IH-30 Garland, Texas 75043 | Several signs of stress and settlement is seen throughout the facility, specifically on the Westside of the building. Recommend a professional structural engineering study be conducted for resolution. | Rider 40 | Facility Repairs to Infrastructure/ foundation | General Revenue (Fund 0001) - Pending LBB approval | 150000 | 150000 | Pending LBB approval. |  |  |  |  | 150000 | Yes
29 | 2-PIE-16-62629 | 2-PIE-16-XXXXX | 2-PIE-16- | 62629 | 2-PIE-16-62629 | 2-PIE-16-62629 | Pierce Sub-District Office (Reg 2) Foundation Study 19692 US Hwy 59 El Campo, Texas 77437 | Northwest wall and a part of Northeast wall are showings signs of structural degradation. Recommend professional study. | Rider 40 | Facility Repairs to Infrastructure/ foundation | General Revenue (Fund 0001) - Pending LBB approval | 150000 | 150000 | Pending LBB approval. |  |  |  |  | 150000 | Yes
30 | 2-BAY-16-62630 | 2-BAY-16-XXXXX | 2-BAY-16- | 62630 | 2-BAY-16-62630 | 2-BAY-16-62630 | Baytown Area Office (Reg 2) Foundation Repairs 5420 Decker Drive Baytown, Texas 77520 | Repair foundation / interior finishes | Rider 40 | Facility Repairs to Infrastructure/ Foundation | General Revenue (Fund 0001) - Pending LBB approval | 150000 | 150000 | Pending LBB approval. |  |  |  |  | 150000 | Yes
31 | 5-CHI-16-62631 | 5-CHI-16-XXXXX | 5-CHI-16- | 62631 | 5-CHI-16-62631 | 5-CHI-16-62631 | Childress Area Office (Reg 5) Foundation Study 1700 Ave. F Northwest Childress, Texas 79201 | The retaining walls are cracking and showing signs of structural problems. Recommend professional study. | Rider 40 | Facility Repairs to Infrastructure/ foundation | General Revenue (Fund 0001) - Pending LBB approval | 150000 | 150000 | Pending LBB approval. |  |  |  |  | 150000 | Yes
32 | 1-SUL-16-62632 | 1-SUL-16-XXXXX | 1-SUL-16- | 62632 | 1-SUL-16-62632 | 1-SUL-16-62632 | Sulphur Springs Area Office (Reg 1) Foundation Study 1528 E. Shannon Road Sulphur Springs, Texas 75482 | Settlement cracks in foundation, exterior walls, and interior wall systems. Recommend a professional structural engineering study be conducted for resolution. | Rider 40 | Facility Repairs to Infrastructure/ foundation | General Revenue (Fund 0001) - Pending LBB approval | 150000 | 150000 | Pending LBB approval. |  |  |  |  | 150000 | Yes
33 | 2-CON-16-62633 | 2-CON-16-XXXXX | 2-CON-16- | 62633 | 2-CON-16-62633 | 2-CON-16-62633 | Conroe District Office (Reg 2) Foundation Study 2 Hilbig St. Conroe, Texas 77301 | Exterior walls are showing stress and damage at the MVT Garage. Recommend professional structure analysis to determine condition and repair of exterior wall and implement repairs. | Rider 40 | Facility Repairs to Infrastructure/ foundation | General Revenue (Fund 0001) - Pending LBB approval | 185000 | 185000 | Pending LBB approval. |  |  |  |  | 185000 | Yes
34 | HQ-L-16-62634 | HQ-L-16-XXXXX | HQ-L-16- | 62634 | HQ-L-16-62634 | HQ-L-16-62634 | Austin HQ (Building L) Car Wash Replacement 5710 Guadalupe Austin, Texas 78752 | Replace car wash at Fleet Operations - Building L | Rider 40 | Facility Repairs to Infrastructure/ foundation | General Revenue (Fund 0001) - Pending LBB approval | 100000 | 100000 | Pending LBB approval. |  |  |  |  | 100000 | Yes
35 | ST-PM-16-62635 | ST-PM-16-XXXXX | ST-PM-16- | 62635 | ST-PM-16-62635 | ST-PM-16-62635 | Statewide TFC Project Mgmt Fees | TFC Project Management fees. | Rider 40 | Professional Fees | General Revenue (Fund 0001) - Pending LBB approval | 616800 | 616800 | Pending LBB approval. |  |  |  |  | 616800 | Yes
36 | ST-CON-16-62636 | ST-CON-16-XXXXX | ST-CON-16- | 62636 | ST-CON-16-62636 | ST-CON-16-62636 | Statewide Unexpected DM repairs/Project Contingency | Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. | Rider 40 | Unexpended DM repairs/Project Contingency | General Revenue (Fund 0001) - Pending LBB approval | 1529759 | 1529759 | Pending LBB approval. |  |  |  |  | 1529759 | Yes
37 | 3-COR-16-62737 | 3-COR-16-XXXXX | 3-COR-16- | 62737 | 3-COR-16-62737 | 3-COR-16-62737 | Corpus Christi District Office (Reg 3) DM Multi-system project 1922 S. Padre Island Drive Corpus Christi, Texas 78416 | Complete ongoing DM projects (HVAC, Sanitary Sewer, Etc.) | DM $21 | Facility Repairs to Infrastructure/ foundation | Unknown | 780000 | 780000 | Unknown |  |  |  |  | 780000 | Yes
38 | 6-ANW-16-62738 | 6-ANW-16-XXXXX | 6-ANW-16- | 62738 | 6-ANW-16-62738 | 6-ANW-16-62738 | Austin Northwest Area Office (Reg 6) Roof Replacement 13730 Research Boulevard Austin, Texas 78750 | Partial roof replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 250000 | 250000 | Unknown |  |  |  |  | 250000 | Yes
39 | 4-ODE-16-62847 | 4-ODE-16-XXXXX | 4-ODE-16- | 62847 | 4-ODE-16-62847 | 4-ODE-16-62847 | Odessa Area Office (Reg 4) HVAC Replacement 1910 IH-20 West Odessa, Texas 79762 | Terminal & Package Units (Building Automation System) | DM $21 | HVAC | Unknown | 234000 | 234000 | Unknown |  |  |  |  | 234000 | Yes
40 | 4-ODE-16-62754 | 4-ODE-16-XXXXX | 4-ODE-16- | 62754 | 4-ODE-16-62754 | 4-ODE-16-62754 | Odessa Area Office (Reg 4) Roof Replacement 1910 IH-20 West Odessa, Texas 79762 | Roof Coverings/openings-built-up roofing replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 249600 | 249600 | Unknown |  |  |  |  | 249600 | Yes
41 | ST-FUEL-16-62739 | ST-FUEL-16-XXXXX | ST-FUEL-16- | 62739 | ST-FUEL-16-62739 | ST-FUEL-16-62739 | Statewide Fuel System Maintenance/Removal | UST/AST fueling systems repairs/maintenance/removal | DM $21 | Site Work Paving | Unknown | 250000 | 250000 | Unknown |  |  |  |  | 250000 | Yes
42 | 5-AMA-16-62740 | 5-AMA-16-XXXXX | 5-AMA-16- | 62740 | 5-AMA-16-62740 | 5-AMA-16-62740 | Amarillo District Office (Reg 5) Exterior Door/Window Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Exterior doors replacement/Window replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 167666.72 | 167666.72 | Unknown |  |  |  |  | 167666.72 | Yes
43 | 6-ADO-16-62741 | 6-ADO-16-XXXXX | 6-ADO-16- | 62741 | 6-ADO-16-62741 | 6-ADO-16-62741 | Austin District Office (Reg 6) HVAC Replacement 9000 IH-35 North Austin, Texas 78753 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | DM $21 | HVAC | Unknown | 192294.48 | 192294.48 | Unknown |  |  |  |  | 192294.48 | Yes
44 | 6-ADO-16-62742 | 6-ADO-16-XXXXX | 6-ADO-16- | 62742 | 6-ADO-16-62742 | 6-ADO-16-62742 | Austin District Office (Reg 6) Roof Replacement 9000 IH-35 North Austin, Texas 78753 | Roof Coverings built-up roofing replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 338000 | 338000 | Unknown |  |  |  |  | 338000 | Yes
45 | 2-HHQ-16-62743 | 2-HHQ-16-XXXXX | 2-HHQ-16- | 62743 | 2-HHQ-16-62743 | 2-HHQ-16-62743 | Houston Regional Headquarters (West Road) Crime Lab (Reg 2) Chiller Replacement 12230 West Road Jersey Village, Texas 77065 | Chiller replacement | DM $21 | HVAC | Unknown | 312000 | 312000 | Unknown |  |  |  |  | 312000 | Yes
46 | 4-SAN-16-62744 | 4-SAN-16-XXXXX | 4-SAN-16- | 62744 | 4-SAN-16-62744 | 4-SAN-16-62744 | San Angelo Sub-District Office (Reg 4) HVAC Replacement 1600 W. Loop 306 San Angelo, Texas 76903 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | DM $21 | HVAC | Unknown | 633900.8 | 633900.8 | Unknown |  |  |  |  | 633900.8 | Yes
47 | 4-SAN-16-62745 | 4-SAN-16-XXXXX | 4-SAN-16- | 62745 | 4-SAN-16-62745 | 4-SAN-16-62745 | San Angelo Sub-District Office (Reg 4) Roof Replacement 1600 W. Loop 306 San Angelo, Texas 76903 | Roof Coverings built-up roofing replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 325000 | 325000 | Unknown |  |  |  |  | 325000 | Yes
48 | 1-HUR-16-62746 | 1-HUR-16-XXXXX | 1-HUR-16- | 62746 | 1-HUR-16-62746 | 1-HUR-16-62746 | Hurst Sub-District Office (Reg 1) Roof Replacement 624 NE Loop 820 Hurst, Texas 76053 | Roof Coverings built-up roofing replacement (Including roof openings) | DM $21 | Roofing and Exterior Repairs | Unknown | 430981.2 | 430981.2 | Unknown |  |  |  |  | 430981.2 | Yes
49 | 3-EAG-16-62747 | 3-EAG-16-XXXXX | 3-EAG-16- | 62747 | 3-EAG-16-62747 | 3-EAG-16-62747 | Eagle Pass Area Office (Reg 3) HVAC Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Terminal & package units replacement/upgrade (Add BAS as needed) | DM $21 | HVAC | Unknown | 10000 | 10000 | Unknown |  |  |  |  | 10000 | Yes
50 | 3-HAR-16-62748 | 3-HAR-16-XXXXX | 3-HAR-16- | 62748 | 3-HAR-16-62748 | 3-HAR-16-62748 | Harlingen Area Office (Reg 3) Roof Replacement 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Roof Coverings built-up roofing replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 325000 | 325000 | Unknown |  |  |  |  | 325000 | Yes
51 | 3-BEE-16-62749 | 3-BEE-16-XXXXX | 3-BEE-16- | 62749 | 3-BEE-16-62749 | 3-BEE-16-62749 | Beeville Area Office (Reg 3) HVAC Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Terminal & package units replacement/upgrade (Add BAS as needed) | DM $21 | HVAC | Unknown | 10000 | 10000 | Unknown |  |  |  |  | 10000 | Yes
52 | 3-BEE-16-62750 | 3-BEE-16-XXXXX | 3-BEE-16- | 62750 | 3-BEE-16-62750 | 3-BEE-16-62750 | Beeville Area Office (Reg 3) Roof Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Roof Coverings built-up roofing replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 150000 | 150000 | Unknown |  |  |  |  | 150000 | Yes
53 | 4-BIG-16-62751 | 4-BIG-16-XXXXX | 4-BIG-16- | 62751 | 4-BIG-16-62751 | 4-BIG-16-62751 | Big Spring Area Office (Reg 4) HVAC Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Terminal & package units replacement/upgrade - including split DX (Add BAS as needed) | DM $21 | HVAC | Unknown | 2954.64 | 2954.64 | Unknown |  |  |  |  | 2954.64 | Yes
54 | 2-BRE-16-62752 | 2-BRE-16-XXXXX | 2-BRE-16- | 62752 | 2-BRE-16-62752 | 2-BRE-16-62752 | Brenham Area Office (Reg 2) HVAC Controls Replacement 975 Hwy 290 West. Brenham, Texas 77834 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | DM $21 | HVAC | Unknown | 168720.24 | 168720.24 | Unknown |  |  |  |  | 168720.24 | Yes
55 | 2-BRE-16-62753 | 2-BRE-16-XXXXX | 2-BRE-16- | 62753 | 2-BRE-16-62753 | 2-BRE-16-62753 | Brenham Area Office (Reg 2) Roof Replacement 975 Hwy 290 West. Brenham, Texas 77834 | Roof Coverings built-up roofing replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 130000 | 130000 | Unknown |  |  |  |  | 130000 | Yes
56 | 2-ORA-16-62755 | 2-ORA-16-XXXXX | 2-ORA-16- | 62755 | 2-ORA-16-62755 | 2-ORA-16-62755 | Orange Area Office (Reg 2) Roof Replacement 711 South Hwy 87 Orange, Texas 77630 | Roof Coverings built-up roofing replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 182000 | 182000 | Unknown |  |  |  |  | 182000 | Yes
57 | 4-OZO-16-62756 | 4-OZO-16-XXXXX | 4-OZO-16- | 62756 | 4-OZO-16-62756 | 4-OZO-16-62756 | Ozona Area Office (Reg 4) HVAC Replacement 1503 Monterey St Ozona, Texas 76943 | HVAC controls & instrumentation replacement, distribution systems, Terminal & package units replacement/upgrade (Add BAS as needed), HVAC test and balance | DM $21 | HVAC | Unknown | 132242.24 | 132242.24 | Unknown |  |  |  |  | 132242.24 | Yes
58 | 4-Pec-16-62757 | 4-Pec-16-XXXXX | 4-Pec-16- | 62757 | 4-Pec-16-62757 | 4-Pec-16-62757 | Pecos Area Office (Reg 4) HVAC Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Terminal & package units replacement/upgrade (Add BAS as needed), Distribution systems, controls and instrumentation replacement | DM $21 | HVAC | Unknown | 117413.92 | 117413.92 | Unknown |  |  |  |  | 117413.92 | Yes
59 | 4-Pec-16-62758 | 4-Pec-16-XXXXX | 4-Pec-16- | 62758 | 4-Pec-16-62758 | 4-Pec-16-62758 | Pecos Area Office (Reg 4) Roof Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Roof Coverings built-up roofing replacement/roof openings | DM $21 | Roofing and Exterior Repairs | Unknown | 133023.28 | 133023.28 | Unknown |  |  |  |  | 133023.28 | Yes
60 | 3-UVA-16-62759 | 3-UVA-16-XXXXX | 3-UVA-16- | 62759 | 3-UVA-16-62759 | 3-UVA-16-62759 | Uvalde Area Office (Reg 3) Roof Replacement 2901 E. Main Uvalde, Texas 78801 | Roof Coverings built-up roofing replacement/roof openings | DM $21 | Roofing and Exterior Repairs | Unknown | 102397.2 | 102397.2 | Unknown |  |  |  |  | 102397.2 | Yes
61 | 1-GAR-16-62760 | 1-GAR-16-XXXXX | 1-GAR-16- | 62760 | 1-GAR-16-62760 | 1-GAR-16-62760 | Garland Regional Office Site (Reg 1) Communication & Security 350 West IH-30 Garland, Texas 75043 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 49042.24 | 49042.24 | Unknown |  |  |  |  | 49042.24 | Yes
62 | 1-GAR-16-62761 | 1-GAR-16-XXXXX | 1-GAR-16- | 62761 | 1-GAR-16-62761 | 1-GAR-16-62761 | Garland Regional Office Site (Reg 1) Landscaping Upgrade 350 West IH-30 Garland, Texas 75043 | Landscaping (xeriscape) upgrade | DM $21 | Site Work Paving | Unknown | 98962.24 | 98962.24 | Unknown |  |  |  |  | 98962.24 | Yes
63 | 1-GAR-16-62762 | 1-GAR-16-XXXXX | 1-GAR-16- | 62762 | 1-GAR-16-62762 | 1-GAR-16-62762 | Garland Regional Office Site (Reg 1) Parking Lot Replacement 350 West IH-30 Garland, Texas 75043 | Parking lot/pedestrian paving/driveways replacement | DM $21 | Site Work Paving | Unknown | 789058.4 | 789058.4 | Unknown |  |  |  |  | 789058.4 | Yes
64 | 1-GAR-16-62763 | 1-GAR-16-XXXXX | 1-GAR-16- | 62763 | 1-GAR-16-62763 | 1-GAR-16-62763 | Garland Regional Office Site (Reg 1) Sanitary Sewer Replacement 350 West IH-30 Garland, Texas 75043 | Sanitary sewer replacement | DM $21 | Site Work Paving | Unknown | 24553.36 | 24553.36 | Unknown |  |  |  |  | 24553.36 | Yes
65 | 1-GAR-16-62764 | 1-GAR-16-XXXXX | 1-GAR-16- | 62764 | 1-GAR-16-62764 | 1-GAR-16-62764 | Garland Regional Office Site (Reg 1) Site Development 350 West IH-30 Garland, Texas 75043 | Site Development (ie: Storm water system, etc.) | DM $21 | Site Work Paving | Unknown | 287119.04 | 287119.04 | Unknown |  |  |  |  | 287119.04 | Yes
66 | 1-GAR-16-62765 | 1-GAR-16-XXXXX | 1-GAR-16- | 62765 | 1-GAR-16-62765 | 1-GAR-16-62765 | Garland Regional Office Site (Reg 1) Water Supply Upgrade 350 West IH-30 Garland, Texas 75043 | Water Supply upgrade/replacement | DM $21 | Site Work Paving | Unknown | 67370.16 | 67370.16 | Unknown |  |  |  |  | 67370.16 | Yes
67 | 2-PIE-16-62766 | 2-PIE-16-XXXXX | 2-PIE-16- | 62766 | 2-PIE-16-62766 | 2-PIE-16-62766 | Pierce Sub-District Office (Reg 2) Ductwork Replacement 19692 US Hwy 59 El Campo, Texas 77437 | Duct work and insulation replacement | DM $21 | HVAC | Unknown | 62400 | 62400 | Unknown |  |  |  |  | 62400 | Yes
68 | 2-BRE-16-62767 | 2-BRE-16-XXXXX | 2-BRE-16- | 62767 | 2-BRE-16-62767 | 2-BRE-16-62767 | Brenham Area Office (Reg 2) Exterior Wall Repair 975 Hwy 290 West. Brenham, Texas 77834 | Exterior walls repair | DM $21 | Roofing and Exterior Repairs | Unknown | 10773.36 | 10773.36 | Unknown |  |  |  |  | 10773.36 | Yes
69 | 2-HHQ-16-62768 | 2-HHQ-16-XXXXX | 2-HHQ-16- | 62768 | 2-HHQ-16-62768 | 2-HHQ-16-62768 | Houston Regional Headquarters (West Road) (Reg 2) Security System Replacement 12230 West Road Jersey Village, Texas 77065 | Security system replacement | DM $21 | Communications and Security | Unknown | 208000 | 208000 | Unknown |  |  |  |  | 208000 | Yes
70 | 4-MID-16-62769 | 4-MID-16-XXXXX | 4-MID-16- | 62769 | 4-MID-16-62769 | 4-MID-16-62769 | Midland Sub District Office (Reg 4) Vacant DL Remodel/Refresh 2405 S. Loop 250 West Midland, Texas 79703 | Remodel vacant DL area including to replacing deteriorated finishes and MEP systems | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 442000 | 442000 | Unknown |  |  |  |  | 442000 | Yes
71 | 5-AMA-16-62770 | 5-AMA-16-XXXXX | 5-AMA-16- | 62770 | 5-AMA-16-62770 | 5-AMA-16-62770 | Amarillo District Office (Reg 5) Security System Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Security system replacement | DM $21 | Communications and Security | Unknown | 343698.16 | 343698.16 | Unknown |  |  |  |  | 343698.16 | Yes
72 | 5-AMA-16-62771 | 5-AMA-16-XXXXX | 5-AMA-16- | 62771 | 5-AMA-16-62771 | 5-AMA-16-62771 | Amarillo District Office (Reg 5) Sprinkler System 4200 Canyon Dr. Amarillo, Texas 79109 | Sprinkler System | DM $21 | Safety | Unknown | 153180.56 | 153180.56 | Unknown |  |  |  |  | 153180.56 | Yes
73 | 5-AMA-16-62772 | 5-AMA-16-XXXXX | 5-AMA-16- | 62772 | 5-AMA-16-62772 | 5-AMA-16-62772 | Amarillo District Office (Reg 5) Foundation Study/Repair 4200 Canyon Dr. Amarillo, Texas 79109 | Standard Foundations | DM $21 | Facility Repairs to Infrastructure/ foundation | Unknown | 40278.16 | 40278.16 | Unknown |  |  |  |  | 40278.16 | Yes
74 | 5-AMA-16-62773 | 5-AMA-16-XXXXX | 5-AMA-16- | 62773 | 5-AMA-16-62773 | 5-AMA-16-62773 | Amarillo District Office (Reg 5) Interior Finishes Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Ceiling, wall, floor finishes replacement | DM $21 | Interior Repairs | Unknown | 575051.36 | 575051.36 | Unknown |  |  |  |  | 575051.36 | Yes
75 | 5-AMA-16-62774 | 5-AMA-16-XXXXX | 5-AMA-16- | 62774 | 5-AMA-16-62774 | 5-AMA-16-62774 | Amarillo District Office (Reg 5) Fittings Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Fittings (Specialties) replacement | DM $21 | Facility Repairs to Infrastructure/ foundation | Unknown | 17077.84 | 17077.84 | Unknown |  |  |  |  | 17077.84 | Yes
76 | 6-ADO-16-62775 | 6-ADO-16-XXXXX | 6-ADO-16- | 62775 | 6-ADO-16-62775 | 6-ADO-16-62775 | Austin District Office Site (Reg 6) Parking Lot Replacement 9000 IH-35 North Austin, Texas 78753 | Parking lot replacement | DM $21 | Site Work Paving | Unknown | 260000 | 260000 | Unknown |  |  |  |  | 260000 | Yes
77 | 6-ADO-16-62776 | 6-ADO-16-XXXXX | 6-ADO-16- | 62776 | 6-ADO-16-62776 | 6-ADO-16-62776 | Austin District Office Site (Reg 6) Site Lighting Replacement/Upgrade 9000 IH-35 North Austin, Texas 78753 | Site Lighting | DM $21 | Site Work Paving | Unknown | 57117.84 | 57117.84 | Unknown |  |  |  |  | 57117.84 | Yes
78 | 6-ADO-16-62777 | 6-ADO-16-XXXXX | 6-ADO-16- | 62777 | 6-ADO-16-62777 | 6-ADO-16-62777 | Austin District Office Site (Reg 6) Communication & Security 9000 IH-35 North Austin, Texas 78753 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 22046.96 | 22046.96 | Unknown |  |  |  |  | 22046.96 | Yes
79 | 6-ADO-16-62778 | 6-ADO-16-XXXXX | 6-ADO-16- | 62778 | 6-ADO-16-62778 | 6-ADO-16-62778 | Austin District Office Storage Hwy Patrol (Reg 6) Special Structures 9000 IH-35 North Austin, Texas 78753 | Special Structures - Storage Bldg < 1000sf | DM $21 | Site Work Paving | Unknown | 12728.56 | 12728.56 | Unknown |  |  |  |  | 12728.56 | Yes
80 | 5-ABI-16-62779 | 5-ABI-16-XXXXX | 5-ABI-16- | 62779 | 5-ABI-16-62779 | 5-ABI-16-62779 | Abilene District Office (Reg 5) Security/Site System Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Security system replacement | DM $21 | Communications and Security | Unknown | 220581.92 | 220581.92 | Unknown |  |  |  |  | 220581.92 | Yes
81 | 3-LAR-16-62780 | 3-LAR-16-XXXXX | 3-LAR-16- | 62780 | 3-LAR-16-62780 | 3-LAR-16-62780 | Laredo District Office (Reg 3) Ceiling Replacement 1901 Bob Bullock Loop Laredo, Texas 78043 | Ceiling/wall finishes replacement | DM $21 | Interior Repairs | Unknown | 389896.32 | 389896.32 | Unknown |  |  |  |  | 389896.32 | Yes
82 | 3-LAR-16-62781 | 3-LAR-16-XXXXX | 3-LAR-16- | 62781 | 3-LAR-16-62781 | 3-LAR-16-62781 | Laredo District Office (Reg 3) Security System Replacement 1901 Bob Bullock Loop Laredo, Texas 78043 | Security system replacement | DM $21 | Communications and Security | Unknown | 373251.84 | 373251.84 | Unknown |  |  |  |  | 373251.84 | Yes
83 | 6-WAC-16-62782 | 6-WAC-16-XXXXX | 6-WAC-16- | 62782 | 6-WAC-16-62782 | 6-WAC-16-62782 | Waco District Office (Reg 6) Interior Finishes Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Ceiling, wall, floor finishes replacement | DM $21 | Interior Repairs | Unknown | 567938.8 | 567938.8 | Unknown |  |  |  |  | 567938.8 | Yes
84 | 6-WAC-16-62783 | 6-WAC-16-XXXXX | 6-WAC-16- | 62783 | 6-WAC-16-62783 | 6-WAC-16-62783 | Waco District Office (Reg 6) Fixed Furnishings Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Fixed furnishings replacement | DM $21 | Interior Repairs | Unknown | 137846.8 | 137846.8 | Unknown |  |  |  |  | 137846.8 | Yes
85 | 3-EAG-16-62784 | 3-EAG-16-XXXXX | 3-EAG-16- | 62784 | 3-EAG-16-62784 | 3-EAG-16-62784 | Eagle Pass Area Office (Reg 3) Interior Finishes Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Ceiling, wall, floor finishes replacement | DM $21 | Interior Repairs | Unknown | 186283.86 | 186283.86 | Unknown |  |  |  |  | 186283.86 | Yes
86 | 3-EAG-16-62785 | 3-EAG-16-XXXXX | 3-EAG-16- | 62785 | 3-EAG-16-62785 | 3-EAG-16-62785 | Eagle Pass Area Office (Reg 3) Electrical Systems 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Other Electrical Systems (Repair illuminated exit signs throughout the facility and add emergency lighting where needed.) | DM $21 | Facility Repairs to Infrastructure/ foundation | Unknown | 150000 | 150000 | Unknown |  |  |  |  | 150000 | Yes
87 | 3-EAG-16-62786 | 3-EAG-16-XXXXX | 3-EAG-16- | 62786 | 3-EAG-16-62786 | 3-EAG-16-62786 | Eagle Pass Area Office (Reg 3) Security System Replacement 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Security system replacement | DM $21 | Communications and Security | Unknown | 125000 | 125000 | Unknown |  |  |  |  | 125000 | Yes
88 | 3-EAG-16-62787 | 3-EAG-16-XXXXX | 3-EAG-16- | 62787 | 3-EAG-16-62787 | 3-EAG-16-62787 | Eagle Pass Area Office (Reg 3) Sprinkler System 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Sprinkler System | DM $21 | Safety | Unknown | 49622.56 | 49622.56 | Unknown |  |  |  |  | 49622.56 | Yes
89 | 3-EAG-16-62788 | 3-EAG-16-XXXXX | 3-EAG-16- | 62788 | 3-EAG-16-62788 | 3-EAG-16-62788 | Eagle Pass Site (Reg 3) Communication & Security 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 9984 | 9984 | Unknown |  |  |  |  | 9984 | Yes
90 | 3-EAG-16-62789 | 3-EAG-16-XXXXX | 3-EAG-16- | 62789 | 3-EAG-16-62789 | 3-EAG-16-62789 | Eagle Pass Site (Reg 3) Landscaping Upgrade 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Landscaping (xeriscape) upgrade | DM $21 | Site Work Paving | Unknown | 4285.84 | 4285.84 | Unknown |  |  |  |  | 4285.84 | Yes
91 | 3-EAG-16-62790 | 3-EAG-16-XXXXX | 3-EAG-16- | 62790 | 3-EAG-16-62790 | 3-EAG-16-62790 | Eagle Pass Site (Reg 3) Site Lighting Replacement/Upgrade 32 Foster Maldonado Boulevard Eagle Pass, Texas 78852 | Site Lighting | DM $21 | Site Work Paving | Unknown | 20368.4 | 20368.4 | Unknown |  |  |  |  | 20368.4 | Yes
92 | 5-AMA-16-62791 | 5-AMA-16-XXXXX | 5-AMA-16- | 62791 | 5-AMA-16-62791 | 5-AMA-16-62791 | Amarillo MVT Building (Reg 5) Electrical Systems 4200 Canyon Dr. Amarillo, Texas 79109 | Other Electrical Systems (Add illuminated exit signs throughout the facility and add emergency lighting where needed.) | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 260 | 260 | Unknown |  |  |  |  | 260 | Yes
93 | 5-AMA-16-62792 | 5-AMA-16-XXXXX | 5-AMA-16- | 62792 | 5-AMA-16-62792 | 5-AMA-16-62792 | Amarillo Site (Reg 5) Communication & Security 4200 Canyon Dr. Amarillo, Texas 79109 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 25084.8 | 25084.8 | Unknown |  |  |  |  | 25084.8 | Yes
94 | 5-AMA-16-62793 | 5-AMA-16-XXXXX | 5-AMA-16- | 62793 | 5-AMA-16-62793 | 5-AMA-16-62793 | Amarillo Site (Reg 5) Fuel Distribution Replacement 4200 Canyon Dr. Amarillo, Texas 79109 | Fuel distribution replacement | DM $21 | Site Work Paving | Unknown | 46800 | 46800 | Unknown |  |  |  |  | 46800 | Yes
95 | 5-AMA-16-62794 | 5-AMA-16-XXXXX | 5-AMA-16- | 62794 | 5-AMA-16-62794 | 5-AMA-16-62794 | Amarillo Site (Reg 5) Parking Lot/Pedestrian Paving 4200 Canyon Dr. Amarillo, Texas 79109 | Parking lot/pedestrian paving replacement | DM $21 | Site Work Paving | Unknown | 291766.8 | 291766.8 | Unknown |  |  |  |  | 291766.8 | Yes
96 | 5-AMA-16-62795 | 5-AMA-16-XXXXX | 5-AMA-16- | 62795 | 5-AMA-16-62795 | 5-AMA-16-62795 | Amarillo Site (Reg 5) Site Lighting Replacement/Upgrade 4200 Canyon Dr. Amarillo, Texas 79109 | Site Lighting | DM $21 | Site Work Paving | Unknown | 65007.28 | 65007.28 | Unknown |  |  |  |  | 65007.28 | Yes
97 | HQ-A-16-62796 | HQ-A-16-XXXXX | HQ-A-16- | 62796 | HQ-A-16-62796 | HQ-A-16-62796 | Austin HQ (Building A) AHU/FCU Replacement 5805 North Lamar Blvd Austin, Texas 78752 | HVAC - replace all AHU and FCUs not already in process/completed | DM $21 | HVAC | Unknown | 520000 | 520000 | Unknown |  |  |  |  | 520000 | Yes
98 | HQ-A-16-62797 | HQ-A-16-XXXXX | HQ-A-16- | 62797 | HQ-A-16-62797 | HQ-A-16-62797 | Austin HQ (Building A) DDC Retrofit 5805 North Lamar Blvd Austin, Texas 78752 | HVAC - retrofit existing pneumatic controls to DDC | DM $21 | HVAC | Unknown | 62400 | 62400 | Unknown |  |  |  |  | 62400 | Yes
99 | HQ-A-16-62798 | HQ-A-16-XXXXX | HQ-A-16- | 62798 | HQ-A-16-62798 | HQ-A-16-62798 | Austin HQ (Building A) Plumbing Fixtures Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Plumbing fixtures replacement (ie: toilets/lavatories) | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 41600 | 41600 | Unknown |  |  |  |  | 41600 | Yes
100 | 3-DEL-16-62799 | 3-DEL-16-XXXXX | 3-DEL-16- | 62799 | 3-DEL-16-62799 | 3-DEL-16-62799 | Del Rio Sub District Office (Reg 3) Security System Replacement 2012 Veteran Boulevard Del Rio, Texas 78840 | Security system replacement | DM $21 | Communications and Security | Unknown | 228853.04 | 228853.04 | Unknown |  |  |  |  | 228853.04 | Yes
101 | 3-HAR-16-62800 | 3-HAR-16-XXXXX | 3-HAR-16- | 62800 | 3-HAR-16-62800 | 3-HAR-16-62800 | Harlingen Area Office (Reg 3) Ceiling Replacement 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Ceiling finishes replacement | DM $21 | Interior Repairs | Unknown | 84252.48 | 84252.48 | Unknown |  |  |  |  | 84252.48 | Yes
102 | 3-HAR-16-62801 | 3-HAR-16-XXXXX | 3-HAR-16- | 62801 | 3-HAR-16-62801 | 3-HAR-16-62801 | Harlingen Area Office (Reg 3) ADA Parking Spaces 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Correct American Disabilities Act (ADA) Parking Spaces. | DM $21 | Site Work Paving | Unknown | 62400 | 62400 | Unknown |  |  |  |  | 62400 | Yes
103 | 3-HAR-16-62802 | 3-HAR-16-XXXXX | 3-HAR-16- | 62802 | 3-HAR-16-62802 | 3-HAR-16-62802 | Harlingen Area Office (Reg 3) Security System Replacement 1630 N. 77 Sunshine Strip Harlingen, Texas 78550 | Security system replacement | DM $21 | Communications and Security | Unknown | 157109.68 | 157109.68 | Unknown |  |  |  |  | 157109.68 | Yes
104 | 4-SAN-16-62803 | 4-SAN-16-XXXXX | 4-SAN-16- | 62803 | 4-SAN-16-62803 | 4-SAN-16-62803 | San Angelo Site (Reg 4) Site Lighting Replacement/Upgrade 1600 W. Loop 306 San Angelo, Texas 76903 | Site Lighting | DM $21 | Site Work Paving | Unknown | 43630.08 | 43630.08 | Unknown |  |  |  |  | 43630.08 | Yes
105 | 5-ABI-16-62804 | 5-ABI-16-XXXXX | 5-ABI-16- | 62804 | 5-ABI-16-62804 | 5-ABI-16-62804 | Abilene Site (Reg 5) Security Lighting Upgrade/Replacement 2720 Industrial Boulevard Abilene, Texas 79605 | Security lighting/site lighting replacement/upgrade | DM $21 | Site Work Paving | Unknown | 77654.72 | 77654.72 | Unknown |  |  |  |  | 77654.72 | Yes
106 | 3-BEE-16-62805 | 3-BEE-16-XXXXX | 3-BEE-16- | 62805 | 3-BEE-16-62805 | 3-BEE-16-62805 | Beeville Area Office (Reg 3) Security System Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Security system replacement | DM $21 | Communications and Security | Unknown | 125000 | 125000 | Unknown |  |  |  |  | 125000 | Yes
107 | 3-BEE-16-62806 | 3-BEE-16-XXXXX | 3-BEE-16- | 62806 | 3-BEE-16-62806 | 3-BEE-16-62806 | Beeville Site (Reg 3) Communication & Security 400 S. Hillside Drive Beeville, Texas 78102 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 3602.56 | 3602.56 | Unknown |  |  |  |  | 3602.56 | Yes
108 | 3-BEE-16-62807 | 3-BEE-16-XXXXX | 3-BEE-16- | 62807 | 3-BEE-16-62807 | 3-BEE-16-62807 | Beeville Site (Reg 3) Driveway Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Roadways (DPS driveway) pavement replacement | DM $21 | Site Work Paving | Unknown | 20000 | 20000 | Unknown |  |  |  |  | 20000 | Yes
109 | 3-BEE-16-62808 | 3-BEE-16-XXXXX | 3-BEE-16- | 62808 | 3-BEE-16-62808 | 3-BEE-16-62808 | Beeville Site (Reg 3) Parking Lot Replacement 400 S. Hillside Drive Beeville, Texas 78102 | Parking Lots/roadway replacement | DM $21 | Site Work Paving | Unknown | 75000 | 75000 | Unknown |  |  |  |  | 75000 | Yes
110 | 3-BEE-16-62809 | 3-BEE-16-XXXXX | 3-BEE-16- | 62809 | 3-BEE-16-62809 | 3-BEE-16-62809 | Beeville Site (Reg 3) Site Lighting Replacement/Upgrade 400 S. Hillside Drive Beeville, Texas 78102 | Site Lighting | DM $21 | Site Work Paving | Unknown | 9337.12 | 9337.12 | Unknown |  |  |  |  | 9337.12 | Yes
111 | 4-BIG-16-62810 | 4-BIG-16-XXXXX | 4-BIG-16- | 62810 | 4-BIG-16-62810 | 4-BIG-16-62810 | Big Spring Area Office (Reg 4) Interior Finishes Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Ceiling, wall, floor finishes replacement | DM $21 | Interior Repairs | Unknown | 227175.52 | 227175.52 | Unknown |  |  |  |  | 227175.52 | Yes
112 | 4-BIG-16-62811 | 4-BIG-16-XXXXX | 4-BIG-16- | 62811 | 4-BIG-16-62811 | 4-BIG-16-62811 | Big Spring Area Office (Reg 4) Exterior Door Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Exterior doors replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 2006.16 | 2006.16 | Unknown |  |  |  |  | 2006.16 | Yes
113 | 4-BIG-16-62812 | 4-BIG-16-XXXXX | 4-BIG-16- | 62812 | 4-BIG-16-62812 | 4-BIG-16-62812 | Big Spring Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 5725 W. IH-20 Big Spring, Texas 79720 | Lighting and Branch Wiring | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 4767.36 | 4767.36 | Unknown |  |  |  |  | 4767.36 | Yes
114 | 4-BIG-16-62813 | 4-BIG-16-XXXXX | 4-BIG-16- | 62813 | 4-BIG-16-62813 | 4-BIG-16-62813 | Big Spring Area Office (Reg 4) Security System Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Security system replacement | DM $21 | Communications and Security | Unknown | 135779.28 | 135779.28 | Unknown |  |  |  |  | 135779.28 | Yes
115 | 4-BIG-16-62814 | 4-BIG-16-XXXXX | 4-BIG-16- | 62814 | 4-BIG-16-62814 | 4-BIG-16-62814 | Big Spring Area Office (Reg 4) Sprinkler System 5725 W. IH-20 Big Spring, Texas 79720 | Sprinkler System | DM $21 | Safety | Unknown | 60514.48 | 60514.48 | Unknown |  |  |  |  | 60514.48 | Yes
116 | 4-BIG-16-62815 | 4-BIG-16-XXXXX | 4-BIG-16- | 62815 | 4-BIG-16-62815 | 4-BIG-16-62815 | Big Spring Site (Reg 4) Communication & Security 5725 W. IH-20 Big Spring, Texas 79720 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 12940.72 | 12940.72 | Unknown |  |  |  |  | 12940.72 | Yes
117 | 4-BIG-16-62816 | 4-BIG-16-XXXXX | 4-BIG-16- | 62816 | 4-BIG-16-62816 | 4-BIG-16-62816 | Big Spring Site (Reg 4) Parking Lot/Driveway Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Parking lot replacement, roadways (DPS driveway) pavement replacement | DM $21 | Site Work Paving | Unknown | 74893.52 | 74893.52 | Unknown |  |  |  |  | 74893.52 | Yes
118 | 4-BIG-16-62817 | 4-BIG-16-XXXXX | 4-BIG-16- | 62817 | 4-BIG-16-62817 | 4-BIG-16-62817 | Big Spring Site (Reg 4) Site Lighting Replacement/Upgrade 5725 W. IH-20 Big Spring, Texas 79720 | Site Lighting | DM $21 | Site Work Paving | Unknown | 33533.76 | 33533.76 | Unknown |  |  |  |  | 33533.76 | Yes
119 | 4-BIG-16-62818 | 4-BIG-16-XXXXX | 4-BIG-16- | 62818 | 4-BIG-16-62818 | 4-BIG-16-62818 | Big Spring Storage Building (Reg 4) Electrical Service Replacement 5725 W. IH-20 Big Spring, Texas 79720 | Electrical service/distribution replacement | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 13395.2 | 13395.2 | Unknown |  |  |  |  | 13395.2 | Yes
120 | 5-WIC-16-62819 | 5-WIC-16-XXXXX | 5-WIC-16- | 62819 | 5-WIC-16-62819 | 5-WIC-16-62819 | Wichita Falls Site (Reg 5) Parking Lot Replacement 5505 N. Central Expressway Wichita Falls, Texas 79306 | Parking lot replacement | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 260000 | 260000 | Unknown |  |  |  |  | 260000 | Yes
121 | 5-WIC-16-62820 | 5-WIC-16-XXXXX | 5-WIC-16- | 62820 | 5-WIC-16-62820 | 5-WIC-16-62820 | Wichita Falls Site (Reg 5) Site Lighting Replacement/Upgrade 5505 N. Central Expressway Wichita Falls, Texas 79306 | Site Lighting | DM $21 | Site Work Paving | Unknown | 40254.24 | 40254.24 | Unknown |  |  |  |  | 40254.24 | Yes
122 | 6-WAC-16-62821 | 6-WAC-16-XXXXX | 6-WAC-16- | 62821 | 6-WAC-16-62821 | 6-WAC-16-62821 | Waco Site (Reg 6) Communication & Security 1617 E. Crest Dr. Waco, Texas 76705 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 40913.6 | 40913.6 | Unknown |  |  |  |  | 40913.6 | Yes
123 | 6-WAC-16-62822 | 6-WAC-16-XXXXX | 6-WAC-16- | 62822 | 6-WAC-16-62822 | 6-WAC-16-62822 | Waco Site (Reg 6) Parking Lot/Paving Replacement 1617 E. Crest Dr. Waco, Texas 76705 | Parking lot/pedestrian paving replacement | DM $21 | Site Work Paving | Unknown | 363811.76 | 363811.76 | Unknown |  |  |  |  | 363811.76 | Yes
124 | 6-WAC-16-62823 | 6-WAC-16-XXXXX | 6-WAC-16- | 62823 | 6-WAC-16-62823 | 6-WAC-16-62823 | Waco Site (Reg 6) Site Lighting Replacement/Upgrade 1617 E. Crest Dr. Waco, Texas 76705 | Site Lighting | DM $21 | Site Work Paving | Unknown | 105996.8 | 105996.8 | Unknown |  |  |  |  | 105996.8 | Yes
125 | 6-WAC-16-62824 | 6-WAC-16-XXXXX | 6-WAC-16- | 62824 | 6-WAC-16-62824 | 6-WAC-16-62824 | Waco Site (Reg 6) Storm Sewer replacement/repair 1617 E. Crest Dr. Waco, Texas 76705 | Storm Sewer replacement/repair | DM $21 | Facility Repairs to Infrastructure/ foundation | Unknown | 211420.56 | 211420.56 | Unknown |  |  |  |  | 211420.56 | Yes
126 | 2-BRE-16-62825 | 2-BRE-16-XXXXX | 2-BRE-16- | 62825 | 2-BRE-16-62825 | 2-BRE-16-62825 | Brenham Site (Reg 2) Communication & Security 975 Hwy 290 West. Brenham, Texas 77834 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 3106.48 | 3106.48 | Unknown |  |  |  |  | 3106.48 | Yes
127 | 2-BRE-16-62826 | 2-BRE-16-XXXXX | 2-BRE-16- | 62826 | 2-BRE-16-62826 | 2-BRE-16-62826 | Brenham Site (Reg 2) Pedestrian paving replacement 975 Hwy 290 West. Brenham, Texas 77834 | Pedestrian paving replacement | DM $21 | Site Work Paving | Unknown | 3934.32 | 3934.32 | Unknown |  |  |  |  | 3934.32 | Yes
128 | 2-BRE-16-62827 | 2-BRE-16-XXXXX | 2-BRE-16- | 62827 | 2-BRE-16-62827 | 2-BRE-16-62827 | Brenham Site (Reg 2) Site Lighting Replacement/Upgrade 975 Hwy 290 West. Brenham, Texas 77834 | Site Lighting | DM $21 | Site Work Paving | Unknown | 8049.6 | 8049.6 | Unknown |  |  |  |  | 8049.6 | Yes
129 | 2-BRE-16-62828 | 2-BRE-16-XXXXX | 2-BRE-16- | 62828 | 2-BRE-16-62828 | 2-BRE-16-62828 | Brenham Site Reg 2) Storm Sewer replacement/repair 975 Hwy 290 West. Brenham, Texas 77834 | Storm Sewer replacement/repair | DM $21 | Site Work Paving | Unknown | 16107.52 | 16107.52 | Unknown |  |  |  |  | 16107.52 | Yes
130 | 3-BRO-16-62829 | 3-BRO-16-XXXXX | 3-BRO-16- | 62829 | 3-BRO-16-62829 | 3-BRO-16-62829 | Brownsville Area Office (Reg 3) Sprinkler System 2901 E. Paredes Line Road Brownsville, Texas 78521 | Sprinkler System | DM $21 | Safety | Unknown | 74402.64 | 74402.64 | Unknown |  |  |  |  | 74402.64 | Yes
131 | 3-BRO-16-62830 | 3-BRO-16-XXXXX | 3-BRO-16- | 62830 | 3-BRO-16-62830 | 3-BRO-16-62830 | Brownsville Area Office (Reg 3) Electrical Systems 2901 E. Paredes Line Road Brownsville, Texas 78521 | Other Electrical Systems (Add emergency lighting where needed.) | DM $21 | Safety | Unknown | 400000 | 400000 | Unknown |  |  |  |  | 400000 | Yes
132 | 3-BRO-16-62831 | 3-BRO-16-XXXXX | 3-BRO-16- | 62831 | 3-BRO-16-62831 | 3-BRO-16-62831 | Brownsville Site (Reg 3) Driveway Replacement 2901 E. Paredes Line Road Brownsville, Texas 78521 | Roadways (DPS driveway) pavement replacement | DM $21 | Site Work Paving | Unknown | 24739.52 | 24739.52 | Unknown |  |  |  |  | 24739.52 | Yes
133 | 3-BRO-16-62832 | 3-BRO-16-XXXXX | 3-BRO-16- | 62832 | 3-BRO-16-62832 | 3-BRO-16-62832 | Brownsville Site (Reg 3) Storm Sewer replacement/repair 2901 E. Paredes Line Road Brownsville, Texas 78521 | Storm Sewer replacement/repair | DM $21 | Site Work Paving | Unknown | 39411.84 | 39411.84 | Unknown |  |  |  |  | 39411.84 | Yes
134 | 4-FOR-16-62833 | 4-FOR-16-XXXXX | 4-FOR-16- | 62833 | 4-FOR-16-62833 | 4-FOR-16-62833 | Fort Stockton Area Office (Reg 4) Security System Replacement 2302 W. Dickinson Boulevard Fort Stockton, Texas 79735 | Security system replacement | DM $21 | Communications and Security | Unknown | 89671.92 | 89671.92 | Unknown |  |  |  |  | 89671.92 | Yes
135 | 4-LAM-16-62834 | 4-LAM-16-XXXXX | 4-LAM-16- | 62834 | 4-LAM-16-62834 | 4-LAM-16-62834 | Lamesa Area Office (Reg 4) Interior Finishes Replacement 2901 E. Main Lamesa, Texas 79331 | Ceiling, wall finishes replacement | DM $21 | Interior Repairs | Unknown | 24428.56 | 24428.56 | Unknown |  |  |  |  | 24428.56 | Yes
136 | 4-LAM-16-62835 | 4-LAM-16-XXXXX | 4-LAM-16- | 62835 | 4-LAM-16-62835 | 4-LAM-16-62835 | Lamesa Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 2901 E. Main Lamesa, Texas 79331 | Lighting and Branch Wiring | DM $21 | Facility Repairs to Infrastructure/ foundation | Unknown | 53836.64 | 53836.64 | Unknown |  |  |  |  | 53836.64 | Yes
137 | 4-LAM-16-62836 | 4-LAM-16-XXXXX | 4-LAM-16- | 62836 | 4-LAM-16-62836 | 4-LAM-16-62836 | Lamesa Area Office (Reg 4) Equipment (Other) 2901 E. Main Lamesa, Texas 79331 | Other Equipment (Replace manufactured kitchen unit.) | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 2618.72 | 2618.72 | Unknown |  |  |  |  | 2618.72 | Yes
138 | 4-LAM-16-62837 | 4-LAM-16-XXXXX | 4-LAM-16- | 62837 | 4-LAM-16-62837 | 4-LAM-16-62837 | Lamesa Area Office (Reg 4) Exterior Door Replacement 2901 E. Main Lamesa, Texas 79331 | Exterior doors replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 2674.88 | 2674.88 | Unknown |  |  |  |  | 2674.88 | Yes
139 | 4-LAM-16-62838 | 4-LAM-16-XXXXX | 4-LAM-16- | 62838 | 4-LAM-16-62838 | 4-LAM-16-62838 | Lamesa Area Office (Reg 4) Fittings Replacement 2901 E. Main Lamesa, Texas 79331 | Fittings (Specialties) replacement (ie: metal toilet partitions and other rest room fittings.) | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 2978.56 | 2978.56 | Unknown |  |  |  |  | 2978.56 | Yes
140 | 4-LAM-16-62839 | 4-LAM-16-XXXXX | 4-LAM-16- | 62839 | 4-LAM-16-62839 | 4-LAM-16-62839 | Lamesa Area Office (Reg 4) Fixed Furnishings Replacement 2901 E. Main Lamesa, Texas 79331 | Fixed furnishings replacement (ie: DL Service Counter) | DM $21 | Interior Repairs | Unknown | 13785.2 | 13785.2 | Unknown |  |  |  |  | 13785.2 | Yes
141 | 4-LAM-16-62840 | 4-LAM-16-XXXXX | 4-LAM-16- | 62840 | 4-LAM-16-62840 | 4-LAM-16-62840 | Lamesa Area Office (Reg 4) HVAC Replacement 2901 E. Main Lamesa, Texas 79331 | Terminal & package units replacement/upgrade (Add BAS as needed) | DM $21 | HVAC | Unknown | 10400 | 10400 | Unknown |  |  |  |  | 10400 | Yes
142 | 4-LAM-16-62841 | 4-LAM-16-XXXXX | 4-LAM-16- | 62841 | 4-LAM-16-62841 | 4-LAM-16-62841 | Lamesa Area Office (Reg 4) Plumbing Fixtures Replacement 2901 E. Main Lamesa, Texas 79331 | Plumbing fixtures replacement (ie: toilets/lavatories) | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 26312 | 26312 | Unknown |  |  |  |  | 26312 | Yes
143 | 4-LAM-16-62842 | 4-LAM-16-XXXXX | 4-LAM-16- | 62842 | 4-LAM-16-62842 | 4-LAM-16-62842 | Lamesa Area Office (Reg 4) Security System Replacement 2901 E. Main Lamesa, Texas 79331 | Security system replacement | DM $21 | Communications and Security | Unknown | 33945.6 | 33945.6 | Unknown |  |  |  |  | 33945.6 | Yes
144 | 4-LAM-16-62843 | 4-LAM-16-XXXXX | 4-LAM-16- | 62843 | 4-LAM-16-62843 | 4-LAM-16-62843 | Lamesa Area Office (Reg 4) Sprinkler System 2901 E. Main Lamesa, Texas 79331 | Sprinkler System | DM $21 | Safety | Unknown | 15128.88 | 15128.88 | Unknown |  |  |  |  | 15128.88 | Yes
145 | 4-LAM-16-62844 | 4-LAM-16-XXXXX | 4-LAM-16- | 62844 | 4-LAM-16-62844 | 4-LAM-16-62844 | Lamesa Site (Reg 4) Communication & Security 2901 E. Main Lamesa, Texas 79331 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 5200 | 5200 | Unknown |  |  |  |  | 5200 | Yes
146 | 4-LAM-16-62845 | 4-LAM-16-XXXXX | 4-LAM-16- | 62845 | 4-LAM-16-62845 | 4-LAM-16-62845 | Lamesa Site (Reg 4) Parking Lot Replacement 2901 E. Main Lamesa, Texas 79331 | Parking lot replacement | DM $21 | Site Work Paving | Unknown | 104000 | 104000 | Unknown |  |  |  |  | 104000 | Yes
147 | 4-LAM-16-62846 | 4-LAM-16-XXXXX | 4-LAM-16- | 62846 | 4-LAM-16-62846 | 4-LAM-16-62846 | Lamesa Site (Reg 4) Site Lighting Replacement/Upgrade 2901 E. Main Lamesa, Texas 79331 | Site Lighting | DM $21 | Site Work Paving | Unknown | 10400 | 10400 | Unknown |  |  |  |  | 10400 | Yes
148 | 4-ODE-16-62848 | 4-ODE-16-XXXXX | 4-ODE-16- | 62848 | 4-ODE-16-62848 | 4-ODE-16-62848 | Odessa Area Office (Reg 4) Interior Finishes Replacement 1910 IH-20 West Odessa, Texas 79762 | Ceiling, wall, floor finishes replacement | DM $21 | Interior Repairs | Unknown | 239200 | 239200 | Unknown |  |  |  |  | 239200 | Yes
149 | 4-ODE-16-62849 | 4-ODE-16-XXXXX | 4-ODE-16- | 62849 | 4-ODE-16-62849 | 4-ODE-16-62849 | Odessa Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 1910 IH-20 West Odessa, Texas 79762 | Lighting and Branch Wiring | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 98800 | 98800 | Unknown |  |  |  |  | 98800 | Yes
150 | 4-ODE-16-62850 | 4-ODE-16-XXXXX | 4-ODE-16- | 62850 | 4-ODE-16-62850 | 4-ODE-16-62850 | Odessa Area Office (Reg 4 Electrical Service Replacement 1910 IH-20 West Odessa, Texas 79762 | Electrical service/distribution replacement | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 34814 | 34814 | Unknown |  |  |  |  | 34814 | Yes
151 | 4-ODE-16-62851 | 4-ODE-16-XXXXX | 4-ODE-16- | 62851 | 4-ODE-16-62851 | 4-ODE-16-62851 | Odessa Area Office (Reg 4) DL Interior Wall Relocation 1910 IH-20 West Odessa, Texas 79762 | Relocate Interior walls (DL area) | DM $21 | Interior Repairs | Unknown | 52000 | 52000 | Unknown |  |  |  |  | 52000 | Yes
152 | 4-ODE-16-62852 | 4-ODE-16-XXXXX | 4-ODE-16- | 62852 | 4-ODE-16-62852 | 4-ODE-16-62852 | Odessa Area Office (Reg 4) Domestic Water Replacement 1910 IH-20 West Odessa, Texas 79762 | Domestic water distribution replacement | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 6674.72 | 6674.72 | Unknown |  |  |  |  | 6674.72 | Yes
153 | 4-ODE-16-62853 | 4-ODE-16-XXXXX | 4-ODE-16- | 62853 | 4-ODE-16-62853 | 4-ODE-16-62853 | Odessa Area Office (Reg 4) Equipment (Other) 1910 IH-20 West Odessa, Texas 79762 | Other Equipment (Replace manufactured refrigerator and remove existing dishwasher and cap plumbing.) | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 1738.88 | 1738.88 | Unknown |  |  |  |  | 1738.88 | Yes
154 | 4-ODE-16-62854 | 4-ODE-16-XXXXX | 4-ODE-16- | 62854 | 4-ODE-16-62854 | 4-ODE-16-62854 | Odessa Area Office (Reg 4) Exterior Window/Door Replacement 1910 IH-20 West Odessa, Texas 79762 | Exterior windows/doors replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 43812.08 | 43812.08 | Unknown |  |  |  |  | 43812.08 | Yes
155 | 4-ODE-16-62855 | 4-ODE-16-XXXXX | 4-ODE-16- | 62855 | 4-ODE-16-62855 | 4-ODE-16-62855 | Odessa Area Office (Reg 4) Fixed Furnishings Replacement 1910 IH-20 West Odessa, Texas 79762 | Fixed furnishings replacement | DM $21 | Interior Repairs | Unknown | 18300.88 | 18300.88 | Unknown |  |  |  |  | 18300.88 | Yes
156 | 4-ODE-16-62856 | 4-ODE-16-XXXXX | 4-ODE-16- | 62856 | 4-ODE-16-62856 | 4-ODE-16-62856 | Odessa Area Office (Reg 4) Foundation Study/Repair 1910 IH-20 West Odessa, Texas 79762 | Standard Foundations | DM $21 | Facility Repairs to Infrastructure/ foundation | Unknown | 40278.16 | 40278.16 | Unknown |  |  |  |  | 40278.16 | Yes
157 | 4-ODE-16-62857 | 4-ODE-16-XXXXX | 4-ODE-16- | 62857 | 4-ODE-16-62857 | 4-ODE-16-62857 | Odessa Area Office (Reg 4) Interior Doors Replacement 1910 IH-20 West Odessa, Texas 79762 | Interior doors replacement | DM $21 | Interior Repairs | Unknown | 86320 | 86320 | Unknown |  |  |  |  | 86320 | Yes
158 | 4-ODE-16-62858 | 4-ODE-16-XXXXX | 4-ODE-16- | 62858 | 4-ODE-16-62858 | 4-ODE-16-62858 | Odessa Area Office (Reg 4) Plumbing Systems (Other) 1910 IH-20 West Odessa, Texas 79762 | Other Plumbing Systems - Natural gas system is quite old, beyond its expected useful life and should be replaced. | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 6383.52 | 6383.52 | Unknown |  |  |  |  | 6383.52 | Yes
159 | 4-ODE-16-62859 | 4-ODE-16-XXXXX | 4-ODE-16- | 62859 | 4-ODE-16-62859 | 4-ODE-16-62859 | Odessa Area Office (Reg 4) Security System Replacement 1910 IH-20 West Odessa, Texas 79762 | Security system replacement | DM $21 | Communications and Security | Unknown | 156000 | 156000 | Unknown |  |  |  |  | 156000 | Yes
160 | 4-ODE-16-62860 | 4-ODE-16-XXXXX | 4-ODE-16- | 62860 | 4-ODE-16-62860 | 4-ODE-16-62860 | Odessa Area Office (Reg 4) Sprinkler System 1910 IH-20 West Odessa, Texas 79762 | Sprinkler System | DM $21 | Safety | Unknown | 78000 | 78000 | Unknown |  |  |  |  | 78000 | Yes
161 | 4-ODE-16-62861 | 4-ODE-16-XXXXX | 4-ODE-16- | 62861 | 4-ODE-16-62861 | 4-ODE-16-62861 | Odessa Site (Reg 4) Communication & Security 1910 IH-20 West Odessa, Texas 79762 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 55000 | 55000 | Unknown |  |  |  |  | 55000 | Yes
162 | 4-NEW-16-62862 | 4-NEW-16-XXXXX | 4-NEW-16- | 62862 | 4-NEW-16-62862 | 4-NEW-16-62862 | New Braunfels Site (Reg 6) Canopy Repair 3003 IH-35 South New Braunfels, Texas 78130 | Canopy repair | DM $21 | Roofing and Exterior Repairs | Unknown | 10400 | 10400 | Unknown |  |  |  |  | 10400 | Yes
163 | 4-NEW-16-62863 | 4-NEW-16-XXXXX | 4-NEW-16- | 62863 | 4-NEW-16-62863 | 4-NEW-16-62863 | New Braunfels Site (Reg 6) Parking Lot Replacement 3003 IH-35 South New Braunfels, Texas 78130 | Parking lot replacement | DM $21 | Site Work Paving | Unknown | 52000 | 52000 | Unknown |  |  |  |  | 52000 | Yes
164 | 4-NEW-16-62864 | 4-NEW-16-XXXXX | 4-NEW-16- | 62864 | 4-NEW-16-62864 | 4-NEW-16-62864 | New Braunfels Site (Reg 6) Site Lighting Replacement/Upgrade 3003 IH-35 South New Braunfels, Texas 78130 | Site Lighting | DM $21 | Site Work Paving | Unknown | 9729.2 | 9729.2 | Unknown |  |  |  |  | 9729.2 | Yes
165 | 4-NEW-16-62865 | 4-NEW-16-XXXXX | 4-NEW-16- | 62865 | 4-NEW-16-62865 | 4-NEW-16-62865 | New Braunfels Site (Reg 6) Fuel Distribution Replacement 3003 IH-35 South New Braunfels, Texas 78130 | Fuel distribution replacement | DM $21 | Site Work Paving | Unknown | 52000 | 52000 | Unknown |  |  |  |  | 52000 | Yes
166 | 4-OZO-16-62866 | 4-OZO-16-XXXXX | 4-OZO-16- | 62866 | 4-OZO-16-62866 | 4-OZO-16-62866 | Ozona Area Office (Reg 4) Interior Finishes Replacement 1503 Monterey St Ozona, Texas 76943 | Ceiling, wall, floor finishes replacement | DM $21 | Interior Repairs | Unknown | 45437.6 | 45437.6 | Unknown |  |  |  |  | 45437.6 | Yes
167 | 4-OZO-16-62867 | 4-OZO-16-XXXXX | 4-OZO-16- | 62867 | 4-OZO-16-62867 | 4-OZO-16-62867 | Ozona Area Office (Reg 4) Exterior Window/Door Replacement 1503 Monterey St Ozona, Texas 76943 | Exterior windows/doors replacement | DM $21 | Roofing and Exterior Repairs | Unknown | 23371.92 | 23371.92 | Unknown |  |  |  |  | 23371.92 | Yes
168 | 4-OZO-16-62868 | 4-OZO-16-XXXXX | 4-OZO-16- | 62868 | 4-OZO-16-62868 | 4-OZO-16-62868 | Ozona Area Office (Reg 4) Lighting/Branch Wiring Replacement/Upgrade 1503 Monterey St Ozona, Texas 76943 | Lighting and Branch Wiring | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 43069.52 | 43069.52 | Unknown |  |  |  |  | 43069.52 | Yes
169 | 4-OZO-16-62869 | 4-OZO-16-XXXXX | 4-OZO-16- | 62869 | 4-OZO-16-62869 | 4-OZO-16-62869 | Ozona Area Office (Reg 4) Domestic Water Replacement 1503 Monterey St Ozona, Texas 76943 | Domestic water distribution replacement | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 4011.28 | 4011.28 | Unknown |  |  |  |  | 4011.28 | Yes
170 | 4-OZO-16-62870 | 4-OZO-16-XXXXX | 4-OZO-16- | 62870 | 4-OZO-16-62870 | 4-OZO-16-62870 | Ozona Area Office (Reg 4) Electrical Service Replacement 1503 Monterey St Ozona, Texas 76943 | Electrical service/distribution replacement | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 20960.16 | 20960.16 | Unknown |  |  |  |  | 20960.16 | Yes
171 | 4-OZO-16-62871 | 4-OZO-16-XXXXX | 4-OZO-16- | 62871 | 4-OZO-16-62871 | 4-OZO-16-62871 | Ozona Area Office (Reg 4) Fittings Replacement 1503 Monterey St Ozona, Texas 76943 | Fittings (Specialties) replacement | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 2399.28 | 2399.28 | Unknown |  |  |  |  | 2399.28 | Yes
172 | 4-OZO-16-62872 | 4-OZO-16-XXXXX | 4-OZO-16- | 62872 | 4-OZO-16-62872 | 4-OZO-16-62872 | Ozona Area Office (Reg 4) Interior Doors Replacement 1503 Monterey St Ozona, Texas 76943 | Interior doors replacement | DM $21 | Interior Repairs | Unknown | 17413.76 | 17413.76 | Unknown |  |  |  |  | 17413.76 | Yes
173 | 4-OZO-16-62873 | 4-OZO-16-XXXXX | 4-OZO-16- | 62873 | 4-OZO-16-62873 | 4-OZO-16-62873 | Ozona Area Office (Reg 4) Plumbing Systems 1503 Monterey St Ozona, Texas 76943 | Plumbing fixtures (ie: toilets/lavatories)/other plumbing systems replacement- Natural gas system is quite old, beyond its expected useful life and should be replaced. | DM $21 | Facility Repairs to Infrastructure/ Foundation | Unknown | 24892.4 | 24892.4 | Unknown |  |  |  |  | 24892.4 | Yes
174 | 4-OZO-16-62874 | 4-OZO-16-XXXXX | 4-OZO-16- | 62874 | 4-OZO-16-62874 | 4-OZO-16-62874 | Ozona Area Office (Reg 4) Sanitary Waste Replacement 1503 Monterey St Ozona, Texas 76943 | Sanitary waste replacement | DM $21 | Site Work Paving | Unknown | 10699.52 | 10699.52 | Unknown |  |  |  |  | 10699.52 | Yes
175 | 4-OZO-16-62875 | 4-OZO-16-XXXXX | 4-OZO-16- | 62875 | 4-OZO-16-62875 | 4-OZO-16-62875 | Ozona Area Office (Reg 4) Security System Replacement 1503 Monterey St Ozona, Texas 76943 | Security system replacement | DM $21 | Communications and Security | Unknown | 7001.28 | 7001.28 | Unknown |  |  |  |  | 7001.28 | Yes
176 | 4-OZO-16-62876 | 4-OZO-16-XXXXX | 4-OZO-16- | 62876 | 4-OZO-16-62876 | 4-OZO-16-62876 | Ozona Area Office (Reg 4) Sprinkler System 1503 Monterey St Ozona, Texas 76943 | Sprinkler System | DM $21 | Safety | Unknown | 11721.84 | 11721.84 | Unknown |  |  |  |  | 11721.84 | Yes
177 | 4-OZO-16-62877 | 4-OZO-16-XXXXX | 4-OZO-16- | 62877 | 4-OZO-16-62877 | 4-OZO-16-62877 | Ozona Area Office (Reg 4) Fixed Furnishings Replacement 1503 Monterey St Ozona, Texas 76943 | Fixed furnishings replacement | DM $21 | Interior Repairs | Unknown | 11021.92 | 11021.92 | Unknown |  |  |  |  | 11021.92 | Yes
178 | 4-OZO-16-62878 | 4-OZO-16-XXXXX | 4-OZO-16- | 62878 | 4-OZO-16-62878 | 4-OZO-16-62878 | Ozona Site (Reg 4) Landscaping Upgrade 1503 Monterey St Ozona, Texas 76943 | Landscaping (xeriscape) upgrade | DM $21 | Site Work Paving | Unknown | 4703.92 | 4703.92 | Unknown |  |  |  |  | 4703.92 | Yes
179 | 4-OZO-16-62879 | 4-OZO-16-XXXXX | 4-OZO-16- | 62879 | 4-OZO-16-62879 | 4-OZO-16-62879 | Ozona Site (Reg 4) Parking Lot Replacement 1503 Monterey St Ozona, Texas 76943 | Parking lot replacement | DM $21 | Site Work Paving | Unknown | 104000 | 104000 | Unknown |  |  |  |  | 104000 | Yes
180 | 4-OZO-16-62880 | 4-OZO-16-XXXXX | 4-OZO-16- | 62880 | 4-OZO-16-62880 | 4-OZO-16-62880 | Ozona Site (Reg 4) Site Lighting Replacement/Upgrade 1503 Monterey St Ozona, Texas 76943 | Site Lighting | DM $21 | Site Work Paving | Unknown | 6039.28 | 6039.28 | Unknown |  |  |  |  | 6039.28 | Yes
181 | 4-OZO-16-62881 | 4-OZO-16-XXXXX | 4-OZO-16- | 62881 | 4-OZO-16-62881 | 4-OZO-16-62881 | Ozona Storage (Reg 4) Special Structures 1503 Monterey St Ozona, Texas 76943 | Special Structures - Storage Bldg < 1000sf | DM $21 | Site Work Paving | Unknown | 7271.68 | 7271.68 | Unknown |  |  |  |  | 7271.68 | Yes
182 | 4-Pec-16-62882 | 4-Pec-16-XXXXX | 4-Pec-16- | 62882 | 4-Pec-16-62882 | 4-Pec-16-62882 | Pecos Area Office (Reg 4) Security System Replacement 148 N. Frontage I-20 West Pecos, Texas 79772 | Security system replacement | DM $21 | Communications and Security | Unknown | 54772.64 | 54772.64 | Unknown |  |  |  |  | 54772.64 | Yes
183 | 6-GEN-16-62883 | 6-GEN-16-XXXXX | 6-GEN-16- | 62883 | 6-GEN-16-62883 | 6-GEN-16-62883 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) 1803 S. General McMullen San Antonio, Texas 78226 | Parking lot replacement | DM $21 | Site Work Paving | Unknown | 260000 | 260000 | Unknown |  |  |  |  | 260000 | Yes
184 | 6-GEN-16-62884 | 6-GEN-16-XXXXX | 6-GEN-16- | 62884 | 6-GEN-16-62884 | 6-GEN-16-62884 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) Sanitary Waste Replacement 1803 S. General McMullen San Antonio, Texas 78226 | Sanitary waste replacement | DM $21 | Site Work Paving | Unknown | 19922.24 | 19922.24 | Unknown |  |  |  |  | 19922.24 | Yes
185 | 6-GEN-16-62885 | 6-GEN-16-XXXXX | 6-GEN-16- | 62885 | 6-GEN-16-62885 | 6-GEN-16-62885 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) Rain Water Drainage Improvements 1803 S. General McMullen San Antonio, Texas 78226 | Rain Water Drainage | DM $21 | Site Work Paving | Unknown | 5254.08 | 5254.08 | Unknown |  |  |  |  | 5254.08 | Yes
186 | 6-GEN-16-62886 | 6-GEN-16-XXXXX | 6-GEN-16- | 62886 | 6-GEN-16-62886 | 6-GEN-16-62886 | San Antonio Northwest Driver License Site (General McMullen) (Reg 6) Site Lighting Replacement/Upgrade 1803 S. General McMullen San Antonio, Texas 78226 | Site Lighting | DM $21 | Site Work Paving | Unknown | 110258.72 | 110258.72 | Unknown |  |  |  |  | 110258.72 | Yes
187 | 6-VIC-16-62887 | 6-VIC-16-XXXXX | 6-VIC-16- | 62887 | 6-VIC-16-62887 | 6-VIC-16-62887 | Victoria Site (Reg 6) Communication & Security 8802 N. Navarro Victoria, Texas 77904 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 13783.12 | 13783.12 | Unknown |  |  |  |  | 13783.12 | Yes
188 | 6-VIC-16-62888 | 6-VIC-16-XXXXX | 6-VIC-16- | 62888 | 6-VIC-16-62888 | 6-VIC-16-62888 | Victoria Site (Reg 6) Driveway Replacement 8802 N. Navarro Victoria, Texas 77904 | Parking lot replacement, pedestrian paving, roadways (DPS driveway) pavement replacement | DM $21 | Site Work Paving | Unknown | 176389.2 | 176389.2 | Unknown |  |  |  |  | 176389.2 | Yes
189 | 6-SEG-16-62889 | 6-SEG-16-XXXXX | 6-SEG-16- | 62889 | 6-SEG-16-62889 | 6-SEG-16-62889 | Seguin Site (Reg 6) Communication & Security 1440 E. Kingsbury Seguin, Texas 78155 | Site Comm & Security (i.e.: fencing, gate access control, etc.) | DM $21 | Site Work Paving | Unknown | 3895.84 | 3895.84 | Unknown |  |  |  |  | 3895.84 | Yes
190 | 6-SEG-16-62890 | 6-SEG-16-XXXXX | 6-SEG-16- | 62890 | 6-SEG-16-62890 | 6-SEG-16-62890 | Seguin Site (Reg 6) Parking Lot Replacement 1440 E. Kingsbury Seguin, Texas 78155 | Parking lot, pedestrian paving replacement | DM $21 | Site Work Paving | Unknown | 161000 | 161000 | Unknown |  |  |  |  | 161000 | Yes
191 | 6-SEG-16-62891 | 6-SEG-16-XXXXX | 6-SEG-16- | 62891 | 6-SEG-16-62891 | 6-SEG-16-62891 | Seguin Site (Reg 6) Site Lighting Replacement/Upgrade 1440 E. Kingsbury Seguin, Texas 78155 | Site Lighting | DM $21 | Site Work Paving | Unknown | 10095.28 | 10095.28 | Unknown |  |  |  |  | 10095.28 | Yes
192 | ST-TEST-16-62892 | ST-TEST-16-XXXXX | ST-TEST-16- | 62892 | ST-TEST-16-62892 | ST-TEST-16-62892 | Statewide Support Project Consultants | Funding for testing, consulting, commissioning, CMT, inspections type of expenditures associated with projects. | DM $21 | Professional Fees | Unknown | 455199.82 | 455199.82 | Unknown |  |  |  |  | 455199.82 | Yes
193 | ST-PM-16-62893 | ST-PM-16-XXXXX | ST-PM-16- | 62893 | ST-PM-16-62893 | ST-PM-16-62893 | Statewide TFC Project Mgmt Fees | TFC Project Management fees. | DM $21 | Professional Fees | Unknown | 616800 | 616800 | Unknown |  |  |  |  | 616800 | Yes
194 | ST-CON-16-62894 | ST-CON-16-XXXXX | ST-CON-16- | 62894 | ST-CON-16-62894 | ST-CON-16-62894 | Statewide Unexpected DM repairs/Project Contingency | Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. | DM $21 | Unexpended DM repairs/Project Contingency | Unknown | 1852154.56 | 1852154.56 | Unknown |  |  |  |  | 1852154.56 | Yes
[11 empty] | Totals: | 38778877 | 38778877 |  |  |  | 0 | 0 | 38778877

## DPS Notes 12.15
| Agency: | Texas Department of Public Safety - 0405
| Date: | 2015-12-15
| Prepared by: | Tavia Wendlandt
Project Priority | Supplemental Information
1-36 | Waiting for LBB approval of plan to begin project.
37-194 | This appropriation was not funded by the Legislature. Agency is attempting to identify savings in order to fund the $21M in deferred maintenance projects.
Waiting for LBB approval of funding to begin project; Exceprt from letter to LBB: “Per Article IX Sec. 14.03 (h) (3) Limitation on Expenditures – Capital Budget, the Department of Public Safety requests to transfer appropriations from a capital budget item to a non-capital budget item. Capital budget authority of $21, 000,000 is included in Article V, Rider 2 b. (2) Deferred Maintenance for deferred maintenance projects at the Department of Public Safety, however additional appropriations of $21,000,000 were not provided. This situation results in a $21,000,000 reduction to our Agency’s operations which cause undue hardship on the Agency’s programs. The Department requests a transfer of $11,139,565 in fiscal year 2016 and $9,860,435 in fiscal year 2017 from a capital budget item to a non-capital budget item.”

## TFC 9.16
| Agency: | Texas Facilities Commission (303)
| Date: | 2016-09-15 | [9 empty] | 2016-09-15
| Prepared by: | John Raff, P.E.
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 303 | Texas School for the Deaf (TSD) / Texas School for the Blind and Visually Impaired (TSBVI) Campus Wide Improvements, Austin TX | Repair/Replacement of fire protection, life safety, mechanical, plumbing and electrical systems and architectural improvements. | GR Funds | 39856898 | 39833856 | 2018-01-16 | 40% | 0% | 34584804 | 1657258 | 3591794 | Yes
2 | 303 | Lyndon B. Johnson Building (LBJ), Austin TX | Repairs to elevators, life safety, mechanical, plumbing and electrical systems. | GR Funds | 15000000 | 15000000 | 2019-12-31 | 33% | 0% | 12984802 | 717698 | 1297500 | Yes
3 | 303 | William B. Travis Building (WBT), Austin TX | Repairs to mechanical systems and enhancement to indoor air quality. | GR Funds | 16732708 | 16544412 | 2019-12-31 | 15% | 0% | 13639964 | 770036 | 2134412 | Yes
4 | 303 | Stephen F. Austin Building (SFA), Austin, TX | Repairs to mechanical and plumbing systems. | GR Funds | 13672475 | 13518617 | 2019-12-31 | 11% | 0% | 1877205 | 310395 | 11331017 | Yes
5 | 303 | 7-Building Improvements Project Austin TX Central Services Bldg. (CSB) Insurance Annex (INX) John H. Reagan Bldg. (JHR) Robert E. Johnson Bldg. (REJ) E.O. Thompson Bldg. (THO) Thomas J. Rusk Bldg. (TJR) William P. Clements Jr. Bldg. (WPC) | CSB- Repair to fire protection, mechanical systems, plumbing systems, paving, elevators and boilers. INX- Repairs to mechanical systems. JHR- Repairs to mechanical and electrical systems. REJ- Repairs to security, mechanical and electrical systems. THO- Repairs t security systems, enhancement to indoor air quality, mechanical systems and architectura systems. TJR- Repairs to security, elevators and mechanical systems. WPC- Repairs to electrical systems and enhancement to indoor air quality. | GR Funds | 14478300 | 14316256 | 2020-02-28 | 21% | 0% | 899087 | 282668 | 13134501 | Yes
6 | 303 | William P. Hobby Complex (WPH), Austin TX | Repairs to mechanical, electrical and plumbing systems and fire protection. | GR Funds | 7621589 | 7537100 | 2020-02-28 | 20% | 0% | 164768 | 294573 | 7077759 | No
7 | 303 | Brown Heatly Bldg. - Elevator, Austin TX | Repairs/Replace Elevators | GR Funds | 2514334 | 2486402 | 2017-01-21 | 20% | 0% | 238812 | 88926.33 | 2158663.67 | No
8 | 303 | 4-Building Elevator Project, Austin TX James Earl Rudder Bldg. (JER) Thomas J. Rusk Bldg. (TJR) William P. Clements Jr. Bldg. (WPC) William P. Hobby Complex (WPH) | Repair/Replace Elevators in buildings - JER, TJR, WPC, WPH | GR Funds | 16991013 | 16799811 | 2017-11-30 | 29% | 0% | 14917520 | 392766 | 1489525 | Yes
9 | 303 | 5-Building Project, Austin TX Insurance Building (INS) Price Daniel Sr. Building (PDB) Supreme Court Building (SCB) Sam Houston Building (SHB) Thomas C. Clark Building (TCC) | INS- Repairs to security, life safety, mechanical systems, exterior windows, architectural finishes, rain water drainage and waterproofing systems. PDB- Repairs to mechanical systems and enhancement to indoor air quality. SCB- Enhancement to indoor air quality, repairs to security systems, elevators, mechanical and electrical systems. SHB- Repairs to mechanical systems. TCC- Enhancement to indoor air quality, repairs to elevators, mechanical, waterproofing systems. | GR Funds | 16791914 | 16602952 | 2020-03-31 | 13% | 0% | 2481200 | 0 | 14121752 | Yes
10 | 303 | John H. Winters Complex (JHW), Austin TX | Repairs to data center, life safety, accessibility, fire protection, mechanical, plumbing, electrical systems and architectural finishes. | GR Funds | 16157401 | 15975579 | 2020-01-31 | 20% | 0% | 12729160 | 734679 | 2511740 | Yes
11 | 303 | DSHS - 4 Building Project, Austin TX Dept. of Health Bldg. F (DHF) Dept. of Health Records Bldg. (DHR) Dept. of Health Tower (DHT) Robert Beirnstein Bldg. (RBB) | DHF- Repairs to mechanical systems. DHR- Repairs to MEP systems, restrooms, paving and architectural finishes. DHT- Repairs to fire protection, MEP systems and architectural finishes. RBB- Repairs to elevators, MEP systems, security systems and enhancement of indoor air quality. | GR Funds | 14960012 | 14791712 | 2020-03-31 | 4% | 0% | 818852 | 13052 | 13959808 | Yes
12 | 303 | Dept. of Health Old Plant (DHOP), Austin TX | DHOP- Repairs to MEP systems, fire protection and security systems. | GR Funds | 1507350 | 1490392 | 2017-02-01 | 100% | 10% | 1379490 | 1808 | 109094 | Yes
13 | 303 | TFC Portfolio Wide Facility Condition Assessment | To provide condition assessment for TFC to include 44 office buildings, 8 warehouse/storage facilities, 9 special use facilities, 47 Texas School for the Deaf buildings, 34 Texas School for the Blind and Visually Impaired campus buildings, 19 parking garages and 33 parking lots. | GR Funds | 0 | 1840000 | 2017-01-05 | 0% | 0% | 0 | 0 | 1840000 | Yes
14 | 303 | 11-Building Project, Austin TX Brown Heatly Bldg. (BHB) Dept. of Assistive and Rehabilitative Services Admin. Bldg. (DARS) Dr. Bob Glaze Laboratory (DBGL) Dept. of Health Bldg. B (DHB) Dept. of Health Bldg. H (DHH) Dept. of Health Old Lab (DHOL) Dept. of Health Lab A600 (A600) Dept. of Health Service Bldg. (DHSB) Dept. of Health Annex (DHX) Disaster Recovery Operations Center (DROC) Human Services Warehouse (HSW) | BHB- Repairs to accessibility, electrical and mechanical systems. DARS- repairs to elevators. DBGL- Repairs to mechanical, roofing systems and enhancement to indoor air quality. DHB- Enhancement to indoor air quality. DHH- Repairs to mechanical and electrical systems. DHOL- Repairs to roofing, MEP systems, elevators and enhancement of indoor air quality. A600- Repairs to roofing, MEP systems, elevators and enhancement of indoor air quality DHSB- Repairs to mechanical and architectural finishes. DHX- Repairs to security systems, elevators, MEP systems and architectural finishes. DROC- Repairs to mechanical, electrical systems and enhancement of indoor air quality. HSW- Repairs to elevators, mechanical systems and enhancement of indoor air quality. | GR Funds | 9886584 | 9775736 | 4/31/2020 | 5% | 0% | 26835 | 142124 | 9606777 | Yes
15 | 303 | 8-Building Project, Austin, TX Park 35 Bldg A (P35A) Park 35 Bldg B (P35B) Park 35 Bldg C (P35C) Park 35 Bldg D (P35D) Park 35 Bldg E (P35E) Promontory Point (PROM) State Records Center (SRC) Wheless Lane Laboratory (WLL) | P35A- Repairs to mechanical, architectural, and enhancement of indoor air quality. P35B- Repairs to roofing, mechanical, electrical and architectural finishes. P35C- Repairs to mechanical systems and inhancement of indoor air quality. P35D- Repairs of mechanical systems. P35E- Enhancement of indoor air quality. Prom- Enhancement to indoor air quality and renovate existing vacant officspace into warehouse/training space. SRC- Enhancement of indoor air quality and repairs to MEP systems. WLL- Repairs to electrical systems and enhancement to indoor air quality. | GR Funds | 8131095 | 8039595 | 4/31/2020 | 2% | 0% | 455100 | 0 | 7584495 | Yes
16 | 303 | Fire Protection- Various Bldg. Austin TX | Repairs/Replacement of fire protection systems to various buildings as determined necessary from assessment. | GR Funds | 14152211 | 13992954 | 2019-06-15 | 0% | 0% | 0 | 0 | 13992954 | No
17 | 303 | Parking Garage Elevator Project, Austin TX Parking Garage A (PKA) B, F, G, H, J, M, N and P | Repair/Replacement of elevators in PKA, PKB, PKF, PKG, PKH, PKJ, PKM, PKN, PKP | GR Funds | 5385467 | 5324864 | 2020-01-15 | 5% | 0% | 534000 | 7738 | 4783126 | Yes
18 | 303 | Waco Office Bldg. (WAC), Waco, TX | Repairs to chillers. | GR Funds | 42280 | 41804 | 2016-08-31 | 0% | 0% | 0 | 0 | 41804 | No
TBD | 303 | GJ Sutton Building (GJS), San Antonio TX | Repairs to MEP systems, fire protection systems, architectural, and security. | GR Funds | 830694 | 830694 | 2019-03-31 | 0% | 0% | 0 | 0 | 830694 | No
TBD | 303 | El Paso Office Building (ELP), El Paso TX | Repairs to mechanical, electrical and security systems. | GR Funds | 814169 | 814169 | 2019-02-28 | 0% | 0% | 0 | 0 | 814169 | No
TBD | 303 | Elias Ramirez Bldg. (ERB), Houston TX | Repairs to ADA paving, mechanical systems and drainage pipes. | GR Funds | 112306 | 112306 | 2019-02-28 | 0% | 0% | 0 | 0 | 112306 | No
TBD | 303 | Fort Worth Office Bldg. (FTW), Fort Worth TX | Repairs to electrical systems and electrical generator. | GR Funds | 209777 | 209777 | 2019-03-31 | 0% | 0% | 0 | 0 | 209777 | No
TBD | 303 | Carlos F. Truan Natural Resource Center (TRC), Corpus Christi, TX | Enhancement to indoor air quality, repairs to elevators, mechanical, waterproofing systems. | GR Funds | 1001586 | 971175 | 2020-01-31 | 0% | 0% | 0 | 0 | 971175 | No
TBD | 303 | Tyler Office Bldg. (TYL), Tyler, TX | Repairs to roofing, plumbing and electrical systems. | GR Funds | 306185 | 306185 | 2020-01-31 | 0% | 0% | 0 | 0 | 306185 | No
|  |  |  | Totals: | 217156348 | 217156348 |  |  |  | 97731599 | 5413721.33 | 114011027.67

## TFC Notes 9.16
| Agency: | Texas Facilities Commission (303)
| Date: | 2016-09-15
| Prepared by: | John Raff, P.E.
Project Priority | Supplemental Information
1 | 09/14/16: Prime Professional Service Provider continues with design. Contractor providing pre-construction services.
2 | 09/14/16: Prime Professional Service Provider continues with assessment and early design activities. Contractor providing pre-construction services.
3 | 09/14/16: Prime Professional Service Provider continues with design. Contractor providing pre-construction services.
4 | 09/14/16: Prime Professional Service Provider continues with assessment and early design activities.
5 | 09/14/16: Prime Professional Service Provider continues with assessment and early design activities.
6
7
8 | 09/14/16: Prime Professional Service Provider continues with assessment and early design activities. Contractor providing pre-construction services.
9 | 09/14/16: Prime Professional Service Provider continues with assessment and early design activities. Contractor has been selected and will go for commission approval on 09/21/2016.
10 | 0914/16: Prime Professional Service Provider has completed assessment and continues with early design activities. Contractor providing pre-construction activities.
11 | 09/14/16: Prime Professional Service Provider continues with assessment and early design activities.
12 | 09/14/16: Design complete currently under construction.
13 | 09/14/16: Prime Professional Service Provider has been selected.
14 | 09/14/16: Prime Professional Service Provider has been selected, awaiting contract execution.
15 | 09/14/16: Prime Professional Service Provider continues with assessment and early design activities.
16
17 | 09/14/16: Prime Professional Service Provider continues with assessment and early design activities. Currently soliciting for contractor.
18

## TFC 6.16
| Agency: | Texas Facilities Commission (303)
| Date: | 2016-06-15 | [9 empty] | 2016-03-15
| Prepared by: | John Raff, P.E.
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 303 | Texas School for the Deaf (TSD) / Texas School for the Blind and Visually Impaired (TSBVI) Campus Wide Improvements, Austin TX | Repair/Replacement of fire protection, life safety, mechanical, plumbing and electrical systems and architectural improvements. | GR Funds | 39856898 | 39833856 | 2018-01-16 | 24% | 0% | 5999186 | 977545 | 32857125 | Yes
2 | 303 | Lyndon B. Johnson Building (LBJ), Austin TX | Repairs to elevators, life safety, mechanical, plumbing and electrical systems. | GR Funds | 15000000 | 15000000 | 2019-12-31 | 23% | 0% | 2122250 | 378674 | 12499076 | Yes
3 | 303 | William B. Travis Building (WBT), Austin TX | Repairs to mechanical systems and enhancement to indoor air quality. | GR Funds | 16732708 | 16544412 | 2019-12-31 | 9% | 0% | 2388000 | 401483 | 13754929 | Yes
4 | 303 | Stephen F. Austin Building (SFA), Austin, TX | Repairs to mechanical and plumbing systems. | GR Funds | 13672475 | 13518617 | 2019-12-31 | 5% | 0% | 2112210 | 75390 | 11331017 | Yes
5 | 303 | 7-Building Improvements Project Austin TX Central Services Bldg. (CSB) Insurance Annex (INX) John H. Reagan Bldg. (JHR) Robert E. Johnson Bldg. (REJ) E.O. Thompson Bldg. (THO) Thomas J. Rusk Bldg. (TJR) William P. Clements Jr. Bldg. (WPC) | CSB- Repair to fire protection, mechanical systems, plumbing systems, paving, elevators and boilers. INX- Repairs to mechanical systems. JHR- Repairs to mechanical and electrical systems. REJ- Repairs to security, mechanical and electrical systems. THO- Repairs t security systems, enhancement to indoor air quality, mechanical systems and architectura systems. TJR- Repairs to security, elevators and mechanical systems. WPC- Repairs to electrical systems and enhancement to indoor air quality. | GR Funds | 14478300 | 14316256 | 2020-02-28 | 11% | 0% | 1072740 | 64433 | 13179083 | Yes
6 | 303 | William P. Hobby Complex (WPH), Austin TX | Repairs to mechanical, electrical and plumbing systems and fire protection. | GR Funds | 7621589 | 7537100 | 2020-02-28 | 10% | 0% | 326512 | 132829 | 7077759 | No
7 | 303 | Brown Heatly Bldg. - Elevator, Austin TX | Repairs/Replace Elevators | GR Funds | 2514334 | 2486402 | 2017-01-21 | 18% | 0% | 41773.67 | 88926.33 | 2355702 | No
8 | 303 | 4-Building Elevator Project, Austin TX James Earl Rudder Bldg. (JER) Thomas J. Rusk Bldg. (TJR) William P. Clements Jr. Bldg. (WPC) William P. Hobby Complex (WPH) | Repair/Replace Elevators in buildings - JER, TJR, WPC, WPH | GR Funds | 16991013 | 16799811 | 2017-11-30 | 18% | 0% | 2344632 | 125618 | 14329561 | Yes
9 | 303 | 5-Building Project, Austin TX Insurance Building (INS) Price Daniel Sr. Building (PDB) Supreme Court Building (SCB) Sam Houston Building (SHB) Thomas C. Clark Building (TCC) | INS- Repairs to security, life safety, mechanical systems, exterior windows, architectural finishes, rain water drainage and waterproofing systems. PDB- Repairs to mechanical systems and enhancement to indoor air quality. SCB- Enhancement to indoor air quality, repairs to security systems, elevators, mechanical and electrical systems. SHB- Repairs to mechanical systems. TCC- Enhancement to indoor air quality, repairs to elevators, mechanical, waterproofing systems. | GR Funds | 16791914 | 16602952 | 2020-03-31 | 0% | 0% | 0 | 0 | 16602952 | Yes
10 | 303 | John H. Winters Complex (JHW), Austin TX | Repairs to data center, life safety, accessibility, fire protection, mechanical, plumbing, electrical systems and architectural finishes. | GR Funds | 16157401 | 15975579 | 2020-01-31 | 8% | 0% | 1003371 | 33180 | 14939028 | Yes
11 | 303 | DSHS - 4 Building Project, Austin TX Dept. of Health Bldg. F (DHF) Dept. of Health Records Bldg. (DHR) Dept. of Health Tower (DHT) Robert Beirnstein Bldg. (RBB) | DHF- Repairs to mechanical systems. DHR- Repairs to MEP systems, restrooms, paving and architectural finishes. DHT- Repairs to fire protection, MEP systems and architectural finishes. RBB- Repairs to elevators, MEP systems, security systems and enhancement of indoor air quality. | GR Funds | 14960012 | 14791712 | 2020-03-31 | 0% | 0% | 0 | 0 | 14791712 | No
12 | 303 | Dept. of Health Old Plant (DHOP), Austin TX | DHOP- Repairs to MEP systems, fire protection and security systems. | GR Funds | 1507350 | 1490392 | 2017-02-01 | 35% | 0% | 9490 | 1808 | 1479094 | No
13 | 303 | TFC Portfolio Wide Facility Condition Assessment | To provide condition assessment for TFC to include 44 office buildings, 8 warehouse/storage facilities, 9 special use facilities, 47 Texas School for the Deaf buildings, 34 Texas School for the Blind and Visually Impaired campus buildings, 19 parking garages and 33 parking lots. | GR Funds | 0 | 1840000 | 2017-01-05 | 0% | 0% | 0 | 0 | 1840000 | Yes
14 | 303 | 11-Building Project, Austin TX Brown Heatly Bldg. (BHB) Dept. of Assistive and Rehabilitative Services Admin. Bldg. (DARS) Dr. Bob Glaze Laboratory (DBGL) Dept. of Health Bldg. B (DHB) Dept. of Health Bldg. H (DHH) Dept. of Health Old Lab (DHOL) Dept. of Health Lab A600 (A600) Dept. of Health Service Bldg. (DHSB) Dept. of Health Annex (DHX) Disaster Recovery Operations Center (DROC) Human Services Warehouse (HSW) | BHB- Repairs to accessibility, electrical and mechanical systems. DARS- repairs to elevators. DBGL- Repairs to mechanical, roofing systems and enhancement to indoor air quality. DHB- Enhancement to indoor air quality. DHH- Repairs to mechanical and electrical systems. DHOL- Repairs to roofing, MEP systems, elevators and enhancement of indoor air quality. A600- Repairs to roofing, MEP systems, elevators and enhancement of indoor air quality DHSB- Repairs to mechanical and architectural finishes. DHX- Repairs to security systems, elevators, MEP systems and architectural finishes. DROC- Repairs to mechanical, electrical systems and enhancement of indoor air quality. HSW- Repairs to elevators, mechanical systems and enhancement of indoor air quality. | GR Funds | 9886584 | 9775736 | 4/31/2020 | 5% | 0% | 88370 | 139942 | 9547424 | No
15 | 303 | 8-Building Project, Austin, TX Park 35 Bldg A (P35A) Park 35 Bldg B (P35B) Park 35 Bldg C (P35C) Park 35 Bldg D (P35D) Park 35 Bldg E (P35E) Promontory Point (PROM) State Records Center (SRC) Wheless Lane Laboratory (WLL) | P35A- Repairs to mechanical, architectural, and enhancement of indoor air quality. P35B- Repairs to roofing, mechanical, electrical and architectural finishes. P35C- Repairs to mechanical systems and inhancement of indoor air quality. P35D- Repairs of mechanical systems. P35E- Enhancement of indoor air quality. Prom- Enhancement to indoor air quality and renovate existing vacant officspace into warehouse/training space. SRC- Enhancement of indoor air quality and repairs to MEP systems. WLL- Repairs to electrical systems and enhancement to indoor air quality. | GR Funds | 8131095 | 8039595 | 4/31/2020 | 0% | 0% | 0 | 0 | 8039595 | No
16 | 303 | Fire Protection- Various Bldg. Austin TX | Repairs/Replacement of fire protection systems to various buildings as determined necessary from assessment. | GR Funds | 14152211 | 13992954 | 2019-06-15 | 0% | 0% | 0 | 0 | 13992954 | No
17 | 303 | Parking Garage Elevator Project, Austin TX Parking Garage A (PKA) B, F, G, H, J, M, N and P | Repair/Replacement of elevators in PKA, PKB, PKF, PKG, PKH, PKJ, PKM, PKN, PKP | GR Funds | 5385467 | 5324864 | 2020-01-15 | 0% | 0% | 0 | 0 | 5324864 | No
18 | 303 | Waco Office Bldg. (WAC), Waco, TX | Repairs to chillers. | GR Funds | 42280 | 41804 | 2016-08-31 | 0% | 0% | 0 | 0 | 41804 | No
TBD | 303 | GJ Sutton Building (GJS), San Antonio TX | Repairs to MEP systems, fire protection systems, architectural, and security. | GR Funds | 830694 | 830694 | 2019-03-31 | 0% | 0% | 0 | 0 | 830694
TBD | 303 | El Paso Office Building (ELP), El Paso TX | Repairs to mechanical, electrical and security systems. | GR Funds | 814169 | 814169 | 2019-02-28 | 0% | 0% | 0 | 0 | 814169
TBD | 303 | Elias Ramirez Bldg. (ERB), Houston TX | Repairs to ADA paving, mechanical systems and drainage pipes. | GR Funds | 112306 | 112306 | 2019-02-28 | 0% | 0% | 0 | 0 | 112306
TBD | 303 | Fort Worth Office Bldg. (FTW), Fort Worth TX | Repairs to electrical systems and electrical generator. | GR Funds | 209777 | 209777 | 2019-03-31 | 0% | 0% | 0 | 0 | 209777
TBD | 303 | Carlos F. Truan Natural Resource Center (TRC), Corpus Christi, TX | Enhancement to indoor air quality, repairs to elevators, mechanical, waterproofing systems. | GR Funds | 1001586 | 971175 | 2020-01-31 | 0% | 0% | 0 | 0 | 971175
TBD | 303 | Tyler Office Bldg. (TYL), Tyler, TX | Repairs to roofing, plumbing and electrical systems. | GR Funds | 306185 | 306185 | 2020-01-31 | 0% | 0% | 0 | 0 | 306185
|  |  |  | Totals: | 217156348 | 217156348 |  |  |  | 17508534.67 | 2419828.33 | 197227985

## TFC Notes 6.16
| Agency: | Texas Facilities Commission (303)
| Date: | 2016-06-15
| Prepared by: | John Raff, P.E.
Project Priority | Supplemental Information
1 | 06/14/16: Prime Professional Service Provider continues with assessment and early design activities.
2 | 06/14/16: Prime Professional Service Provider continues with assessment and early design activities.
3 | 06/14/16: Prime Professional Service Provider continues with assessment and early design activities.
4 | 06/14/16: Prime Professional Service Provider continues with assessment and early design activities.
5 | 06/14/16: Prime Professional Service Provider contract has been executed for Phase 1 Assessment activities.
6
7
8 | 06/14/16: Prime Professional Service Provider contract has been executed and assesment is under way.
9 | 06/14/16: Prime Professional Service Provider contract is being finalized.
10 | 06/14/16: Prime Professional Service Provider continues with assessment and early design activities.
12
13 | 06/14/16: Prime Professional Service Provider has been selected.
14
15
16
17
18

## TFC 3.16
| Agency: | Texas Facilities Commission (303)
| Date: | 2016-03-15 | [9 empty] | 2016-03-15
| Prepared by: | John Raff, P.E.
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 303 | Texas School for the Deaf (TSD) / Texas School for the Blind and Visually Impaired (TSBVI) Campus Wide Improvements, Austin TX | Repair/Replacement of fire protection, life safety, mechanical, plumbing and electrical systems and architectural improvements. | GR Funds | 39856898 | 39833856 | 2018-01-16 | 16% | 0% | 5999186 | 268981 | 33565689 | YES
2 | 303 | Lyndon B. Johnson Building (LBJ), Austin TX | Repairs to elevators, life safety, mechanical, plumbing and electrical systems. | GR Funds | 15000000 | 15000000 | 2019-12-31 | 13% | 0% | 2122250 | 80250 | 12797500 | YES
3 | 303 | William B. Travis Building (WBT), Austin TX | Repairs to mechanical systems and enhancement to indoor air quality. | GR Funds | 16732708 | 16544412 | 2019-12-31 | 5% | 0% | 2388000 | 0 | 14156412 | YES
4 | 303 | Stephen F. Austin Building (SFA), Austin, TX | Repairs to mechanical and plumbing systems. | GR Funds | 13672475 | 13518617 | 2019-12-31 | 5% | 0% | 0 | 0 | 13518617 | YES
5 | 303 | 7-Building Improvements Project Austin TX Central Services Bldg. (CSB) Insurance Annex (INX) John H. Reagan Bldg. (JHR) Robert E. Johnson Bldg. (REJ) E.O. Thompson Bldg. (THO) Thomas J. Rusk Bldg. (TJR) William P. Clements Jr. Bldg. (WPC) | CSB- Repair to fire protection, mechanical systems, plumbing systems, paving, elevators and boilers. INX- Repairs to mechanical systems. JHR- Repairs to mechanical and electrical systems. REJ- Repairs to security, mechanical and electrical systems. THO- Repairs t security systems, enhancement to indoor air quality, mechanical systems and architectura systems. TJR- Repairs to security, elevators and mechanical systems. WPC- Repairs to electrical systems and enhancement to indoor air quality. | GR Funds | 14478300 | 14316256 | 2020-02-28 | 0% | 0% | 334169 | 0 | 13982087 | YES
6 | 303 | William P. Hobby Complex (WPH), Austin TX | Repairs to mechanical, electrical and plumbing systems and fire protection. | GR Funds | 7621589 | 7537100 | 2020-02-28 | 0% | 0% | 226063 | 13651.88 | 7297385.12 | YES
7 | 303 | Brown Heatly Bldg. - Elevator, Austin TX | Repairs/Replace Elevators | GR Funds | 2514334 | 2486402 | 2017-01-21 | 17% | 0% | 41773.67 | 88926.33 | 2355702 | YES
8 | 303 | 4-Building Elevator Project, Austin TX James Earl Rudder Bldg. (JER) Thomas J. Rusk Bldg. (TJR) William P. Clements Jr. Bldg. (WPC) William P. Hobby Complex (WPH) | Repair/Replace Elevators in buildings - JER, TJR, WPC, WPH | GR Funds | 16991013 | 16799811 | 2017-11-30 | 1% | 0% | 942374 | 0 | 15857437 | YES
9 | 303 | 5-Building Project, Austin TX Insurance Building (INS) Price Daniel Sr. Building (PDB) Supreme Court Building (SCB) Sam Houston Building (SHB) Thomas C. Clark Building (TCC) | INS- Repairs to security, life safety, mechanical systems, exterior windows, architectural finishes, rain water drainage and waterproofing systems. PDB- Repairs to mechanical systems and enhancement to indoor air quality. SCB- Enhancement to indoor air quality, repairs to security systems, elevators, mechanical and electrical systems. SHB- Repairs to mechanical systems. TCC- Enhancement to indoor air quality, repairs to elevators, mechanical, waterproofing systems. | GR Funds | 16791914 | 16602952 | 2020-03-31 | 0% | 0% | 0 | 0 | 16602952 | YES
10 | 303 | John H. Winters Complex (JHW), Austin TX | Repairs to data center, life safety, accessibility, fire protection, mechanical, plumbing, electrical systems and architectural finishes. | GR Funds | 16157401 | 15975579 | 2020-01-31 | 0% | 0% | 25200 | 0 | 15950379 | YES
11 | 303 | DSHS - 4 Building Project, Austin TX Dept. of Health Bldg. F (DHF) Dept. of Health Records Bldg. (DHR) Dept. of Health Tower (DHT) Robert Beirnstein Bldg. (RBB) | DHF- Repairs to mechanical systems. DHR- Repairs to MEP systems, restrooms, paving and architectural finishes. DHT- Repairs to fire protection, MEP systems and architectural finishes. RBB- Repairs to elevators, MEP systems, security systems and enhancement of indoor air quality. | GR Funds | 14960012 | 14791712 | 2020-03-31 | 0% | 0% | 0 | 0 | 14791712 | YES
12 | 303 | Dept. of Health Old Plant (DHOP), Austin TX | DHOP- Repairs to MEP systems, fire protection and security systems. | GR Funds | 1507350 | 1490392 | 2017-02-01 | 35% | 0% | 9490 | 1808 | 1479094 | YES
13 | 303 | TFC Portfolio Wide Facility Condition Assessment | To provide condition assessment for TFC to include 44 office buildings, 8 warehouse/storage facilities, 9 special use facilities, 47 Texas School for the Deaf buildings, 34 Texas School for the Blind and Visually Impaired campus buildings, 19 parking garages and 33 parking lots. | GR Funds | 0 | 1840000 | 2017-01-05 | 0% | 0% | 0 | 0 | 1840000 | YES
14 | 303 | 11-Building Project, Austin TX Brown Heatly Bldg. (BHB) Dept. of Assistive and Rehabilitative Services Admin. Bldg. (DARS) Dr. Bob Glaze Laboratory (DBGL) Dept. of Health Bldg. B (DHB) Dept. of Health Bldg. H (DHH) Dept. of Health Old Lab (DHOL) Dept. of Health Lab A600 (A600) Dept. of Health Service Bldg. (DHSB) Dept. of Health Annex (DHX) Disaster Recovery Operations Center (DROC) Human Services Warehouse (HSW) | BHB- Repairs to accessibility, electrical and mechanical systems. DARS- repairs to elevators. DBGL- Repairs to mechanical, roofing systems and enhancement to indoor air quality. DHB- Enhancement to indoor air quality. DHH- Repairs to mechanical and electrical systems. DHOL- Repairs to roofing, MEP systems, elevators and enhancement of indoor air quality. A600- Repairs to roofing, MEP systems, elevators and enhancement of indoor air quality DHSB- Repairs to mechanical and architectural finishes. DHX- Repairs to security systems, elevators, MEP systems and architectural finishes. DROC- Repairs to mechanical, electrical systems and enhancement of indoor air quality. HSW- Repairs to elevators, mechanical systems and enhancement of indoor air quality. | GR Funds | 9886584 | 9775736 | 4/31/2020 | 0% | 0% | 88370 | 58239 | 9629127 | YES
15 | 303 | 8-Building Project, Austin, TX Park 35 Bldg A (P35A) Park 35 Bldg B (P35B) Park 35 Bldg C (P35C) Park 35 Bldg D (P35D) Park 35 Bldg E (P35E) Promontory Point (PROM) State Records Center (SRC) Wheless Lane Laboratory (WLL) | P35A- Repairs to mechanical, architectural, and enhancement of indoor air quality. P35B- Repairs to roofing, mechanical, electrical and architectural finishes. P35C- Repairs to mechanical systems and inhancement of indoor air quality. P35D- Repairs of mechanical systems. P35E- Enhancement of indoor air quality. Prom- Enhancement to indoor air quality and renovate existing vacant officspace into warehouse/training space. SRC- Enhancement of indoor air quality and repairs to MEP systems. WLL- Repairs to electrical systems and enhancement to indoor air quality. | GR Funds | 8131095 | 8039595 | 4/31/2020 | 0% | 0% | 0 | 0 | 8039595 | YES
16 | 303 | Fire Protection- Various Bldg. Austin TX | Repairs/Replacement of fire protection systems to various buildings as determined necessary from assessment. | GR Funds | 14152211 | 13992954 | 2019-06-15 | 0% | 0% | 0 | 0 | 13992954 | YES
17 | 303 | Parking Garage Elevator Project, Austin TX Parking Garage A (PKA) B, F, G, H, J, M, N and P | Repair/Replacement of elevators in PKA, PKB, PKF, PKG, PKH, PKJ, PKM, PKN, PKP | GR Funds | 5385467 | 5324864 | 2020-01-15 | 0% | 0% | 0 | 0 | 5324864 | YES
18 | 303 | Waco Office Bldg. (WAC), Waco, TX | Repairs to chillers. | GR Funds | 42280 | 41804 | 2016-08-31 | 0% | 0% | 0 | 0 | 41804 | YES
TBD | 303 | GJ Sutton Building (GJS), San Antonio TX | Repairs to MEP systems, fire protection systems, architectural, and security. | GR Funds | 830694 | 830694 | 2019-03-31 | 0% | 0% | 0 | 0 | 830694
TBD | 303 | El Paso Office Building (ELP), El Paso TX | Repairs to mechanical, electrical and security systems. | GR Funds | 814169 | 814169 | 2019-02-28 | 0% | 0% | 0 | 0 | 814169
TBD | 303 | Elias Ramirez Bldg. (ERB), Houston TX | Repairs to ADA paving, mechanical systems and drainage pipes. | GR Funds | 112306 | 112306 | 2019-02-28 | 0% | 0% | 0 | 0 | 112306
TBD | 303 | Fort Worth Office Bldg. (FTW), Fort Worth TX | Repairs to electrical systems and electrical generator. | GR Funds | 209777 | 209777 | 2019-03-31 | 0% | 0% | 0 | 0 | 209777
TBD | 303 | Carlos F. Truan Natural Resource Center (TRC), Corpus Christi, TX | Enhancement to indoor air quality, repairs to elevators, mechanical, waterproofing systems. | GR Funds | 1001586 | 971175 | 2020-01-31 | 0% | 0% | 0 | 0 | 971175
TBD | 303 | Tyler Office Bldg. (TYL), Tyler, TX | Repairs to roofing, plumbing and electrical systems. | GR Funds | 306185 | 306185 | 2020-01-31 | 0% | 0% | 0 | 0 | 306185
|  |  |  | Totals: | 217156348 | 217156348 |  |  |  | 12176875.67 | 511856.21 | 204467616.12

## TFC Notes 3.16
| Agency: | Texas Facilities Commission (303)
| Date: | 2016-03-15
| Prepared by: | John Raff, P.E.
Project Priority | Supplemental Information
1 | 03/15/16: Prime Professional Service Provider contract has been executed. CMR selection pending. A 1.083% was deducted from the TSBVI budget and credited toward the TFC Portfolio Wide Facility Condition Assessment project (No. 13).
2 | 03/15/16: Prime Professional Service Provider contract has been executed. 03/21/16 CMR solicitation.
3 | 03/15/16: Prime Professional Service Provider contract has been executed. A 1.125% was deducted from original budget and credited toward the TFC Portfolio Wide Facility Condition Assessment project (No. 13).
4 | 03/15/16: Prime Professional Service Provider contract has been executed. A 1.125% was deducted from original budget and credited toward the TFC Portfolio Wide Facility Condition Assessment project (No. 13).
5 | 03/15/16: Prime Professional Service Provider contract has been selected. A 1.119% was deducted from original budget and credited toward the TFC Portfolio Wide Facility Condition Assessment project (No. 13).
6 | 03/15/16: A 1.119% was deducted from the original budget and credited toward the TFC Portfolio Wide Facility Condition Assessment project (No. 13).
7 | 03/15/16: A 1.111% was deducted from the original budget and credited toward the TFC Portfolio Wide Facility Condition Assessment project (No. 13).
8 | 03/15/16: Prime Professional Service Provider contract has been selected. A 1.125% was deducted from the original budget and credited toward the TFC Portfolio Wide Facility Condition Assessment project (No. 13).
9 | 03/15/16: Prime Professional Service Provider contract has been selected. A 1.125% was deducted from the original budget and credited toward the TFC Portfolio Wide Facility Condition Assessment project (No. 13).
10 | 03/15/2016: Prime Professional Service contract has been executed. A 1.125% was deducted from the original budget and credited toward the TFC Portfolio Wide Facility Condition Assessment project (No. 13).
12 | 03/15/2016: Project was changed order into an existing project. Design is 35% complete. A 1.125% was deducted from the original budget and credited toward the TFC Portfolio Wide Facility Condition Assessment project (No. 13).
13 | 03/15/2016: A professional service that supports the entire deferred maintenance program and all current projects. Services were aggregated to achieve best value for the State and are tracked as a separate Project. Project was added utilizing funds of approximate 1.25% from each project as noted in the supplemental notes to provide condition assessment for TFC to include 44 office buildings, 8 warehouse/storage facilities, 9 special use facilities, 47 Texas School for the Deaf buildings, 34 Texas School for the Blind and Visually Impaired campus buildings, 19 parking garages and 33 parking lots.
14 | 3/15/2016: A 1.121% was deducted from the original budget and creditied toward the TFC Portfolio Wide Facility Condition Assessment project (No.13).
15 | 3/15/2016: A 1.125% was deducted from the original budget and creditied toward the TFC Portfolio Wide Facility Condition Assessment project (No.13).
16 | 3/15/2016: A 1.125% was deducted from the original budget and creditied toward the TFC Portfolio Wide Facility Condition Assessment project (No.13).
17 | 3/15/2016: A 1.125% was deducted from the original budget and creditied toward the TFC Portfolio Wide Facility Condition Assessment project (No.13).
18 | 3/15/2016: A 1.125% was deducted from the original budget and creditied toward the TFC Portfolio Wide Facility Condition Assessment project (No.13).

## TFC 12.15
| Agency: | Texas Facilities Commission (303)
| Date: | 2015-12-14 | [9 empty] | 2015-11-30
| Prepared by: | John Raff, P.E.
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 303 | Texas School for the Deaf (TSD) / Texas School for the Blind and Visually Impaired (TSBVI) Campus Wide Improvements, Austin TX | Repair/Replacement of fire protection, life safety, mechanical, plumbing and electrical systems and architectural improvements. | GR Funds | 39856898 | 39856898 | 2019-11-30 | 0% | 0% | 0 | 0 | 39856898 | YES
2 | 303 | Lyndon B. Johnson Building (LBJ), Austin TX | Repairs to elevators, life safety, mechanical, plumbing and electrical systems. | GR Funds | 15000000 | 15000000 | 2019-12-31 | 0% | 0% | 0 | 0 | 15000000 | YES
3 | 303 | William B. Travis Building (WBT), Austin TX | Repairs to mechanical systems and enhancement to indoor air quality. | GR Funds | 16732708 | 16732708 | 2019-12-31 | 0% | 0% | 0 | 0 | 16732708 | YES
4 | 303 | Stephen F. Austin Building (SFA), Austin, TX | Repairs to mechanical and plumbing systems. | GR Funds | 13672475 | 13672475 | 2019-12-31 | 0% | 0% | 0 | 0 | 13672475 | YES
5 | 303 | 7-Building Improvements Project Austin TX Central Services Bldg. (CSB) Insurance Annex (INX) John H. Reagan Bldg. (JHR) Robert E. Johnson Bldg. (REJ) E.O. Thompson Bldg. (THO) Thomas J. Rusk Bldg. (TJR) William P. Clements Jr. Bldg. (WPC) | CSB- Repair to fire protection, mechanical systems, plumbing systems, paving, elevators and boilers. INX- Repairs to mechanical systems. JHR- Repairs to mechanical and electrical systems. REJ- Repairs to security, mechanical and electrical systems. THO- Repairs t security systems, enhancement to indoor air quality, mechanical systems and architectura systems. TJR- Repairs to security, elevators and mechanical systems. WPC- Repairs to electrical systems and enhancement to indoor air quality. | GR Funds | 14478300 | 14478300 | 2020-02-28 | 0% | 0% | 0 | 0 | 14478300 | YES
6 | 303 | William P. Hobby Complex (WPH), Austin TX | Repairs to mechanical, electrical and plumbing systems and fire protection. | GR Funds | 7621589 | 7621589 | 2020-02-28 | 0% | 0% | 0 | 0 | 7621589
7 | 303 | Brown Heatly Bldg. - Elevator, Austin TX | Repairs/Replace Elevators | GR Funds | 2514334 | 2514334 | 2018-11-30 | 0% | 0% | 0 | 0 | 2514334 | YES
8 | 303 | 4-Building Elevator Project, Austin TX James Earl Rudder Bldg. (JER) Thomas J. Rusk Bldg. (TJR) William P. Clements Jr. Bldg. (WPC) William P. Hobby Complex (WPH) | Repair/Replace Elevators in buildings - JER, TJR, WPC, WPH | GR Funds | 16991013 | 16991013 | 2020-01-31 | 0% | 0% | 0 | 0 | 16991013 | YES
9 | 303 | 5-Building Project, Austin TX Insurance Building (INS) Price Daniel Sr. Building (PDB) Supreme Court Building (SCB) Sam Houston Building (SHB) Thomas C. Clark Building (TCC) | INS- Repairs to security, life safety, mechanical systems, exterior windows, architectural finishes, rain water drainage and waterproofing systems. PDB- Repairs to mechanical systems and enhancement to indoor air quality. SCB- Enhancement to indoor air quality, repairs to security systems, elevators, mechanical and electrical systems. SHB- Repairs to mechanical systems. TCC- Enhancement to indoor air quality, repairs to elevators, mechanical, waterproofing systems. | GR Funds | 16791914 | 16791914 | 2020-03-31 | 0% | 0% | 0 | 0 | 16791914 | YES
10 | 303 | John H. Winters Complex (JHW), Austin TX | Repairs to data center, life safety, accessibility, fire protection, mechanical, plumbing, electrical systems and architectural finishes. | GR Funds | 16157401 | 16157401 | 2020-01-31 | 0% | 0% | 0 | 0 | 16157401 | YES
11 | 303 | DSHS - 4 Building Project, Austin TX Dept. of Health Bldg. F (DHF) Dept. of Health Records Bldg. (DHR) Dept. of Health Tower (DHT) Robert Beirnstein Bldg. (RBB) | DHF- Repairs to mechanical systems. DHR- Repairs to MEP systems, restrooms, paving and architectural finishes. DHT- Repairs to fire protection, MEP systems and architectural finishes. RBB- Repairs to elevators, MEP systems, security systems and enhancement of indoor air quality. | GR Funds | 14960012 | 14960012 | 2020-03-31 | 0% | 0% | 0 | 0 | 14960012
12 | 303 | Dept. of Health Old Plant (DHOP), Austin TX | DHOP- Repairs to MEP systems, fire protection and security systems. | GR Funds | 1507350 | 1507350 | 2019-02-28 | 0% | 0% | 0 | 0 | 1507350
13 | 303 | 11-Building Project, Austin TX Brown Heatly Bldg. (BHB) Dept. of Assistive and Rehabilitative Services Admin. Bldg. (DARS) Dr. Bob Glaze Laboratory (DBGL) Dept. of Health Bldg. B (DHB) Dept. of Health Bldg. H (DHH) Dept. of Health Old Lab (DHOL) Dept. of Health Lab A600 (A600) Dept. of Health Service Bldg. (DHSB) Dept. of Health Annex (DHX) Disaster Recovery Operations Center (DROC) Human Services Warehouse (HSW) | BHB- Repairs to accessibility, electrical and mechanical systems. DARS- repairs to elevators. DBGL- Repairs to mechanical, roofing systems and enhancement to indoor air quality. DHB- Enhancement to indoor air quality. DHH- Repairs to mechanical and electrical systems. DHOL- Repairs to roofing, MEP systems, elevators and enhancement of indoor air quality. A600- Repairs to roofing, MEP systems, elevators and enhancement of indoor air quality DHSB- Repairs to mechanical and architectural finishes. DHX- Repairs to security systems, elevators, MEP systems and architectural finishes. DROC- Repairs to mechanical, electrical systems and enhancement of indoor air quality. HSW- Repairs to elevators, mechanical systems and enhancement of indoor air quality. | GR Funds | 9886584 | 9886584 | 4/31/2020 | 0% | 0% | 0 | 0 | 9886584
14 | 303 | 8-Building Project, Austin, TX Park 35 Bldg A (P35A) Park 35 Bldg B (P35B) Park 35 Bldg C (P35C) Park 35 Bldg D (P35D) Park 35 Bldg E (P35E) Promontory Point (PROM) State Records Center (SRC) Wheless Lane Laboratory (WLL) | P35A- Repairs to mechanical, architectural, and enhancement of indoor air quality. P35B- Repairs to roofing, mechanical, electrical and architectural finishes. P35C- Repairs to mechanical systems and inhancement of indoor air quality. P35D- Repairs of mechanical systems. P35E- Enhancement of indoor air quality. Prom- Enhancement to indoor air quality and renovate existing vacant officspace into warehouse/training space. SRC- Enhancement of indoor air quality and repairs to MEP systems. WLL- Repairs to electrical systems and enhancement to indoor air quality. | GR Funds | 8131095 | 8131095 | 4/31/2020 | 0% | 0% | 0 | 0 | 8131095
15 | 303 | Fire Protection- Various Bldg. Austin TX | Repairs/Replacement of fire protection systems to various buildings as determined necessary from assessment. | GR Funds | 14152211 | 14152211 | 2019-06-15 | 0% | 0% | 0 | 0 | 14152211
16 | 303 | Parking Garage Elevator Project, Austin TX Parking Garage A (PKA) B, F, G, H, J, M, N and P | Repair/Replacement of elevators in PKA, PKB, PKF, PKG, PKH, PKJ, PKM, PKN, PKP | GR Funds | 5385467 | 5385467 | 2020-01-15 | 0% | 0% | 0 | 0 | 5385467
TBD | 303 | GJ Sutton Building (GJS), San Antonio TX | Repairs to MEP systems, fire protection systems, architectural, and security. | GR Funds | 830694 | 830694 | 2019-03-31 | 0% | 0% |  |  | 830694
TBD | 303 | El Paso Office Building (ELP), El Paso TX | Repairs to mechanical, electrical and security systems. | GR Funds | 814169 | 814169 | 2019-02-28 | 0% | 0% |  |  | 814169
TBD | 303 | Elias Ramirez Bldg. (ERB), Houston TX | Repairs to ADA paving, mechanical systems and drainage pipes. | GR Funds | 112306 | 112306 | 2019-02-28 | 0% | 0% |  |  | 112306
TBD | 303 | Fort Worth Office Bldg. (FTW), Fort Worth TX | Repairs to electrical systems and electrical generator. | GR Funds | 209777 | 209777 | 2019-03-31 | 0% | 0% |  |  | 209777
TBD | 303 | Carlos F. Truan Natural Resource Center (TRC), Corpus Christi, TX | Enhancement to indoor air quality, repairs to elevators, mechanical, waterproofing systems. | GR Funds | 1001586 | 1001586 | 2020-01-31 | 0% | 0% |  |  | 1001586
TBD | 303 | Tyler Office Bldg. (TYL), Tyler, TX | Repairs to roofing, plumbing and electrical systems. | GR Funds | 306185 | 306185 | 2020-01-31 | 0% | 0% |  |  | 306185
TBD | 303 | Waco Office Bldg. (WAC), Waco, TX | Repairs to chillers. | GR Funds | 42280 | 42280 |  | 0% | 0% |  |  | 42280
|  |  |  | Totals: | 217156348 | 217156348 |  |  |  | 0 | 0 | 217156348

## TFC Notes 12.15
| Agency: | Texas Facilities Commission (303)
| Date: | 2015-12-14
| Prepared by: | John Raff, P.E.
Project Priority | Supplemental Information
1 | 12/14/15: Prime Professional Service Provider contract has been awarded by Commission. Professional services agreement is pending.
2 | 12/14/15: Prime Professional Service Provider contract has been awarded by Commission. Professional services agreement is pending.
3 | 12/14/15: Prime Professional Service Provider contract has been awarded by Commission. Professional services agreement is pending.
4 | 12/14/15: Prime Professional Service Provider has been selected. Contract award by Commission is pending.
5 | 12/14/15: Professional Services have been solicited. Professional Service provider evaluation and selection pending.
7 | 12/14/15: Prime Professional Service Provider has been selected. Contract award by Commission is pending.
8 | 12/14/15: Professional Services have been solicited. Professional Service provider evaluation and selection pending.
9 | 12/14/15: Professional Services have been solicited. Professional Service provider evaluation and selection pending.
10 | 12/14/15: Prime Professional Service Provider has been selected. Contract award by Commission is pending.

## TxDOT 9.16
|  |  |  | 2668 | Texas Department of Transportation #601 |  |  | Legend: Used latest budget estimate available in order of: 1. Contracted Amt. 2 Start Estimate Amt. 3 Orig/Current Estimate. | Contracted Amt. (PO iss/Cmsn date) thorugh Aug 26,2016
|  |  |  | Date: | 2016-09-01 |  |  |  | Start Estimate
Priority Audit Trail |  |  |  | Prepared by: | Diana Miller |  |  |  | Current Estimate
Q1 | Q2 | Q4 JOC Priority | Q4 JOC Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q4 AY16) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Comment
#N/A | 1 | 1 | 1 | 15470402973 | Drainage Flume - NE Bexar Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 24120 | 2015-12-23 | 100% | 100% | 24120 | 24120 | 0
E4 | 3 | 3 | 2 | 03470402975 | Stairs & Handicap Ramp for Mod Building - Henrietta Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 24105 | 2016-03-07 | 100% | 100% | 24105 | 24105 | 0
E1 | 4 | 4 | 3 | 20470402970 | Remove and Install 10 and 8.5 ton Roof Top HVAC Units - Beaumont District Headquarters | HVAC | Highway Trans. Fund 6 | 0 | 17650 | 2015-12-31 | 100% | 100% | 17650 | 17650 | 0
11 | 7 | 5 | 4 | 04470401499 | Install Automatic Gate - Dumas Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 10000 | 12935.51 | 2016-04-01 | 100% | 100% | 12935.51 | 12935.5 | 0.01 | Contract #5342 - combined 4 Projects
20 | 5 | 6 | 5 | 04470401510 | Install Automatic Gate - Darouzett Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 10000 | 12935.51 | 2016-04-01 | 100% | 100% | 12935.51 | 12935.5 | 0.01 | Contract #5342 - combined 4 Projects
22 | 6 | 7 | 6 | 04470401512 | Install Automatic Gate - Gruver Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 10000 | 12935.52 | 2016-04-01 | 100% | 100% | 12935.52 | 12935.5 | 0.02 | Contract #5342 - combined 4 Projects
23 | 8 | 8 | 7 | 04470401513 | Install Automatic Gate - Panhandle Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12000 | 12935.51 | 2016-04-01 | 100% | 100% | 12935.51 | 12935.5 | 0.01 | Contract #5342 - combined 4 Projects
10 | 9 | 9 | 8 | 08470401498 | New Perimeter Fence - Jayton Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 15000 | 22782 | 2016-05-11 | 100% | 100% | 22782 | 22782 | 0
38 | 23 | 10 | 9 | 20470401541 | A/C Unit Replacement - Anahuac Maintenance Office | HVAC | Highway Trans. Fund 6 | 7500 | 7580 | 2016-01-25 | 100% | 100% | 7580 | 7580 | 0
40 | 10 | 11 | 10 | 20470401543 | Replace Generator - Woodville Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 40000 | 21177.75 | 2016-03-22 | 100% | 100% | 21177.75 | 21177.75 | 0
#N/A | 12 | 12 | 11 | 10470401428 | Replace Roof On Shop - Tyler District Headquarters | Roofing | Highway Trans. Fund 6 | 500000 | 898100 | 2017-01-05 | 100% | 50% | 898100 | 17285 | 880815 | Phase I only
21 | 13 | 13 | 12 | 04470401511 | Replace Generator - Darouzett Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12500 | 11483.33 | 2016-03-18 | 100% | 100% | 11483.33 | 11483 | 0.33 | Contract #5514 - combined with 3 Projects
24 | 14 | 14 | 13 | 04470401514 | Replace Generator - Panhandle Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12500 | 11483.33 | 2016-04-01 | 100% | 100% | 11483.33 | 11483 | 0.33 | Contract #5514 - combined with 3 Projects
37 | 15 | 15 | 14 | 04470401540 | Replace Generator - Claude Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12500 | 11483.34 | 2016-04-01 | 100% | 100% | 11483.34 | 11483 | 0.34 | Contract #5514 - combined with 3 Projects
#N/A | 16 | 16 | 15 | 02470402980 | Replace Fuel Station Gas Pipeline - Fort Worth District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 31340 | 2015-12-30 | 100% | 100% | 31340 | 31340 | 0
19 | 47 | 17 | 16 | 38470401508 | Upgrade Obsolete Johnson Control Panels - Camp Hubbard State Headquarters | HVAC | Highway Trans. Fund 6 | 30000 | 28310 | 2016-07-18 | 100% | 100% | 28310 | 28310 | 0
#N/A | 17 | 19 | 17 | 38470402984 | Upgrade Security (C-CURE) - Card Reader - Austin Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 0 | 96624 | 2016-05-12 | 100% | 100% | 96624 | 96624 | 0 | January 2016 Phase I - Pedestals piece
446 | 18 | 20 | 18 | 04470401935 | Replace Fuel Pumps - Pampa Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 17000 | 2016-04-19 | 100% | 100% | 17000 | 17000 | 0 | Combined RFC -w1939 *1-5-16 Approved to submit with 1939 as one RFC
450 | 19 | 21 | 19 | 04470401939 | Replace Fuel Pumps - Perryton Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 17000 | 2016-04-19 | 100% | 100% | 17000 | 17000 | 0 | Combined RFC with 1935 *1-5-16 Approved to submit with 1936 as one RFC
230 | 20 | 22 | 20 | 14470401612 | Card Reader Pedestals for the Upgrade Security (C-CURE). - Austin Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1120000 | 53643 | 2016-08-16 | 100% | 100% | 53643 | 0 | 53643 | January 2016- Phase I at $53K completed.
34 | 22 | 23 | 21 | 16470401536 | Replace Existing Secuity Fence Around Perimeter Of Property - San Patricio Co | Safety/Security | Highway Trans. Fund 6 | 150000 | 47998 | 2016-04-26 | 100% | 100% | 47998 | 45498 | 2500
33 | 21 | 24 | 22 | 16470401535 | Replace Existing Secuity Fence Around Perimeter Of Property - Nueces East | Safety/Security | Highway Trans. Fund 6 | 125000 | 54899 | 2016-07-14 | 100% | 100% | 54899 | 46034.18 | 8864.82
31 | 25 | 25 | 23 | 16470401532 | Install Yard Illumination In Back Yard Area (Rebid) - Jim Wells Co. | Safety/Security | Highway Trans. Fund 6 | 40000 | 47600 | 2016-10-21 | 100% | 50% | 47600 | 0 | 47600
32 | 26 | 26 | 24 | 16470401533 | Install Exterior Lighting In Back Yard Area (Rebid) - Live Oak Co. | Safety/Security | Highway Trans. Fund 6 | 40000 | 64800 | 2016-10-13 | 100% | 75% | 64800 | 0 | 64800
185 | 27 | 27 | 25 | 18470401674 | Apply Ceramic Roof Coating (Rebid) - Rockwall Maintenance Office | Roofing | Highway Trans. Fund 6 | 120000 | 72930 | 2016-08-10 | 100% | 100% | 72930 | 12001.5 | 60928.5 | Lag in remainder payment
E2 | 24 | 28 | 26 | 01470402967 | Shop Floor Replacement (Project was rebid) - Paris District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 49643 | 2016-09-27 | 100% | 75% | 49643 | 0 | 49643
52 | 28 | 29 | 27 | 15470401602 | Upgrade Security (C-CURE) - San Antonio District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 477770 | 2017-01-20 | 100% | 10% | 477770 | 0 | 477770
51 | 29 | 30 | 28 | 06470401588 | Upgrade Security (C-CURE) - Odessa District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 163331 | 2016-09-29 | 100% | 75% | 163331 | 116698.64 | 46632.36
193 | 30 | 31 | 29 | 07470401686 | Upgrade Security (C-CURE) - San Angelo District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 89400 | 2016-09-30 | 100% | 70% | 89400 | 0 | 89400
#N/A | 31 | 32 | 30 | 18470402978 | Replace Chiller, provide temporary unit until work complete - Dallas District Headquarters | HVAC | Highway Trans. Fund 6 | 0 | 247496 | 2016-06-06 | 100% | 100% | 247496 | 247496 | 0
14 | 32 | 33 | 31 | 08470401502 | AC Unit Needs Replacing (Old R22 Unit) - Gail Maintenance Office | HVAC | Highway Trans. Fund 6 | 7500 | 9701 | 2016-03-03 | 100% | 100% | 9701 | 0 | 9701
180 | 33 | 34 | 32 | 18470401669 | HVAC - Split Unit (Meeting & Stock Rooms) - Waxahachie Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 10000 | 17240.7 | 2016-04-14 | 100% | 100% | 17240.7 | 17240.7 | 0
188 | 34 | 35 | 33 | 18470401677 | HVAC - Upgrade Existing System - Rockwall Maintenance Office | HVAC | Highway Trans. Fund 6 | 15000 | 19795.4 | 2016-04-14 | 100% | 100% | 19795.4 | 19795.4 | 0
#N/A | 35 | 36 | 34 | 38470402989 | Riverside 150 Datacenter UPS –- Austin - Riverside Annex II | Safety/Security | Highway Trans. Fund 6 | 0 | 739994 | 2017-02-28 | 100% | 100% | 739994 | 0 | 739994
118 | 36 | 37 | 35 | 07470401589 | New Roof - Junction Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 16200 | 44134 | 2016-12-13 | 100% | 0% | 44134 | 0 | 44134
142 | 39 | 38 | 36 | 04470401619 | Install Automatic Gate - Canyon Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 100% | 100% | 12867 | 12867 | 0 | Contract # 5485 - combined with 6 Project Ids
144 | 40 | 39 | 37 | 04470401625 | Install Automatic Gate - Borger Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 100% | 100% | 12867 | 12867 | 0 | Contract # 5485 - combined with 6 Project Ids
61 | 51 | 40 | 38 | 04470401693 | Replace Generator - Hereford Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 10950 | 10950 | 0 | Contract #5499 - combined with 6 project ids
72 | 37 | 41 | 39 | 04470401704 | Install Automatic Gate - Perryton Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 15000 | 12867 | 2016-05-24 | 100% | 100% | 12867 | 12867.01 | -0.01 | Contract # 5485 - combined with 6 Project Ids
73 | 49 | 42 | 40 | 04470401705 | Replace Generator - Perryton Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 10950 | 10950 | 0 | Contract #5499 - combined with 6 project ids
84 | 53 | 43 | 41 | 04470401723 | Replace Generator - Groom Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 10950 | 10950 | 0 | Contract #5499 - combined with 6 project ids
93 | 38 | 44 | 42 | 04470401734 | Install Automatic Gate - Dalhart Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 10000 | 12865 | 2016-05-24 | 100% | 100% | 12865 | 12864.99 | 0.01 | Contract # 5485 - combined with 6 Project Ids
145 | 126 | 45 | 43 | 04470401626 | Replace Generator - Borger Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 10950 | 10950 | 0 | Contract #5499 - combined with 6 project ids
146 | 42 | 46 | 44 | 04470401627 | Install Automatic Gate - Pampa Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 100% | 100% | 12867 | 12867 | 0 | Contract # 5485 - combined with 6 Project Ids
147 | 127 | 47 | 45 | 04470401628 | Replace Generator - Pampa Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 10950 | 10950 | 0 | Contract #5499 - combined with 6 project ids
195 | 131 | 48 | 46 | 04470401691 | Replace Generator - Canadian Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-10 | 100% | 100% | 10950 | 10950 | 0 | Contract #5499 - combined with 6 project ids
196 | 41 | 49 | 47 | 04470401692 | Install Automatic Gate - Amarillo Area Engineer and Mainteannce Office | Safety/Security | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 100% | 100% | 12867 | 12867 | 0 | Contract # 5485 - combined with 6 Project Ids
#N/A | 202 | 50 | 48 | 38470402988 | New Discharge air temp sensors and HVAC - Cedar Park | HVAC | Highway Trans. Fund 6 | 0 | 135601.03 | 2017-02-28 | 100% | 25% | 135601.03 | 0 | 135601.03
717 | 212 | 51 | 49 | 15470402206 | Replace Windows - Seguin Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 24300 | 2016-04-18 | 100% | 100% | 24300 | 0 | 24300
17 | 43 | 52 | 50 | 38470401506 | Replace Fence Along Mopac With Standard Fence - Camp Hubbard State Headquarters | Safety/Security | Highway Trans. Fund 6 | 45000 | 66250 | 2016-09-02 | 100% | 90% | 66250 | 65408.73 | 841.27
45 | 82 | 53 | 51 | 22470401549 | 3-Ton Standalone Unit (Duct Work, Vents, Air Handler, Etc) - Brackettville | HVAC | Highway Trans. Fund 6 | 8000 | 13045.73 | 2016-03-21 | 100% | 100% | 13045.73 | 13045.73 | 0
64 | 75 | 54 | 52 | 20470401696 | Replace HVAC Units - Liberty Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 20000 | 22500 | 2016-04-08 | 100% | 100% | 22500 | 22500 | 0
176 | 71 | 55 | 53 | 20470401663 | A/C Unit Replacement - Port Arthur Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 8000 | 10752 | 2016-06-13 | 100% | 100% | 10752 | 0 | 10752
177 | 72 | 56 | 54 | 20470401664 | A/C Unit Replacement - Port Arthur Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 18000 | 16500 | 2016-04-06 | 100% | 100% | 16500 | 16500 | 0
62 | 55 | 57 | 55 | 20470401694 | Replace Generator - Kountze Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 40000 | 42458 | 2016-09-19 | 100% | 80% | 42458 | 0 | 42458
150 | 89 | 58 | 56 | 20470401631 | A/C Unit Replacement - Beaumont District Headquarters | HVAC | Highway Trans. Fund 6 | 85000 | 81928 | 2016-08-16 | 100% | 100% | 81928 | 0 | 81928
149 | 56 | 59 | 57 | 20470401630 | Install Gates - Beaumont Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 16000 | 24999 | 2016-09-09 | 100% | 75% | 24999 | 0 | 24999
137 | 145 | 60 | 58 | 14470401613 | New Generators/Upgrades - Georgetown AE/M, Bastrop AE/M, Mason MNT, Austin DHQ | Safety/Security | Highway Trans. Fund 6 | 425000 | 184921 | 2016-09-30 | 100% | 50% | 184921 | 22783.6 | 162137.4 | 5 locations using same Project ID
1095 | 1103 | 61 | 59 | 02470402586 | Replace Flooring - Decatur Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 7830.7 | 2016-06-17 | 100% | 100% | 7830.7 | 7830.7 | 0
#N/A | 50 | 64 | 60 | 15470402986 | SFMO - add door in cmu wall at the Bandera Maintenance Building - Bandera Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 23700 | 2016-05-31 | 100% | 100% | 23700 | 0 | 23700
181 | 91 | 184 | 61 | 22470401670 | Replace HVAC For Sign Shop - Del Rio Maintenance Office | HVAC | Highway Trans. Fund 6 | 30000 | 12205 | 2016-04-18 | 100% | 100% | 12205 | 0 | 12205 | 15 KW NG - Entered as one PO by district with Proj ID 1766
278 | 290 | 736 | 62 | 22470401766 | Replace Computer/Storage Room HVAC - Laredo Traffic | HVAC | Highway Trans. Fund 6 | 15000 | 12475 | 2016-04-18 | 100% | 100% | 12475 | 0 | 12475 | PO entered by District as one PO with 1670 - we took over project on 7/6/16 per WR
55 | 93 | 65 | 63 | 16470401655 | Upgrade Security (C-CURE) - Corpus Christi District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350222 | 2016-12-08 | 100% | 100% | 350222 | 0 | 350222
100 | 79 | 66 | 64 | 17470402668 | Improve Lab Ventilation - Bryan District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 334068 | 2016-09-16 | 100% | 75% | 334068 | 201758.49 | 132309.51
111 | 66 | 67 | 65 | 08470401577 | Replace AC Unit (R22 Unit) - Colorado City Maintenance Office | HVAC | Highway Trans. Fund 6 | 10000 | 13074 | 2016-05-27 | 100% | 100% | 13074 | 0 | 13074
178 | 58 | 68 | 66 | 20470401665 | Replace Generator - Port Arthur Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 80000 | 47082 | 2016-09-12 | 100% | 75% | 47082 | 0 | 47082
7 | 61 | 69 | 67 | 11470401494 | Replace HVAC Units- - Lufkin District Headquarters | HVAC | Highway Trans. Fund 6 | 15000 | 58593 | 2016-12-04 | 100% | 0% | 58593 | 0 | 58593 | Combined w/11-1671 1494
66 | 159 | 70 | 68 | 07470401698 | Replace 2 Penthouse Type HVAC Units - REBID first 2bidders disqual by HUB (6/20/16) - San Angelo District Headquarters | HVAC | Highway Trans. Fund 6 | 220000 | 196428 | 2016-10-07 | 100% | 80% | 196428 | 0 | 196428
114 | 107 | 71 | 69 | 02470401581 | Chiller Replacement - Fort Worth District Headquarters | HVAC | Highway Trans. Fund 6 | 200000 | 49296 | 2016-08-11 | 100% | 100% | 49296 | 49296 | 0
#N/A | #N/A | 72 | 70 | 12470402994 | Replace HVAC system - Galveston Area Office - LaMarque | HVAC | Highway Trans. Fund 6 | 0 | 16896 | 2016-06-13 | 100% | 100% | 16896 | 0 | 16896
#N/A | 208 | 73 | 71 | 15470402988 | Bandera MNT Building structure - foundation - Bandera MNT | Capital Repairs | Highway Trans. Fund 6 | 0 | 24999 | 2016-06-06 | 100% | 100% | 24999 | 0 | 24999
292 | 304 | 76 | 72 | 16470401781 | Replace HVAC Unit At Vehicle Titles And Registration - Corpus Christi DHQ - District Headquarters | HVAC | Highway Trans. Fund 6 | 18000 | 21639 | 2016-05-19 | 100% | 100% | 21639 | 0 | 21639
309 | 321 | 77 | 73 | 16470401798 | Install Mini Split Condenser, Air Handler - Beeville Maintenance Office | HVAC | Highway Trans. Fund 6 | 15000 | 19886 | 2016-04-27 | 100% | 100% | 19886 | 0 | 19886
71 | 76 | 78 | 74 | 08470401703 | Replace AC Unit (Old R22 Unit) - Snyder Maintenance Office | HVAC | Highway Trans. Fund 6 | 7500 | 8338 | 2016-05-26 | 100% | 100% | 8338 | 0 | 8338
92 | 95 | 79 | 75 | 08470401733 | Replace AC Unit (R22 Unit) - Aspermont Maintenance Office | HVAC | Highway Trans. Fund 6 | 7500 | 9306 | 2016-05-24 | 100% | 100% | 9306 | 0 | 9306
257 | 269 | 80 | 76 | 04470401745 | Install Automatic Gate - Amarillo (East) Area Engineer and Maintenance Facility | Safety/Security | Highway Trans. Fund 6 | 10000 | 13200 | 2016-08-04 | 100% | 100% | 13200 | 0 | 13200
955 | 963 | 81 | 77 | 03470402446 | Replace Flooring At Maintenance - Vernon Area Engineer And Maintenance - Vernon Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 22253.67 | 2016-08-01 | 100% | 75% | 22253.67 | 0 | 22253.67
115 | 88 | 82 | 78 | 02470401582 | Exterior Lighting - Fort Worth District Headquarters | Safety/Security | Highway Trans. Fund 6 | 30000 | 37759 | 2016-08-19 | 100% | 100% | 37759 | 28424 | 9335 | Two phases one in March and one in July for Install.
170 | 98 | 83 | 79 | 05470401656 | New HVAC Relocate From Roof - Plains Maintenance Office | HVAC | Highway Trans. Fund 6 | 25000 | 8400 | 2016-06-09 | 100% | 100% | 8400 | 0 | 8400
394 | 406 | 84 | 80 | 06470401883 | Repair/Replace ATG System On Above Ground Fuel Tanks - Odessa Maintenance Office | Site Work | Highway Trans. Fund 6 | 12000 | 10311 | 2016-06-27 | 100% | 100% | 10311 | 0 | 10311
597 | 607 | 85 | 81 | 06470402086 | Repair/Replace ATG System On Above Ground Fuel Tanks - Stanton Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12000 | 10646 | 2016-06-28 | 100% | 100% | 10646 | 0 | 10646
905 | 913 | 86 | 82 | 06470402396 | Repair/Replace ATG System On Above Ground Fuel Tanks - Iraan Maintenance Office | Site Work | Highway Trans. Fund 6 | 12000 | 10321 | 2016-06-29 | 100% | 100% | 10321 | 0 | 10321
13 | 86 | 87 | 83 | 03470401501 | New Fencing - Bowie Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 50000 | 39750 | 2016-08-10 | 100% | 100% | 39750 | 0 | 39750
83 | 77 | 88 | 84 | 04470401722 | HVAC Replacement - Groom Maintenance Office | HVAC | Highway Trans. Fund 6 | 8000 | 5485 | 2016-08-04 | 100% | 100% | 5485 | 5485 | 0
186 | 92 | 89 | 85 | 18470401675 | Fence - Repair/Replace Chain Link/Rails - Rockwall Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 25000 | 90934 | 2016-06-13 | 100% | 100% | 90934 | 97668.29 | -6734.29
1011 | 1019 | 90 | 86 | 18470402502 | Countertops - Restrooms (Solid Surface) - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 23553.39 | 2016-06-17 | 100% | 100% | 23553.39 | 23553.39 | 0
308 | 320 | 92 | 87 | 09470401797 | Install Gate and Controls - Hillsboro Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 17000 | 10993.93 | 2016-05-27 | 100% | 100% | 10993.93 | 10993.93 | 0
#N/A | 207 | 179 | 88 | 16470402987 | Roof Repairs - Port Aransas Ferry Landing | Capital Repairs | Highway Trans. Fund 6 | 0 | 85000 | 2016-08-05 | 100% | 100% | 85000 | 33250 | 51750
830 | 838 | 94 | 89 | 18470402320 | Siding - Partial Replacement - Rockwall Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 5000 | 2016-05-25 | 100% | 100% | 5000 | 0 | 5000
#N/A | #N/A | 95 | 90 | 10470402998 | EMERGENCY HVAC Unit - Henderson Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 12953 | 2016-04-11 | 100% | 100% | 12953 | 0 | 12953
260 | 272 | 96 | 91 | 18470401748 | Generator Replaced With Diesel - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 15000 | 24894 | 2016-07-29 | 100% | 100% | 24894 | 24464.58 | 429.42
640 | 650 | 97 | 92 | 12470402129 | New Carpet/VCT - Angleton Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 9981.88 | 2016-07-12 | 100% | 100% | 9981.88 | 0 | 9981.88
839 | 847 | 98 | 93 | 11470402329 | Renovate Bathrooms - Lufkin Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 24248 | 2016-08-31 | 100% | 90% | 24248 | 0 | 24248
#N/A | #N/A | 99 | 94 | 02470402997 | Air Handler Replacement - District Headquarters | HVAC | Highway Trans. Fund 6 | 0 | 8242 | 2016-05-25 | 100% | 100% | 8242 | 0 | 8242
655 | 665 | 100 | 95 | 05470402144 | New VCT Floor - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 20000 | 19883.4 | 2016-07-18 | 100% | 100% | 19883.4 | 19883.4 | 0
652 | 662 | 101 | 96 | 18470402141 | Window - Ceramic Coating (Warehouse/Facilities/Shop) - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 15000 | 8785 | 2016-06-08 | 100% | 100% | 8785 | 8785 | 0
828 | 836 | 102 | 97 | 18470402318 | Paint Exterior - Rockwall Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24690 | 2016-06-17 | 100% | 100% | 24690 | 24690 | 0
25 | 96 | 103 | 98 | 09470401517 | Fence in Front of Facility - Waco District Headquarters | Safety/Security | Highway Trans. Fund 6 | 110000 | 150905 | 2016-12-02 | 100% | 0% | 150905 | 0 | 150905
1063 | 1071 | 104 | 99 | 24470402554 | Lab Dock Storage, Install Soffit Filler To Close Off Gap At Top. - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 2360 | 2016-05-23 | 100% | 100% | 2360 | 2360 | 0
943 | 951 | 105 | 100 | 12470402434 | Replace Gutter System - Houston NE Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 8547 | 2016-08-11 | 100% | 100% | 8547 | 0 | 8547
1064 | 1072 | 106 | 101 | 12470402555 | Replace Insulation (Laboratory) - Angleton Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 8000 | 4138.5 | 2016-06-02 | 100% | 100% | 4138.5 | 0 | 4138.5
#N/A | #N/A | 107 | 102 | 04470402995 | Sewer Line Replacement - Amarillo District Headquarters | Site Work | Highway Trans. Fund 6 | 0 | 18708 | 2016-07-18 | 100% | 100% | 18708 | 0 | 18708
#N/A | 200 | 108 | 103 | 15470402985 | Fencing, gate operators, preliminary asbestos testing. - Seguin Warehouse and Seguin Mantenance Office | Safety/Security | Highway Trans. Fund 6 | 0 | 189301 | 2016-11-04 | 100% | 0% | 189301 | 0 | 189301
288 | 300 | 109 | 104 | 21470401777 | Replace HVAC Units - San Benito Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 12000 | 8587.65 | 2016-05-18 | 100% | 100% | 8587.65 | 8587.65 | 0
306 | 318 | 110 | 105 | 10470401795 | Replace HVAC In Bldg. B - South Tyler Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 15000 | 6550 | 2016-06-02 | 100% | 100% | 6550 | 6550 | 0
91 | 138 | 111 | 106 | 19470401731 | Replace HVAC Systems - Carthage Maintenance Office | HVAC | Highway Trans. Fund 6 | 16000 | 18733 | 2016-07-01 | 100% | 100% | 18733 | 0 | 18733
#N/A | #N/A | 112 | 107 | 10470403005 | HVAC Replacement - Canton Maintenance | Capital Repairs | Highway Trans. Fund 6 | 0 | 6450 | 2016-05-09 | 100% | 100% | 6450 | 6450 | 0
101 | 133 | 113 | 108 | 05470401554 | Upgrade Security (C-CURE) - Lubbock District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 191717.47 | 2016-10-13 | 100% | 0% | 191717.47 | 0 | 191717.47
41 | 73 | 114 | 109 | 25470401544 | New Electronic Gate To Yard, Redesign Parking Area (Rebid) - Paducah Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 35000 | 79900 | 2016-11-04 | 100% | 75% | 79900 | 0 | 79900
313 | 325 | 115 | 110 | 22470401802 | Replace Two HVAC Units - La Pryor Maintenance Office | HVAC | Highway Trans. Fund 6 | 15000 | 12858 | 2016-06-16 | 100% | 100% | 12858 | 12858 | 0
152 | 78 | 116 | 111 | 20470401633 | Install Gates & Install/Repair Fencing - Beaumont District Headquarters | Safety/Security | Highway Trans. Fund 6 | 24000 | 21848 | 2016-07-08 | 100% | 100% | 21848 | 21848 | 0
539 | 549 | 117 | 112 | 11470402028 | Upgrade Interior Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 15000 | 23250 | 2016-06-03 | 100% | 100% | 23250 | 0 | 23250
768 | 776 | 118 | 113 | 17470402257 | Paint Building - Brenham Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 4987.78 | 2016-06-16 | 100% | 100% | 4987.78 | 0 | 4987.78
136 | 60 | 119 | 114 | 14470401611 | Upgrade Security (C-CURE) - Austin District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 420890 | 2017-02-13 | 100% | 0% | 420890 | 0 | 420890
#N/A | 102 | 120 | 115 | 05470402987 | AE Office Mold Remediation - Lubbock District Headquarters | Safety/Security | Highway Trans. Fund 6 | 0 | 34462.75 | 2016-12-20 | 100% | 0% | 34462.75 | 0 | 34462.75
413 | 425 | 121 | 116 | 20470401902 | Replace Fuel Dispensers - District Headquarters | Site Work | Highway Trans. Fund 6 | 15000 | 14703 | 2016-06-24 | 100% | 100% | 14703 | 14703 | 0
386 | 398 | 122 | 117 | 08470401875 | Sidewalks at the DMV Building Need to be Cut Out and Replaced in Various Areas - District Headquarters | Site Work | Highway Trans. Fund 6 | 7500 | 4950 | 2016-05-09 | 100% | 100% | 4950 | 0 | 4950
619 | 629 | 123 | 118 | 04470402108 | New Overhead Doors - Claude Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 6450 | 2016-06-21 | 100% | 100% | 6450 | 0 | 6450
620 | 630 | 124 | 119 | 04470402109 | Install Overhead Doors and Openers - Stratford Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 8400 | 2016-06-23 | 100% | 100% | 8400 | 0 | 8400
1083 | 1091 | 125 | 120 | 05470402574 | New VCT Floor - NE Special Crews | Capital Repairs | Highway Trans. Fund 6 | 10000 | 8890.1 | 2016-08-02 | 100% | 100% | 8890.1 | 0 | 8890.1
1153 | 1161 | 126 | 121 | 17470402644 | Replace Sidewalk Lab To Area Office - Brenham Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12500 | 3345 | 2016-06-16 | 100% | 100% | 3345 | 0 | 3345
#N/A | 211B | 127 | 122 | 02470402999 | Weatherford MNT gates 2. - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 0 | 24142.5 | 2016-08-26 | 100% | 100% | 24142.5 | 0 | 24142.5 | Due to security issues project approved. Created child number to PARENT#02470401548 split off $45,000 from total project for various locations listed. CHILD# 02470402999.
211 | 225 | 684 | 123 | 02470401548 | Phase I - Weatherford Gates (JOC211) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 0 | 24142.5 | 2016-09-12 | 100% | 75% | 24142.5 | 0 | 24142.5 | Phase I - Weatherford Gates. Due to security issues project approved. Created child number to PARENT#02470401548 split off $45,000 from total project for various locations listed. CHILD# 02470402999.
30 | 52 | 128 | 124 | 19470401530 | Replace 1 HVAC System - Atlanta District Headquarters | HVAC | Highway Trans. Fund 6 | 10000 | 20362.5 | 2016-06-20 | 100% | 100% | 20362.5 | 20362.01 | 0.49
102 | 68 | 129 | 125 | 19470401567 | Replace 2 HVAC Systems - Atlanta District Headquarters | HVAC | Highway Trans. Fund 6 | 20000 | 20362.5 | 2016-06-20 | 100% | 100% | 20362.5 | 20362.01 | 0.49
163 | 67 | 130 | 126 | 19470401646 | Replace HVAC System - Atlanta District Headquarters | HVAC | Highway Trans. Fund 6 | 10000 | 20362.5 | 2016-06-20 | 100% | 100% | 20362.5 | 20362.99 | -0.49
161 | 90 | 131 | 127 | 19470401644 | Replace 3 HVAC Systems - Atlanta District Headquarters | HVAC | Highway Trans. Fund 6 | 30000 | 20362.5 | 2016-06-20 | 100% | 100% | 20362.5 | 20362.99 | -0.49
130 | 110 | 132 | 128 | 15470401601 | Replace Roof Top Package HVAC 10 Ton System - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 15000 | 10983 | 2016-06-15 | 100% | 100% | 10983 | 0 | 10983
80 | 112 | 133 | 129 | 19470401719 | Replaces HVAC System - Daingerfield Maintenance Office | HVAC | Highway Trans. Fund 6 | 16000 | 19500 | 2016-07-26 | 100% | 100% | 19500 | 19500 | 0
184 | 111 | 134 | 130 | 19470401673 | Replace 1 HVAC System - Mt Pleasant Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 10000 | 21250 | 2016-08-22 | 100% | 100% | 21250 | 0 | 21250
538 | 548 | 136 | 131 | 11470402027 | Install Vinyl Plank Flooring - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 20800 | 2016-08-23 | 100% | 100% | 20800 | 0 | 20800
989 | 997 | 137 | 132 | 11470402480 | Upgrade Interior Lighting - Nacogdoches Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 22238.5 | 2016-06-16 | 100% | 100% | 22238.5 | 0 | 22238.5
706 | 716 | 138 | 133 | 08470402195 | Replace Flooring At The Special Crews Building - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 16700 | 4949.1 | 2016-07-26 | 100% | 100% | 4949.1 | 4949.1 | 0
#N/A | #N/A | 139 | 134 | 10470403004 | HVAC Replacement - Palestine Maintenance | Capital Repairs | Highway Trans. Fund 6 | 0 | 1500 | 2016-05-31 | 100% | 100% | 1500 | 6350 | -4850
#N/A | #N/A | 140 | 135 | 10470403006 | HVAC Replacement - Athens Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 6450 | 2016-06-06 | 100% | 100% | 6450 | 6450 | 0 | Two phases as of 8/23/16
#N/A | #N/A | 141 | 136 | 02470401308 | HVAC Replacement - Stephenvill Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 0 | 24693 | 2016-06-30 | 100% | 100% | 24693 | 24693 | 0
897 | 905 | 316 | 137 | 17470402388 | Repair Roof - Buffalo Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 7500 | 4500 | 2016-06-09 | 100% | 100% | 4500 | 0 | 4500
153 | 108 | 142 | 138 | 20470401634 | Modifications/Upgrade Electrical - Beaumont District Headquarters | Safety/Security | Highway Trans. Fund 6 | 60000 | 29500 | 2016-08-01 | 100% | 100% | 29500 | 0 | 29500
#N/A | #N/A | 143 | 139 | 13470403007 | Replace rusted Caged Safety Ladders - Port Lavaca Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 24700 | 2016-11-01 | 100% | 75% | 24700 | 0 | 24700
658 | 668 | 144 | 140 | 05470402147 | Replace Stairs Going Into Maint. Office - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 7000 | 12850 | 2016-08-31 | 100% | 90% | 12850 | 0 | 12850
303 | 315 | 145 | 141 | 02470401792 | 9 HVAC Units Transvision Building - District Headquarters | HVAC | Highway Trans. Fund 6 | 270000 | 283175 | 2016-12-02 | 100% | 0% | 283175 | 240 | 282935
70 | 121 | 147 | 142 | 13470401702 | Install ADA Into Time Room - Wharton Cty Maint. | Safety/Security | Highway Trans. Fund 6 | 10000 | 24300 | 2016-08-09 | 100% | 100% | 24300 | 24300 | 0
57 | 45 | 74 | 143 | 21470401684 | HVAC With Study/Assessment (rebid) - Pharr District Headquarters/Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 300000 | 572000 | 2017-04-18 | 100% | 0% | 572000 | 0 | 572000 | Project was re-bid
#N/A | R5 | 148 | 144 | 10470401503 | Replace Boilers at Administration Office - Tyler District Headquarters | HVAC | Highway Trans. Fund 6 | 180000 | 91250 | 2017-04-18 | 100% | 0% | 91250 | 0 | 91250 | Combined let 1503,1571,1572,1572 - Was going to be completed w/FY15 funds - but needs to be done with FY16 as of 5/31/16. Bundled as one RFC for total of $365K
105 | 185 | 149 | 145 | 10470401571 | Modifications/Upgrade HVAC - Tyler District Headquarters | HVAC | Highway Trans. Fund 6 | 180000 | 91250 | 2017-04-18 | 100% | 0% | 91250 | 0 | 91250 | Combined let 1503,1571,1572,1572 - Replace 2 Boilers-HQ.Bundled as one RFC for total of $365K
106 | 186 | 150 | 146 | 10470401572 | Modifications/Upgrade HVAC - Tyler District Headquarters | HVAC | Highway Trans. Fund 6 | 300000 | 91250 | 2017-04-18 | 100% | 0% | 91250 | 0 | 91250 | Combined let 1503,1571,1572,1572 - 60 ton chiller and air handler. Bundled as one RFC for total of $365K
107 | 187 | 151 | 147 | 10470401573 | Replace 5 Air Handler Units - Tyler District Headquarters | HVAC | Highway Trans. Fund 6 | 85000 | 91250 | 2017-04-18 | 100% | 0% | 91250 | 0 | 91250 | Combined let 1503,1571,1572,1572 - Aged and constant maintenance. Bundled as one RFC for total of $365K
162 | 74 | 152 | 148 | 19470401645 | Replace Generator - Atlanta District Headquarters | Safety/Security | Highway Trans. Fund 6 | 250000 | 379500 | 2017-02-10 | 100% | 0% | 379500 | 0 | 379500
43 | 11 | 153 | 149 | 18470401546 | Upgrade Security (C-CURE) - Dallas District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 193000 | 2016-10-28 | 100% | 0% | 193000 | 0 | 193000
4 | 48 | 154 | 150 | 01470401491 | Upgrade Security (C-CURE) - Paris District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 169000 | 2016-11-15 | 100% | 0% | 169000 | 0 | 169000
36 | 117 | 155 | 151 | 21470401539 | Security Fence - Zapata Maintenance Office Sub-Section | Safety/Security | Highway Trans. Fund 6 | 39800 | 59275 | 2016-10-07 | 100% | 65% | 59275 | 0 | 59275
#N/A | #N/A | 156 | 152 | 09470402996 | Limestone County Fence Replacement - Limestone - Waco District | Safety/Security | Highway Trans. Fund 6 | 0 | 53710 | 2016-08-18 | 100% | 100% | 53710 | 18000 | 35710
9 | 141 | 205 | 153 | 16470401496 | Replace Roof - Rockport Maintenance Office | Roofing | Highway Trans. Fund 6 | 300000 | 236800 | 2016-11-14 | 100% | 75% | 236800 | 0 | 236800
#N/A | #N/A | 157 | 154 | 17470403003 | Paint and Carpet - Madisonville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 21594.42 | 2016-12-15 | 100% | 0% | 21594.42 | 11500 | 10094.42 | Note changed Proj ID from 17-4704 to 09-4704
194 | 154 | 158 | 155 | 15470401687 | Install Gate Operator & Exterior Lighting - Kerrville Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 45000 | 35900 | 2016-10-26 | 100% | 0% | 35900 | 0 | 35900
821 | 829 | 159 | 156 | 11470402311 | Replace Fuel Dispensers - District Headquarters | Site Work | Highway Trans. Fund 6 | 15000 | 14980 | 2016-09-16 | 100% | 75% | 14980 | 0 | 14980
426 | 438 | 160 | 157 | 11470401915 | Replace Bathroom Sewer Dainage System - Crockett Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 11840 | 2016-08-01 | 100% | 100% | 11840 | 0 | 11840
76 | 123 | 161 | 158 | 21470401711 | Upgrade Fencing - Brownsville Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 39000 | 75900 | 2016-10-26 | 100% | 0% | 75900 | 0 | 75900
#N/A | #N/A | 162 | 159 | 13470403016 | Edna Caged Ladder Replacement - Edna Maintenance | Safety/Security | Highway Trans. Fund 6 | 0 | 15700 | 2016-09-02 | 100% | 85% | 15700 | 0 | 15700
85 | 116 | 249 | 160 | 15470401724 | Replace Roof - Uvalde Maintenance Office | Roofing | Highway Trans. Fund 6 | 100000 | 337200 | 2017-02-07 | 100% | 0% | 337200 | 0 | 337200
95 | 139 | 163 | 161 | 19470401736 | Replace HVAC - Jefferson Maintenance Office | HVAC | Highway Trans. Fund 6 | 8500 | 5395 | 2016-09-09 | 100% | 0% | 5395 | 0 | 5395
68 | 113 | 164 | 162 | 07470401700 | Replace Roof (Project was rebid) - San Angelo District Headquarters | Roofing | Highway Trans. Fund 6 | 250000 | 384800 | 2017-02-01 | 100% | 0% | 384800 | 0 | 384800 | Combined Let w 1685,1700 - Roof Replacement - Dist. Shop
266 | 278 | 166 | 163 | 12470401754 | Replace Emergency Generator - Brookshire Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 20000 | 30300 | 2016-11-21 | 100% | 75% | 30300 | 0 | 30300
259 | 271 | 168 | 164 | 19470401747 | Replace 2 HVAC Systems Add 1 HVAC For Shop - Linden Maintenance Office | HVAC | Highway Trans. Fund 6 | 30000 | 13595 | 2016-09-02 | 100% | 0% | 13595 | 0 | 13595
556 | 566 | 169 | 165 | 20470402045 | Paint Interior of Facilities - Woodville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 2500 | 18848 | 2016-07-08 | 100% | 100% | 18848 | 18848 | 0
1032 | 1040 | 170 | 166 | 20470402523 | Interior Lighting - Jasper Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24694 | 2016-07-13 | 100% | 100% | 24694 | 24394 | 300
1102 | 1110 | 171 | 167 | 20470402593 | Replace Electrical Panels - Liberty Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 24800 | 2016-09-15 | 100% | 80% | 24800 | 0 | 24800
28 | 136 | 172 | 168 | 21470401526 | Replace Existing Generator - San Isidro Maintenance Office Sub-Section | Safety/Security | Highway Trans. Fund 6 | 15000 | 23942 | 2016-09-27 | 100% | 65% | 23942 | 0 | 23942
947 | 955 | 173 | 169 | 08470402438 | Install Overhead Door Openers and Push Buttons in all Bay Door Openings. Total of 10 Door Openers. - Roby Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12000 | 9658 | 2016-07-07 | 100% | 100% | 9658 | 0 | 9658
808 | 816 | 174 | 170 | 20470402297 | Replace Doors, Frames & Locksets - Port Arthur Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 6000 | 24895 | 2016-08-26 | 100% | 75% | 24895 | 0 | 24895
657 | 667 | 212 | 171 | 05470402146 | Replace Stairs Going In To District Break Room - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 11400 | 2016-08-31 | 100% | 75% | 11400 | 0 | 11400
889 | 897 | 213 | 172 | 08470402380 | New VCT Floor - Snyder Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24884.6 | 2016-12-01 | 100% | 0% | 24884.6 | 0 | 24884.6
#N/A | #N/A | 214 | 173 | 03470403021 | Seymour Termite - Seymour | Capital Repairs | Highway Trans. Fund 6 | 0 | 18850 | 2016-08-12 | 100% | 100% | 18850 | 0 | 18850
283 | 295 | 292 | 174 | 15470401771 | Replace Generator - Bexar Metro Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 45000 | 29100 | 2016-10-12 | 100% | 75% | 29100 | 0 | 29100
798 | 806 | 1111 | 175 | 09470402287 | Upgrade Interior Lighting - Meridian Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 42748.32 | 2016-07-08 | 100% | 100% | 42748.32 | 0 | 42748.32
63 | 119 | 175 | 176 | 20470401695 | Replace Generator - Liberty Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 120000 | 67179 | 2017-01-23 | 100% | 0% | 67179 | 0 | 67179
#N/A | #N/A | 176 | 177 | 01470403019 | Emory Generator - Emory Maintenance | Safety/Security | Highway Trans. Fund 6 | 0 | 18968 | 2016-08-29 | 100% | 75% | 18968 | 0 | 18968
#N/A | #N/A | 660 | 178 | 12470403017 | Fuel System Repair (Rebid) - Angleton Area Engineer & Maintenance | Capital Repairs | Highway Trans. Fund 6 | 0 | 31000 | 2017-01-03 | 100% | 0% | 0 | 0 | 31000 | 0
441 | 453 | 177 | 179 | 18470401930 | Asphalt Overlay Parking Lot - Rockwall Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 24000 | 2016-11-23 | 0% | 0% | 0 | 0 | 24000 | Combine this and 1931 re-submit SS (6-20-16)
442 | 454 | 178 | 180 | 18470401931 | Parking Lot Striping- Rockwall Maintenance Office | Site Work | Highway Trans. Fund 6 | 5000 | 13000 | 2016-11-23 | 0% | 0% | 0 | 0 | 13000 | Combine this and 1931 re-submit SS (6-20-16)
18 | 149 | 206 | 181 | 38470401507 | Replace Roof (C.H. Bldg. 6) - Camp Hubbard State Headquarters | Roofing | Highway Trans. Fund 6 | 285000 | 489000.01 | 2017-02-07 | 100% | 0% | 489000.01 | 0 | 489000.01
919 | 927 | 209 | 182 | 17470402410 | Replace Siding On A Wash Bay - Brenham Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 16900 | 2016-07-13 | 100% | 100% | 16900 | 0 | 16900
1178 | 1186 | 217 | 183 | 17470402670 | New Canopy And Lights - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 12500 | 22020 | 2016-07-26 | 100% | 100% | 22020 | 22020 | 0
6 | 64 | 216 | 184 | 38470401493 | Replace Or Rebuild Existing Generator - Camp Hubbard State Headquarters | Safety/Security | Highway Trans. Fund 6 | 75000 | 278320 | 2017-03-08 | 100% | 0% | 278320 | 0 | 278320
935 | 943 | 220 | 185 | 04470402426 | New Compressor/Relocate - Groom Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 8047.5 | 2016-07-07 | 100% | 100% | 8047.5 | 0 | 8047.5
1140 | 1148 | 234 | 186 | 11470402631 | Upgrade Interior Lighting - Hemphill Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24473.6 | 2016-08-17 | 100% | 100% | 24473.6 | 0 | 24473.6
1117 | 1125 | 167 | 187 | 10470402608 | Repaint Bldg. B - South Tyler Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 69200 | 2016-08-24 | 100% | 100% | 69200 | 0 | 69200
54 | 118 | 199 | 188 | 16470401650 | Replace Roof - Corpus Christi District Headquarters | Roofing | Highway Trans. Fund 6 | 225000 | 240343.79 | 2017-01-24 | 100% | 0% | 240343.79 | 0 | 240343.79 | Let 1650, 1651, 1652 and 1653 together
166 | 129 | 200 | 189 | 16470401651 | Replace Roof On The District Hq Administration Bldg - Corpus Christi District Headquarters | Roofing | Highway Trans. Fund 6 | 300000 | 240343.79 | 2017-01-24 | 100% | 0% | 240343.79 | 0 | 240343.79 | Let 1650, 1651, 1652 and 1653 together
167 | 130 | 201 | 190 | 16470401652 | Replace Roof On The Lab Building - Corpus Christi District Headquarters | Roofing | Highway Trans. Fund 6 | 35000 | 240343.79 | 2017-01-24 | 100% | 0% | 240343.79 | 0 | 240343.79 | Let 1650, 1651, 1652 and 1653 together
168 | 135 | 202 | 191 | 16470401653 | Replace Roof On The Special Crews Office Building - Corpus Christi District Headquarters | Roofing | Highway Trans. Fund 6 | 350000 | 240343.8 | 2016-12-13 | 100% | 0% | 240343.8 | 0 | 240343.8 | Let 1650, 1651, 1652 and 1653 together
172 | 162 | 218 | 192 | 11470401658 | Replace Emergency Generator - Crockett Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 38000 | 59530.04 | 2017-01-17 | 100% | 0% | 59530.04 | 0 | 59530.04
694 | 704 | 91 | 193 | 02470402183 | Replace\New Windows At Laboratory - Fort Worth DHQ - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 20000 | 70316 | 2016-08-01 | 100% | 100% | 70316 | 0 | 70316
#N/A | #N/A | #N/A | 194 | 10470403023 | Athens HVAC - Athens Maint. & Eng. Office | HVAC | Highway Trans. Fund 6 | 0 | 6350 | 2016-06-24 | 100% | 100% | 6350 | 6350 | 0
923 | 931 | 193 | 195 | 06470402414 | Remove and Replace Existing Shower Floor Tile - Balmorhea Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 3845 | 2016-10-28 | 100% | 25% | 3845 | 0 | 3845
924 | 932 | 194 | 196 | 06470402415 | Remove and Replace Floor Tile Main Office - Balmorhea Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 9540 | 2016-10-28 | 100% | 25% | 9540 | 0 | 9540
996 | 1004 | 197 | 197 | 06470402487 | Enclose 3 Bays With Insulated Overhead Doors To Secure Equipment & Weather Protection - Stanton Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 12400 | 2016-10-04 | 100% | 75% | 12400 | 0 | 12400
727 | 735 | 225 | 198 | 05470402216 | Paint Exterior - Ralls Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 21891 | 2016-09-23 | 100% | 0% | 21891 | 0 | 21891
883 | 891 | 198 | 199 | 24470402374 | Repair / Replace Plumbing Lines Fro Meter To Houses - Terlingua Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 18000 | 8640 | 2016-11-14 | 100% | 25% | 8640 | 0 | 8640
#N/A | #N/A | 662 | 200 | 15470403020 | New Braunfels Security Gate escalated 5-24-16 - New Braunfels | Safety/Security | Highway Trans. Fund 6 | 0 | 36300 | 2016-09-26 | 100% | 0% | 36300 | 0 | 36300 | Child of Proj ID#15470401560 New Braunfels Security Gate escalated 5-24-16
424 | 436 | 189 | 201 | 16470401913 | Replace 3 Existing Fuel Dispensers At The Fuel Station. - District Headquarters | Site Work | Highway Trans. Fund 6 | 20000 | 43087.87 | 2016-12-01 | 100% | 0% | 43087.87 | 0 | 43087.87 | Combined with 16-2012 and 16-2454
895 | 903 | 210 | 202 | 17470402386 | Paint Building - Huntsville Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 13800 | 2016-08-01 | 100% | 100% | 13800 | 0 | 13800
994 | 1002 | 281 | 203 | 11470402485 | Upgrade Exterior Lighting - San Augustine Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24234.8 | 2016-07-28 | 100% | 100% | 24234.8 | 23992.45 | 242.35
1139 | 1147 | 306 | 204 | 11470402630 | Replace Fuel Dispensers - Hemphill Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 15380 | 2016-09-28 | 100% | 0% | 15380 | 0 | 15380
35 | 137 | 312 | 205 | 21470401538 | Replace Generators - Zapata Maintenance Office Sub-Section | Safety/Security | Highway Trans. Fund 6 | 20000 | 71895 | 2016-10-06 | 100% | 65% | 71895 | 0 | 71895 | Combined with 21-1710 and 21-1712
277 | 289 | 187 | 206 | 22470401765 | Replace 8 HVAC Units - Laredo Lab/FIN/Stratus | HVAC | Highway Trans. Fund 6 | 80000 | 86258 | 2016-09-16 | 100% | 85% | 86258 | 0 | 86258
46 | 83 | 247 | 207 | 05470401553 | Replace Roof - Lubbock District Headquarters | Roofing | Highway Trans. Fund 6 | 50000 | 82146.33 | 2017-02-07 | 100% | 75% | 82146.33 | 0 | 82146.33 | Combined Let w1553,1738,2343
50 | 147 | 248 | 208 | 06470401587 | Replace Roof - Odessa District Headquarters | Roofing | Highway Trans. Fund 6 | 300000 | 341000 | 2017-04-11 | 100% | 0% | 341000 | 0 | 341000 | Combined Let -1587,1725 Roof Replacement - Odessa DHQ - Area Engineer Building
86 | 148 | 250 | 209 | 06470401725 | Replace Roof - Midland Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 65000 | 341000 | 2017-04-11 | 100% | 0% | 341000 | 0 | 341000 | Combined Let -1587,1725 Roof Replacement - Odessa DHQ - Area Engineer Building
94 | 105 | 252 | 210 | 04470401735 | Roof - Dalhart Maintenance Office | Roofing | Highway Trans. Fund 6 | 175000 | 375000 | 2017-02-07 | 100% | 0% | 375000 | 0 | 375000
97 | 97 | 253 | 211 | 05470401738 | Replace Roof - Lubbock District Headquarters | Roofing | Highway Trans. Fund 6 | 65000 | 82146.33 | 2017-02-07 | 100% | 0% | 82146.33 | 0 | 82146.33 | Combined Let w1553,1738,2343
852 | 860 | 1149 | 212 | 05470402343 | Replace Roof - District Headquarters-LBB AE's | Capital Repairs | Highway Trans. Fund 6 | 50000 | 82146.34 | 2017-02-07 | 100% | 0% | 82146.34 | 0 | 82146.34 | Combined Let w1553,1738,2343
555 | 565 | 221 | 213 | 20470402044 | Install Additional Unit Heater - Woodville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 3000 | 24726 | 2016-07-18 | 100% | 100% | 24726 | 24726 | 0
868 | 876 | 231 | 214 | 05470402359 | New VCT Floor - Tahoka Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 9769.7 | 2016-08-25 | 100% | 100% | 9769.7 | 0 | 9769.7
1033 | 1041 | 232 | 215 | 20470402524 | Paint Office Interior - Jasper Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24812 | 2016-10-14 | 100% | 0% | 24812 | 0 | 24812
981 | 989 | 242 | 216 | 11470402472 | Replace Fuel Dispensers - Livingston Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 14990 | 2016-10-07 | 100% | 0% | 14990 | 0 | 14990
990 | 998 | 280 | 217 | 11470402481 | Install Electric Baydoor Openers - San Augustine Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24948 | 2016-08-01 | 100% | 100% | 24948 | 24948 | 0
626 | 636 | 135 | 218 | 17470402115 | Repair Roof - Huntsville Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 15000 | 6925 | 2016-08-11 | 100% | 100% | 6925 | 0 | 6925
#N/A | 199 | 211 | 219 | 14470402984 | New Generator/Upgrade - San Marcos Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 63227 | 2016-10-24 | 100% | 0% | 63227 | 0 | 63227 | New Generator/Upgrade---Split off of 14470401613
843 | 851 | 279 | 220 | 11470402333 | Replace Windows - Lufkin Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24950 | 2016-09-23 | 100% | 75% | 24950 | 0 | 24950
#N/A | #N/A | #N/A | 221 | 12470403027 | Replace HVAC unit - EPO - Northeast Harris Co. Maintenance Office | HVAC | Highway Trans. Fund 6 | 0 | 39777 | 2016-06-28 | 100% | 100% | 39777 | 0 | 39777
982 | 990 | 243 | 222 | 11470402473 | Replace Windows - Livingston Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24875 | 2016-11-04 | 100% | 0% | 24875 | 0 | 24875
297 | 309 | 288 | 223 | 20470401786 | Install/Repair Fence - Liberty Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 7000 | 14049.13 | 2016-10-28 | 100% | 0% | 14049.13 | 0 | 14049.13
807 | 815 | 392 | 224 | 20470402296 | Paint Interior Of Facility - Port Arthur Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24450 | 2016-10-14 | 100% | 0% | 24450 | 0 | 24450
258 | 270 | 727 | 225 | 04470401746 | New Generator - Loop Maintenance | Safety/Security | Highway Trans. Fund 6 | 12500 | 13100 | 2016-08-04 | 100% | 100% | 13100 | 0 | 13100
684 | 694 | 1021 | 226 | 17470402173 | Improve Lighting In Yard/Shed - Caldwell Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 5000 | 8460 | 2016-09-16 | 100% | 0% | 8460 | 0 | 8460
#N/A | #N/A | #N/A | 227 | 01470403022 | Paris Fuel Station Generator - Paris | Site Work | Highway Trans. Fund 6 | 0 | 8618 | 2016-08-04 | 100% | 100% | 8618 | 8618 | 0
542 | 552 | 230 | 228 | 11470402031 | Replace Flooring - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 24789 | 2016-09-30 | 100% | 0% | 24789 | 0 | 24789
148 | 106 | 255 | 229 | 04470401629 | Replace Roof - Pampa Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 175000 | 315000 | 2017-02-07 | 100% | 0% | 315000 | 0 | 315000
1100 | 1108 | 282 | 230 | 20470402591 | Paint Office Interior - Liberty Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 15887 | 2016-08-04 | 100% | 100% | 15887 | 15887 | 0
#N/A | #N/A | #N/A | 231 | 23470403024 | Commanche Sewer Repair - Brownwood District Headquarters | Site Work | Highway Trans. Fund 6 | 0 | 15500 | 2016-10-06 | 100% | 0% | 15500 | 0 | 15500
724 | 732 | 237 | 232 | 05470402213 | New VCT Floor - Brownfield Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 22885.2 | 2016-08-24 | 100% | 100% | 22885.2 | 0 | 22885.2
131 | 151 | 254 | 233 | 08470401604 | Replace Generator - Abilene District Headquarters | Safety/Security | Highway Trans. Fund 6 | 58000 | 44300 | 2016-10-28 | 100% | 0% | 44300 | 0 | 44300
744 | 752 | 239 | 234 | 08470402233 | Repair Damage To Walls And Wood In Area Ofice - Big Spring Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 8000 | 2417.35 | 2016-09-28 | 100% | 0% | 2417.35 | 0 | 2417.35
#N/A | #N/A | 661 | 235 | 14470403018 | San Marcos Septic replacement - San Marcos Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 28350 | 2016-10-21 | 100% | 0% | 28350 | 0 | 28350
616 | 626 | 270 | 236 | 18470402105 | Paint Exterior - Ennis Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24420.15 | 2016-09-28 | 100% | 75% | 24420.15 | 0 | 24420.15
922 | 930 | 295 | 237 | 17470402413 | Install Automatic Gate On Rear Gate - Bryan Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 15881.34 | 2016-11-25 | 100% | 0% | 15881.34 | 0 | 15881.34
615 | 625 | 300 | 238 | 18470402104 | Floor Tile Abatement - Corridors Only (Stain Concrete) - Ennis Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 20727.6 | 2016-10-17 | 100% | 25% | 20727.6 | 0 | 20727.6
1154 | 1162 | 1355 | 239 | 17470402645 | Improve Lighting In Yard/Shed - Hearne Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 24064.26 | 2016-10-04 | 100% | 0% | 24064.26 | 17229.26 | 6835
1099 | 1107 | 233 | 240 | 20470402590 | Interior Lighting - Liberty Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24630 | 2016-10-07 | 100% | 0% | 24630 | 0 | 24630
844 | 852 | 240 | 241 | 11470402334 | Underskirt Fuel Awning - Lufkin Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 6000 | 24860 | 2016-10-03 | 100% | 0% | 24860 | 0 | 24860
517 | 527 | 269 | 242 | 18470402006 | Paint Exterior - Waxahachie Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24840.25 | 2016-09-28 | 100% | 75% | 24840.25 | 0 | 24840.25
913 | 921 | 272 | 243 | 18470402404 | Paint Exterior - Hutchins Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 19460 | 2016-09-28 | 100% | 0% | 19460 | 0 | 19460
848 | 856 | 299 | 244 | 20470402338 | Paint Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 24958 | 2016-08-15 | 100% | 100% | 24958 | 24958 | 0
930 | 938 | 1206 | 245 | 17470402421 | Improve Lighting In Yard/Shed - Buffalo Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 8043.23 | 2016-10-07 | 100% | 100% | 8043.23 | 8043.23 | 0
171 | 99 | 185 | 246 | 05470401657 | Replace Roof - Plains Maintenance Office | Roofing | Highway Trans. Fund 6 | 50000 | 190675 | 2016-12-05 | 100% | 0% | 190675 | 0 | 190675
842 | 850 | 219 | 247 | 11470402332 | Replace Fuel Dispensers - Lufkin Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 20878 | 2016-09-14 | 100% | 0% | 20878 | 0 | 20878
87 | 104 | 251 | 248 | 03470401726 | Replace Roof - Vernon Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 120000 | 259975 | 2016-12-01 | 100% | 0% | 259975 | 0 | 259975
784 | 792 | 257 | 249 | 11470402273 | Replace Windows - Crockett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24625 | 2016-10-14 | 100% | 0% | 24625 | 0 | 24625
995 | 1003 | 258 | 250 | 11470402486 | Upgrade Interior Lighting - San Augustine Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 21561.58 | 2016-08-09 | 100% | 100% | 21561.58 | 21561.58 | 0
1035 | 1043 | 266 | 251 | 20470402526 | Replace Carpet And VCT - Jasper Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24320 | 2016-10-28 | 100% | 0% | 24320 | 0 | 24320
622 | 632 | 278 | 252 | 20470402111 | Interior Lighting - Newton Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24725 | 2016-10-14 | 100% | 0% | 24725 | 0 | 24725
543 | 553 | 289 | 253 | 11470402032 | Upgrade Interior Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 22849 | 2016-09-16 | 100% | 80% | 22849 | 0 | 22849
362 | 374 | 388 | 254 | 20470401851 | Reconfigure Parking Lot - Newton Maintenance Office | Site Work | Highway Trans. Fund 6 | 10000 | 24100 | 2016-08-04 | 100% | 100% | 24100 | 0 | 24100
984 | 992 | 394 | 255 | 11470402475 | Install Electric Baydoor Openers - Nacogdoches Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 23750 | 2016-09-26 | 100% | 0% | 0 | 0 | 23750
154 | 178 | 397 | 256 | 20470401635 | Replace Roof - Beaumont District Headquarters | Roofing | Highway Trans. Fund 6 | 95000 | 149643 | 2016-11-29 | 100% | 0% | 149643 | 0 | 149643
1156 | 1164 | 1357 | 257 | 17470402647 | Improve Lighting In Yard/Shed - Huntsville Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 15662.84 | 2016-10-05 | 100% | 0% | 15662.84 | 0 | 15662.84
550 | 560 | 284 | 258 | 04470402039 | Remove Oh Door In Breakroom And Install Walk Door - Dumas Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 5000 | 2016-08-03 | 100% | 100% | 5000 | 0 | 5000
157 | 168 | 353 | 259 | 03470401639 | Upgrade Security (C-CURE) - Wichita Falls District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 297573.85 | 2016-12-19 | 100% | 0% | 297573.85 | 0 | 297573.85
90 | 142 | 207 | 260 | 16470401730 | Replace Roof On The Maintenance Building - Nueces East | Roofing | Highway Trans. Fund 6 | 250000 | 139013 | 2017-02-28 | 100% | 0% | 0 | 0 | 139013
1081 | 1089 | 285 | 261 | 05470402572 | Replace Windows AE's Office - Littlefield Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 4684 | 2016-09-05 | 100% | 25% | 4684 | 0 | 4684
979 | 987 | 241 | 262 | 11470402470 | Replace Windows - Center Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24325 | 2016-10-28 | 100% | 0% | 24325 | 0 | 24325
540 | 550 | 277 | 263 | 11470402029 | Paint Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 24675 | 2016-09-16 | 100% | 80% | 24675 | 0 | 24675
104 | 156 | 263 | 264 | 38470401570 | Modifications/Upgrade HVAC - Camp Hubbard State Headquarters | HVAC | Highway Trans. Fund 6 | 200000 | 111777 | 2017-01-05 | 100% | 0% | 111777 | 0 | 111777
1142 | 1150 | 283 | 265 | 11470402633 | Upgrade Interior Lighting - Groveton Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 23380 | 2016-09-16 | 100% | 80% | 23380 | 0 | 23380
#N/A | #N/A | #N/A | 266 | 03470403031 | Phase III Wichita falls flooring - Wichita Falls | Capital Repairs | Highway Trans. Fund 6 | 0 | 98925 | 2016-09-28 | 100% | 0% | 98925 | 0 | 98925 | Appoved to fund phase II of Project ID #03-2972 that was done w/District funds
#N/A | #N/A | #N/A | 267 | 06470403032 | Odessa Shop HVAC - Odessa | HVAC | Highway Trans. Fund 6 | 0 | 12483 | 2016-08-09 | 100% | 100% | 12483 | 0 | 12483
#N/A | #N/A | #N/A | 268 | 05470401969 | New 2" Water Line Installation - Tulia Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 40000 | 2016-11-23 | 100% |  | 0 | 0 | 40000 | July SS recd' to be Rebid in Sept
16 | 65 | 226 | 269 | 38470401505 | Install Generator For Data Center (Camp Hubbard Bldg. 6) - Camp Hubbard State Headquarters | Safety/Security | Highway Trans. Fund 6 | 517000 | 475000 | 2017-06-07 | 100% | 0% | 0 | 0 | 475000
725 | 733 | 1052 | 270 | 05470402214 | Remove In-Ground Hydraulic Floor Lift - Brownfield Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 3000 | 6050 | 2016-08-17 | 100% | 100% | 6050 | 0 | 6050
815 | 823 | 1124 | 271 | 05470402305 | Remove In-Ground Hydraulic Floor Lift - Levelland Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 3000 | 5500 | 2016-08-12 | 100% | 100% | 5500 | 0 | 5500
837 | 845 | 1141 | 272 | 05470402327 | Remove In-Ground Hydraulic Floor Lift - Lamesa Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 3000 | 4600 | 2016-08-15 | 100% | 100% | 4600 | 0 | 4600
869 | 877 | 1162 | 273 | 05470402360 | Remove In-Ground Hydraulic Floor Lift - Tahoka Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 3000 | 5600 | 2016-08-19 | 100% | 100% | 5600 | 0 | 5600
99 | 46 | 75 | 274 | 21470401775 | Complete Power Project (Single, Electrical Power Upgrade Project, To Encompass All Of The Electrical Issues To Include Study/Assessment) - Pharr District Headquarters | Safety/Security | Highway Trans. Fund 6 | 300000 | 474700 | 2017-06-21 | 100% | 0% | 0 | 0 | 474700 | Let in March - but had to be rebid
192 | 115 | 165 | 275 | 07470401685 | Replace Roofing - San Angelo District Headquarters | Roofing | Highway Trans. Fund 6 | 125000 | 384800 | 2017-02-08 | 100% | 0% | 0 | 0 | 384800 | Combined Let w 1685,1700 - Roof Replacement - Dist. Shop
722 | 730 | 236 | 276 | 05470402211 | Repaint Exterior, Old Faded Peeling - Bovina Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 23703.5 | 2016-09-15 | 100% | 0% | 23703.5 | 0 | 23703.5
742 | 750 | 238 | 277 | 08470402231 | New VCT Floor - Big Spring Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 14962.05 | 2016-09-14 | 100% | 0% | 14962.05 | 0 | 14962.05
#N/A | #N/A | #N/A | 278 | 05470403029 | Upgrade Light - | Safety/Security | Highway Trans. Fund 6 | 0 | 12500 | 2016-09-08 | 100% | 0% | 12500 | 0 | 12500
138 | 143 | 343 | 279 | 06470401615 | Replace Main HVAC Multi-Zone Units - Odessa District Headquarters | HVAC | Highway Trans. Fund 6 | 160000 | 240000 | 2017-01-10 | 100% | 0% | 0 | 0 | 240000
757 | 765 | 303 | 280 | 06470402246 | Repaint Exterior - McCamey Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15765 | 2016-10-10 | 100% | 25% | 15765 | 0 | 15765
1097 | 1105 | 320 | 281 | 20470402588 | Install Roll-Up Door Opener - Anahuac Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 3000 | 11407.14 | 2016-09-23 | 100% | 0% | 11407.14 | 0 | 11407.14
841 | 849 | 360 | 282 | 11470402331 | Replace Flooring - Lufkin Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12000 | 24875 | 2016-11-28 | 100% | 0% | 24875 | 0 | 24875
978 | 986 | 389 | 283 | 11470402469 | Replace Overhead Doors - Center Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 23475 | 2016-09-23 | 100% | 0% | 23475 | 0 | 23475
586 | 596 | 301 | 284 | 06470402075 | Paint Building Exterior - McCamey Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 21364 | 2016-10-10 | 100% | 25% | 21364 | 0 | 21364
887 | 895 | 315 | 285 | 08470402378 | Convert Old Propane Gas Heaters In Shop To Natural Gas - Snyder Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 5700 | 2016-11-23 | 100% | 0% | 5700 | 0 | 5700
1080 | 1088 | 319 | 286 | 05470402571 | New VCT Floor - Littlefield Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 24201 | 2016-10-03 | 100% | 0% | 24201 | 0 | 24201
1090 | 1098 | 339 | 287 | 20470402581 | Interior Lighting - Beaumont Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 23425 | 2016-10-14 | 100% | 0% | 23425 | 0 | 23425
627 | 637 | 980 | 288 | 17470402116 | Restroom Remodels - Buffalo Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 12400 | 2016-10-31 | 100% | 0% | 0 | 0 | 12400
1106 | 1114 | 1323 | 289 | 17470402597 | Restroom Remodels, Training Building - Bryan Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 11850 | 2016-11-18 | 100% | 0% | 11850 | 0 | 11850
587 | 597 | 302 | 290 | 06470402076 | Replace Linolium With Tile In Offices - McCamey Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 13963.75 | 2016-10-06 | 100% | 25% | 13963.75 | 0 | 13963.75
#N/A | #N/A | #N/A | 291 | 12470403033 | Replace 10 Ton HVAC - La Marque Area Engineer & Maintenance | HVAC | Highway Trans. Fund 6 | 0 | 23295 | 2016-09-16 | 100% | 0% | 23295 | 0 | 23295
159 | 101 | 222 | 292 | 04470401641 | Upgrade Generator - Amarillo District Headquarters | Safety/Security | Highway Trans. Fund 6 | 400000 | 825000 | 2017-07-12 | 100% | 0% | 0 | 0 | 825000
787 | 795 | 290 | 293 | 11470402276 | Upgrade Interior Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 23000 | 2016-09-19 | 100% | 0% | 0 | 0 | 23000 | 0
387 | 399 | 322 | 294 | 08470401876 | Replace Water Cut Offs On The Complex For Various Buildings - District Headquarters | Site Work | Highway Trans. Fund 6 | 8500 | 5326.5 | 2016-12-01 | 100% | 0% | 5326.5 | 0 | 5326.5
987 | 995 | 329 | 295 | 11470402478 | Replace Windows - Nacogdoches Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24968 | 2016-10-10 | 100% | 0% | 24968 | 0 | 24968
1101 | 1109 | 330 | 296 | 20470402592 | Replace Carpet And VCT - Liberty Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 23780 | 2016-10-10 | 100% | 0% | 0 | 0 | 23780
983 | 991 | 390 | 297 | 11470402474 | Upgrade Interior Lighting - Livingston Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 23500 | 2016-10-14 | 100% | 25% | 23500 | 0 | 23500
15 | 80 | 260 | 298 | 38470401504 | Demolish Existing Building and Convert To Parking - Camp Hubbard State Headquarters | Site Work | Highway Trans. Fund 6 | 200000 | 175000 | 2017-01-31 | 100% | 0% | 175000 | 0 | 175000 | Testing done on this Proj ID funds moved to 38-3033
#N/A | #N/A | #N/A | 299 | 02470403030 | EMERGENCY -Staircase Replacement (Ft. Worth DHQ Admin Bldg) - Ft. Worth | Capital Repairs | Highway Trans. Fund 6 | 0 | 35000 | 2016-11-30 | 100% | 0% | 0 | 0 | 35000
900 | 908 | 337 | 300 | 25470402391 | Paint Interior & Exterior, Resurface Parking Area - Quanah Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 47113 | 2016-10-19 | 100% | 0% | 47113 | 0 | 47113
544 | 554 | 305 | 301 | 16470402033 | Replace 2 Existing Fuel Dispensers At The Fuel Station - Refugio Co. | Site Work | Highway Trans. Fund 6 | 12000 | 15714.65 | 2016-12-07 | 100% | 0% | 15714.65 | 0 | 15714.65 | Combined Let 2033,2126, 2264
637 | 647 | 323 | 302 | 16470402126 | Replace 2 Existing Fuel Dispensers At The Fuel Station - Goliad Co. | Site Work | Highway Trans. Fund 6 | 12000 | 15714.65 | 2016-12-07 | 100% | 0% | 15714.65 | 0 | 15714.65 | Combined Let 2033,2126, 2264
775 | 783 | 336 | 303 | 16470402264 | Replace 2 Existing Fuel Dispensers At The Fuel Station - Karnes Co. | Site Work | Highway Trans. Fund 6 | 12000 | 15714.65 | 2016-12-07 | 100% | 0% | 15714.65 | 0 | 15714.65 | Combined Let 2033,2126, 2264
#N/A | #N/A | 309 | 304 | 01470402991 | Fuel Canopy - Sulphur Springs | Capital Repairs | Highway Trans. Fund 6 | 0 | 52000 | 2017-01-17 | 100% | 0% | 0 | 0 | 52000 | 0
#N/A | #N/A | 663 | 305 | 08470402681 | Add Canopy To Back Of Welding Shop 45' X 25' Area - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 84997 | 2016-12-05 | 100% | 0% | 84997 | 0 | 84997
853 | 861 | 1150 | 306 | 05470402344 | Replace Steps With ADA Ramp Back Door - District Headquarters-LBB AE's | Capital Repairs | Highway Trans. Fund 6 | 12000 | 24900 | 2016-11-14 | 100% | 0% | 0 | 0 | 24900
845 | 853 | 314 | 307 | 11470402335 | Upgrade Interior Lighting - Lufkin Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 24842 | 2016-10-17 | 100% | 0% | 24842 | 0 | 24842
980 | 988 | 317 | 308 | 11470402471 | Upgrade Interior Lighting - Center Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 21138.23 | 2016-09-14 | 100% | 0% | 21138.23 | 0 | 21138.23
888 | 896 | 1176 | 309 | 08470402379 | Convert The Old Salt Bin Into A Sign And Traffic Control Room Storage - Snyder Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 16824 | 2016-11-01 | 100% | 0% | 16824 | 0 | 16824
993 | 1001 | 395 | 310 | 11470402484 | Replace Windows - San Augustine Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 24325 | 2016-11-18 | 100% | 0% | 24325 | 0 | 24325
361 | 373 | 775 | 311 | 20470401850 | Replace Fuel Dispensers - Anahuac Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 17600 | 2016-11-08 | 100% | 0% | 17600 | 0 | 17600
541 | 551 | 915 | 312 | 11470402030 | Renovate Baydoor Offices - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 24827 | 2016-11-04 | 100% | 0% | 24827 | 0 | 24827
#N/A | #N/A | #N/A | 313 | 16470403037 | New Waterline - Emergency request - Robstown MNT | Safety/Security | Highway Trans. Fund 6 | 0 | 70000 | 2016-12-27 | 100% | 0% | 0 | 0 | 70000
339 | 351 | 293 | 314 | 22470401828 | Parking Lot Lighting - Del Rio Maintenance Office (US 90) | Site Work | Highway Trans. Fund 6 | 35000 | 24895 | 2016-09-30 | 100% | 0% | 24895 | 0 | 24895
#N/A | #N/A | #N/A | 315 | 05470403035 | Replace Carpeting - Lubbock SE Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 18796 | 2016-10-07 | 100% | 0% | 18796 | 0 | 18796
67 | 160 | 146 | 316 | 07470401699 | Modifications/Upgrade HVAC - San Angelo District Headquarters | HVAC | Highway Trans. Fund 6 | 300000 | 150000 | 2016-12-27 | 100% | 0% | 0 | 0 | 150000 | REBID first 2bidders disqual by HUB (6/20/16)San Angelo District Headquarters
49 | 132 | 227 | 317 | 02470401585 | Upgrade Security (C-CURE) - Fort Worth District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 775000 | 2017-05-10 | 100% | 0% | 0 | 0 | 775000
877 | 885 | 294 | 318 | 20470402368 | Install Overhead Doors - Kountze Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 40000 | 2016-11-02 | 100% | 0% | 0 | 0 | 40000
1126 | 1134 | 1340 | 319 | 13470402617 | Repair Sheetrock And Paint Walls - Hallettsville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 8000 | 23400 | 2016-10-07 | 100% | 0% | 23400 | 0 | 23400
833 | 841 | 1137 | 320 | 22470402323 | Retrofit Locker Room Into Storage/Supply Room - Carrizo Springs | Capital Repairs | Highway Trans. Fund 6 | 5000 | 24950 | 2016-11-02 | 100% | 0% | 0 | 0 | 24950
312 | 324 | 223 | 321 | 19470401801 | Replace 2 HVAC Systems - District Headquarters | HVAC | Highway Trans. Fund 6 | 35000 | 90000 | 2016-11-16 | 100% | 0% | 0 | 0 | 90000
583 | 593 | 407 | 322 | 06470402072 | Repaint Exterior - Andrews Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 15000 | 2016-12-08 | 100% | 0% | 0 | 0 | 15000
#N/A | 44 | 18 | 323 | 38470402974 | Paving Overlay Parking Lot - Camp Hubbard State Headquarters | Site Work | Highway Trans. Fund 6 | 0 | 951815 | 2017-05-03 | 100% |  | 0 | 0 | 951815 | Rebid
1161 | 1169 | 246 | 324 | 11470402652 | Renovate Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 23628 | 2016-10-31 | 100% | 0% | 0 | 0 | 23628
752 | 760 | 298 | 325 | 20470402241 | Flag Pole Lights - Districtwide | Capital Repairs | Highway Trans. Fund 6 | 12000 | 19000 | 2016-10-31 | 100% | 0% | 0 | 0 | 19000
621 | 631 | 313 | 326 | 20470402110 | Install Storm Shutters - Anahuac Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 14000 | 23000 | 2016-10-31 | 100% | 0% | 0 | 0 | 23000
143 | 177 | 345 | 327 | 08470401623 | Replace Roof - Big Spring Maintenance Office | Roofing | Highway Trans. Fund 6 | 60000 | 420000 | 2017-04-05 | 100% | 0% | 0 | 0 | 420000
286 | 298 | 357 | 328 | 05470401774 | Replace Roof - Littlefield Maintenance Office | Roofing | Highway Trans. Fund 6 | 45000 | 550000 | 2017-06-02 | 100% | 0% | 0 | 0 | 550000
110 | 165 | 408 | 329 | 10470401576 | Upgrade Security (C-CURE) - Tyler District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 1150000 | 2017-05-10 | 100% | 0% | 0 | 0 | 1150000
572 | 582 | 940 | 330 | 05470402061 | Remove In-Ground Hydraulic Floor Lift - Post Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 3000 | 5937.5 | 2016-10-11 | 100% | 0% | 0 | 0 | 5937.5
721 | 729 | 1050 | 331 | 05470402210 | Remove In-Ground Hydraulic Floor Lift - Bovina Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 3000 | 5937.5 | 2016-10-11 | 100% | 0% | 0 | 0 | 5937.5
728 | 736 | 1054 | 332 | 05470402217 | Remove In-Ground Hydraulic Floor Lift - Ralls Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 3000 | 5937.5 | 2016-10-11 | 100% | 0% | 0 | 0 | 5937.5
778 | 786 | 1094 | 333 | 05470402267 | Remove In-Ground Hydraulic Floor Lift - Plains Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 3000 | 5937.5 | 2016-10-11 | 100% | 0% | 0 | 0 | 5937.5
#N/A | #N/A | #N/A | 334 | 24470403036 | El Paso DHQ C UPS System - El Paso DHQ | Safety/Security | Highway Trans. Fund 6 | 0 | 15000 | 2016-10-31 | 100% | 0% | 0 | 0 | 15000
164 | 170 | 291 | 335 | 16470401648 | Modifications/Upgrade Electrical - Corpus Christi District Headquarters | Safety/Security |  | 250000 | 385000 | 2017-08-31 | 100% |  | 0 | 0 | 385000
818 | 826 | 331 | 336 | 11470402308 | Paint Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 23500 | 2016-11-01 | 100% | 0% | 0 | 0 | 23500
132 | 172 | 350 | 337 | 08470401605 | Replace Roof - Abilene District Headquarters | Roofing | Highway Trans. Fund 6 | 65000 | 425000 | 2017-04-05 | 100% | 0% | 0 | 0 | 425000 | Combined Let 1605,1606,1607
133 | 173 | 351 | 338 | 08470401606 | Replace Roof (Warehouse) - Abilene District Headquarters | Roofing | Highway Trans. Fund 6 | 130000 | 425000 | 2017-04-05 | 100% | 0% | 0 | 0 | 425000 | Combined Let 1605,1606,1607
134 | 174 | 352 | 339 | 08470401607 | Reroof Building Or Repatch In Areas - Abilene District Headquarters | Roofing | Highway Trans. Fund 6 | 10000 | 425000 | 2017-04-05 | 100% | 0% | 0 | 0 | 425000 | Combined Let 1605,1606,1607
124 | 189 | 368 | 340 | 15470401595 | Replace Roof - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 75000 | 198614 | 2017-10-04 | 100% | 0% | 0 | 0 | 198614 | Combined into one State Let for $2.1M
125 | 190 | 369 | 341 | 15470401596 | Replace Roof - San Antonio District Headquarters | Roofing | Highway Trans. Fund 7 | 100000 | 331024 | 2017-10-04 | 100% | 0% | 0 | 0 | 331024 | Combined into one State Let for $2.1M
126 | 191 | 370 | 342 | 15470401597 | Replace Roof - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 100000 | 264819 | 2017-10-04 | 100% | 0% | 0 | 0 | 264819 | Combined into one State Let for $2.1M
127 | 192 | 371 | 343 | 15470401598 | Replace Roof - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 125000 | 331024 | 2017-10-04 | 100% | 0% | 0 | 0 | 331024 | Combined into one State Let for $2.1M
128 | 193 | 372 | 344 | 15470401599 | Replace Roof - Buildings 1, 3 & 4 - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 250000 | 662048 | 2017-10-04 | 100% | 0% | 0 | 0 | 662048 | Combined into one State Let for $2.1M
129 | 194 | 373 | 345 | 15470401600 | Replace Roof - Buildings 8 & 9 - San Antonio District Headquarters | Roofing | Highway Trans. Fund 6 | 150000 | 397228 | 2017-10-04 | 100% | 0% | 0 | 0 | 397228 | Combined into one State Let for $2.1M
854 | 862 | 393 | 346 | 11470402345 | Upgrade Interior Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 23854 | 2016-10-31 | 100% | 0% | 0 | 0 | 23854
882 | 890 | 412 | 347 | 24470402373 | Paint Interior Walls - Terlingua Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 17500 | 17500 | 2016-11-15 | 100% | 0% | 0 | 0 | 17500
561 | 571 | 929 | 348 | 24470402050 | Add Rolling Doors To Existing Storage Bldg. - Fort Hancock Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 6000 | 6000 | 2016-11-08 | 100% | 0% | 0 | 0 | 6000
581 | 591 | 949 | 349 | 11470402070 | Renovate Bathroom - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 23248.91 | 2016-11-18 | 100% | 0% | 0 | 0 | 23248.91
#N/A | #N/A | 405 | 350 | 24470402817 | Add 25' To Roof At Existing Salt / Sand Canopy - El Paso | Site Work | Highway Trans. Fund 6 | 0 | 66900 | 2017-01-17 | 100% | 0% | 0 | 0 | 66900
#N/A | #N/A | 664 | 351 | 18470402685 | Canopy At Mechanic Shop - Waxahachie Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 7 | 0 | 78700 | 2017-01-03 | 100% |  | 0 |  | 78700
#N/A | #N/A | #N/A | 352 | 06470403038 | New Generator - Odessa | Safety/Security | Highway Trans. Fund 6 | 0 | 300000 | 2017-04-26 | 0% | 0% | 0 | 0 | 300000
307 | 319 | 256 | 353 | 10470401796 | Upgrade HVAC In Maint &Area Office - South Tyler Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 150000 | 150000 | 2016-11-30 | 0% | 0% | 0 | 0 | 150000
56 | 158 | 262 | 354 | 13470401661 | Convert Flat Roof To Gable Style - Port Lavaca MNT - Calhoun Cty Maint. | Roofing | Highway Trans. Fund 6 | 250000 | 250000 | 2017-02-28 | 0% | 0% | 0 | 0 | 250000
3 | 198 | 341 | 355 | 01470401490 | Replace Roof And Walls - Paris District Headquarters | Roofing | Highway Trans. Fund 6 | 50000 | 50000 | 2017-01-31 | 0% | 0% | 0 | 0 | 50000
69 | 120 | 342 | 356 | 15470401701 | Replace Roof - Pearsall Maintenance Office | Roofing | Highway Trans. Fund 6 | 65000 | 65000 | 2017-03-28 | 0% | 0% | 0 | 0 | 65000
140 | 176 | 344 | 357 | 15470401617 | Replace Roof - Seguin Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 100000 | 100000 | 2017-03-28 | 0% | 0% | 0 | 0 | 100000
281 | 293 | 356 | 358 | 05470401769 | Replace Roof - District Headquarters | Roofing | Highway Trans. Fund 6 | 40000 | 40000 | 2017-04-11 | 0% | 0% | 0 | 0 | 40000
108 | 195 | 365 | 359 | 10470401574 | Replace Roof (Goat shed) - Tyler District Headquarters | Roofing | Highway Trans. Fund 6 | 100000 | 100000 | 2017-05-23 | 0% | 0% | 0 | 0 | 100000
256 | 268 | 399 | 360 | 13470401744 | Roof Replacement - Gonzales Maintenance Office | Roofing | Highway Trans. Fund 6 | 200000 | 200000 | 2017-04-11 | 0% | 0% | 0 | 0 | 200000
267 | 279 | 400 | 361 | 12470401755 | Replace Roof - Houston South Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 45000 | 45000 | 2017-04-11 | 0% | 0% | 0 | 0 | 45000
139 | 175 | 403 | 362 | 12470401620 | Replace Roof - Humble Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 87000 | 87000 | 2017-02-28 | 0% | 0% | 0 | 0 | 87000
174 | 155 | 409 | 363 | 21470401660 | Upgrade Security (C-CURE) - Pharr District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000 | 2017-02-14 | 0% | 0% | 0 | 0 | 350000
#N/A | #N/A | 665 | 364 | 08470402690 | Build Canopy Over The Back Door Of Building. - Sweetwater Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 25000 | 2017-01-03 | 0% | 0% | 0 | 0 | 25000
315 | 327 | 749 | 365 | 18470401804 | Fire/Sprinkler Upgrade (Obsolete Panels) - Corsicana Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 25000 | 25000 | 2016-12-28 | 0% | 0% | 0 | 0 | 25000
#N/A | #N/A | #N/A | 366 | 15470403028 | Replace Roof in Kerrville - San Antonio | Roofing | Highway Trans. Fund 6 | 0 | 120000 | 2017-03-28 | 0% | 0% | 0 | 0 | 120000
#N/A | #N/A | #N/A | 367 | 12470402639 | Install Safety Flooring - District Headquarters | Capital Repairs | TXDOT Funding not allocated | 45000 | 45000 | 2017-01-10 | 0% |  | 0 | 0 | 45000
293 | 305 | 741 | 368 | 18470401782 | Fire/Sprinkler Upgrade (Obsolete Panels) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 25000 | 25000 | 2016-12-14 | 0% | 0% | 0 | 0 | 25000
817 | 825 | 63 | 369 | 11470402307 | Foundation Repairs - to be resubmitted - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000 | 2016-12-06 | 0% | 0% | 0 | 0 | 40000
1129 | 1137 | 215 | 370 | 17470402620 | Enclose Two Bays Of Equipment Shed - Brenham Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000 | 2016-12-27 | 0% | 0% | 0 | 0 | 10000
5 | 167 | 259 | 371 | 22470401492 | Replace Generators (x2) - Del Rio Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 50000 | 50000 | 2017-01-03 | 0% | 0% | 0 | 0 | 50000
160 | 179 | 398 | 372 | 19470401643 | Building 300 Storage Needs Replace Roof - Atlanta District Headquarters | Roofing | Highway Trans. Fund 6 | 200000 | 200000 | 2017-05-23 | 0% | 0% | 0 | 0 | 200000
269 | 281 | 401 | 373 | 12470401757 | Replace Roof - Rosenberg Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 10000 | 10000 | 2017-05-09 | 0% | 0% | 0 | 0 | 10000
322 | 334 | 402 | 374 | 18470401811 | Roof - Coating Metal Roof Over Storage/Salt Shed - Ennis Maintenance Office | Roofing | Highway Trans. Fund 6 | 40000 | 40000 | 2017-04-11 | 0% | 0% | 0 | 0 | 40000
1089 | 1097 | 655 | 375 | 38470402580 | Repair Drainage Issues Around Hangars Water Run Off Going Inside. - TxDOT Flight Services | Capital Repairs | Highway Trans. Fund 6 | 60000 | 125000 | 2017-01-24 | 0% | 0% | 0 | 0 | 125000
#N/A | 85 | 657 | 376 | 08470402983 | Baird MNT slab repair - Baird | Capital Repairs | Highway Trans. Fund 6 | 0 | 50000 | 2017-02-28 | 0% | 0% | 0 | 0 | 50000
#N/A | #N/A | #N/A | 377 | 16470403034 | Water Well - Alice Maintenance | Capital Repairs | Highway Trans. Fund 6 | 0 | 35000 | 2016-11-16 | 0% | 0% | 0 | 0 | 35000
871 | 879 | 186 | 378 | 04470402362 | Install Overhead Doors And Openers - Canadian Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000 | 2016-11-03 | 0% | 0% | 0 | 0 | 25000
300 | 312 | 332 | 379 | 24470401789 | Upgrade Evaporative AC Unit In The Shop. Add Heaters And Double Door. - El Paso (East) Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 35000 | 35000 | 2016-11-15 | 0% | 0% | 0 | 0 | 35000
649 | 659 | 335 | 380 | 25470402138 | Replace Floor Tiles - Munday Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 9500 | 9500 | 2016-10-27 | 0% | 0% | 0 | 0 | 9500
659 | 669 | 362 | 381 | 06470402148 | Paint Exterior Walls & Re-Insulate Weldging Shop - Kermit Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000 | 2017-01-23 | 0% | 0% | 0 | 0 | 20000
811 | 819 | 647 | 382 | 24470402301 | Install Bird Screens @ Truck Bays - Dell City Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5500 | 5500 | 2016-12-15 | 0% | 0% | 0 | 0 | 5500
1093 | 1101 | 1318 | 383 | 18470402584 | Flooring Replaced - Remove VCT And Replace With VCT - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-10 | 0% | 0% | 0 | 0 | 10000
#N/A | 100 | 93 | 384 | 19470402979 | Escalated $30K from Restroom Upgrades in Proj #19470402619 - Riverside | Capital Repairs | Highway Trans. Fund 6 | 0 | 30000 | 2017-03-14 | 0% | 0% | 0 | 0 | 30000 | Phase 1 of Project ID: 19470402619
1072 | 1080 | 244 | 385 | 17470402563 | Install Welding Ventilation Hood - Hearne Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 7500 | 7500 | 2017-01-04 | 0% | 0% | 0 | 0 | 7500
#N/A | #N/A | 268 | 386 | 11470402989 | SFMO Fire Wall - Livingston Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 50000 | 2017-01-10 | 0% | 0% | 0 | 0 | 50000
298 | 310 | 347 | 387 | 20470401787 | Rehab Roof With Insulation - Liberty Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 95000 | 95000 | 2016-10-19 | 0% | 0% | 0 | 0 | 95000
#N/A | #N/A | 396 | 388 | 11470402990 | SMFO Fire Exit - Lufkin District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 150000 | 2017-01-10 | 0% | 0% | 0 | 0 | 150000
#N/A | #N/A | #N/A | 389 | 38470403025 | Relace cooling tower and add Isolations valves - State Headquarters | Safety/Security | Highway Trans. Fund 6 | 0 | 225000 | 2017-03-07 | 0% | 0% | 0 | 0 | 225000
#N/A | #N/A | #N/A | 390 | 38470403026 | Relace existing batteries on UPS and install battery monitoring - State Headquarters | Safety/Security | Highway Trans. Fund 6 | 0 | 148235 | 2017-01-24 | 0% | 0% | 0 | 0 | 148235
316 | 328 | 376 | 391 | 18470401805 | Generator Backup Power Completed - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 90000 | 90000 | 2017-03-20 | 0% | 0% | 0 | 0 | 90000
317 | 329 | 386 | 392 | 18470401806 | HVAC Upgrade - Leibert System @ Server Room - District Headquarters | HVAC | Highway Trans. Fund 6 | 45000 | 45000 | 2017-03-20 | 0% | 0% | 0 | 0 | 45000
822 | 830 | 1128 | 393 | 11470402312 | Upgrade Interior Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000 | 2016-12-04 | 0% | 0% | 0 | 0 | 8000
650 | 660 | 271 | 394 | 18470402139 | Paint Exterior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000 | 2016-12-22 | 0% | 0% | 0 | 0 | 20000
1094 | 1102 | 273 | 395 | 18470402585 | Paint Exterior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000 | 2016-12-21 | 0% | 0% | 0 | 0 | 15000
285 | 297 | 275 | 396 | 18470401773 | Install Gate - Electric W/Remote On Ih35 Service Road - Denton Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 20000 | 20000 | 2016-12-22 | 0% | 0% | 0 | 0 | 20000
1146 | 1154 | 296 | 397 | 18470402637 | Floor Tile Removal - Corridors Only (Stain Concrete) - Corsicana Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000 | 2016-12-21 | 0% | 0% | 0 | 0 | 10000
1147 | 1155 | 297 | 398 | 18470402638 | Paint Exterior - Corsicana Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000 | 2016-12-21 | 0% | 0% | 0 | 0 | 10000
1022 | 1030 | 318 | 399 | 18470402513 | Paint Exterior And Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000 | 2016-10-25 | 0% | 0% | 0 | 0 | 10000
1079 | 1087 | 333 | 400 | 18470402570 | Paint Exterior - Denton Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000 | 2016-12-21 | 0% | 0% | 0 | 0 | 10000
310 | 322 | 747 | 401 | 18470401799 | Install Gates - Electric/Key Pad - Cedar Hill Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 20000 | 20000 | 2016-11-24 | 0% | 0% | 0 | 0 | 20000
827 | 835 | 1133 | 402 | 18470402317 | Electrical Panel Upgrades - Rockwall Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000 | 2016-11-10 | 0% | 0% | 0 | 0 | 15000
912 | 920 | 1194 | 403 | 18470402403 | Electrical Panel Upgrades - Hutchins Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000 | 2016-11-10 | 0% | 0% | 0 | 0 | 25000
1020 | 1028 | 1265 | 404 | 18470402511 | Reconfigure To Allow For Drivethrough - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 21500 | 21500 | 2016-11-15 | 0% | 0% | 0 | 0 | 21500
864 | 872 | 325 | 405 | 16470402355 | Replace Flooring At Maintenance - Kingsville MNT - Kingsville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000 | 2016-12-28 | 0% | 0% | 0 | 0 | 20000
958 | 966 | 327 | 406 | 16470402449 | Replace Flooring At Area Engineer And Maintenance - Corpus Christi AEM - Corpus Christi Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000 | 2016-11-25 | 0% | 0% | 0 | 0 | 20000
967 | 975 | 338 | 407 | 16470402458 | Replace Flooring At Area Engineer And Maintenance - Sinton AEM - Sinton Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000 | 2016-11-25 | 0% | 0% | 0 | 0 | 20000
#N/A | #N/A | #N/A | 408 | 05470403039 | Replace carpet - Lubbock | Capital repairs | Highway Trans. Fund 6 | 0 | 14000 | 2016-11-17 | 0% | 0% | 0 | 0 | 14000
359 | 371 | 649 | 409 | 21470401848 | Repave Parking Lot - Zapata Maintenance Office Sub-Section | Site Work | Highway Trans. Fund 6 | 19780 | 19780 | 2016-11-23 | 0% | 0% | 0 | 0 | 19780
1085 | 1093 | 650 | 410 | 21470402576 | Flooring Replacement - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 7000 | 7000 | 2016-11-30 | 0% | 0% | 0 | 0 | 7000
1053 | 1061 | 1291 | 411 | 10470402544 | Reconfigure To Allow For Drivethrough - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 21500 | 21500 | 2016-12-13 | 0% | 0% | 0 | 0 | 21500
709 | 719 | 192 | 412 | 02470402198 | Reconfigure To Allow For Drivethrough - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 21500 | 21500 | 2017-01-31 | 0% | 0% | 0 | 0 | 21500
26 | 81 | 261 | 413 | 09470401518 | Modifications/Upgrade HVAC - Waco District Headquarters | HVAC | Highway Trans. Fund 6 | 300000 | 300000 | 2017-03-28 | 0% | 0% | 0 | 0 | 300000
103 | 153 | 287 | 414 | 05470401568 | Replace Generator - Post RDC | Safety/Security | Highway Trans. Fund 6 | 75000 | 75000 | 2017-03-14 | 0% | 0% | 0 | 0 | 75000
#N/A | #N/A | 308 | 415 | 38470403002 | Install Bird Screens at Hangars 3 and 4 - Approved in Sr. Mgr Mtg 4/5/16 | Site Work | Highway Trans. Fund 6 | 0 | 115000 | 2017-03-28 | 0% | 0% | 0 | 0 | 115000
334 | 346 | 310 | 416 | 01470401823 | Resurface Parking Lot - District Headquarters | Site Work | Highway Trans. Fund 6 | 164000 | 164000 | 2017-04-11 | 0% | 0% | 0 | 0 | 164000
299 | 311 | 348 | 417 | 24470401788 | Install/Repair Roof - El Paso (East) Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 100000 | 100000 | 2017-05-03 | 0% | 0% | 0 | 0 | 100000
355 | 367 | 359 | 418 | 23470401844 | Demolish Old Structures On Adjacent Site - Breckenridge Maintenance Office | Site Work | Highway Trans. Fund 6 | 39500 | 39500 | 2017-02-21 | 0% | 0% | 0 | 0 | 39500
514 | 524 | 380 | 419 | 09470402003 | Site Drainage Improvements - Waco Area Engineer & Maintenance Office - Bagby | Site Work | Highway Trans. Fund 6 | 25200 | 25200 | 2018-03-22 | 0% | 0% | 0 | 0 | 25200
381 | 393 | 790 | 420 | 05470401870 | Site Work And Concrete Flume - Post RDC | Site Work | Highway Trans. Fund 6 | 50000 | 50000 | 2017-01-31 | 0% | 0% | 0 | 0 | 50000
677 | 687 | 1014 | 421 | 38470402166 | Replace Data Closet AC - Camp Hubbard State Headquarters | Capital Repairs | Highway Trans. Fund 6 | 6000 | 6000 | 2017-01-13 | 0% | 0% | 0 | 0 | 6000
198 | 157 | 229 | 422 | 23470402339 | Renovate Existing Facilities. | Capital Construction | Highway Trans. Fund 6 | 6000000 | 6350000 | 2018-01-24 | 0% | 0% | 0 | 0 | 6350000 | Ccure project 23470401667 cancelled and combined with this project. 04/14/16 - Brownwood District Headquarters
E5 | 84 | 387 | 423 | 10470402976 | Fire supression system water line - Athens Regional Distribution Center | Site Work | Highway Trans. Fund 6 | 0 | 200000 | 2017-06-07 | 0% | 0% | 0 | 0 | 200000
191 | 164 | 265 | 424 | 21470401683 | Replace Roof - Pharr District Headquarters | Roofing | Highway Trans. Fund 6 | 250000 | 250000 | 2017-04-04 | 0% | 0% | 0 | 0 | 250000
78 | 114 | 304 | 425 | 21470401713 | Replace Roof - Mission Maintenance Office | Roofing | Highway Trans. Fund 6 | 300000 | 300000 | 2017-04-04 | 0% | 0% | 0 | 0 | 300000
263 | 275 | 355 | 426 | 22470401751 | Roof Repairs - Cotulla Maintenance Office | Roofing | Highway Trans. Fund 6 | 50000 | 50000 | 2017-03-28 | 0% | 0% | 0 | 0 | 50000
289 | 301 | 358 | 427 | 21470401778 | Replace Roof - San Benito Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 300000 | 300000 | 2017-03-28 | 0% | 0% | 0 | 0 | 300000
688 | 698 | 651 | 428 | 24470402177 | Insulate Interior Of Stock Room / Storage - Fort Davis Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 22500 | 22500 | 2017-01-02 | 0% | 0% | 0 | 0 | 22500
380 | 392 | 235 | 429 | 05470401869 | Nw Side Of Long Building Dirt Work To Shed Water - Post RDC | Site Work | Highway Trans. Fund 6 | 10000 | 10000 | 2017-02-13 | 0% | 0% | 0 | 0 | 10000
109 | 161 | 264 | 430 | 10470401575 | Replace Roof At North Tyler Fuel Station - North Tyler Maintenance Office | Roofing | Highway Trans. Fund 6 | 85000 | 85000 | 2017-04-25 | 0% | 0% | 0 | 0 | 85000
141 | 196 | 374 | 431 | 10470401621 | Replace Roof On Old Lab - Tyler District Headquarters | Roofing | Highway Trans. Fund 6 | 200000 | 200000 | 2017-08-15 | 0% | 0% | 0 | 0 | 200000
135 | 63 | 228 | 432 | 14470401610 | Replace Generator - Austin District Headquarters | Safety/Security | Highway Trans. Fund 6 | 250000 | 250000 | 2017-05-31 | 0% | 0% | 0 | 0 | 250000
#N/A | 205 | 286 | 433 | 24470402992 | El Paso Generator Replacement - El Paso District Headquarters | Safety/Security | Highway Trans. Fund 6 | 0 | 115000 | 2017-04-26 | 0% | 0% | 0 | 0 | 115000
287 | 299 | 346 | 434 | 21470401776 | HVAC Upgrade In HQ Bldg. - District Headquarters | HVAC | Highway Trans. Fund 6 | 300000 | 300000 | 2017-05-03 | 0% | 0% | 0 | 0 | 300000
81 | 125 | 363 | 435 | 38470401720 | Replacement of R22 to 410 HVAC System - Riverside Annex II RA150-200 | HVAC | Highway Trans. Fund 6 | 200000 | 200000 | 2017-04-26 | 0% | 0% | 0 | 0 | 200000
326 | 338 | 378 | 436 | 38470401815 | Replacement of R22 to 410 HVAC System - Riverside Annex I RA118 | HVAC | Highway Trans. Fund 6 | 200000 | 200000 | 2017-06-07 | 0% | 0% | 0 | 0 | 200000
329 | 341 | 379 | 437 | 38470401818 | Replacement of R22 to 410 HVAC System - Riverside Annex II RA150-200 | HVAC | Highway Trans. Fund 6 | 360000 | 500000 | 2017-06-07 | 0% | 0% | 0 | 0 | 500000 | (increase est to $500K per WR 8-15-16)
328 | 340 | 404 | 438 | 38470401817 | Replace Roof - Riverside Annex II RA150-200 | Roofing | Highway Trans. Fund 6 | 450000 | 450000 | 2017-03-29 | 0% | 0% | 0 | 0 | 450000
8 | 150 | 410 | 439 | 11470401495 | Upgrade Security (C-CURE) - Lufkin District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000 | 2017-04-26 | 0% | 0% | 0 | 0 | 350000
175 | 166 | 645 | 440 | 13470401662 | Upgrade Security (C-CURE) - Yoakum District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000 | 2017-06-07 | 0% | 0% | 0 | 0 | 350000
155 | 62 | 646 | 441 | 20470401636 | Upgrade Security (C-CURE) - Beaumont District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000 | 2017-03-22 | 0% | 0% | 0 | 0 | 350000
#N/A | #N/A | #N/A | 442 | 38470403008 | Cedar Park Generator & Electrical Upgrades - Cedar Park | Safety/Security | Highway Trans. Fund 6 | 0 | 505000 | 2017-06-15 | 0% | 0% | 0 | 0 | 505000
704 | 714 | 224 | 443 | 08470402193 | Add Wall, Lighting, And Ventilation - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 7000 | 7000 | 2017-02-10 | 0% | 0% | 0 | 0 | 7000
#N/A | 211 | 340 | 444 | 09470402991 | SMFO Fire Exit - Waco District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 0 | 125000 | 2017-03-30 | 0% | 0% | 0 | 0 | 125000
#N/A | 201 | 648 | 445 | 38470402977 | ADA entrances and driveway - Riverside | Safety/Security | Highway Trans. Fund 6 | 0 | 90000 | 2017-04-19 | 0% | 0% | 0 | 0 | 90000
116 | 188 | 366 | 446 | 02470401583 | Replace Roof (3 Buildings) - Fort Worth District Headquarters | Roofing | Highway Trans. Fund 6 | 492000 | 492000 | 2017-08-03 | 0% | 0% | 0 | 0 | 492000
117 | 180 | 367 | 447 | 02470401584 | Roof Replacement and Interior upgrade. Increase approved to include Modular Furniture - Fort Worth District Headquarters | Roofing | Highway Trans. Fund 6 | 480000 | 980000 | 2017-08-03 | 0% | 0% | 0 | 0 | 980000
335 | 347 | 311 | 448 | 21470401824 | Reconfigure Parking Lot - Pharr Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 41000 | 41000 | 2017-05-31 | 0% | 0% | 0 | 0 | 41000
1111 | 1119 | 406 | 449 | 24470402602 | Install Truck Lift - El Paso (West) Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12500 | 12500 | 2016-12-13 | 0% | 0% | 0 | 0 | 12500
904 | 912 | 1187 | 450 | 06470402395 | Enclose 3 Bays With Insulated Overhead Doors To Secure Equipment & Weather Protection - Iraan Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000 | 2016-12-08 | 0% | 0% | 0 | 0 | 20000
59 | 54 | 413 | 451 | 38470401689 | Modifications/Upgrade HVAC. Increase approved Consultant expenses much higher than anticipated. - Camp Hubbard State Headquarters | HVAC | Highway Trans. Fund 6 | 287500 | 3000000 | 2017-12-28 | 0% | 0% | 0 | 0 | 3000000
197 | 197 | 411 | 452 | 18470402299 | Remodel The District Main Office (increase est to $8M per WR 8-15-16) - Dallas District Headquarters | Capital Construction | Highway Trans. Fund 6 | 5653246 | 8000000 | 2018-09-28 | 0% | 0% | 0 | 0 | 8000000
|  |  | 453 | 38470402678-dm | Site Work and unplanned projects | Site Work | Highway Trans. Fund 6 |  | 4239292 | 2017-04-04 | 0% | 0% | 0 | 0 | 4239292
PROJECTS LISTED ABOVE CURRENTLY FUNDED $62.4 | [7 empty] | 39445926 | 62400000.32 |  |  |  | 18103047.41 | 2247514.28 | 60152486.04
PROJECTS LISTED BELOW WAITING FOR TXDOT FUNDING ALLOCATION
29 | 59 | 180 | 454 | 08470401527 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
173 | 57 | 181 | 455 | 11470401659 | Replace HVAC Controls - Lufkin District Headquarters | HVAC | Highway Trans. Fund 6 | 30000 | 30000
772 | 780 | 182 | 456 | 16470402261 | Replace Overhead Gas Heaters In Auto Shop - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 24000 | 24000
264 | 276 | 196 | 457 | 22470401752 | Upgrade Propane Generator - Cotulla Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 25000 | 25000
183 | 152 | 208 | 458 | 04470401672 | Install Rooftop HVAC To Heat And Cool Shop - Amarillo District Headquarters | HVAC | Highway Trans. Fund 6 | 50000 | 50000
319 | 331 | 276 | 459 | 12470401808 | Upgrade Site Lighting - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 100000 | 100000
#N/A | #N/A | 307 | 460 | 38470403000 | Retrofit Hangar 2 for Additional Maintenance Hangar/New Emergency Generator | Site Work | Highway Trans. Fund 6 | 0 | 990000
261 | 273 | 354 | 461 | 22470401749 | Replace Roof - Del Rio Maintenance Office | Roofing | Highway Trans. Fund 6 | 50000 | 50000
98 | 169 | 364 | 462 | 15470401739 | Modifications/Upgrade HVAC - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 150000 | 150000
253 | 265 | 375 | 463 | 15470401741 | Replace All VAV and Upgrade To Electrical Control - District Headquarters | HVAC | Highway Trans. Fund 6 | 85000 | 85000
324 | 336 | 377 | 464 | 15470401813 | Replace 3 Each 20 Ton Chillers For Backup - District Headquarters | HVAC | Highway Trans. Fund 6 | 125000 | 125000
119 | 181 | 381 | 465 | 15470401590 | Install All New Hot And Chill Water Valves And Connect To New Control System - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 150000 | 150000
120 | 109 | 382 | 466 | 15470401591 | New Boiler - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 20000 | 20000
122 | 183 | 383 | 467 | 15470401593 | Replace 60 Ton Chiller - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 150000 | 150000
123 | 184 | 384 | 468 | 15470401594 | Replace All VAV and Upgrade To Electrical Control - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 100000 | 100000
279 | 291 | 385 | 469 | 15470401767 | Replace 2 - 75 Ton Chillers And Add Chiller For (Backup) - San Antonio Transguide | HVAC | Highway Trans. Fund 6 | 150000 | 150000
301 | 313 | 652 | 470 | 24470401790 | Upgrade Front/Rear Entrance Gates - El Paso (East) Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 75000 | 75000
302 | 314 | 653 | 471 | 24470401791 | Secure The Lobby Area - El Paso (West) Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 125000 | 125000
121 | 182 | 654 | 472 | 15470401592 | New HVAC In Shop Restrooms - San Antonio District Headquarters | HVAC | Highway Trans. Fund 6 | 20000 | 20000
47 | 134 | 656 | 473 | 21470401559 | Upgrade Lighting And Gates - Hebbronville Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 0 | 336000
#N/A | #N/A | 666 | 474 | 11470402692 | Fuel Canopy - Standalone per Byron Hicks 6/3/16 - Center Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 21000
#N/A | #N/A | 667 | 475 | 24470402703 | Install Canopy At Truck Wash Pit Standalone per Byron Hicks 6/3/16 - Marfa Sub-Section | Site Work | Highway Trans. Fund 6 | 0 | 21500
#N/A | #N/A | 668 | 476 | 24470402704 | Install A Canopy Over Existing Truck Wash Standalone per Byron Hicks 6/3/16 - Presidio Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 21500
#N/A | #N/A | 669 | 477 | 24470402705 | Install A Canopy Over Existing Truck Wash Standalone per Byron Hicks 6/3/16 - Terlingua Sub-Section | Site Work | Highway Trans. Fund 6 | 0 | 21500
#N/A | #N/A | 670 | 478 | 24470402706 | Install Canopy Over Existing Truck Wash Pit Standalone per Byron Hicks 6/3/16 - Van Horn Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 11500
#N/A | #N/A | 671 | 479 | 11470402711 | Fuel Canopy Standalone per Byron Hicks 6/3/16 - Shepherd Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 21000
199 | 213 | 673 | 480 | 24470401509 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1008000 | 1008000
200 | 214 | 674 | 481 | 07470401516 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1008000 | 1008000
201 | 215 | 675 | 482 | 07470401520 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 224000 | 224000
202 | 216 | 676 | 483 | 25470401521 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 224000 | 224000
204 | 218 | 677 | 484 | 05470401523 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1680000 | 1680000
205 | 219 | 678 | 485 | 06470401524 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1120000 | 1120000
206 | 220 | 679 | 486 | 08470401528 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1120000 | 1120000
207 | 221 | 680 | 487 | 04470401529 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1680000 | 1680000
208 | 222 | 681 | 488 | 17470401531 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
209 | 223 | 682 | 489 | 16470401534 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 896000 | 350000
210 | 224 | 683 | 490 | 11470401537 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 784000 | 784000
211 | 225 | 684 | 491 | 02470401548 | Upgrade Security (C-CURE) Phase I above the line w JOC 211A - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 305000 | [6 empty] | Split off for phases of this project above.
212 | 226 | 685 | 492 | 15470401550 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1008000 | 350000
213 | 227 | 686 | 493 | 18470401551 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
214 | 228 | 687 | 494 | 05470401552 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
215 | 229 | 688 | 495 | 01470401556 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
216 | 230 | 689 | 496 | 01470401557 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 672000 | 672000
203 | 217 | 690 | 497 | 25470401522 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1120000 | 1120000
218 | 232 | 691 | 498 | 15470401560 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 536000
219 | 233 | 692 | 499 | 10470401561 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 560000
220 | 234 | 693 | 500 | 10470401562 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
221 | 235 | 694 | 501 | 09470401563 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
222 | 236 | 695 | 502 | 03470401564 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
223 | 237 | 696 | 503 | 03470401565 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 784000 | 784000
224 | 238 | 697 | 504 | 13470401566 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1008000 | 1008000
225 | 239 | 698 | 505 | 21470401569 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 1008000 | 1008000
226 | 240 | 699 | 506 | 22470401586 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 560000
227 | 241 | 700 | 507 | 09470401603 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
228 | 242 | 701 | 508 | 19470401608 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
229 | 243 | 702 | 509 | 19470401609 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 672000 | 672000
217 | 231 | 703 | 510 | 21470401558 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
231 | 244 | 704 | 511 | 06470401614 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
233 | 245 | 705 | 512 | 13470401618 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
234 | 246 | 706 | 513 | 13470401622 | Repair Leaking Metal Roofs - Austin Cty Maint. | Roofing | Highway Trans. Fund 6 | 50000 | 50000
235 | 247 | 707 | 514 | 04470401624 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
236 | 248 | 708 | 515 | 23470401637 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 784000 | 784000
237 | 249 | 709 | 516 | 17470401647 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 784000 | 784000
238 | 250 | 710 | 517 | 20470401666 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
239 | 251 | 711 | 518 | 18470401668 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 560000
240 | 252 | 712 | 519 | 02470401678 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 672000 | 672000
241 | 253 | 713 | 520 | 12470401679 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 784000 | 784000
242 | 254 | 714 | 521 | 11470401681 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
243 | 255 | 715 | 522 | 20470401706 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 672000 | 672000
244 | 256 | 716 | 523 | 23470401707 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 224000 | 224000
245 | 257 | 717 | 524 | 06470401709 | Install Motion Sensors On Install Automatic Gate - Iraan Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 1500 | 1500
246 | 258 | 718 | 525 | 12470401714 | Upgrade Security (C-CURE) - Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 560000
247 | 259 | 719 | 526 | 24470401715 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
248 | 260 | 720 | 527 | 22470401716 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 336000 | 336000
249 | 261 | 721 | 528 | 06470401717 | Install Motion Sensors On Install Automatic Gate - Balmorhea Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 1500 | 1500
250 | 262 | 722 | 529 | 14470401727 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 560000 | 560000
251 | 263 | 723 | 530 | 16470401732 | Upgrade Security (C-CURE) - Area Engineer and Maintenance Offices | Safety/Security | Highway Trans. Fund 6 | 448000 | 448000
252 | 264 | 724 | 531 | 15470401740 | New Boiler - District Headquarters | HVAC | Highway Trans. Fund 6 | 20000 | 20000
254 | 266 | 725 | 532 | 10470401742 | Site Improvements - Jacksonville Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 12000 | 12000
255 | 267 | 726 | 533 | 13470401743 | Convert Flat Roof To Gable Style - Gonzales Cty Maint. | Roofing | Highway Trans. Fund 6 | 250000 | 250000
262 | 274 | 728 | 534 | 22470401750 | Upgrade HVAC - Del Rio Maintenance Office (US 90) | HVAC | Highway Trans. Fund 6 | 10000 | 10000
268 | 280 | 729 | 535 | 12470401756 | Replace Roof - Humble Area Engineer & Maintenance Office | Roofing | Highway Trans. Fund 6 | 87000 | 87000
270 | 282 | 730 | 536 | 22470401758 | New HVAC In Shop Restrooms - District Headquarters | HVAC | Highway Trans. Fund 6 | 20000 | 20000
271 | 283 | 731 | 537 | 22470401759 | Replace Roof - District Headquarters | Roofing | Highway Trans. Fund 6 | 225000 | 225000
272 | 284 | 732 | 538 | 22470401760 | Upgrade Security (C-CURE) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000
273 | 285 | 733 | 539 | 22470401761 | Exterior Lighting - Laredo Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 40000 | 40000
275 | 287 | 734 | 540 | 22470401763 | Restrooms HVAC - Laredo Auto Shop | HVAC | Highway Trans. Fund 6 | 20000 | 20000
276 | 288 | 735 | 541 | 22470401764 | Repair MNT To Auto Shop Roof - Laredo District Headquarters | Roofing | Highway Trans. Fund 6 | 250000 | 250000
280 | 292 | 737 | 542 | 24470401768 | Upgrade Security (C-CURE) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000
282 | 294 | 738 | 543 | 15470401770 | HVAC Upgrade- I had below line but SS was accepted? - Bexar Metro Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 15000 | 15000
290 | 302 | 739 | 544 | 20470401779 | Install Card Reader Access - Beaumont Area Engineer & Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 16000 | 16000
291 | 303 | 740 | 545 | 25470401780 | Upgrade Security (C-CURE) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000
294 | 306 | 742 | 546 | 13470401783 | Upgrade Apu To Supply Entire Maintenace Building - Fayette Cty Maint. | Safety/Security | Highway Trans. Fund 6 | 125000 | 125000
295 | 307 | 743 | 547 | 20470401784 | A/C Unit Replacement - Liberty Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 7500 | 7500
296 | 308 | 744 | 548 | 20470401785 | A/C Unit Replacement - Liberty Area Engineer & Maintenance Office | HVAC | Highway Trans. Fund 6 | 18000 | 18000
304 | 316 | 745 | 549 | 22470401793 | HVAC Replacement - Freer | HVAC | Highway Trans. Fund 6 | 17000 | 17000
314 | 326 | 748 | 550 | 22470401803 | Install Gate Operator And Key Pad - La Pryor on HWY 57 | Safety/Security | Highway Trans. Fund 6 | 5000 | 5000
318 | 330 | 750 | 551 | 12470401807 | Install CCTV Security Camera (Parking Garage) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 20000 | 20000
320 | 332 | 751 | 552 | 12470401809 | Upgrade Security (C-CURE) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000
321 | 333 | 752 | 553 | 16470401810 | Replace Roof On The Maintenance Building - Aransas Co. | Roofing | Highway Trans. Fund 6 | 250000 | 250000
327 | 339 | 754 | 554 | 38470401816 | Install Redundant UPS for Data Center - Riverside Annex II RA150-200 | Safety/Security | Highway Trans. Fund 6 | 250000 | 250000
330 | 342 | 755 | 555 | 38470401819 | Roof and Weatherize Exterior - Riverside Annex II RA150-200 | Roofing | Highway Trans. Fund 6 | 350000 | 350000
332 | 344 | 756 | 556 | 21470401821 | Add Exit Only Gate To East Side - Edcouch Maintenance Office | Safety/Security | Highway Trans. Fund 6 | 16000 | 16000
333 | 345 | 757 | 557 | 17470401822 | Upgrade Security (C-CURE) - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000
336 | 348 | 758 | 558 | 21470401825 | Rework Concrete Drainage Structure - Pharr Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 11000 | 11000
337 | 349 | 759 | 559 | 22470401826 | Sprinkler System Repair & Upgrade - Del Rio | Site Work | Highway Trans. Fund 6 | 20000 | 20000
338 | 350 | 760 | 560 | 22470401827 | Furnish/Install Bollard - Del Rio Maintenance Office | Site Work | Highway Trans. Fund 6 | 5000 | 5000
342 | 354 | 761 | 561 | 07470401831 | Install New 10,000 Gallon Brine Storge Tank - Eden Maintenance Office | Site Work | Highway Trans. Fund 6 | 6000 | 6000
343 | 355 | 762 | 562 | 07470401832 | Pavement Seal Coat And Restripe - Eden Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
346 | 358 | 765 | 563 | 24470401835 | Install Back Rockwall - Fort Hancock Sub-Section | Site Work | Highway Trans. Fund 6 | 18000 | 18000
348 | 360 | 767 | 564 | 07470401837 | Pavement Seal Coat And Restripe - Leakey Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
352 | 364 | 770 | 565 | 07470401841 | Pavement Seal Coat And Restripe - Ballinger Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
356 | 368 | 772 | 566 | 16470401845 | Add Additional Lateral Lines To Septic System At The Alice Ae Office - Jim Wells Co. | Site Work | Highway Trans. Fund 6 | 15000 | 15000
357 | 369 | 773 | 567 | 18470401846 | Asphalt Overlay Parking Lot - Ennis Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
360 | 372 | 774 | 568 | 20470401849 | Rehab Parking Lot And Drainage - Anahuac Maintenance Office | Site Work | Highway Trans. Fund 6 | 30000 | 30000
363 | 375 | 776 | 569 | 20470401852 | Remove Out Of Service Emulsion, Linseed Oil & Asts - Newton Maintenance Office | Site Work | Highway Trans. Fund 6 | 55000 | 55000
364 | 376 | 777 | 570 | 20470401853 | Electric Service To Yard - Stowel Maintenance Office | Site Work | Highway Trans. Fund 6 | 4000 | 4000
366 | 378 | 778 | 571 | 18470401855 | Site Improvements - District Headquarters | Site Work | Highway Trans. Fund 6 | 207000 | 207000
367 | 379 | 779 | 572 | 18470401856 | Asphalt Overlay Parking Lot - District Headquarters | Site Work | Highway Trans. Fund 6 | 75000 | 75000
369 | 381 | 780 | 573 | 22470401858 | Fuel Pump Replacements - Brackettville | Site Work | Highway Trans. Fund 6 | 15000 | 15000
370 | 382 | 781 | 574 | 22470401859 | Landscaping & Irrigation - Brackettville | Site Work | Highway Trans. Fund 6 | 45000 | 45000
371 | 383 | 782 | 575 | 07470401860 | Overlay And Restripe Parking Lot - San Angelo Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
372 | 384 | 783 | 576 | 07470401861 | Install New Automated Vehicle Entry Gate - San Angelo Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
373 | 385 | 784 | 577 | 07470401862 | Pavement Seal Coat and Restripe - San Angelo Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
374 | 386 | 785 | 578 | 07470401863 | Replace Underground Fuel Tanks With New Above Ground Tanks - San Angelo Maintenance Office | Site Work | Highway Trans. Fund 6 | 75000 | 75000
376 | 388 | 786 | 579 | 07470401865 | Pavement Seal Coat And Restripe - Sterling City Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
377 | 389 | 787 | 580 | 07470401866 | Replace Automated Swing Gate With Automated Sliding Gate - Sterling City Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
379 | 391 | 789 | 581 | 25470401868 | Resurface Parking Lot - Munday Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
382 | 394 | 791 | 582 | 21470401871 | New Fire Proof Overhead Doors - Raymondville Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
383 | 395 | 792 | 583 | 21470401872 | Resurface Maintenance Yard - Raymondville Maintenance Office | Site Work | Highway Trans. Fund 6 | 134800 | 134800
384 | 396 | 793 | 584 | 10470401873 | Modifications/Upgrade Site - District Headquarters | Site Work | Highway Trans. Fund 6 | 110000 | 110000
385 | 397 | 794 | 585 | 08470401874 | Parking Lot Reconfiguration - District Headquarters | Site Work | Highway Trans. Fund 6 | 150000 | 150000
388 | 400 | 795 | 586 | 24470401877 | Demolish Old Emulsion Tank - Fort Davis Maintenance Office | Site Work | Highway Trans. Fund 6 | 8500 | 8500
389 | 401 | 796 | 587 | 24470401878 | Install Sprinkler System - Fort Davis Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
390 | 402 | 797 | 588 | 02470401879 | Site Improvements - District Headquarters | Site Work | Highway Trans. Fund 6 | 303000 | 303000
391 | 403 | 798 | 589 | 06470401880 | Modifications/Upgrade Site - District Headquarters | Site Work | Highway Trans. Fund 6 | 150000 | 150000
392 | 404 | 799 | 590 | 06470401881 | Xeroscape Grounds - District Headquarters | Site Work | Highway Trans. Fund 6 | 264000 | 264000
393 | 405 | 800 | 591 | 06470401882 | Reconfigure Parking In Front Of Office - Odessa Maintenance Office | Site Work | Highway Trans. Fund 6 | 30000 | 30000
396 | 408 | 801 | 592 | 07470401885 | Replace Underground Fuel Tanks With New Above Ground Tanks - Junction Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 75000 | 75000
398 | 410 | 802 | 593 | 07470401887 | Pavement Seal Coat And Restripe - Junction Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
400 | 412 | 804 | 594 | 15470401889 | Change Out Galvanized Water Main Piping - District Headquarters | Site Work | Highway Trans. Fund 6 | 25000 | 25000
401 | 413 | 805 | 595 | 15470401890 | Change Out Galvanized Water Main Piping - District Headquarters | Site Work | Highway Trans. Fund 6 | 25000 | 25000
402 | 414 | 806 | 596 | 15470401891 | Parking Lot Resurfacing & Reconfiguration - District Headquarters | Site Work | Highway Trans. Fund 6 | 200000 | 200000
403 | 415 | 807 | 597 | 06470401892 | Connect to City Sewer Utililty Line - Monahans Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
405 | 417 | 808 | 598 | 15470401894 | Replace Radio Tower - Seguin Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 150000 | 150000
406 | 418 | 809 | 599 | 07470401895 | Pavement Seal Coat And Restripe - Sonora Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
407 | 419 | 810 | 600 | 13470401896 | Install Above Ground Fuel System/New Dispenser - Austin Cty Maint. | Site Work | Highway Trans. Fund 6 | 250000 | 250000
408 | 420 | 811 | 601 | 13470401897 | Install Above Ground Fuel System/New Dispenser - Colorado Cty Maint. | Site Work | Highway Trans. Fund 6 | 250000 | 250000
409 | 421 | 812 | 602 | 20470401898 | Additional Sidewalks - Beaumont Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 15000
410 | 422 | 813 | 603 | 20470401899 | Modifications/Upgrade Site Utilities - District Headquarters | Site Work | Highway Trans. Fund 6 | 101000 | 101000
411 | 423 | 814 | 604 | 20470401900 | Rehab Parking Lot And Stripe - District Headquarters | Site Work | Highway Trans. Fund 6 | 450000 | 450000
414 | 426 | 815 | 605 | 20470401903 | Re-Stripe Parking Lots And Hc Spaces - Districtwide | Site Work | Highway Trans. Fund 6 | 25000 | 25000
415 | 427 | 816 | 606 | 07470401904 | Pavement Seal Coat And Restripe - Rocksprings Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
417 | 429 | 818 | 607 | 03470401906 | Construct In-Ground Storm Shelter - District Headquarters | Site Work | Highway Trans. Fund 6 | 45000 | 45000
418 | 430 | 819 | 608 | 03470401907 | Modifications/Upgrade Site Utilities - District Headquarters | Site Work | Highway Trans. Fund 6 | 200000 | 200000
419 | 431 | 820 | 609 | 03470401908 | Repave Parking Lot - Wichita Falls DHQ - District Headquarters | Site Work | Highway Trans. Fund 6 | 150000 | 150000
420 | 432 | 821 | 610 | 16470401909 | Modifications/Upgrade Site - District Headquarters | Site Work | Highway Trans. Fund 6 | 100000 | 100000
421 | 433 | 822 | 611 | 16470401910 | Modifications/Upgrade Site Utilities - District Headquarters | Site Work | Highway Trans. Fund 6 | 125000 | 125000
422 | 434 | 823 | 612 | 16470401911 | Rehab Existing Parking Lots On Entire Campus - District Headquarters | Site Work | Highway Trans. Fund 6 | 200000 | 200000
423 | 435 | 824 | 613 | 16470401912 | Repair Sidewalk Or Parking Lot - Corpus Christi DHQ - District Headquarters | Site Work | Highway Trans. Fund 6 | 25000 | 25000
425 | 437 | 825 | 614 | 16470401914 | Replace Fuel Dispenser At Maintenance Special Jobs - Corpus Christi DHQ - District Headquarters | Site Work | Highway Trans. Fund 6 | 20000 | 20000
427 | 439 | 826 | 615 | 06470401916 | Paint 10000 Gal Asphalt Tank & Insulate - Crane Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 15000
428 | 440 | 827 | 616 | 21470401917 | Upgrade Landscaping to include Hike And Bike Trail - District Headquarters | Site Work | Highway Trans. Fund 6 | 100000 | 100000
429 | 441 | 828 | 617 | 21470401918 | Increase Parking Area - District Headquarters | Site Work | Highway Trans. Fund 6 | 350000 | 350000
430 | 442 | 829 | 618 | 21470401919 | Parking Lot Improvements - District Headquarters | Site Work | Highway Trans. Fund 6 | 400000 | 400000
432 | 444 | 830 | 619 | 07470401921 | Pavement Seal Coat And Restripe - Ozona Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
434 | 446 | 832 | 620 | 13470401923 | Install Above Ground Fuel System/New Dispenser - District Headquarters | Site Work | Highway Trans. Fund 6 | 250000 | 250000
435 | 447 | 833 | 621 | 13470401924 | Replace Deteriorating Natural Gas Lines And Exterior Valves - District Headquarters | Site Work | Highway Trans. Fund 6 | 40000 | 40000
436 | 448 | 834 | 622 | 20470401925 | Rehab Parking Lot And Stripe - Port Arthur Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 100000 | 100000
437 | 449 | 835 | 623 | 23470401926 | Site Improvements - District Headquarters | Site Work | Highway Trans. Fund 6 | 155000 | 155000
438 | 450 | 836 | 624 | 18470401927 | Asphalt Overlay Parking Lot - Waxahachie Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 40000 | 40000
440 | 452 | 837 | 625 | 18470401929 | Asphalt Emulsion Tank Installation - Rockwall Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
444 | 456 | 839 | 626 | 07470401933 | Pavement Seal Coat And Restripe - District Headquarters | Site Work | Highway Trans. Fund 6 | 30000 | 30000
445 | 457 | 840 | 627 | 07470401934 | Replace Underground Fuel Tanks With New Above Ground Tanks - District Headquarters | Site Work | Highway Trans. Fund 6 | 75000 | 75000
447 | 458 | 841 | 628 | 20470401936 | Rehab Parking Lot And Stripe - Kountze Maintenance Office | Site Work | Highway Trans. Fund 6 | 100000 | 100000
448 | 459 | 842 | 629 | 24470401937 | Resufacing of Parking Lot - Terlingua Sub-Section | Site Work | Highway Trans. Fund 6 | 25000 | 25000
449 | 460 | 843 | 630 | 13470401938 | Build New Berm Around Asphalt Tanks - Wharton Cty Maint. | Site Work | Highway Trans. Fund 6 | 40000 | 40000
452 | 462 | 844 | 631 | 18470401941 | Asphalt Overlay Parking Lot - Hutchins Maintenance Office | Site Work | Highway Trans. Fund 6 | 40000 | 40000
453 | 463 | 845 | 632 | 18470401942 | Parking Lot Striping - Hutchins Maintenance Office | Site Work | Highway Trans. Fund 6 | 10000 | 10000
454 | 464 | 846 | 633 | 18470401943 | Modular Building/Site Prep - NW Dallas Maintenance Office | Site Work | Highway Trans. Fund 6 | 110000 | 110000
455 | 465 | 847 | 634 | 24470401944 | Demolish Old Emulsion Tank - Alpine Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 8400 | 8400
457 | 467 | 848 | 635 | 21470401946 | Fuel Tank Relocation - San Benito Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 125000 | 125000
458 | 468 | 849 | 636 | 21470401947 | Improve Drainage - San Benito Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 150000 | 150000
459 | 469 | 850 | 637 | 21470401948 | Repair Sewer Line At Rear Of Yard, Add Approx. 8 Manholes. - San Benito Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 50000 | 50000
460 | 470 | 851 | 638 | 21470401949 | Resurface Parking Lot - San Benito Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 26200 | 26200
461 | 471 | 852 | 639 | 07470401950 | Pavement Seal Coat And Restripe - Robert Lee Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
464 | 474 | 854 | 640 | 21470401953 | Repair Fuel Dispensing Pumps & Tanks - Laguna Vista Maintenance Office Sub-Section | Site Work | Highway Trans. Fund 6 | 12000 | 12000
465 | 475 | 855 | 641 | 15470401954 | Connect To City Water/Sewer - Bandera Maintenance Office | Site Work | Highway Trans. Fund 6 | 350000 | 350000
466 | 476 | 856 | 642 | 24470401955 | Demolish Old Emulsion Tank - Pine Springs Sub-Section | Site Work | Highway Trans. Fund 6 | 8500 | 8500
469 | 479 | 857 | 643 | 07470401958 | Install New Above Ground Fuel Tanks - Big Lake Maintenance Office | Site Work | Highway Trans. Fund 6 | 50000 | 50000
470 | 480 | 858 | 644 | 07470401959 | Pavement Seal Coat And Restripe - Big Lake Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
472 | 482 | 860 | 645 | 14470401961 | Parking Lot Overlay - Burnet Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 95000 | 95000
473 | 483 | 861 | 646 | 23470401962 | Remove Underground Fuel Tanks And Install Above Ground Tanks - Goldthwaite Maintenance Office | Site Work | Highway Trans. Fund 6 | 75000 | 75000
474 | 484 | 862 | 647 | 07470401963 | Replace Underground Fuel Tanks With New Above Ground Tanks - Menard Maintenance Office | Site Work | Highway Trans. Fund 6 | 75000 | 75000
475 | 485 | 863 | 648 | 16470401964 | Repair Fuel Monitoring System - Corpus Christi AEM - Corpus Christi Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 5000 | 5000
476 | 486 | 864 | 649 | 16470401965 | Replace Existing Sewage Line Running To Lift Station - San Patricio Co | Site Work | Highway Trans. Fund 6 | 30000 | 30000
477 | 487 | 865 | 650 | 16470401966 | Replace Sewer Line - Sinton Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 25000 | 25000
478 | 488 | 866 | 651 | 10470401967 | Parking Improvements - Jacksonville Maintenance Office | Site Work | Highway Trans. Fund 6 | 120000 | 120000
479 | 489 | 867 | 652 | 22470401968 | Irrigation Replacement - Del Rio Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 15000
481 | 491 | 869 | 653 | 22470401970 | Install French Drainage - Cotulla Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
482 | 492 | 870 | 654 | 22470401971 | Install Irrigation And Landscaping - Cotulla Maintenance Office | Site Work | Highway Trans. Fund 6 | 4250 | 4250
483 | 493 | 871 | 655 | 22470401972 | Repave & Stripe Empl & Visitor Parking Lot - Cotulla Maintenance Office | Site Work | Highway Trans. Fund 6 | 105000 | 105000
484 | 494 | 872 | 656 | 20470401973 | Add Connection To Public Supply For Water And Sanitary Sewer System - Jasper Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 150000 | 150000
485 | 495 | 873 | 657 | 20470401974 | Remove Out Of Service Emulsion, Linseed Oil & Asts - Jasper Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
486 | 496 | 874 | 658 | 12470401975 | Sitework Modifications (Drivewal And Visitor Parking) - Conroe Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 70000 | 70000
487 | 497 | 875 | 659 | 22470401976 | Parking Lot Reconfiguration - District Headquarters | Site Work | Highway Trans. Fund 6 | 125000 | 125000
488 | 498 | 876 | 660 | 22470401977 | Irrigation, Landscaping, Grass Seeds, Planting/Adding Trees - Laredo Administration & Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 225000 | 225000
489 | 499 | 877 | 661 | 22470401978 | Reconfigure Landscaping For Walking Trail - Laredo District Headquarters | Site Work | Highway Trans. Fund 6 | 80000 | 80000
490 | 500 | 878 | 662 | 24470401979 | Site Improvements - District Headquarters | Site Work | Highway Trans. Fund 6 | 318000 | 318000
491 | 501 | 879 | 663 | 13470401980 | Replace Natural Gas Lines - District Headquarters | Site Work | Highway Trans. Fund 6 | 40000 | 40000
492 | 502 | 880 | 664 | 25470401981 | Replace Fuel Station - Clarendon Maintenance Office | Site Work | Highway Trans. Fund 6 | 50000 | 50000
493 | 503 | 881 | 665 | 18470401982 | Asphalt Overlay Parking Lot - Denton Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 40000 | 40000
496 | 506 | 882 | 666 | 20470401985 | Regrade Parking And Drainage - Liberty Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 75000 | 75000
497 | 507 | 883 | 667 | 24470401986 | Install/Repair Rock Wall Front And Rear - El Paso (East) Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 100000 | 100000
499 | 509 | 884 | 668 | 22470401988 | Irrigation And Landscaping - Freer | Site Work | Highway Trans. Fund 6 | 10000 | 10000
500 | 510 | 885 | 669 | 38470401989 | Retrofit Of Existing Exterior Light Fixture - CEDAR PARK Research and Technology Center | Site Work | Highway Trans. Fund 6 | 60000 | 60000
501 | 511 | 886 | 670 | 10470401990 | Sewer Connect To City - South Tyler Area Engineer And Maintenance Facility - South Tyler Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 300000 | 300000
502 | 512 | 887 | 671 | 16470401991 | Repair Fuel Monitoring System - Beeville MNT - Beeville Maintenance Office | Site Work | Highway Trans. Fund 6 | 5000 | 5000
503 | 513 | 888 | 672 | 16470401992 | Replace\New Fuel Dispenser/Fuel Pump At Maintenance - Beeville MNT - Beeville Maintenance Office | Site Work | Highway Trans. Fund 6 | 20000 | 20000
504 | 514 | 889 | 673 | 08470401993 | Reroute Wash Bay Drain To City Sewer Drain - Abilene Maintenance Office | Site Work | Highway Trans. Fund 6 | 10000 | 10000
505 | 515 | 890 | 674 | 22470401994 | Resurface 2 Acres Of Parking Area In Yard & Strip Where Needed - La Pryor Maintenance Office | Site Work | Highway Trans. Fund 6 | 152000 | 152000
508 | 518 | 891 | 675 | 13470401997 | Eliminate Wash Rack Waste Water Recycle System And Convert To City Utilities - Fayette Cty Maint. | Site Work | Highway Trans. Fund 6 | 75000 | 75000
509 | 519 | 892 | 676 | 18470401998 | Asphalt Overlay Parking Lot - Corsicana Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 40000 | 40000
511 | 521 | 893 | 677 | 21470402000 | Replace Fuel Pump Canopy - Laguna Vista Maintenance Office Sub-Section | Site Work | Highway Trans. Fund 6 | 13000 | 13000
512 | 522 | 894 | 678 | 15470402001 | Parking Lot Reconfiguration - New Braunfels Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 50000 | 50000
513 | 523 | 895 | 679 | 10470402002 | Parking Improvements - Athens Area Engineer & Maintenance Office | Site Work | Highway Trans. Fund 6 | 70000 | 70000
515 | 525 | 896 | 680 | 17470402004 | Parking Area Pavement - District Headquarters | Site Work | Highway Trans. Fund 6 | 450000 | 450000
518 | 528 | 897 | 681 | 24470402007 | Insulate Interior Roof And Walls, Spray Foam. - Marathon Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
519 | 529 | 898 | 682 | 16470402008 | Replace Floor In Lab Building District - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
520 | 530 | 899 | 683 | 16470402009 | Install Electrical - George West MNT - George West Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
521 | 531 | 900 | 684 | 16470402010 | Replace Metal Siding On Office Building With New Siding - Goliad Co. | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
522 | 532 | 901 | 685 | 16470402011 | Replace Sliding Garage Doors With Overhead Doors - Goliad Co. | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
524 | 534 | 902 | 686 | 19470402013 | Remodel Inside Of Building - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 90000 | 90000
525 | 535 | 903 | 687 | 19470402014 | Window Replacement - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
526 | 536 | 904 | 688 | 25470402015 | Re-Skin Exterior, Insulate Bujilding, Install Windows, Roof, & Doors, Upgrade Rest Room - Guthrie Maintenance Office SS | Capital Construction | Highway Trans. Fund 6 | 300000 | 300000
527 | 537 | 905 | 689 | 01470402016 | Abatement Of Roof And Walls (Monitoring) - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
528 | 538 | 906 | 690 | 01470402017 | Abatement Of Roof And Walls (Remediation) - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
529 | 539 | 907 | 691 | 01470402018 | Abatement Of Roof And Walls (Testing) - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
530 | 540 | 908 | 692 | 01470402019 | Boiler And Chiller Repairs - District Headquarters | HVAC | Highway Trans. Fund 6 | 100000 | 100000
532 | 542 | 909 | 693 | 01470402021 | Renovate DHQ Campus - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 1950000 | 1950000
533 | 543 | 910 | 694 | 21470402022 | Add Office And Reconfigure Space - Pharr Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 4000 | 4000
534 | 544 | 911 | 695 | 21470402023 | Add Vestibule - Pharr Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10200 | 10200
535 | 545 | 912 | 696 | 22470402024 | Convert 2Nd Floor Into Four Offices And Restroom Renovation - Del Rio Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
536 | 546 | 913 | 697 | 22470402025 | Replace Flooring In Mechanical Room - Del Rio Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
537 | 547 | 914 | 698 | 22470402026 | Roof & Exterior Painting - Del Rio Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 70000 | 70000
545 | 555 | 916 | 699 | 16470402034 | Replace Flooring In Office Building And Paint Walls - Refugio Co. | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
546 | 556 | 917 | 700 | 16470402035 | Replace Metal Siding On Office Building With New Siding - Refugio Co. | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
547 | 557 | 918 | 701 | 16470402036 | Repair Structure At Maintenance - Refugio Maintenance - Refugio Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
548 | 558 | 919 | 702 | 06470402037 | Replace Garage Door W/Panel & Electric Open. - Andrews Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
549 | 559 | 920 | 703 | 06470402038 | Replace Metal Roof & Exterior Walls, Insulate - Andrews Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 22000 | 22000
551 | 561 | 921 | 704 | 03470402040 | Close In Front Of New Truck Shed And Add 4 Roll Up Doors - Bowie Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 80000 | 80000
552 | 562 | 922 | 705 | 10470402041 | Replace Windows - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
553 | 563 | 923 | 706 | 38470402042 | Complete Renovation Of 5th Floor - Camp Hubbard State Headquarters | Capital Construction | Highway Trans. Fund 6 | 500000 | 500000
554 | 564 | 924 | 707 | 38470402043 | Retrofit Of Existing Exterior Light Fixture - Camp Hubbard State Headquarters | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
557 | 567 | 925 | 708 | 20470402046 | Reskin, Replace Lighting And Reroof Bld - Woodville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 95000 | 95000
558 | 568 | 926 | 709 | 25470402047 | Replace Floor Tiles, Upgrade Rest Room; Redesign Office Space - Memphis Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
559 | 569 | 927 | 710 | 25470402048 | Re-Skin Exterior, Install Roof, New Windows and Remove Sky Lights W/ Roof Replacement; Redesign Parking Area - Memphis Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 335000 | 335000
560 | 570 | 928 | 711 | 04470402049 | Retrofit Shop Bays For 10 Yard Trucks - Canadian Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
562 | 572 | 930 | 712 | 24470402051 | Exterior Renovations - Fort Hancock Sub-Section | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
563 | 573 | 931 | 713 | 24470402052 | Install Entrance Weather Canopy, Front Door. Add Rolling Doors To Existing Storage Bldg. - Fort Hancock Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 8100 | 8100
564 | 574 | 932 | 714 | 04470402053 | New Shop Heaters - Darouzett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
565 | 575 | 933 | 715 | 04470402054 | Abate and Remodel Office Area - Darrouzett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
566 | 576 | 934 | 716 | 04470402055 | Retrofit Shop Bays For 10 Yard Trucks - Gruver Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
567 | 577 | 935 | 717 | 04470402056 | Electrical Upgrades - Channing Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
568 | 578 | 936 | 718 | 04470402057 | New Unit Heaters - Channing Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
569 | 579 | 937 | 719 | 04470402058 | Replace Roof, Re-Skin Exterior, Install New Insulation And Windows - Channing Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 175000 | 175000
570 | 580 | 938 | 720 | 04470402059 | Retrofit Shop Bays For 10 Yard Trucks - Channing Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
571 | 581 | 939 | 721 | 17470402060 | Install Bathroom/Showers In Shop/Welding Shop - Brenham Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
573 | 583 | 941 | 722 | 05470402062 | Re-Skin Renovate Shop - Post Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
574 | 584 | 942 | 723 | 04470402063 | Enlarge Supervisor Office And Breakroom - Panhandle Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
575 | 585 | 943 | 724 | 04470402064 | Install Overhead Doors And Openers - Panhandle Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
576 | 586 | 944 | 725 | 04470402065 | Retrofit Shop Bays For 10 Yard Trucks - Panhandle Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
577 | 587 | 945 | 726 | 25470402066 | Upgrade Electrical & Lights In Maintenance Barn - Munday Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 30000 | 30000
578 | 588 | 946 | 727 | 16470402067 | Replace Metal Siding On Equipment Shed And Roof With New Siding And Roof - Goliad Co. | Capital Repairs | Highway Trans. Fund 6 | 60000 | 60000
579 | 589 | 947 | 728 | 16470402068 | Replace Exterior Door At Equipment Storage - Goliad MNT - Goliad Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
580 | 590 | 948 | 729 | 16470402069 | Replace Exterior Windows At Laboratory - Goliad MNT - Goliad Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
582 | 592 | 950 | 730 | 11470402071 | Renovate Interior - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
588 | 598 | 951 | 731 | 06470402077 | Upgrade Electrical Wiring & Lights In Shop Area - McCamey Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 7000 | 7000
589 | 599 | 952 | 732 | 07470402078 | Erect Buildings Over Lifts - Ballinger Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
590 | 600 | 953 | 733 | 09470402079 | Replace Windows - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 33450 | 33450
591 | 601 | 954 | 734 | 06470402080 | Replace Windows - Sanderson Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
592 | 602 | 955 | 735 | 23470402081 | Renovate Facilities - Comanche Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 294000 | 294000
593 | 603 | 956 | 736 | 17470402082 | Add Lighting And Catwalks To V-Box Area - Brenham Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
594 | 604 | 957 | 737 | 17470402083 | Install Above Ground Fuel Tank - Brenham Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 350000 | 350000
595 | 605 | 958 | 738 | 17470402084 | New Sidewalk Lab To Parking Lot - Brenham Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12500 | 12500
596 | 606 | 959 | 739 | 06470402085 | Install Shed Kit - Stanton Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
598 | 608 | 960 | 740 | 21470402087 | Reconfigure Two Restrooms & Office - San Isidro Maintenance Office Sub-Section | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
599 | 609 | 961 | 741 | 15470402088 | Refurbish Shop Building Skin And Roof - Pearsall Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 95000 | 95000
600 | 610 | 962 | 742 | 38470402089 | Austin HQ Campus Repairs - Austin HQ | Capital Construction | Highway Trans. Fund 6 | 5000000 | 5000000
601 | 611 | 963 | 743 | 09470402090 | New Insulation & Replace Windows - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 52200 | 52200
602 | 612 | 964 | 744 | 03470402091 | Replace Exterior Windows At Warehouse - Bowie Maintenance - Bowie Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
603 | 613 | 965 | 745 | 19470402092 | Remodel Inside Of Building - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 87000 | 87000
604 | 614 | 966 | 746 | 23470402093 | Renovate Facilities - Brady Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 317000 | 317000
605 | 615 | 967 | 747 | 17470402094 | Reskin Shed - Bryan Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
606 | 616 | 968 | 748 | 17470402095 | Fence/Gate Work - Madisonville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
607 | 617 | 969 | 749 | 17470402096 | Improve Lighting In Yard/Shed - Madisonville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
608 | 618 | 970 | 750 | 17470402097 | Install Above Ground Fuel Tank - Madisonville Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 350000 | 350000
609 | 619 | 971 | 751 | 17470402098 | Replace Fuel Canopy - Madisonville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
611 | 621 | 972 | 752 | 25470402100 | Rewire Office, New Lights; Heaters In Truck Barn - Crowell Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
612 | 622 | 973 | 753 | 25470402101 | Re-Skin Exterior, Insulate Building, Install Windows, Roof and Lights; Redesign Office Space - Matador Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 325000 | 325000
613 | 623 | 974 | 754 | 16470402102 | Install Redundant 2000 Gallon Diesel Tank To Existing Fuel Island - Nueces East | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
614 | 624 | 975 | 755 | 18470402103 | Electrical Panel Upgrades - Ennis Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
618 | 628 | 976 | 756 | 21470402107 | Renovate Building Into Offices. Renovate Restrooms. - Zapata Maintenance Office Sub-Section | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
623 | 633 | 977 | 757 | 20470402112 | Abate Transit Siding - Woodville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
624 | 634 | 978 | 758 | 20470402113 | Replace Roof, Lighting & Siding - Woodville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
625 | 635 | 979 | 759 | 23470402114 | Renovate Facilities - Coleman Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 350000 | 350000
630 | 640 | 981 | 760 | 17470402119 | Replace Flooring (Carpet & Tile) - Cameron Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
631 | 641 | 982 | 761 | 17470402120 | Redo Walls In Office - Cameron Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
632 | 642 | 983 | 762 | 17470402121 | Reskin MNT Office Building - Cameron Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
634 | 644 | 984 | 763 | 25470402123 | Replace Restrooms - Paducah Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
635 | 645 | 985 | 764 | 25470402124 | Insulate, New Windows And Roof - Silverton Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 275000 | 275000
636 | 646 | 986 | 765 | 25470402125 | Re-Skin Exterior, Insulate Building,Install Windows and Roof - Silverton Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 175000 | 175000
638 | 648 | 987 | 766 | 16470402127 | Replace Exterior Door At Equipment Storage - Goliad MNT - Goliad Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 16000 | 16000
639 | 649 | 988 | 767 | 18470402128 | Upgrade Lighting - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
641 | 651 | 989 | 768 | 22470402130 | Deactivate Or Remove Mag Locks - Brackettville | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
642 | 652 | 990 | 769 | 22470402131 | Furnish/Install Exterior Safety Lights - Brackettville | Safety/Security | Highway Trans. Fund 6 | 1500 | 1500
643 | 653 | 991 | 770 | 22470402132 | Renovate Breakroom - Brackettville | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
644 | 654 | 992 | 771 | 22470402133 | Restroom Renovations (Both Men and Women) - Brackettville | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
645 | 655 | 993 | 772 | 22470402134 | Retrofit Bay Area Into Conference Room. (17'X28') 14' Ceiling. Tile Flooring, HVAC, Electrical, Communications, Removal Of Exiting Door. - Brackettville | Capital Repairs | Highway Trans. Fund 6 | 55000 | 55000
646 | 656 | 994 | 773 | 07470402135 | Erect Buildings Over Lifts - Sterling City Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
647 | 657 | 995 | 774 | 17470402136 | Restroom Remodels - Navasota Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
648 | 658 | 996 | 775 | 25470402137 | New Partition Walls & Larger Break Room, Upgrade Rest Room, New Windows & Doors, Redesign Office Space - Munday Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
653 | 663 | 997 | 776 | 05470402142 | Campuswide Electrical Upgrade - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 150000 | 150000
656 | 666 | 998 | 777 | 05470402145 | New VCT Floor - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 78000 | 78000
660 | 670 | 999 | 778 | 21470402149 | Add Large Conference Room - Hebbronville Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 252000 | 252000
661 | 671 | 1000 | 779 | 21470402150 | Restroom Renovation - Hebbronville Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
662 | 672 | 1001 | 780 | 21470402151 | Locker Room With Showers - Hebbronville Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 0 | 0
663 | 673 | 1002 | 781 | 21470402152 | Phone/Computer Access - Hebbronville Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 0
664 | 674 | 1003 | 782 | 21470402153 | Ventilation Upgrade - Hebbronville Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 0
665 | 675 | 1004 | 783 | 09470402154 | Remodel Office - Marlin Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 488000 | 488000
666 | 676 | 1005 | 784 | 03470402155 | Building Renovation - Electra Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
667 | 677 | 1006 | 785 | 03470402156 | Reskin And Replace Windows - Electra Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 90000 | 90000
668 | 678 | 1007 | 786 | 13470402157 | Paint Metal On Shed - Edna Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12000 | 12000
669 | 679 | 1008 | 787 | 13470402158 | Paint Interior/Exterior Of Mechanic/Warehouse - Jackson Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
672 | 682 | 1009 | 788 | 17470402161 | Install Above Ground Fuel Tank - Navasota Maintenance Office | Site Work | Highway Trans. Fund 6 | 350000 | 350000
673 | 683 | 1010 | 789 | 16470402162 | Interior Renovations - Karnes City Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 350000 | 350000
674 | 684 | 1011 | 790 | 16470402163 | Repair Plumbing System - Karnes City AEM - Karnes City Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
675 | 685 | 1012 | 791 | 05470402164 | Security System Upgrade - C-Cure - District Headquarters | Safety/Security | Highway Trans. Fund 6 | 40000 | 40000
676 | 686 | 1013 | 792 | 05470402165 | Add New Wall To Dock With Overhead Door Wk Door - Post RDC | Capital Repairs | Highway Trans. Fund 6 | 90000 | 90000
678 | 688 | 1015 | 793 | 10470402167 | Demolish Abandoned Structure - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
679 | 689 | 1016 | 794 | 10470402168 | Exterior Renovations - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
680 | 690 | 1017 | 795 | 10470402169 | Replace Carpet In Administration Building - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
681 | 691 | 1018 | 796 | 09470402170 | Renovate Maintenance Facility - Mexia Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
682 | 692 | 1019 | 797 | 08470402171 | Construct Concrete Apron Around The District Headquarters - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
683 | 693 | 1020 | 798 | 08470402172 | Repair And Replace All Plumbing Fixtures - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 100000 | 100000
685 | 695 | 1022 | 799 | 17470402174 | New Fuel Canopy - Caldwell Maintenance Office | Site Work | Highway Trans. Fund 6 | 35000 | 35000
686 | 696 | 1023 | 800 | 17470402175 | Repaving Of Parking Areas - Caldwell Maintenance Office | Site Work | Highway Trans. Fund 6 | 400000 | 400000
689 | 699 | 1024 | 801 | 02470402178 | Convert Conference Room To EOC - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 153000 | 153000
690 | 700 | 1025 | 802 | 02470402179 | Electrical Upgrade For The Whole District Headquarters - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 300000 | 300000
691 | 701 | 1026 | 803 | 02470402180 | Install Interior Walls At Warehouse - Fort Worth DHQ Ware House Office - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
692 | 702 | 1027 | 804 | 02470402181 | Install Interiors At Shop - Fort Worth DHQ Locker Rooms - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
693 | 703 | 1028 | 805 | 02470402182 | Modifications/Upgrade HVAC - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 125000 | 125000
695 | 705 | 1029 | 806 | 12470402184 | Paint Exterior (5 Buildings) - Rosenberg Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 97000 | 97000
696 | 706 | 1030 | 807 | 12470402185 | Renovate Interior - Rosenberg Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 150000 | 150000
697 | 707 | 1031 | 808 | 12470402186 | Renovate Interior - Rosenberg Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 240000 | 240000
698 | 708 | 1032 | 809 | 05470402187 | Electrical Up-Grade Panel To Switches,Light Plug - Post Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
699 | 709 | 1033 | 810 | 06470402188 | Repair/Replace Carpet In Tp&D Area - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
700 | 710 | 1034 | 811 | 06470402189 | Upgrade The District Complex Plumbing System - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 280000 | 280000
701 | 711 | 1035 | 812 | 15470402190 | Repair Foundation - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
702 | 712 | 1036 | 813 | 15470402191 | Repair Sidewalks - District Headquarters | Site Work | Highway Trans. Fund 6 | 8000 | 8000
703 | 713 | 1037 | 814 | 15470402192 | Restroom Renovation/Addition - Seguin RDC | Capital Construction | Highway Trans. Fund 6 | 80000 | 80000
705 | 715 | 1038 | 815 | 08470402194 | New Carpet - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
707 | 717 | 1039 | 816 | 25470402196 | Re-Skin Exterior, Insulate Building, Install Windows and Roof, Redesign Office Space - Wellington Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 325000 | 325000
708 | 718 | 1040 | 817 | 02470402197 | Lab Upgrades - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 558500 | 558500
710 | 720 | 1041 | 818 | 12470402199 | Renovate 3 Buildings Into One - Houston South Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 1200000 | 1200000
711 | 721 | 1042 | 819 | 12470402200 | Renovate Interior - Houston South Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 29000 | 29000
712 | 722 | 1043 | 820 | 12470402201 | Renovate Interior - Houston South Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 485000 | 485000
713 | 723 | 1044 | 821 | 12470402202 | Renovate Interior - Houston South Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 0 | 0
715 | 724 | 1045 | 822 | 06470402204 | Replace/Repair Windows - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
718 | 726 | 1047 | 823 | 15470402207 | Restroom Renovation/Addition - Seguin Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
719 | 727 | 1048 | 824 | 04470402208 | Abate Inside,Replace Windows And Replace Roof - Canyon Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
720 | 728 | 1049 | 825 | 05470402209 | Electrical Up-Grade Panel To Switches,Light Plug - Bovina Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
723 | 731 | 1051 | 826 | 05470402212 | Electrical Up-Grade Panel To Switches,Light Plug - Brownfield Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
726 | 734 | 1053 | 827 | 05470402215 | Electrical Up-Grade Panel To Switches,Light Plug - Ralls Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
729 | 737 | 1055 | 828 | 15470402218 | Carpet & Paint - Tilden Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
730 | 738 | 1056 | 829 | 15470402219 | Relocate Radio Tower - Tilden Maintenance Office | Site Work | Highway Trans. Fund 6 | 0 | 0
731 | 739 | 1057 | 830 | 15470402220 | Upgrade Restrooms - Tilden Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
732 | 740 | 1058 | 831 | 38470402221 | Renovate Interior Office Space, Include Abatement, New Lighting, New Windows, New Duct Work - Camp Hubbard State Headquarters | Capital Construction | Highway Trans. Fund 6 | 1000000 | 1000000
733 | 741 | 1059 | 832 | 10470402222 | Elevated Water Storage - North Tyler Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
734 | 742 | 1060 | 833 | 10470402223 | Remodel Office & New Roof - North Tyler Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 300000 | 300000
735 | 743 | 1061 | 834 | 13470402224 | Paint Interior Structure Of Equip Shed - Austin Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
736 | 744 | 1062 | 835 | 13470402225 | Rehab. Of Mechanic Area (Front Wall W/ Door) - Austin Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
737 | 745 | 1063 | 836 | 13470402226 | Level And Paint Interior Of Office Building - Colorado Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
739 | 747 | 1064 | 837 | 13470402228 | Level Building (Maintenance Bldg) - Columbus Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
740 | 748 | 1065 | 838 | 13470402229 | Paint Office & Warehouse Exterior - Columbus Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
741 | 749 | 1066 | 839 | 13470402230 | Paint Exterior Structure Of Fuel Canopy - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
743 | 751 | 1067 | 840 | 08470402232 | Paint Exterior - Big Spring Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
745 | 753 | 1068 | 841 | 20470402234 | Install Rotary Lift & 2 Ton Overhead Crane And Trolley - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 13000 | 13000
748 | 756 | 1069 | 842 | 20470402237 | Interior Remodel - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 6700 | 6700
749 | 757 | 1070 | 843 | 20470402238 | Interior Remodel - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 39000 | 39000
750 | 758 | 1071 | 844 | 20470402239 | Repair ADA Ramps - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
751 | 759 | 1072 | 845 | 20470402240 | Replace 25 Infra-Red Heaters - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
753 | 761 | 1073 | 846 | 20470402242 | Replace Fuel Dispensers Districtwide - Districtwide | Site Work | Highway Trans. Fund 6 | 150000 | 150000
754 | 762 | 1074 | 847 | 25470402243 | Replace Windows & Locks - Dickens Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
755 | 763 | 1075 | 848 | 12470402244 | Renovate Interior - La Marque Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 300000 | 300000
756 | 764 | 1076 | 849 | 12470402245 | Replace Siding (8 Buildings) - La Marque Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 640000 | 640000
758 | 766 | 1077 | 850 | 03470402247 | Building Renovations - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 112000 | 112000
759 | 767 | 1078 | 851 | 03470402248 | Foundation And Cosmetic Repairs - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 160000 | 160000
760 | 768 | 1079 | 852 | 13470402249 | Close Open Bay And Add To Sign Room - Colorado Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
#N/A | #N/A | 1080 | 853 | 08470402250 | Replace 5 Overhead Roll Up Doors And Paint 3 - Colorado Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
762 | 770 | 1081 | 854 | 13470402251 | Replace Oh Doors On Shed - Columbus Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 12000 | 12000
763 | 771 | 1082 | 855 | 13470402252 | Bird Proof Underside Of Roof-Purlins - Matagorda Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 6000 | 6000
764 | 772 | 1083 | 856 | 13470402253 | Construct Elevated Platform For Wash Rack - Matagorda Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
765 | 773 | 1084 | 857 | 19470402254 | Renovation Of Warehouse - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 515000 | 515000
766 | 774 | 1085 | 858 | 19470402255 | Remodel Inside Of Building - Texarkana Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 80000 | 80000
767 | 775 | 1086 | 859 | 19470402256 | Replace Overhead Doors - Texarkana Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 111000 | 111000
769 | 777 | 1087 | 860 | 17470402258 | Remove Fuel Awning/Install New Awning For Parking - Brenham Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 250000 | 250000
770 | 778 | 1088 | 861 | 16470402259 | Repair Structure At Administration - Corpus Christi DHQ - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 7500 | 7500
771 | 779 | 1089 | 862 | 16470402260 | Replace Flooring At Administration - Corpus Christi DHQ - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
773 | 781 | 1090 | 863 | 16470402262 | Replace\New Exterior Walls At Equipment Storage - Goliad MNT - Goliad Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 90000 | 90000
774 | 782 | 1091 | 864 | 16470402263 | Remodel Inside Office (Lights, Ceiling, Floor, Paint) - Karnes Co. | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
776 | 784 | 1092 | 865 | 02470402265 | Renovate Maintenance Facility - Mineral Wells Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 500000 | 500000
777 | 785 | 1093 | 866 | 05470402266 | Electrical Up-Grade Panel To Switches,Light Plug - Plains Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
779 | 787 | 1095 | 867 | 05470402268 | Electrical Up-Grade Panel To Switches,Light Plug - Seminole Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
780 | 788 | 1096 | 868 | 05470402269 | New VCT Floor - Seminole Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
782 | 790 | 1098 | 869 | 11470402271 | Paint Entire Facility Interior And Exterior - Crockett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
783 | 791 | 1099 | 870 | 11470402272 | Replace Fuel Dispensers - Crockett Maintenance Office | Site Work | Highway Trans. Fund 6 | 15000 | 15000
785 | 793 | 1100 | 871 | 11470402274 | Upgrade Exterior Lighting - Crockett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
786 | 794 | 1101 | 872 | 11470402275 | Upgrade Interior Lighting - Crockett Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
788 | 796 | 1102 | 873 | 06470402277 | Paint Exterior And Interior - Crane Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
789 | 797 | 1103 | 874 | 06470402278 | Reconfigure Bay For Break Room Locker Room. New Kitchenette Lockers Flooring Walls Plumbing Electrical - Crane Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
790 | 798 | 1104 | 875 | 06470402279 | Remove & Replace Windows In Main Office - Crane Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
791 | 799 | 1105 | 876 | 06470402280 | Upgrade Electrical Wiring, Lights And Breakers - Crane Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 4000 | 4000
793 | 801 | 1106 | 877 | 21470402282 | Upgrade Conference Rooms - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 51000 | 51000
794 | 802 | 1107 | 878 | 21470402283 | Repair Plumbing Problems - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 20000 | 20000
795 | 803 | 1108 | 879 | 21470402284 | Building Renovation - Falfurrias Maintenance Office Sub-Section | Capital Construction | Highway Trans. Fund 6 | 163300 | 163300
796 | 804 | 1109 | 880 | 21470402285 | Upgrade Mechanic Shop - Falfurrias Maintenance Office Sub-Section | Capital Construction | Highway Trans. Fund 6 | 190000 | 190000
797 | 805 | 1110 | 881 | 09470402286 | Retrofit Truck Bays To Conference Rooms and Meeting Space - Meridian Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
799 | 807 | 1112 | 882 | 03470402288 | Retrofit Warehouse Space To Large Meeting Room - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 28500 | 28500
800 | 808 | 1113 | 883 | 03470402289 | Building Remodel - Nocona Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 90000 | 90000
801 | 809 | 1114 | 884 | 13470402290 | Interior Renovation (Floors & Walls) - Calhoun Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 60000 | 60000
802 | 810 | 1115 | 885 | 13470402291 | Paint Exterior Structure Of Canopy, Mechanci Shop, & Stock Room - Calhoun Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
803 | 811 | 1116 | 886 | 13470402292 | Paint Interior Structure Of Equip Shed - Calhoun Cty Maint. | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
804 | 812 | 1117 | 887 | 13470402293 | Replace Shifting Concrete Pad Under Pad Mount Electrical Transformer - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
809 | 817 | 1119 | 888 | 23470402298 | Renovate Lab - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 712000 | 712000
810 | 818 | 1120 | 889 | 18470402300 | Electrical - Additional Service - Waxahachie Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
812 | 820 | 1121 | 890 | 12470402302 | Renovate Interior - Rosenberg Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 120000 | 120000
813 | 821 | 1122 | 891 | 22470402303 | Exterior Warehouse Painting - Del Rio Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
814 | 822 | 1123 | 892 | 05470402304 | Electrical Up-Grade Panel To Switches,Light Plug - Levelland Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
816 | 824 | 1125 | 893 | 05470402306 | Electrical Up-Grade Panel To Switches,Light Plug - SE Maint. Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
819 | 827 | 1126 | 894 | 11470402309 | Repair Dist Shop Parking Lot And Stripe Existing Lots At Dist HQ - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
820 | 828 | 1127 | 895 | 11470402310 | Replace Fuel Awning - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 21000 | 21000
823 | 831 | 1129 | 896 | 04470402313 | Abate Windows And Paint Exterior Of Shop - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
824 | 832 | 1130 | 897 | 19470402314 | Major Renovation - Mt Pleasant Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 767000 | 767000
825 | 833 | 1131 | 898 | 19470402315 | Remodel Inside Of Building - Mt Pleasant Area Engineer & Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 65000 | 65000
826 | 834 | 1132 | 899 | 19470402316 | Replace Overhead Doors - Mt Pleasant Area Engineer & Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 128300 | 128300
829 | 837 | 1134 | 900 | 18470402319 | Renovate Interior - Rockwall Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
831 | 839 | 1135 | 901 | 22470402321 | Replace Two Overhead Doors - Carrizo Springs | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
832 | 840 | 1136 | 902 | 22470402322 | Restroom Renovation - Carrizo Springs | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
834 | 842 | 1138 | 903 | 05470402324 | Electrical Up-Grade Panel To Switches,Light Plug - FloydADA Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
835 | 843 | 1139 | 904 | 05470402325 | Electrical Up-Grade Panel To Switches,Light Plug - Lamesa Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
836 | 844 | 1140 | 905 | 05470402326 | New VCT Floor - Lamesa Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
838 | 846 | 1142 | 906 | 11470402328 | Paint Entire Facility Interior And Exterior - Lufkin Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
840 | 848 | 1143 | 907 | 11470402330 | Renovate Interior - Lufkin Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000 | [6 empty] | A Phase was broken out as Project #19470402979
846 | 854 | 1144 | 908 | 07470402336 | Modifications/Upgrade Electrical - District Headquarters | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
847 | 855 | 1145 | 909 | 07470402337 | Reconfigure To Allow For Drivethrough - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 21500 | 21500
849 | 857 | 1146 | 910 | 12470402340 | Renovate Interior/Exterior (20K Sf Concrete Tilt Wall Aquired Building) - Houston Northwest | Capital Construction | Highway Trans. Fund 6 | 2000000 | 2000000
850 | 858 | 1147 | 911 | 12470402341 | Renovation And Upgrade To AEM - West Harris Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 2000000 | 2000000
851 | 859 | 1148 | 912 | 05470402342 | New VCT Floor - District Headquarters-LBB AE's | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
855 | 863 | 1151 | 913 | 04470402346 | Retrofit Shop Bays For 10 Yard Trucks - Vega Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
856 | 864 | 1152 | 914 | 04470402347 | Upgrade Current Welding Shop - Vega Maintenance Office | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
857 | 865 | 1153 | 915 | 19470402348 | Remodel Inside Of Building Paint Floor And Ceiling - New Boston Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 80000 | 80000
858 | 866 | 1154 | 916 | 19470402349 | Replace Overhead Doors - New Boston Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 99400 | 99400
859 | 867 | 1155 | 917 | 15470402350 | Paint, Carpet Replacement - Devine Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
860 | 868 | 1156 | 918 | 15470402351 | Restroom Upgrades - Devine Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
861 | 869 | 1157 | 919 | 13470402352 | Replace All Exterior Roof Facial & Renovate All Exterior Entrances - District Headquarters | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
862 | 870 | 1158 | 920 | 16470402353 | Replace Metal Siding On Equipment Shed And Roof With New Siding And Roof - Goliad Co. | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
863 | 871 | 1159 | 921 | 16470402354 | Paint Interior Walls At Maintenance - Kingsville Maintenance - Kingsville Maintenance Office | Capital Repairs | Highway Trans. Fund 6 | 7500 | 7500
866 | 874 | 1160 | 922 | 05470402357 | Electrical Up-Grade Panel To Switches,Light Plug | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
867 | 875 | 1161 | 923 | 05470402358 | Electrical Up-Grade Panel To Switches,Light Plug | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
870 | 878 | 1163 | 924 | 04470402361 | Foundation Repair | Capital Construction | Highway Trans. Fund 6 | 0 | 0
872 | 880 | 1164 | 925 | 04470402363 | Renovation Of Building Exterior | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
873 | 881 | 1165 | 926 | 04470402364 | Restroom Abatement And Remodel | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
874 | 882 | 1166 | 927 | 04470402365 | Lighting Upgrades | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
875 | 883 | 1167 | 928 | 04470402366 | Retrofit Shop Bays For 10 Yard Trucks | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
876 | 884 | 1168 | 929 | 14470402367 | Foundation Repair | Capital Construction | Highway Trans. Fund 6 | 350000 | 350000
878 | 886 | 1169 | 930 | 20470402369 | Paint Office Exterior | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
879 | 887 | 1170 | 931 | 20470402370 | Replace Electrical Panels And Upgrade Electrical Wiring. | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
880 | 888 | 1171 | 932 | 24470402371 | Additional Outside LED Lighting For Houses. | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
881 | 889 | 1172 | 933 | 24470402372 | Interior Renovation; Electrical, HVAC, Walls Finish, Framing, Floors And Kitchen | Capital Repairs | Highway Trans. Fund 6 | 36000 | 36000
884 | 892 | 1173 | 934 | 05470402375 | Electrical Up-Grade Panel To Switches,Light Plug | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
885 | 893 | 1174 | 935 | 05470402376 | New VCT Floor | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
886 | 894 | 1175 | 936 | 07470402377 | Paint Interior Of Facility | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
890 | 898 | 1177 | 937 | 04470402381 | Replace Roof, Re-Skin Exterior, Install New Insulation And Windows | Capital Construction | Highway Trans. Fund 6 | 175000 | 175000
891 | 899 | 1178 | 938 | 04470402382 | Retrofit Shop Bays For 10 Yard Trucks | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
892 | 900 | 1179 | 939 | 08470402383 | Convert Old Shop Into Breakroom | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
893 | 901 | 1180 | 940 | 23470402384 | Renovate Office | Capital Construction | Highway Trans. Fund 6 | 311000 | 311000
894 | 902 | 1181 | 941 | 17470402385 | Install Above Ground Fuel Tank | Site Work | Highway Trans. Fund 6 | 350000 | 350000
896 | 904 | 1182 | 942 | 17470402387 | Repair Foundation/Porch/Walls | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
898 | 906 | 1183 | 943 | 17470402389 | Replace Fuel Canopy | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
899 | 907 | 1184 | 944 | 17470402390 | Replace Wiring In Building | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
901 | 909 | 1185 | 945 | 25470402392 | Replace Floor Tiles; Upgrade Rest Rooms, Redesign Office Space | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
902 | 910 | 1186 | 946 | 16470402393 | Replace Electrical Panels At Right Of Way - Corpus Christi District Headquarters And Area Engineer And Maintenance Special Jobs | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
906 | 914 | 1188 | 947 | 06470402397 | Replace Windows | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
907 | 915 | 1189 | 948 | 21470402398 | New 4K Gallon Fuel Tanks/Replace Fuel Pumps | Capital Construction | Highway Trans. Fund 6 | 300000 | 300000
908 | 916 | 1190 | 949 | 21470402399 | New Heavy Equipment Overhead Doors | Capital Construction | Highway Trans. Fund 6 | 57000 | 57000
909 | 917 | 1191 | 950 | 21470402400 | New Heavy Equipment Pull Through Stalls | Capital Repairs | Highway Trans. Fund 6 | 21500 | 21500
910 | 918 | 1192 | 951 | 21470402401 | Renovate Building | Capital Construction | Highway Trans. Fund 6 | 112000 | 112000
911 | 919 | 1193 | 952 | 13470402402 | Interior Renovation (Floors & Walls) | Capital Repairs | Highway Trans. Fund 6 | 60000 | 60000
914 | 922 | 1195 | 953 | 24470402405 | Remodel Bay For Maintenance Training And Breakroom, Add One Additional Office In Bay. | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
915 | 923 | 1196 | 954 | 12470402406 | Renovate Restrooms (Locker Rooms) | Capital Repairs | Highway Trans. Fund 6 | 42000 | 42000
916 | 924 | 1197 | 955 | 12470402407 | Replace Windows | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
917 | 925 | 1198 | 956 | 21470402408 | Upgrade Mechanic Shop | Capital Construction | Highway Trans. Fund 6 | 0 | 0
921 | 929 | 1200 | 957 | 17470402412 | Install Above Ground Fuel Tank | Capital Repairs | Highway Trans. Fund 6 | 350000 | 350000
925 | 933 | 1201 | 958 | 21470402416 | Upgrade Ballasts | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
926 | 934 | 1202 | 959 | 24470402417 | Convert Bay Into A Break Room | Capital Repairs | Highway Trans. Fund 6 | 19500 | 19500
927 | 935 | 1203 | 960 | 24470402418 | Extend Office Space Along Same Roof Line To The South 16 Feet | Capital Repairs | Highway Trans. Fund 6 | 80000 | 80000
928 | 936 | 1204 | 961 | 19470402419 | Install Overhead Door Operators & Gate | Capital Repairs | Highway Trans. Fund 6 | 32200 | 32200
929 | 937 | 1205 | 962 | 19470402420 | Remodel Inside Of Building | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
931 | 939 | 1207 | 963 | 17470402422 | Remove Undergrnd/Install Above Grnd Fuel Tanks | Site Work | Highway Trans. Fund 6 | 350000 | 350000
932 | 940 | 1208 | 964 | 21470402423 | Building Renovation | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
933 | 941 | 1209 | 965 | 21470402424 | Replace Overhead Doors | Capital Repairs | Highway Trans. Fund 6 | 12000 | 12000
934 | 942 | 1210 | 966 | 04470402425 | Electrical Upgrades | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
936 | 944 | 1211 | 967 | 04470402427 | Retrofit Shop Bays For 10 Yard Trucks | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
937 | 945 | 1212 | 968 | 15470402428 | Paint, Carpet Replacement | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
938 | 946 | 1213 | 969 | 15470402429 | Restroom Upgrades | Capital Repairs | Highway Trans. Fund 6 | 0 | 0
939 | 947 | 1214 | 970 | 15470402430 | Window Replacement | Capital Construction | Highway Trans. Fund 6 | 180000 | 180000
940 | 948 | 1215 | 971 | 15470402431 | Asbestos Abatement, Carpet & Paint | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
941 | 949 | 1216 | 972 | 15470402432 | Restroom Upgrade | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
942 | 950 | 1217 | 973 | 12470402433 | Locker Room Upgrades/Addition Of Showers | Capital Repairs | Highway Trans. Fund 6 | 42000 | 42000
944 | 952 | 1218 | 974 | 15470402435 | Replace Irrigation System | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
948 | 956 | 1219 | 975 | 08470402439 | Repair Structural Damage to Columns | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
950 | 958 | 1220 | 976 | 08470402441 | Upgrade Wash Bay | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
951 | 959 | 1221 | 977 | 24470402442 | Additional Outside LED Lighting For Houses. | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
953 | 961 | 1222 | 978 | 24470402444 | Renovate Stock Area; Insulate Metal Walls, Ceiling | Capital Repairs | Highway Trans. Fund 6 | 11500 | 11500
954 | 962 | 1223 | 979 | 07470402445 | Construct Buildings Over Lifts | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
956 | 964 | 1224 | 980 | 14470402447 | Foundation Repair | Capital Construction | Highway Trans. Fund 6 | 167200 | 167200
957 | 965 | 1225 | 981 | 17470402448 | Replace Fuel Canopy - Navasota MNT | Site Work | Highway Trans. Fund 6 | 35000 | 35000
959 | 967 | 1226 | 982 | 16470402450 | Replace Flooring In Office Building And Paint Walls | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
960 | 968 | 1227 | 983 | 19470402451 | Install Overhead Door Operators & Gate | Capital Repairs | Highway Trans. Fund 6 | 82600 | 82600
961 | 969 | 1228 | 984 | 19470402452 | Remodel Inside Of Building Including Bathrooms | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
964 | 972 | 1229 | 985 | 16470402455 | Replace Flooring In Office Building And Paint Walls | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
965 | 973 | 1230 | 986 | 16470402456 | Paint Interior Walls At Area Engineer And Maintenance - Sinton AEM | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
968 | 976 | 1231 | 987 | 16470402459 | Replace Existing Floor Tile And Paint Office | Capital Repairs | Highway Trans. Fund 6 | 17500 | 17500
969 | 977 | 1232 | 988 | 16470402460 | Install Storm Shutters On All Windows And Doors | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
970 | 978 | 1233 | 989 | 16470402461 | Install Exteriors At Maintenance - Rockport MNT | Capital Repairs | Highway Trans. Fund 6 | 28000 | 28000
971 | 979 | 1234 | 990 | 16470402462 | Repair Exterior Windows At Maintenance - Rockport MNT | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
973 | 981 | 1235 | 991 | 12470402464 | Renovate Interior | Capital Construction | Highway Trans. Fund 6 | 120000 | 120000
974 | 982 | 1236 | 992 | 12470402465 | Renovate Interior | Capital Construction | Highway Trans. Fund 6 | 320000 | 320000
975 | 983 | 1237 | 993 | 22470402466 | Storage Shed Asbestos Testing & Abatement | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
976 | 984 | 1238 | 994 | 22470402467 | Storage Shed Repairs | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
977 | 985 | 1239 | 995 | 11470402468 | Paint Entire Facility Interior And Exterior | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
985 | 993 | 1240 | 996 | 11470402476 | Paint Entire Facility Interior And Exterior | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
986 | 994 | 1241 | 997 | 11470402477 | Replace Fuel Dispensers | Site Work | Highway Trans. Fund 6 | 30000 | 30000
988 | 996 | 1242 | 998 | 11470402479 | Upgrade Exterior Lighting | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
991 | 999 | 1243 | 999 | 11470402482 | Paint Entire Facility Interior And Exterior | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
992 | 1000 | 1244 | 1000 | 11470402483 | Replace Fuel Dispensers | Site Work | Highway Trans. Fund 6 | 30000 | 30000
997 | 1005 | 1245 | 1001 | 06470402488 | Install Ladder Or Staircase | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
998 | 1006 | 1246 | 1002 | 06470402489 | Reinstall Evaporative Coolers In Wall | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
999 | 1007 | 1247 | 1003 | 21470402490 | Exterior Facade Repairs To Warehouse, Shop & Teleconference Training Center | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1000 | 1008 | 1248 | 1004 | 21470402491 | Renovate Shop | Capital Construction | Highway Trans. Fund 6 | 117000 | 117000
1001 | 1009 | 1249 | 1005 | 21470402492 | Install Vehicle Exhaust System. Replace Existing Ceiling Fans. | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1002 | 1010 | 1250 | 1006 | 21470402493 | Replace All Windows/Frames. | Capital Repairs | Highway Trans. Fund 6 | 85000 | 85000
1004 | 1012 | 1251 | 1007 | 15470402495 | Restroom Upgrade | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1005 | 1013 | 1252 | 1008 | 04470402496 | Electrical Upgrades | Capital Repairs | Highway Trans. Fund 6 | 8000 | 8000
1006 | 1014 | 1253 | 1009 | 04470402497 | Retrofit Shop Bays For 10 Yard Trucks | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
1007 | 1015 | 1254 | 1010 | 04470402498 | Shop Lighting Upgrades | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1008 | 1016 | 1255 | 1011 | 19470402499 | Remodel Inside Of Building | Capital Repairs | Highway Trans. Fund 6 | 65000 | 65000
1009 | 1017 | 1256 | 1012 | 19470402500 | Replace Overhead Doors | Capital Construction | Highway Trans. Fund 6 | 113000 | 113000
1012 | 1020 | 1257 | 1013 | 02470402503 | Remodel Old Sign Shop Into A Fitness Center | Capital Construction | Highway Trans. Fund 6 | 831000 | 831000
1013 | 1021 | 1258 | 1014 | 06470402504 | Paint Exterior Walls | Capital Repairs | Highway Trans. Fund 6 | 21000 | 21000
1014 | 1022 | 1259 | 1015 | 13470402505 | Paint Exterior Structure Of Fuel Canopy | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
1015 | 1023 | 1260 | 1016 | 04470402506 | Lighting Upgrades | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1016 | 1024 | 1261 | 1017 | 04470402507 | Retrofit Shop Bays For 10 Yard Trucks | Capital Construction | Highway Trans. Fund 6 | 100000 | 100000
1017 | 1025 | 1262 | 1018 | 19470402508 | Install Overhead Door Operators & Gate | Capital Repairs | Highway Trans. Fund 6 | 83000 | 83000
1018 | 1026 | 1263 | 1019 | 19470402509 | Replace VCT Flooring And Paint Interior | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1019 | 1027 | 1264 | 1020 | 18470402510 | Modular Furniture Installation | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1023 | 1031 | 1266 | 1021 | 22470402514 | Relocate Generator From Freer | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1024 | 1032 | 1267 | 1022 | 22470402515 | Men's Restroom Renovation | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
1025 | 1033 | 1268 | 1023 | 05470402516 | Repaint Exterior, Old Faded Peeling | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1026 | 1034 | 1269 | 1024 | 05470402517 | Repaint Exterior, Old Faded Peeling | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1027 | 1035 | 1270 | 1025 | 13470402518 | Paint Interior Structure Of Equip Shed | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1028 | 1036 | 1271 | 1026 | 22470402519 | Men's Restroom Renovation | Capital Repairs | Highway Trans. Fund 6 | 24000 | 24000
1029 | 1037 | 1272 | 1027 | 22470402520 | Replace Breakroom Flooring | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1030 | 1038 | 1273 | 1028 | 20470402521 | Replace AV Electrical Circuit | Capital Repairs | Highway Trans. Fund 6 | 1500 | 0
1034 | 1042 | 1274 | 1029 | 20470402525 | Remodel Rest Rooms & Wall Repair | Capital Repairs | Highway Trans. Fund 6 | 54000 | 54000
1036 | 1044 | 1275 | 1030 | 20470402527 | Replace Siding And Roofing | Capital Repairs | Highway Trans. Fund 6 | 65000 | 65000
1037 | 1045 | 1276 | 1031 | 20470402528 | Upgrade Electrical | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1038 | 1046 | 1277 | 1032 | 12470402529 | New Carpet/VCT | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1039 | 1047 | 1278 | 1033 | 12470402530 | Paint Exterior | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1040 | 1048 | 1279 | 1034 | 12470402531 | Reconfigure Cubicles (Space Management) | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1042 | 1050 | 1280 | 1035 | 22470402533 | Administration: Nail Down Spanish Tiles; Remove/Replace Broken Spanish Tiles | Capital Construction | Highway Trans. Fund 6 | 120000 | 120000
1043 | 1051 | 1281 | 1036 | 22470402534 | Remove Worn Out Existing VCT Flooring & Replace Ceramic Tile | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
1044 | 1052 | 1282 | 1037 | 22470402535 | Retrofit To Video Teleconference Room | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1045 | 1053 | 1283 | 1038 | 22470402536 | Bat Issues (Clean Up And Resolution) | Capital Construction | Highway Trans. Fund 6 | 300000 | 300000
1046 | 1054 | 1284 | 1039 | 22470402537 | Minor Restrooms Renovation | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
1047 | 1055 | 1285 | 1040 | 22470402538 | Exterior Painting | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1048 | 1056 | 1286 | 1041 | 22470402539 | Carpet Replacement | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1049 | 1057 | 1287 | 1042 | 22470402540 | Modular Unit (12) | Capital Repairs | Highway Trans. Fund 6 | 96000 | 96000
1050 | 1058 | 1288 | 1043 | 15470402541 | Proportionate Share Of 1St Floor Renovation | Capital Construction | Highway Trans. Fund 6 | 1000000 | 1000000
1051 | 1059 | 1289 | 1044 | 10470402542 | Demo Warehouse Office | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1052 | 1060 | 1290 | 1045 | 10470402543 | Install New Elevator | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
1054 | 1062 | 1292 | 1046 | 13470402545 | Paint Interior Office | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
1055 | 1063 | 1293 | 1047 | 13470402546 | Sealing Exterior Block Walls | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1056 | 1064 | 1294 | 1048 | 13470402547 | Paint Exterior Structure Of Fuel Canopy | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
1057 | 1065 | 1295 | 1049 | 13470402548 | Replace Wash Rack Canopy | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1058 | 1066 | 1296 | 1050 | 16470402549 | Install Storm Shutters On All Windows And Doors | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1059 | 1067 | 1297 | 1051 | 16470402550 | Paint Exterior Walls At Shop - Corpus Christi DHQ | Capital Repairs | Highway Trans. Fund 6 | 27500 | 27500
1060 | 1068 | 1298 | 1052 | 24470402551 | Install LED Lighting In Wall Packs | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
1061 | 1069 | 1299 | 1053 | 24470402552 | Install Vestabule / Canopy Near Breakroom | Capital Repairs | Highway Trans. Fund 6 | 36000 | 36000
1062 | 1070 | 1300 | 1054 | 24470402553 | Install Vestibule Front And Rear, Lobby Entries | Capital Repairs | Highway Trans. Fund 6 | 48000 | 48000
1065 | 1073 | 1301 | 1055 | 05470402556 | New VCT Floor | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1066 | 1074 | 1302 | 1056 | 15470402557 | Interior LED Lighting Upgrade | Capital Repairs | Highway Trans. Fund 6 | 7500 | 7500
1067 | 1075 | 1303 | 1057 | 15470402558 | Raise Truck Wash Canopy | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1068 | 1076 | 1304 | 1058 | 15470402559 | Retrofit Equipment Bay For Enclosed Climate Control LED Storage | Capital Repairs | Highway Trans. Fund 6 | 2000 | 2000
1069 | 1077 | 1305 | 1059 | 09470402560 | Upgrade Shop And Office | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1070 | 1078 | 1306 | 1060 | 13470402561 | Level Building & Repair Exterior Cracks In Brick | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1071 | 1079 | 1307 | 1061 | 13470402562 | Level Building (Area Engineers Bldg) | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1073 | 1081 | 1308 | 1062 | 17470402564 | Redo HVAC/Vent/Pipes | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1076 | 1084 | 1309 | 1063 | 05470402567 | Repaint Exterior | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1077 | 1085 | 1310 | 1064 | 03470402568 | Renovate Building For Storage | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1078 | 1086 | 1311 | 1065 | 25470402569 | Convert Truck Barn To Drive Thru, New Heaters In Truck Barn | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
1082 | 1090 | 1312 | 1066 | 05470402573 | Electrical Up-Grade Panel To Switches,Light Plug | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
1086 | 1094 | 1314 | 1067 | 15470402577 | Interior Paint | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1087 | 1095 | 1315 | 1068 | 38470402578 | Building Renovations | Capital Construction | Highway Trans. Fund 6 | 430000 | 430000
1088 | 1096 | 1316 | 1069 | 38470402579 | New Epoxy Flooring In Hangars 2,3 And 4 | Capital Construction | Highway Trans. Fund 6 | 210000 | 210000
1092 | 1100 | 1317 | 1070 | 16470402583 | Paint Interior Walls At Vehicle Titles And Registration - Corpus Christi DHQ | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
1096 | 1104 | 1319 | 1071 | 13470402587 | Interior Renovation (Floors, Ceiling, & Ac Ducts) | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1103 | 1111 | 1320 | 1072 | 20470402594 | Rest Room/Shower/Ac/Water Heater | Capital Repairs | Highway Trans. Fund 6 | 9500 | 9500
1104 | 1112 | 1321 | 1073 | 17470402595 | Renovate Maintenance Building | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
1105 | 1113 | 1322 | 1074 | 17470402596 | Replace Fuel Canopy - Bryan AEM | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1107 | 1115 | 1324 | 1075 | 25470402598 | Convert Truck Barn To Drive Thru, New Heaters In Truck Barn | Capital Construction | Highway Trans. Fund 6 | 200000 | 200000
1108 | 1116 | 1325 | 1076 | 24470402599 | Install New Front Doors (Building ) And Secure The Lobby Area | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1109 | 1117 | 1326 | 1077 | 24470402600 | Modify Interior Doorway, At Stockroom Forklift Access. | Capital Repairs | Highway Trans. Fund 6 | 5900 | 5900
1110 | 1118 | 1327 | 1078 | 24470402601 | Building Renovations | Capital Construction | Highway Trans. Fund 6 | 120000 | 120000
1112 | 1120 | 1328 | 1079 | 24470402603 | Larger Restroom In Our Maintenance Section | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1113 | 1121 | 1329 | 1080 | 02470402604 | Emergency Generator At Intelligent Transportation Management Center - Fort Worth DHQ | Capital Construction | Highway Trans. Fund 6 | 120000 | 120000
1114 | 1122 | 1330 | 1081 | 22470402605 | Interior & Exterior Painting & Sheet Metal Painting | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1115 | 1123 | 1331 | 1082 | 22470402606 | Overhead Projector & Electrical | Capital Repairs | Highway Trans. Fund 6 | 2500 | 2500
1116 | 1124 | 1332 | 1083 | 38470402607 | Interior Renovations | Capital Construction | Highway Trans. Fund 6 | 180000 | 180000
1118 | 1126 | 1333 | 1084 | 09470402609 | Upgrade Lab | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1119 | 1127 | 1334 | 1085 | 09470402610 | Replace Plumbing | Capital Repairs | Highway Trans. Fund 6 | 12000 | 12000
1120 | 1128 | 1335 | 1086 | 13470402611 | Painting Interior Structure Of Equip Shed | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1121 | 1129 | 1336 | 1087 | 16470402612 | Install Redundant 2000 Gallon Diesel Tank To Existing Fuel Island | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1122 | 1130 | 1337 | 1088 | 18470402613 | Upgrade Electrical | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1124 | 1132 | 1338 | 1089 | 13470402615 | Replace Tin & Paint Exterior Struct Of Wash Rack | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1125 | 1133 | 1339 | 1090 | 13470402616 | Paint Exterior Structure Of Fuel Canopy | Capital Repairs | Highway Trans. Fund 6 | 5000 | 5000
1127 | 1135 | 1341 | 1091 | 19470402618 | Remodel Inside Of Building | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1128 | 1136 | 1342 | 1092 | 19470402619 | Restroom Upgrades | Capital Construction | Highway Trans. Fund 6 | 181000 | 151000
1134 | 1142 | 1343 | 1093 | 17470402625 | Close In Part Of Shed For Work Area | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1135 | 1143 | 1344 | 1094 | 22470402626 | Install Interior Lighting | Capital Repairs | Highway Trans. Fund 6 | 25000 | 25000
1136 | 1144 | 1345 | 1095 | 22470402627 | Renovation Conference Room | Capital Construction | Highway Trans. Fund 6 | 150000 | 150000
1137 | 1145 | 1346 | 1096 | 22470402628 | Renovate Maintenance Facility | Capital Construction | Highway Trans. Fund 6 | 125000 | 125000
1138 | 1146 | 1347 | 1097 | 22470402629 | Retrofit Existing Office Space | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1143 | 1151 | 1348 | 1098 | 16470402634 | Repair Plumbing System At Truck Wash Bay - Kingsville MNT | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1144 | 1152 | 1349 | 1099 | 16470402635 | Repair Plumbing System At Truck Wash Bay - Robstown Maintenance | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1145 | 1153 | 1350 | 1100 | 22470402636 | Bay Wash Repairs | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1149 | 1157 | 1352 | 1101 | 12470402640 | Renovate Restrooms (Locker Rooms) | Capital Repairs | Highway Trans. Fund 6 | 42000 | 42000
1150 | 1158 | 1353 | 1102 | 12470402641 | Replace Emergency Exit Signage | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
1151 | 1159 | 1354 | 1103 | 12470402642 | Upgrade Lighting (LED) | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
1155 | 1163 | 1356 | 1104 | 17470402646 | New Fuel Canopy - Hearne AEM | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1157 | 1165 | 1358 | 1105 | 16470402648 | Install Electrical Wiring - Alice AEM | Capital Repairs | Highway Trans. Fund 6 | 40000 | 40000
1159 | 1167 | 1360 | 1106 | 12470402650 | Renovate Interior | Capital Construction | Highway Trans. Fund 6 | 500000 | 500000
1160 | 1168 | 1361 | 1107 | 22470402651 | Demo (D) And Install (I) Of 2 Lamp T8 Light Fixture (D-2 & I-6 @ Fueling Station; D-57 & I-45 @ Warehouse; And D-39 & I-31 @ MNT Vehicle | Capital Repairs | Highway Trans. Fund 6 | 18000 | 18000
1163 | 1171 | 1362 | 1108 | 15470402654 | Interior Paint | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1164 | 1172 | 1363 | 1109 | 15470402655 | Retrofit Shop Bay To Meeting Room | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1165 | 1173 | 1364 | 1110 | 38470402656 | Retrofit Of Existing Exterior Light Fixture | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1166 | 1174 | 1365 | 1111 | 38470402657 | EOC Technology Renovation (Electronics) | Capital Repairs | Highway Trans. Fund 6 | 60000 | 60000
1167 | 1175 | 1366 | 1112 | 38470402658 | Retrofit Of Existing Exterior Light Fixture | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1168 | 1176 | 1367 | 1113 | 03470402659 | Upgrade Electrical | Capital Repairs | Highway Trans. Fund 6 | 80000 | 80000
1169 | 1177 | 1368 | 1114 | 16470402660 | Install Storm Shutters On All Windows And Doors | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1170 | 1178 | 1369 | 1115 | 11470402661 | Upgrade Interior Lighting | Capital Repairs | Highway Trans. Fund 6 | 15000 | 15000
1174 | 1182 | 1370 | 1116 | 17470402665 | Add Awning To Shop Building | Capital Repairs | Highway Trans. Fund 6 | 35000 | 35000
1175 | 1183 | 1371 | 1117 | 17470402666 | Administration Bldg Foundation Repair | Capital Repairs | Highway Trans. Fund 6 | 50000 | 50000
1176 | 1184 | 1372 | 1118 | 17470402667 | Awnings Between Buildings W/ Lights | Capital Repairs | Highway Trans. Fund 6 | 30000 | 30000
1179 | 1187 | 1374 | 1119 | 17470402671 | New Fuel Canopy | Capital Repairs | Highway Trans. Fund 6 | 45000 | 45000
1180 | 1188 | 1375 | 1120 | 17470402672 | Overhead Crane Shops | Capital Repairs | Highway Trans. Fund 6 | 75000 | 75000
1181 | 1189 | 1376 | 1121 | 17470402673 | Paint Signal Warehouse Walls | Capital Repairs | Highway Trans. Fund 6 | 10000 | 10000
1182 | 1190 | 1377 | 1122 | 17470402674 | Repair Admin Building Water Intrusion | Capital Repairs | Highway Trans. Fund 6 | 20000 | 20000
1184 | 1192 | 1378 | 1123 | 21470402676 | Building Finish Out | Capital Construction | Highway Trans. Fund 6 | 120000 | 120000
1185 | 1193 | 1379 | 1124 | 38470402678 | Emergency Repairs - Statewide | Safety/Security | Highway Trans. Fund 6 | 50866849 | 53108324.68
SUBTOTAL PROJECTS NOT FUNDED WITH DM | [7 empty] | 147935549 | 150218524.68
805 | 813 | 1118 | 1125 | 13470402294 | Replace Flooring |  | Other Funds Identified | 10000 | -10000
716 | 725 | 1046 | 1126 | 15470402205 | Exterior Paint - Project done with Other Funds |  | Other Funds Identified | 15000 | -15000
SUBTOTAL PROJECTS CHANGED TO OTHER FUNDING SOURCE | [7 empty] | 25000 | -25000
PROJECTS BELOW WERE REMOVED OR CANCELLED FROM LIST
Removed | R1 | R1 | R1 | 38470402968 | Condition Assessment |  |  | 5000000 | -5000000
Removed | R2 | R2 | R2 | 38470402969 | Condition Assessment Software |  |  | 1000000 | -1000000
531 | 541 | R5 | R3 | 01470402020 | Demolish Existing Building |  |  | 29500 | -29500
156 | R17 | R6 | R4 | 03470401638 | In-Ground Shelter |  |  | 144125 | -144125
#N/A | 206 | R108 | R5 | 03470402987 | Lift Station Grinder Pump Replacements |  |  | 0 | 0
53 | R19 | R7 | R6 | 04470401642 | Upgrade Security (C-CURE) |  |  | 350000 | -350000
340 | 352 | R8 | R7 | 04470401829 | Sprinkler System Repairs |  |  | 8000 | -8000
189 | 70 | R9 | R8 | 05470401680 | Retrofit Existing Gate Opener W/C-Cure |  |  | 18000 | -18000
96 | 103 | R10 | R9 | 05470401737 | Install New Gate Opener To Existing Gate |  |  | 6500 | -6500
305 | 317 | 746 | R10 | 05470401794 | Replace Roof |  |  | 40000 | -40000
654 | 664 | R11 | R11 | 05470402143 | Install Exit Loops |  |  | 2500 | -2500
781 | 789 | 1097 | R12 | 05470402270 | Remove in ground hydraulic lift - Completed w/District funds Remove |  |  | 3000 | -3000
1084 | 1092 | 1313 | R13 | 05470402575 | Remove In-Ground Hydraulic Floor Lift |  |  | 3000 | -3000
Removed | R4 | R12 | R14 | 06470401497 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
Removed | R6 | R13 | R15 | 06470401515 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
Removed | R8 | R14 | R16 | 06470401525 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
Removed | R12 | R15 | R17 | 06470401555 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
232 | R16 | R16 | R18 | 06470401616 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
323 | 335 | 753 | R19 | 06470401812 | Install Motion Sensors On Install Automatic Gate |  |  | 1500 | -1500
350 | 362 | R17 | R20 | 06470401839 | Paint Asphalt Tank Bases And Hardware. Deteriorating Paint And Rusting Steel |  |  | 10000 | -10000
354 | 366 | R18 | R21 | 06470401843 | Repair Irrigation Systems |  |  | 5000 | -5000
395 | 407 | R19 | R22 | 06470401884 | Replace Irrigation System For New Yard Design |  |  | 10000 | -10000
404 | 416 | R20 | R23 | 06470401893 | Repair Irrigation Systems |  |  | 5000 | -5000
451 | 461 | R21 | R24 | 06470401940 | Repair Irrigation Systems |  |  | 5000 | -5000
456 | 466 | R22 | R25 | 06470401945 | Repair Irrigation Systems |  |  | 5000 | -5000
467 | 477 | R23 | R26 | 06470401956 | Repair Irrigation Systems |  |  | 5000 | -5000
584 | 594 | R24 | R27 | 06470402073 | Repair/Replace Atg System On Above Ground Fuel Tanks |  |  | 12000 | -12000
585 | 595 | R25 | R28 | 06470402074 | Seal Roof Penetrations |  |  | 3000 | -3000
714 | R29 | R26 | R29 | 06470402203 | Repair/Replace Atg System On Above Ground Fuel Tanks |  |  | 12000 | -12000
792 | 800 | R27 | R30 | 06470402281 | Upgrade Rain Gutters |  |  | 7000 | -7000
1162 | 1170 | R28 | R31 | 06470402653 | Paint Cat-Walk |  |  | 10000 | -10000
341 | 353 | R29 | R32 | 07470401830 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
344 | 356 | 763 | R33 | 07470401833 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
347 | 359 | 766 | R34 | 07470401836 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
349 | 361 | 768 | R35 | 07470401838 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
351 | 363 | 769 | R36 | 07470401840 | Demolish Old Asphalt Storage Tank |  |  | 30000 | -30000
353 | 365 | 771 | R37 | 07470401842 | Replace Old Asphalt Storage Tank |  |  | 122000 | -122000
375 | 387 | R30 | R38 | 07470401864 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
378 | 390 | 788 | R39 | 07470401867 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
397 | 409 | R31 | R40 | 07470401886 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
399 | 411 | 803 | R41 | 07470401888 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
416 | 428 | 817 | R42 | 07470401905 | Replace Old Asphalt Storage Tank |  |  | 122000 | -122000
431 | 443 | R32 | R43 | 07470401920 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
433 | 445 | 831 | R44 | 07470401922 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
462 | 472 | 853 | R45 | 07470401951 | Demolish Old Asphalt Storage Tank |  |  | 30000 | -30000
468 | 478 | R33 | R46 | 07470401957 | Demolish Old Asphalt Storage Tank |  |  | 15000 | -15000
471 | 481 | 859 | R47 | 07470401960 | Replace Old Asphalt Storage Tank |  |  | 61000 | -61000
112 | R13 | R34 | R48 | 08470401578 | Replace Roof |  |  | 40000 | -40000
113 | R14 | R35 | R49 | 08470401579 | Modifications/Upgrade HVAC |  |  | 120000 | -120000
48 | R15 | R36 | R50 | 08470401580 | Upgrade Security (C-CURE) |  |  | 350000 | -350000
945 | 953 | R37 | R51 | 08470402436 | Install Floor Tile |  |  | 18000 | -18000
946 | 954 | R38 | R52 | 08470402437 | Level Wash Bay |  |  | 1500 | -1500
949 | 957 | R39 | R53 | 08470402440 | Upgrade Power Washer Building |  |  | 2500 | -2500
1133 | 1141 | R40 | R54 | 08470402624 | Install Double Pane Glass Windows In Store Front Entry Area |  |  | 4500 | -4500
#N/A | 146 | 267 | R55 | 08470402982 | Spalling Concrete hazard - Add approved 1/5/16 Soloman create schedule..DUPLICATE WITH PROJECT ID 08-2983 |  |  | 0 | 0
27 | R7 | R41 | R56 | 09470401519 | Upgrade Security (C-CURE) |  |  | 350000 | -350000
284 | 296 | R42 | R57 | 09470401772 | Replace Roof |  |  | 350000 | -350000
182 | 163 | 183 | R58 | 11470401671 | Replace Boiler At Warehouse-Count as one project (combined with /11-1494 ) |  |  | 45000 | -45000
190 | R21 | R43 | R59 | 11470401682 | Replace Emergency Generator |  |  | 38000 | -38000
1141 | 1149 | R44 | R60 | 11470402632 | Replace Fuel Dispensers |  |  | 20000 | -20000
#N/A | 144 | 195 | R61 | 11470402981 | Foundation repair - Project is same as PROJ ID 11470402307 |  |  | 0 | 0
1041 | 1049 | R45 | R62 | 12470402532 | Renovate Breakroom |  |  | 5000 | -5000
158 | R18 | R46 | R63 | 13470401640 | Replace APU (Generator) |  |  | 10000 | -10000
495 | 505 | R47 | R64 | 13470401984 | Replace Asphalt Tank Berm |  |  | 10000 | -10000
738 | 746 | R48 | R65 | 13470402227 | Paint Exterior Structure Of Fuel Canopy |  |  | 5000 | -5000
1123 | 1131 | R49 | R66 | 13470402614 | Replace Tin At Mechanic Shop |  |  | 7000 | -7000
60 | 87 | R50 | R67 | 15470401690 | Replace Roof |  |  | 100000 | -100000
325 | 337 | 349 | R68 | 15470401814 | Replace Roof |  |  | 100000 | -100000
1003 | 1011 | R51 | R69 | 15470402494 | Paint, Carpet Replacement |  |  | 20000 | -20000
165 | 128 | R52 | R70 | 16470401649 | Replace Existing Security And Access Control System To C-Cure |  |  | 300000 | -300000
169 | 171 | R53 | R71 | 16470401654 | Upgrade HQ Campus Emergency Generator |  |  | 200000 | -200000
74 | R24 | R54 | R72 | 16470401708 | Replace Roof |  |  | 300000 | -300000
88 | R27 | R55 | R73 | 16470401728 | Replace Roof At Area Engineer And Maintenance - Corpus Christi AEM |  |  | 24000 | -24000
89 | R28 | R56 | R74 | 16470401729 | Replace\New Security Fence - Corpus Christi AEM |  |  | 17000 | -17000
523 | 533 | 190 | R75 | 16470402012 | Replace 2 Existing Fuel Dispensers At The Fuel Station - Merged into 16-1913 |  |  | 12000 | -12000
865 | 873 | 326 | R76 | 16470402356 | Replace Flooring In Office Building And Paint Walls | Capital Repairs |  | 25000 | -25000
903 | 911 | R57 | R77 | 16470402394 | Replace\New Electrical Panel At Right Of Way - Corpus Christi DHQ |  |  | 15000 | -15000
962 | 970 | R58 | R78 | 16470402453 | Replace Ceiling Tiles In Office Building |  |  | 7500 | -7500
963 | 971 | 191 | R79 | 16470402454 | Replace 2 Existing Dual Product Fuel Dispensers At The Fuel Station - Merged into 16-1913 |  |  | 15000 | -15000
966 | 974 | R59 | R80 | 16470402457 | Replace Ceilings At Area Engineer And Maintenance - Sinton AEM |  |  | 7500 | -7500
972 | 980 | 328 | R81 | 16470402463 | Replace Flooring At Maintenance - Rockport MNT |  |  | 15000 | -15000
1158 | 1166 | 1359 | R82 | 16470402649 | Repair Sewer System - Alice AEM |  |  | 10000 | -10000
628 | 638 | 204 | R83 | 17470402117 | Upgrade HVAC System |  |  | 20000 | -20000
629 | 639 | R60 | R84 | 17470402118 | Improve Lighting In Yard/Shed |  |  | 5000 | -5000
633 | 643 | R82 | R85 | 17470402122 | Cameron Maintenance Office |  |  | 25000 | -25000
670 | 680 | R61 | R86 | 17470402159 | Demolish Old Ae Building |  |  | 12500 | -12500
671 | 681 | R62 | R87 | 17470402160 | Improve Lighting In Yard/Shed |  |  | 5000 | -5000
687 | 697 | R63 | R88 | 17470402176 | Replace Gutters |  |  | 5000 | -5000
918 | 926 | 1199 | R89 | 17470402409 | Upgrade Lighting In Washbay-CANCELLED COMPLETED BY DISTRICT |  |  | 5000 | -5000
920 | 928 | R64 | R90 | 17470402411 | Improve Lighting In Yard/Shed |  |  | 5000 | -5000
1074 | 1082 | R65 | R91 | 17470402565 | Redo Lighting In Washbay |  |  | 5000 | -5000
1075 | 1083 | R66 | R92 | 17470402566 | Replace Ceiling Tiles |  |  | 10000 | -10000
1130 | 1138 | R67 | R93 | 17470402621 | Improve Lighting In Yard/Shed |  |  | 5000 | -5000
1131 | 1139 | R68 | R94 | 17470402622 | Install Electric Door Openers For Roll-Up Doors |  |  | 7500 | -7500
1132 | 1140 | R69 | R95 | 17470402623 | Replace Windows On Storage Shed |  |  | 5000 | -5000
1152 | 1160 | 245 | R96 | 17470402643 | Add Network Connections To Lab Area |  |  | 7500 | -7500
1177 | 1185 | 1373 | R97 | 17470402669 | Install A/C System To HQ Warehouse - CANCELLED AC included in a portion of bldg. |  |  | 25000 | -25000
1183 | 1191 | R70 | R98 | 17470402675 | Upgrade Used Oil & Antifreeze Containers |  |  | 5000 | -5000
42 | R10 | R71 | R99 | 18470401545 | Relocate And Add HVAC To Break Room |  |  | 15000 | -15000
44 | R11 | R72 | R100 | 18470401547 | Fence - Repair Chain Link/Top Rail At Easement |  |  | 10000 | -10000
187 | R20 | R73 | R101 | 18470401676 | New Generator - Diesel |  |  | 25000 | -25000
311 | 323 | R74 | R102 | 18470401800 | New Generator - Diesel |  |  | 15000 | -15000
358 | 370 | R75 | R103 | 18470401847 | Parking Lot Striping |  |  | 5000 | -5000
368 | 380 | R76 | R104 | 18470401857 | Parking Lot Striping |  |  | 20000 | -20000
439 | 451 | R77 | R105 | 18470401928 | Parking Lot Striping |  |  | 10000 | -10000
494 | 504 | R78 | R106 | 18470401983 | Parking Lot Striping |  |  | 10000 | -10000
510 | 520 | R79 | R107 | 18470401999 | Parking Lot Striping |  |  | 10000 | -10000
617 | 627 | R81 | R108 | 18470402106 | Restroom Partitions Replaced |  |  | 3000 | -3000
651 | 661 | R83 | R109 | 18470402140 | Restroom Partitions Replacement - Men's Restroom |  |  | 1500 | -1500
1010 | 1018 | R84 | R110 | 18470402501 | Analysis By Engineering Consultant |  |  | 45000 | -45000
1021 | 1029 | R85 | R111 | 18470402512 | Countertops - Restrooms On 4Th Floor |  |  | 5000 | -5000
1 | 140 | R4 | R112 | 19470401488 | Install LED Parking Lot Lighting |  |  | 85000 | -85000
2 | R3 | R3 | R113 | 19470401489 | Upgrade Security (C-CURE) |  |  | 350000 | -350000
39 | R9 | R86 | R114 | 20470401542 | Install Card Reader Access |  |  | 12000 | -12000
151 | 69 | 274 | R115 | 20470401632 | Fence Repairs |  |  | 9000 | -9000
265 | 277 | R87 | R116 | 20470401753 | Rehab Metal Roofing |  |  | 95000 | -95000
365 | 377 | R88 | R117 | 20470401854 | Remove Out Of Service Emulsion, Linseed Oil & Asts |  |  | 20000 | -20000
412 | 424 | R89 | R118 | 20470401901 | Remove Out Of Service Emulsion, Linseed Oil & Asts |  |  | 20000 | -20000
746 | 754 | R90 | R119 | 20470402235 | Paint Flag Pole |  |  | 3000 | -3000
747 | 755 | R91 | R120 | 20470402236 | Rebuild Overhead Door (10) |  |  | 4000 | -4000
806 | 814 | 324 | R121 | 20470402295 | Asbestos Abatement 8-17-16 cancelled during scrub |  |  | 5000 | -5000
1031 | 1039 | R92 | R122 | 20470402522 | Clean Fuel Tanks |  |  | 4000 | -4000
1091 | 1099 | R93 | R123 | 20470402582 | Repair Heating System |  |  | 7500 | -7500
1098 | 1106 | 391 | R124 | 20470402589 | Abate Floor Tile 8-17-16 cancelled during scrub |  |  | 10000 | -10000
75 | 122 | 321 | R125 | 21470401710 | Replace Generator- Merged into 21-1538 |  |  | 40000 | -40000
77 | 124 | 334 | R126 | 21470401712 | Replace Generator- Merged into 21-1538 |  |  | 40000 | -40000
82 | R26 | R94 | R127 | 21470401721 | Replace Generator |  |  | 15000 | -15000
1171 | 1179 | R95 | R128 | 21470402662 | Bird Net For Truck Wash And Equip. Shed |  |  | 1000 | -1000
1172 | 1180 | R96 | R129 | 21470402663 | Repaint Generator |  |  | 500 | -500
1173 | 1181 | R97 | R130 | 21470402664 | Repair Wall Packs |  |  | 2500 | -2500
274 | 286 | 361 | R131 | 22470401762 | Furnish/Install HVAC -- 6/6/16 Per Byron this project is cancelled. |  |  | 100000 | -100000
443 | 455 | 838 | R132 | 22470401932 | Upgrade Sprinkler System |  |  | 5000 | -5000
498 | 508 | R98 | R133 | 22470401987 | Flag Pole Lighting |  |  | 3000 | -3000
516 | 526 | R99 | R134 | 22470402005 | Parking Lot Striping |  |  | 30000 | -30000
179 | 94 | R100 | R135 | 23470401667 | Upgrade Security (C-CURE) |  |  | 350000 | -350000
65 | R23 | R101 | R136 | 24470401697 | Modifications/Upgrade Electrical |  |  | 150000 | -150000
79 | R25 | R102 | R137 | 24470401718 | Replace Roof |  |  | 285000 | -285000
345 | 357 | 764 | R138 | 24470401834 | Demolish Old Asphalt Storage Tank. |  |  | 8400 | -8400
463 | 473 | R103 | R139 | 24470401952 | Demolish Old Emulsion Tank |  |  | 8500 | -8500
506 | 516 | R104 | R140 | 24470401995 | Demolish Old Emulsion Tank |  |  | 8500 | -8500
507 | 517 | R105 | R141 | 24470401996 | Demolish Old Emulsion Tank |  |  | 8500 | -8500
952 | 960 | R106 | R142 | 24470402443 | Install Garage Door Openers |  |  | 7000 | -7000
610 | 620 | R80 | R143 | 25470402099 | Crowell Maintenance |  |  | 25000 | -25000
58 | R22 | R107 | R144 | 38470401688 | Modifications/Upgrade Electrical |  |  | 517000 | -517000
331 | 343 | 188 | R145 | 38470401820 | Upgrade Obsolete Johnson Control Panels |  |  | 30000 | -30000
SUBTOTAL PROJECTS REMOVED OR CANCELLED | [7 empty] | 12593525 | -12593525
TOTAL AY16/17 FUNDING ALLOCATION | [7 empty] | 200000000 | 200000000
Note on C5: Diana Miller: Priority based on Actual Start Sheet submissions followed by Forecast SS date.
Note on D5: Diana Miller: Priority based on Actual Start Sheet submissions followed by Forecast SS date.

## TxDOT 6.16
|  |  | Agency: | Texas Department of Transportation #601 |  |  | Legend: Used latest budget estimate available in order of 1. Contracted 2. Start Estimate 3. Current anticipated estimate. | Contracted Amt.
|  |  | Date: | 2016-05-31 |  |  |  | Start Estimate |  | 2016-06-15
Priority Audit Trail |  |  | Prepared by: | Diana Miller |  |  |  | Current Estimate | Project 100% Complete
|  |  | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q3 AY16) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Comment
Q1 | Q2 | Q3JOC Priority
#N/A | 1 | 1 | 15470402973 | NE Bexar Maintenance Office | Drainage Flume | Highway Trans. Fund 6 | 0 | 24120 | 2015-12-17 | 100% | 100% | 24120 | 24120 | 0
E3 | 2 | 2 | 03470402972 | District Headquarters | Foundation Repair at DHQ | Highway Trans. Fund 6 | 0 | 18000 | 2016-01-08 | 100% | 100% | 18000 | 18000 | 0
E4 | 3 | 3 | 03470402975 | Henrietta Maintenance Office | Stairs & Handicap Ramp for Mod Building | Highway Trans. Fund 6 | 0 | 24105 | 2016-02-18 | 100% | 100% | 24105 | 24105 | 0
E1 | 4 | 4 | 20470402970 | Beaumont District Headquarters | Remove and Install 10 and 8.5 ton Roof Top HVAC Units | Highway Trans. Fund 6 | 0 | 17650 | 2016-12-31 | 100% | 100% | 17650 | 17650 | 0
11 | 7 | 5 | 04470401499 | Dumas Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 12935.51 | 2016-05-31 | 100% | 100% | 12935.51 | 12935.51 | 0
20 | 5 | 6 | 04470401510 | Darouzett Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 12935.51 | 2016-05-31 | 100% | 100% | 12935.51 | 12935.51 | 0
22 | 6 | 7 | 04470401512 | Gruver Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 12935.52 | 2016-05-31 | 100% | 100% | 12935.52 | 12935.52 | 0
23 | 8 | 8 | 04470401513 | Panhandle Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 12000 | 12935.51 | 2016-05-31 | 100% | 100% | 12935.51 | 12935.51 | 0
10 | 9 | 9 | 08470401498 | Jayton Maintenance Office | New Perimeter Fence | Highway Trans. Fund 6 | 15000 | 22782 | 2016-03-14 | 100% | 100% | 22782 | 22782 | 0
38 | 23 | 10 | 20470401541 | Anahuac Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 7500 | 7580 | 2016-01-25 | 100% | 100% | 7580 | 7580 | 0 | AC is still under warranty, scope changed to fix controllers on four ton unit
40 | 10 | 11 | 20470401543 | Woodville Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 21177.75 | 2016-03-16 | 100% | 100% | 21177.75 | 21177.75 | 0
#N/A | 12 | 12 | 10470401428 | Tyler District Headquarters | Replace Roof On Shop | Highway Trans. Fund 6 | 500000 | 898100 | 2016-10-14 |  | 0% | 898100 | 0 | 898100 | 2/2/16 Addendum to increase estimate to $928K due to leaking and causing problems on the inside
21 | 13 | 13 | 04470401511 | Darouzett Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 11483.33 | 2016-04-15 | 100% | 100% | 11483.33 | 11483 | 0.33
24 | 14 | 14 | 04470401514 | Panhandle Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 11483.33 | 2016-04-15 | 100% | 100% | 11483.33 | 11483 | 0.33
37 | 15 | 15 | 04470401540 | Claude Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 11483.34 | 2016-04-15 | 100% | 100% | 11483.34 | 11483 | 0.34
#N/A | 16 | 16 | 02470402980 | Fort Worth District Headquarters | Replace Fuel Station Gas Pipeline | Highway Trans. Fund 6 | 0 | 31340 | 2016-02-03 | 100% | 100% | 31340 | 31340 | 0
19 | 47 | 17 | 38470401508 | Camp Hubbard State Headquarters | Upgrade Obsolete Johnson Control Panels | Highway Trans. Fund 6 | 30000 | 28310 | 2016-11-08 | 0% | 0% | 28310 | 0 | 28310
#N/A | 44 | 18 | 38470402974 | Camp Hubbard State Headquarters | Paving Overlay Parking Lot | Highway Trans. Fund 6 | 0 | 795000 | 2017-03-24 | 100% | 100% | 0 | 0 | 795000 | Project is being re-scoped.
#N/A | 17 | 19 | 38470402984 | Austin Maintenance Offices | Upgrade Security (C-CURE) Card Reader pedestals piece of this is now Proj ID #14470402984 | Highway Trans. Fund 6 | 0 | 96624 | 2016-05-12 | 0% | 0% | 96624 | 0 | 96624 | Part of Orig ID #14470401612
446 | 18 | 20 | 04470401935 | Pampa Area Engineer & Maintenance Office | Replace Fuel Pumps | Highway Trans. Fund 6 | 15000 | 17000 | 2016-04-19 | 0% | 0% | 17000 | 0 | 17000
450 | 19 | 21 | 04470401939 | Perryton Maintenance Office | Replace Fuel Pumps | Highway Trans. Fund 6 | 15000 | 17000 | 2016-04-19 | 0% | 0% | 17000 | 0 | 17000
230 | 20 | 22 | 14470401612 | Austin Maintenance Offices | Card Reader Pedestals for the Upgrade Security (C-CURE). Part of Orig ID #14470401612 | Highway Trans. Fund 6 | 1120000 | 60444 | 2016-09-05 | 0% | 0% | 60444 | 0 | 60444 | Part of Orig Proj ID #14470402984
34 | 22 | 23 | 16470401536 | San Patricio Co | Replace Existing Secuity Fence Around Perimeter Of Property | Highway Trans. Fund 6 | 150000 | 47998 | 2016-04-26 | 0% | 0% | 47998 | 0 | 47998
33 | 21 | 24 | 16470401535 | Nueces East | Replace Existing Secuity Fence Around Perimeter Of Property | Highway Trans. Fund 6 | 125000 | 54899 | 2016-06-24 | 0% | 0% | 54899 | 0 | 54899
31 | 25 | 25 | 16470401532 | Jim Wells Co. | Install Yard Illumination In Back Yard Area | Highway Trans. Fund 6 | 40000 | 47600 | 2016-07-14 | 0% | 0% | 47600 | 0 | 47600
32 | 26 | 26 | 16470401533 | Live Oak Co. | Install Exterior Lighting In Back Yard Area | Highway Trans. Fund 6 | 40000 | 64800 | 2016-07-14 | 0% | 0% | 64800 | 0 | 64800
185 | 27 | 27 | 18470401674 | Rockwall Maintenance Office | Apply Ceramic Roof Coating | Highway Trans. Fund 6 | 120000 | 74000 | 2016-07-08 | 100% | 0% | 0 | 0 | 74000
E2 | 24 | 28 | 01470402967 | Paris District Headquarters | Shop Floor Replacement | Highway Trans. Fund 6 | 0 | 70000 | 2016-08-31 | 100% | 0% | 0 | 0 | 70000
52 | 28 | 29 | 15470401602 | San Antonio District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 440000 | 2016-10-24 | 100% | 0% | 0 | 0 | 440000
51 | 29 | 30 | 06470401588 | Odessa District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 163331 | 2016-08-16 | 0% | 0% | 163331 | 0 | 163331
193 | 30 | 31 | 07470401686 | San Angelo District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 89400 | 2016-07-22 | 0% | 0% | 89400 | 0 | 89400
#N/A | 31 | 32 | 18470402978 | Dallas District Headquarters | Replace Chiller, provide temporary unit until work complete | Highway Trans. Fund 6 | 0 | 247496 | 2016-03-22 | 0% | 0% | 247496 | 0 | 247496
14 | 32 | 33 | 08470401502 | Gail Maintenance Office | AC Unit Needs Replacing (Old R22 Unit) | Highway Trans. Fund 6 | 7500 | 9701 | 2016-03-23 | 100% | 100% | 9701 | 9701 | 0
180 | 33 | 34 | 18470401669 | Waxahachie Area Engineer & Maintenance Office | HVAC - Split Unit (Meeting & Stock Rooms) | Highway Trans. Fund 6 | 10000 | 17240.7 | 2016-04-13 | 100% | 100% | 17240.7 | 17240.7 | 0
188 | 34 | 35 | 18470401677 | Rockwall Maintenance Office | HVAC - Upgrade Existing System | Highway Trans. Fund 6 | 15000 | 19795.4 | 2016-04-13 | 100% | 100% | 19795.4 | 19795.4 | 0
#N/A | 35 | 36 | 38470402989 | Austin - Riverside Annex II | Riverside 150 Datacenter UPS – approved to add as new for $795k. Warren will confirm with MEP that scope and estimate are good to go to start sheet. Warren & Art to prepare schedule. | Highway Trans. Fund 6 | 0 | 795000 | 2016-12-19 | 100% | 0% | 0 | 0 | 795000
118 | 36 | 37 | 07470401589 | Junction Area Engineer & Maintenance Office | New Roof | Highway Trans. Fund 6 | 16200 | 44134 | 2016-07-19 | 0% | 0% | 44134 | 0 | 44134
142 | 39 | 38 | 04470401619 | Canyon Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 0% | 0% | 12867 | 0 | 12867
144 | 40 | 39 | 04470401625 | Borger Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 0% | 0% | 12867 | 0 | 12867
61 | 51 | 40 | 04470401693 | Hereford Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-17 | 0% | 0% | 10950 | 0 | 10950
72 | 37 | 41 | 04470401704 | Perryton Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 15000 | 12867 | 2016-05-24 | 0% | 0% | 12867 | 0 | 12867
73 | 49 | 42 | 04470401705 | Perryton Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-17 | 0% | 0% | 10950 | 0 | 10950
84 | 53 | 43 | 04470401723 | Groom Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-17 | 0% | 0% | 10950 | 0 | 10950
93 | 38 | 44 | 04470401734 | Dalhart Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 12865 | 2016-05-24 | 0% | 0% | 12865 | 0 | 12865
145 | 126 | 45 | 04470401626 | Borger Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-17 | 0% | 0% | 10950 | 0 | 10950
146 | 42 | 46 | 04470401627 | Pampa Area Engineer & Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 0% | 0% | 12867 | 0 | 12867
147 | 127 | 47 | 04470401628 | Pampa Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-17 | 0% | 0% | 10950 | 0 | 10950
195 | 131 | 48 | 04470401691 | Canadian Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 10950 | 2016-06-20 | 0% | 0% | 10950 | 0 | 10950
196 | 41 | 49 | 04470401692 | Amarillo Area Engineer and Mainteannce Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 12867 | 2016-05-24 | 0% | 0% | 12867 | 0 | 12867
#N/A | 202 | 50 | 38470402988 | Cedar Park | New Discharge air temp sensors and HVAC | Highway Trans. Fund 6 | 0 | 133479.85 | 2016-10-03 | 100% | 0% | 0 | 0 | 133479.85
717 | 212 | 51 | 15470402206 | Seguin Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 0 | 24300 | 2016-04-08 | 100% | 100% | 24300 | 24300 | 0
17 | 43 | 52 | 38470401506 | Camp Hubbard State Headquarters | Replace Fence Along Mopac With Standard Fence | Highway Trans. Fund 6 | 45000 | 66250 | 2016-06-30 | 0% | 0% | 66250 | 0 | 66250
45 | 82 | 53 | 22470401549 | Brackettville | 3-Ton Standalone Unit (Duct Work, Vents, Air Handler, Etc) | Highway Trans. Fund 6 | 8000 | 13045.73 | 2016-03-18 | 100% | 100% | 13045.73 | 13045.73 | 0
64 | 75 | 54 | 20470401696 | Liberty Area Engineer & Maintenance Office | Replace HVAC Units | Highway Trans. Fund 6 | 20000 | 22500 | 2016-04-08 | 100% | 100% | 22500 | 22500 | 0
176 | 71 | 55 | 20470401663 | Port Arthur Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 8000 | 10752 | 2016-07-15 | 0% | 0% | 10752 | 0 | 10752
177 | 72 | 56 | 20470401664 | Port Arthur Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 18000 | 16500 | 2016-03-31 | 100% | 100% | 16500 | 16500 | 0
62 | 55 | 57 | 20470401694 | Kountze Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 42458 | 2016-08-19 | 0% | 0% | 42458 | 0 | 42458
150 | 89 | 58 | 20470401631 | Beaumont District Headquarters | A/C Unit Replacement | Highway Trans. Fund 6 | 85000 | 81928 | 2016-08-23 | 0% | 0% | 81928 | 0 | 81928
149 | 56 | 59 | 20470401630 | Beaumont Area Engineer & Maintenance Office | Install Gates | Highway Trans. Fund 6 | 16000 | 24999 | 2016-05-04 | 0% | 0% | 24999 | 0 | 24999
137 | 145 | 60 | 14470401613 | Georgetown AE/M, Bastrop AE/M, Mason MNT, Austin DHQ | New Generators/Upgrades | Highway Trans. Fund 6 | 425000 | 184921 | 2016-12-13 | 0% | 0% | 184921 | 0 | 184921 | New Generator/Upgrade---Split off of Project ID # 14470401613
1095 | 1103 | 61 | 02470402586 | Decatur Area Engineer & Maintenance Office | Replace Flooring At Area Engineer And Maintenance - Decatur Area Engineer And Maintenance | Highway Trans. Fund 6 | 10000 | 7830.7 | 2016-08-12 | 0% | 0% | 7830.7 | 0 | 7830.7
#N/A | #N/A | 62 | 14470402990 | Austin District Headquarters | Austin Dist. Elevator Project Addition - Approved to be added to program plan, not funded at this time. | Highway Trans. Fund 6 | 0 | 7000 | 2016-04-01 | 100% | 100% | 7000 | 7000 | 0
817 | 825 | 63 | 11470402307 | District Headquarters | Foundation Repairs | Highway Trans. Fund 6 | 40000 | 26400 | 2016-09-19 | 100% | 0% | 0 | 0 | 26400
#N/A | 50 | 64 | 15470402986 | Bandera Maintenance Office | SFMO - add door in cmu wall at the Bandera Maintenance Building | Highway Trans. Fund 6 | 0 | 23700 | 2016-04-16 | 100% | 100% | 23700 | 23700 | 0
55 | 93 | 65 | 16470401655 | Corpus Christi District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350222 | 2016-10-17 | 0% | 0% | 350222 | 0 | 350222
100 | 79 | 66 | 17470402668 | Bryan District Headquarters | Improve Lab Ventilation | Highway Trans. Fund 6 | 5000 | 334068 | 2016-11-11 | 0% | 0% | 334068 | 0 | 334068
111 | 66 | 67 | 08470401577 | Colorado City Maintenance Office | Replace AC Unit (R22 Unit) | Highway Trans. Fund 6 | 10000 | 13074 | 2016-05-30 | 0% | 0% | 13074 | 0 | 13074
178 | 58 | 68 | 20470401665 | Port Arthur Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 80000 | 47082 | 2016-08-09 | 0% | 0% | 47082 | 0 | 47082
7 | 61 | 69 | 11470401494 | Lufkin District Headquarters | Replace HVAC Units | Highway Trans. Fund 6 | 15000 | 78593 | 2016-07-21 | 0% | 0% | 78593 | 0 | 78593
66 | 159 | 70 | 07470401698 | San Angelo District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 220000 | 196428 | 2016-08-29 | 0% | 0% | 196428 | 0 | 196428
114 | 107 | 71 | 02470401581 | Fort Worth District Headquarters | Chiller Replacement | Highway Trans. Fund 6 | 200000 | 49296 | 2016-07-20 | 0% | 0% | 49296 | 0 | 49296
#N/A | #N/A | 72 | 12470402994 | Galveston Area Office - LaMarque | Replace HVAC system | Highway Trans. Fund 6 | 0 | 16896 | 2016-08-05 | 0% | 0% | 16896 | 0 | 16896
#N/A | 208 | 73 | 15470402988 | Bandera MNT | Bandera MNT Building structure - foundation | Highway Trans. Fund 6 | 0 | 24999 | 2016-05-02 | 0% | 0% | 24999 | 0 | 24999
57 | 45 | 74 | 21470401684 | Pharr District Headquarters/Area Engineer & Maintenance Office | HVAC With Study/Assessment | Highway Trans. Fund 6 | 300000 | 572000 | 2017-01-18 | 100% | 0% | 0 | 0 | 572000
99 | 46 | 75 | 21470401775 | Pharr District Headquarters | Complete Power Project (Single, Electrical Power Upgrade Project, To Encompass All Of The Electrical Issues To Include Study/Assessment) | Highway Trans. Fund 6 | 300000 | 231900 | 2017-03-17 | 100% | 0% | 0 | 0 | 231900
292 | 304 | 76 | 16470401781 | District Headquarters | Replace HVAC Unit At Vehicle Titles And Registration - Corpus Christi DHQ | Highway Trans. Fund 6 | 18000 | 21639 | 2016-05-19 | 100% | 100% | 21639 | 21639 | 0
309 | 321 | 77 | 16470401798 | Beeville Maintenance Office | Install Mini Split Condenser, Air Handler | Highway Trans. Fund 6 | 15000 | 19886 | 2016-04-27 | 100% | 100% | 19886 | 19886 | 0
71 | 76 | 78 | 08470401703 | Snyder Maintenance Office | Replace AC Unit (Old R22 Unit) | Highway Trans. Fund 6 | 7500 | 8338 | 2016-05-26 | 0% | 0% | 8338 | 0 | 8338
92 | 95 | 79 | 08470401733 | Aspermont Maintenance Office | Replace AC Unit (R22 Unit) | Highway Trans. Fund 6 | 7500 | 9306 | 2016-05-24 | 0% | 0% | 9306 | 0 | 9306
257 | 269 | 80 | 04470401745 | Amarillo (East) Area Engineer and Maintenance Facility | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 13200 | 2016-06-17 | 0% | 0% | 13200 | 0 | 13200
955 | 963 | 81 | 03470402446 | Vernon Area Engineer & Maintenance Office | Replace Flooring At Maintenance - Vernon Area Engineer And Maintenance | Highway Trans. Fund 6 | 15000 | 22253.67 | 2016-06-24 | 0% | 0% | 22253.67 | 0 | 22253.67
115 | 88 | 82 | 02470401582 | Fort Worth District Headquarters | Exterior Lighting | Highway Trans. Fund 6 | 30000 | 28424 | 2016-07-29 | 0% | 0% | 28424 | 0 | 28424
170 | 98 | 83 | 05470401656 | Plains Maintenance Office | New HVAC Relocate From Roof | Highway Trans. Fund 6 | 25000 | 8400 | 2016-07-22 | 0% | 0% | 8400 | 0 | 8400
394 | 406 | 84 | 06470401883 | Odessa Maintenance Office | Repair/Replace ATG System On Above Ground Fuel Tanks | Highway Trans. Fund 6 | 12000 | 10311 | #N/A | 0% | 0% | 10311 | 0 | 10311 | 3/29/16 this was moved above line to address the 2 fueling stations on this site. One was not needed. Project #06470402203 cancelled.
597 | 607 | 85 | 06470402086 | Stanton Maintenance Office | Repair/Replace ATG System On Above Ground Fuel Tanks | Highway Trans. Fund 6 | 12000 | 10646 | 2016-06-24 | 0% | 0% | 10646 | 0 | 10646
905 | 913 | 86 | 06470402396 | Iraan Maintenance Office | Repair/Replace ATG System On Above Ground Fuel Tanks | Highway Trans. Fund 6 | 12000 | 10321 | 2016-06-24 | 0% | 0% | 10321 | 0 | 10321
13 | 86 | 87 | 03470401501 | Bowie Maintenance Office | New Fencing | Highway Trans. Fund 6 | 50000 | 39750 | 2016-06-27 | 0% | 0% | 39750 | 0 | 39750
83 | 77 | 88 | 04470401722 | Groom Maintenance Office | HVAC Replacement | Highway Trans. Fund 6 | 8000 | 5350 | 2016-06-28 | 100% | 0% | 0 | 0 | 5350
186 | 92 | 89 | 18470401675 | Rockwall Maintenance Office | Fence - Repair/Replace Chain Link/Rails | Highway Trans. Fund 6 | 25000 | 90934 | 2016-06-17 | 0% | 0% | 90934 | 0 | 90934
1011 | 1019 | 90 | 18470402502 | District Headquarters | Countertops - Restrooms (Solid Surface) | Highway Trans. Fund 6 | 5000 | 23553.39 | 2016-07-01 | 0% | 0% | 23553.39 | 0 | 23553.39
694 | 704 | 91 | 02470402183 | District Headquarters | Replace\New Windows At Laboratory - Fort Worth DHQ | Highway Trans. Fund 6 | 20000 | 70396 | 2016-09-28 | 0% | 0% | 70396 | 0 | 70396
308 | 320 | 92 | 09470401797 | Hillsboro Area Engineer & Maintenance Office | Install Gate and Controls | Highway Trans. Fund 6 | 17000 | 10993.93 | 2016-05-25 | 0% | 0% | 10993.93 | 0 | 10993.93
#N/A | 100 | 93 | 19470402979 | District Headquarters | Escalated $30K from Restroom Upgrades in Proj #19470402619 | Highway Trans. Fund 6 | 0 | 2605.8 | 2016-07-07 | 0% | 0% | 2605.8 | 0 | 2605.8 | Phase 1 of Project ID: 19470402619
830 | 838 | 94 | 18470402320 | Rockwall Maintenance Office | Siding - Partial Replacement | Highway Trans. Fund 6 | 10000 | 4776.84 | 2016-05-25 | 0% | 0% | 4776.84 | 0 | 4776.84
#N/A | #N/A | 95 | 10470402998 | Henderson Maintenance Office | EMERGENCY HVAC Unit | Highway Trans. Fund 6 | 0 | 12953 | 2016-04-11 | 100% | 100% | 12953 | 12953 | 0
260 | 272 | 96 | 18470401748 | District Headquarters | Generator Replaced With Diesel | Highway Trans. Fund 6 | 15000 | 24894 | 2016-09-29 | 0% | 0% | 24894 | 0 | 24894
640 | 650 | 97 | 12470402129 | Angleton Area Engineer & Maintenance Office | New Carpet/VCT | Highway Trans. Fund 6 | 10000 | 10000 | 2016-07-06 | 100% | 0% | 0 | 0 | 10000
839 | 847 | 98 | 11470402329 | Lufkin Maintenance Office | Renovate Bathrooms | Highway Trans. Fund 6 | 40000 | 24000 | 2016-06-07 | 100% | 0% | 0 | 0 | 24000
#N/A | #N/A | 99 | 02470402997 | District Headquarters | Air Handler Replacement | Highway Trans. Fund 6 | 0 | 8242 | 2016-05-25 | 0% | 0% | 8242 | 0 | 8242
655 | 665 | 100 | 05470402144 | District Headquarters | New VCT Floor | Highway Trans. Fund 6 | 20000 | 19883.4 | 2016-07-29 | 0% | 0% | 19883.4 | 0 | 19883.4
652 | 662 | 101 | 18470402141 | District Headquarters | Window - Ceramic Coating (Warehouse/Facilities/Shop) | Highway Trans. Fund 6 | 15000 | 8785 | 2016-06-17 | 0% | 0% | 8785 | 0 | 8785
828 | 836 | 102 | 18470402318 | Rockwall Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 24690 | 2016-07-08 | 0% | 0% | 24690 | 0 | 24690
25 | 96 | 103 | 09470401517 | Waco District Headquarters | Fence in Front of Facility | Highway Trans. Fund 6 | 110000 | 28501 | 2016-08-31 | 100% | 0% | 0 | 0 | 28501
1063 | 1071 | 104 | 24470402554 | District Headquarters | Lab Dock Storage, Install Soffit Filler To Close Off Gap At Top. | Highway Trans. Fund 6 | 5000 | 2360 | 2016-05-23 | 100% | 100% | 2360 | 2360 | 0
943 | 951 | 105 | 12470402434 | Houston NE Area Engineer & Maintenance Office | Replace Gutter System | Highway Trans. Fund 6 | 10000 | 8500 | 2016-09-21 | 100% | 0% | 0 | 0 | 8500
1064 | 1072 | 106 | 12470402555 | Angleton Area Engineer & Maintenance Office | Replace Insulation (Laboratory) | Highway Trans. Fund 6 | 8000 | 4138.5 | 2016-05-26 | 100% | 100% | 4138.5 | 4138.5 | 0
#N/A | #N/A | 107 | 04470402995 | Amarillo District Headquarters | Sewer Line Replacement | Highway Trans. Fund 6 | 0 | 18708 | 2016-06-15 | 0% | 0% | 18708 | 0 | 18708
#N/A | 200 | 108 | 15470402985 | Seguin Warehouse and Seguin Mantenance Office | Fencing, gate operators, preliminarty asbestos testing. | Highway Trans. Fund 6 | 0 | 189301 | 2016-08-30 | 0% | 0% | 189301 | 0 | 189301
288 | 300 | 109 | 21470401777 | San Benito Area Engineer & Maintenance Office | Replace HVAC Units | Highway Trans. Fund 6 | 12000 | 8587.65 | 2016-05-18 | 100% | 100% | 8587.65 | 8587.65 | 0
306 | 318 | 110 | 10470401795 | South Tyler Area Engineer & Maintenance Office | Replace HVAC In Bldg. B | Highway Trans. Fund 6 | 15000 | 6550 | 2016-06-27 | 0% | 0% | 6550 | 0 | 6550
91 | 138 | 111 | 19470401731 | Carthage Maintenance Office | Replace HVAC Systems | Highway Trans. Fund 6 | 16000 | 19890 | 2016-06-21 | 100% | 0% | 0 | 0 | 19890
#N/A | #N/A | 112 | 10470403005 | Canton Maintenance | Replace HVAC Systems | Highway Trans. Fund 6 | 0 | 6450 | 2016-07-08 | 0% | 0% | 0 | 0 | 6450
101 | 133 | 113 | 05470401554 | Lubbock District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 191717.47 | 2016-09-30 | 0% | 0% | 191717.47 | 0 | 191717.47
41 | 73 | 114 | 25470401544 | Paducah Maintenance Office | New Electronic Gate To Yard, Redesign Parking Area | Highway Trans. Fund 6 | 35000 | 35000 | 2016-09-01 | 0% | 0% | 0 | 0 | 35000
313 | 325 | 115 | 22470401802 | La Pryor Maintenance Office | Replace Two HVAC Units | Highway Trans. Fund 6 | 15000 | 12858 | 2016-06-15 | 0% | 0% | 12858 | 0 | 12858
152 | 78 | 116 | 20470401633 | Beaumont District Headquarters | Install Gates & Install/Repair Fencing | Highway Trans. Fund 6 | 24000 | 21848 | 2016-07-08 | 0% | 0% | 21848 | 0 | 21848
539 | 549 | 117 | 11470402028 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 23250 | 2016-06-02 | 0% | 0% | 23250 | 0 | 23250
768 | 776 | 118 | 17470402257 | Brenham Area Engineer & Maintenance Office | Paint Building | Highway Trans. Fund 6 | 10000 | 4987.78 | 2016-09-05 | 0% | 0% | 4987.78 | 0 | 4987.78
136 | 60 | 119 | 14470401611 | Austin District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 365000 | 2017-03-14 | 100% | 0% | 0 | 0 | 365000
#N/A | 102 | 120 | 05470402987 | Lubbock District Headquarters | AE Office Mold Remediation | Highway Trans. Fund 6 | 0 | 2596.38 | 2016-11-10 | 0% | 0% | 2596.38 | 0 | 2596.38
413 | 425 | 121 | 20470401902 | District Headquarters | Replace Fuel Dispensers | Highway Trans. Fund 6 | 15000 | 14703 | 2016-06-23 | 0% | 0% | 14703 | 0 | 14703
386 | 398 | 122 | 08470401875 | District Headquarters | Sidewalks at the DMV Building Need to be Cut Out and Replaced in Various Areas | Highway Trans. Fund 6 | 7500 | 4950 | 2016-05-09 | 100% | 100% | 4950 | 4950 | 0
619 | 629 | 123 | 04470402108 | Claude Maintenance Office | New Overhead Doors | Highway Trans. Fund 6 | 15000 | 9460 | 2016-07-01 | 100% | 0% | 0 | 0 | 9460
620 | 630 | 124 | 04470402109 | Stratford Maintenance Office | Install Overhead Doors and Openers | Highway Trans. Fund 6 | 25000 | 8400 | 2016-07-01 | 100% | 0% | 8400 | 0 | 8400
1083 | 1091 | 125 | 05470402574 | NE Special Crews | New VCT Floor | Highway Trans. Fund 6 | 10000 | 8890.1 | 2016-08-19 | 100% | 0% | 8890.1 | 0 | 8890.1
1153 | 1161 | 126 | 17470402644 | Brenham Area Engineer & Maintenance Office | Replace Sidewalk Lab To Area Office | Highway Trans. Fund 6 | 12500 | 3345 | 2016-09-16 | 100% | 0% | 3345 | 0 | 3345
#N/A | 211B | 127 | 02470402999 | Weatherford Maintenance Offices | Due to security issues project approved. Need to create child number to PARENT#02470401548 split off $45,000 from total project for various locations listed. CHILD# 02470402999. Clay and Art to create schedule. | Highway Trans. Fund 6 | 0 | 24142.5 | 2016-09-08 | 100% | 0% | 24142.5 | 0 | 24142.5 | Phase I of Project ID #02470401548
30 | 52 | 128 | 19470401530 | Atlanta District Headquarters | Replace 1 HVAC System | Highway Trans. Fund 6 | 10000 | 20362.5 | 2016-06-24 | 100% | 0% | 20362.5 | 0 | 20362.5
102 | 68 | 129 | 19470401567 | Atlanta District Headquarters | Replace 2 HVAC Systems | Highway Trans. Fund 6 | 20000 | 20362.5 | 2016-06-24 | 100% | 0% | 20362.5 | 0 | 20362.5
163 | 67 | 130 | 19470401646 | Atlanta District Headquarters | Replace HVAC System | Highway Trans. Fund 6 | 10000 | 20362.5 | 2016-07-15 | 100% | 0% | 20362.5 | 0 | 20362.5
161 | 90 | 131 | 19470401644 | Atlanta District Headquarters | Replace 3 HVAC Systems | Highway Trans. Fund 6 | 30000 | 20362.5 | 2016-06-28 | 100% | 0% | 20362.5 | 0 | 20362.5
130 | 110 | 132 | 15470401601 | San Antonio District Headquarters | Replace Roof Top Package HVAC 10 Ton System | Highway Trans. Fund 6 | 15000 | 10983 | 2016-11-14 | 100% | 0% | 10983 | 0 | 10983
80 | 112 | 133 | 19470401719 | Daingerfield Maintenance Office | Replaces HVAC System | Highway Trans. Fund 6 | 16000 | 9795 | 2016-06-24 | 100% | 0% | 0 | 0 | 9795
184 | 111 | 134 | 19470401673 | Mt Pleasant Area Engineer & Maintenance Office | Replace 1 HVAC System | Highway Trans. Fund 6 | 10000 | 11455 | 2016-06-24 | 100% | 0% | 0 | 0 | 11455
626 | 636 | 135 | 17470402115 | Buffalo Maintenance Office | Repair Roof | Highway Trans. Fund 6 | 7500 | 4500 | 2016-08-19 | 100% | 0% | 4500 | 0 | 4500
538 | 548 | 136 | 11470402027 | District Headquarters | Install Vinyl Plank Flooring | Highway Trans. Fund 6 | 10000 | 24500 | 2016-07-04 | 100% | 0% | 0 | 0 | 24500
989 | 997 | 137 | 11470402480 | Nacogdoches Area Engineer & Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 22000 | 2016-07-04 | 100% | 0% | 0 | 0 | 22000
706 | 716 | 138 | 08470402195 | District Headquarters | Replace Flooring At The Special Crews Building | Highway Trans. Fund 6 | 16700 | 5124.1 | 2016-07-11 | 100% | 0% | 0 | 0 | 5124.1
#N/A | #N/A | 139 | 10470403004 | Palestine Area Engineer & Maintenance | HVAC Replacement | Highway Trans. Fund 6 | 0 | 4850 | 2016-07-08 | 100% | 0% | 4850 | 0 | 4850
#N/A | #N/A | 140 | 10470403006 | Athens Area Engineer & Maintenance Office | HVAC Replacement | Highway Trans. Fund 6 | 0 | 6450 | 2016-07-08 | 0% | 0% | 0 | 0 | 6450
#N/A | #N/A | 141 | 02470401308 | Stephenvill Area Engineer & Maintenance Office | HVAC Replacement | Highway Trans. Fund 6 | 0 | 24693 | 2016-08-16 | 100% | 0% | 24693 | 0 | 24693
153 | 108 | 142 | 20470401634 | Beaumont District Headquarters | Modifications/Upgrade Electrical | Highway Trans. Fund 6 | 60000 | 45000 | 2016-09-14 | 100% | 0% | 0 | 0 | 45000
#N/A | #N/A | 143 | 13470403007 | Port Lavaca Maintenance Office | Replace rusted Caged Safety Ladders | Highway Trans. Fund 6 | 0 | 28000 | 2016-10-28 | 100% | 0% | 0 | 0 | 28000
658 | 668 | 144 | 05470402147 | District Headquarters | Replace Stairs Going Into Maint. Office | Highway Trans. Fund 6 | 7000 | 12100 | 2016-08-25 | 100% | 0% | 0 | 0 | 12100
303 | 315 | 145 | 02470401792 | District Headquarters | 9 Crac HVAC Units Transvision Building | Highway Trans. Fund 6 | 270000 | 270000 | 2016-11-01 | 100% | 0% | 0 | 0 | 270000
67 | 160 | 146 | 07470401699 | San Angelo District Headquarters | Replace 2 Penthouse Type HVAC Units | Highway Trans. Fund 6 | 300000 | 150000 | 2016-10-04 | 100% | 0% | 0 | 0 | 150000
70 | 121 | 147 | 13470401702 | Wharton Cty Maint. | Install ADA Into Time Room | Highway Trans. Fund 6 | 10000 | 29000 | 2016-10-26 | 100% | 0% | 0 | 0 | 29000
#N/A | R5 | 148 | 10470401503 | Tyler District Headquarters | Replace rusted Caged Safety Ladders | Highway Trans. Fund 6 | 180000 | 91250 | 2017-01-20 | 100% | 0% | 0 | 0 | 91250 | Was going to be completed w/FY15 funds - but needs to be done with FY16 as of 5/31/16. Bundled as one RFC for total of $365K
105 | 185 | 149 | 10470401571 | Tyler District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 180000 | 91250 | 2017-01-17 | 100% | 0% | 0 | 0 | 91250 | Replace 2 Boilers-HQ.Bundled as one RFC for total of $365K
106 | 186 | 150 | 10470401572 | Tyler District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 300000 | 91250 | 2017-01-19 | 100% | 0% | 0 | 0 | 91250 | 60 ton chiller and air handler. Bundled as one RFC for total of $365K
107 | 187 | 151 | 10470401573 | Tyler District Headquarters | Replace 5 Air Handler Units | Highway Trans. Fund 6 | 85000 | 91250 | 2017-01-17 | 100% | 0% | 0 | 0 | 91250 | Aged and constant maintenance. Bundled as one RFC for total of $365K
162 | 74 | 152 | 19470401645 | Atlanta District Headquarters | Replace Generator | Highway Trans. Fund 6 | 250000 | 389500 | 2017-02-16 | 100% | 0% | 0 | 0 | 389500
43 | 11 | 153 | 18470401546 | Dallas District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 160000 | 2016-10-12 | 100% | 0% | 0 | 0 | 160000
4 | 48 | 154 | 01470401491 | Paris District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 170000 | 2016-11-22 | 100% | 0% | 0 | 0 | 170000
36 | 117 | 155 | 21470401539 | Zapata Maintenance Office Sub-Section | Security Fence | Highway Trans. Fund 6 | 39800 | 62000 | 2016-09-05 | 100% | 0% | 0 | 0 | 62000
#N/A | #N/A | 156 | 09470402996 | Limestone - Waco District | 3/29/16 Clay and Art to prep schedule | Highway Trans. Fund 6 | 0 | 65000 | 2016-08-08 | 100% | 0% | 0 | 0 | 65000
#N/A | #N/A | 157 | 17470403003 | Madisonville Maintenance Office | Paint and Carpet | Highway Trans. Fund 6 | 0 | 15000 | 2016-10-04 | 0% | 0% | 0 | 0 | 15000 | Scope changed to Replace Flooring.
194 | 154 | 158 | 15470401687 | Kerrville Area Engineer & Maintenance Office | Install Gate Operator & Exterior Lighting | Highway Trans. Fund 6 | 45000 | 45000 | 2016-08-25 | 0% | 0% | 0 | 0 | 45000
821 | 829 | 159 | 11470402311 | District Headquarters | Replace Fuel Dispensers | Highway Trans. Fund 6 | 15000 | 15000 | 2016-08-18 | 0% | 0% | 0 | 0 | 15000
426 | 438 | 160 | 11470401915 | Crockett Maintenance Office | Replace Bathroom Sewer Dainage System | Highway Trans. Fund 6 | 15000 | 15000 | 2016-09-29 | 0% | 0% | 0 | 0 | 15000
76 | 123 | 161 | 21470401711 | Brownsville Maintenance Office | Upgrade Fencing | Highway Trans. Fund 6 | 39000 | 80000 | 2016-09-23 | 100% | 0% | 0 | 0 | 80000
#N/A | #N/A | 162 | 13470403016 | Edna Maintenance | Edna Caged Ladder Replacement | Highway Trans. Fund 6 | 0 | 16000 | TBD | 0% | 0% | 0 | 0 | 16000
95 | 139 | 163 | 19470401736 | Jefferson Maintenance Office | Replace HVAC | Highway Trans. Fund 6 | 8500 | 8500 | 2016-08-03 | 0% | 0% | 0 | 0 | 8500
68 | 113 | 164 | 07470401700 | San Angelo District Headquarters | Replace Roof | Highway Trans. Fund 6 | 250000 | 395076.5 | 2016-12-26 | 100% | 0% | 0 | 0 | 395076.5
192 | 115 | 165 | 07470401685 | San Angelo District Headquarters | Replace Roof | Highway Trans. Fund 6 | 125000 | 395076.5 | 2016-12-26 | 100% | 0% | 0 | 0 | 395076.5
266 | 278 | 166 | 12470401754 | Brookshire Maintenance Office | Replace Emergency Generator | Highway Trans. Fund 6 | 20000 | 31000 | 2016-07-25 | 100% | 0% | 0 | 0 | 31000
1117 | 1125 | 167 | 10470402608 | South Tyler Area Engineer & Maintenance Office | Repaint Bldg. B | Highway Trans. Fund 6 | 5000 | 5000 | 2016-08-08 | 0% | 0% | 0 | 0 | 5000
259 | 271 | 168 | 19470401747 | Linden Maintenance Office | Replace 2 HVAC Systems Add 1 HVAC For Shop | Highway Trans. Fund 6 | 30000 | 30000 | 2016-06-24 | 0% | 0% | 0 | 0 | 30000
556 | 566 | 169 | 20470402045 | Woodville Maintenance Office | Paint Interior of Facilities | Highway Trans. Fund 6 | 2500 | 2500 | 2016-08-31 | 0% | 0% | 0 | 0 | 2500
1032 | 1040 | 170 | 20470402523 | Jasper Area Engineer & Maintenance Office | Interior Lighting | Highway Trans. Fund 6 | 20000 | 20000 | 2016-08-31 | 0% | 0% | 0 | 0 | 20000
1102 | 1110 | 171 | 20470402593 | Liberty Area Engineer & Maintenance Office | Replace Electrical Panels | Highway Trans. Fund 6 | 5000 | 5000 | 2016-08-31 | 0% | 0% | 0 | 0 | 5000
28 | 136 | 172 | 21470401526 | San Isidro Maintenance Office Sub-Section | Replace Existing Generator | Highway Trans. Fund 6 | 15000 | 23942 | 2016-10-12 | 100% | 0% | 0 | 0 | 23942
947 | 955 | 173 | 08470402438 | Roby Maintenance Office | Install Overhead Door Openers and Push Buttons in all Bay Door Openings. Total of 10 Door Openers. | Highway Trans. Fund 6 | 12000 | 10000 | 2016-08-17 | 100% | 0% | 0 | 0 | 10000
808 | 816 | 174 | 20470402297 | Port Arthur Area Engineer & Maintenance Office | Replace Doors, Frames & Locksets | Highway Trans. Fund 6 | 6000 | 6000 | 2016-10-21 | 0% | 0% | 0 | 0 | 6000
63 | 119 | 175 | 20470401695 | Liberty Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 120000 | 65000 | 2016-10-27 | 100% | 0% | 0 | 0 | 65000
#N/A | #N/A | 176 | 01470403019 | Emory Facility | Emory Generator | Highway Trans. Fund 6 | 0 | 18956 | 2016-07-29 | 100% | 0% | 0 | 0 | 18956
441 | 453 | 177 | 18470401930 | Rockwall Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-02 | 0% | 0% | 0 | 0 | 20000
442 | 454 | 178 | 18470401931 | Rockwall Maintenance Office | Parking Lot Striping | Highway Trans. Fund 6 | 5000 | 5000 | 2016-09-02 | 0% | 0% | 0 | 0 | 5000
#N/A | 207 | 179 | 16470402987 | Port Aransas Ferry Landing | Roof Repairs | Highway Trans. Fund 6 | 0 | 111800 | 2016-06-22 | 100% | 0% | 0 | 0 | 111800
29 | 59 | 180 | 08470401527 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000
173 | 57 | 181 | 11470401659 | Lufkin District Headquarters | Replace HVAC Controls | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000
772 | 780 | 182 | 16470402261 | District Headquarters | Replace Overhead Gas Heaters In Auto Shop | Highway Trans. Fund 6 | 24000 | 24000 | TBD | 0% | 0% | 0 | 0 | 24000
182 | 163 | 183 | 11470401671 | Lufkin District Headquarters | Replace Boiler At Warehouse | Highway Trans. Fund 6 | 45000 | 45000 | 2016-09-01 | 0% | 0% | 0 | 0 | 45000
181 | 91 | 184 | 22470401670 | Del Rio Maintenance Office | Replace HVAC For Sign Shop | Highway Trans. Fund 6 | 30000 | 30000 | 2016-06-21 | 0% | 0% | 0 | 0 | 30000
171 | 99 | 185 | 05470401657 | Plains Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 50000 | 50000 | 2016-09-14 | 0% | 0% | 0 | 0 | 50000
871 | 879 | 186 | 04470402362 | Canadian Maintenance Office | Install Overhead Doors And Openers | Highway Trans. Fund 6 | 25000 | 25000 | 2016-07-01 | 0% | 0% | 0 | 0 | 25000
277 | 289 | 187 | 22470401765 | Laredo Lab/FIN/Stratus | Replace 8 HVAC Units | Highway Trans. Fund 6 | 80000 | 80000 | 2016-10-03 | 0% | 0% | 0 | 0 | 80000
331 | 343 | 188 | 38470401820 | Riverside Annex II RA150-200 | Upgrade Obsolete Johnson Control Panels | Highway Trans. Fund 6 | 30000 | 30000 | 2016-09-19 | 0% | 0% | 0 | 0 | 30000
424 | 436 | 189 | 16470401913 | District Headquarters | Replace 3 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-19 | 0% | 0% | 0 | 0 | 20000
523 | 533 | 190 | 16470402012 | Kleburg Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 12000 | 12000 | 2016-09-19 | 0% | 0% | 0 | 0 | 12000
963 | 971 | 191 | 16470402454 | San Patricio Co | Replace 2 Existing Dual Product Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 15000 | 15000 | 2016-09-19 | 0% | 0% | 0 | 0 | 15000
709 | 719 | 192 | 02470402198 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 6 | 21500 | 21500 | 2016-09-06 | 0% | 0% | 0 | 0 | 21500
923 | 931 | 193 | 06470402414 | Balmorhea Maintenance Office | Remove and Replace Existing Shower Floor Tile | Highway Trans. Fund 6 | 5000 | 5000 | 2016-09-09 | 0% | 0% | 0 | 0 | 5000
924 | 932 | 194 | 06470402415 | Balmorhea Maintenance Office | Remove and Replace Floor Tile Main Office | Highway Trans. Fund 6 | 10000 | 10000 | 2016-09-09 | 0% | 0% | 0 | 0 | 10000
#N/A | 144 | 195 | 11470402981 | Lufkin | Foundation repair - Project being scoped | Highway Trans. Fund 6 | 0 | 0 | 2016-12-19 | 0% | 0% | 0 | 0 | 0
264 | 276 | 196 | 22470401752 | Cotulla Maintenance Office | Upgrade Propane Generator | Highway Trans. Fund 6 | 25000 | 25000 | 2016-09-20 | 0% | 0% | 0 | 0 | 25000
996 | 1004 | 197 | 06470402487 | Stanton Maintenance Office | Enclose 3 Bays With Insulated Overhead Doors To Secure Equipment & Weather Protection | Highway Trans. Fund 6 | 20000 | 20000 | 2016-08-30 | 0% | 0% | 0 | 0 | 20000
883 | 891 | 198 | 24470402374 | Terlingua Sub-Section | Repair / Replace Plumbing Lines Fro Meter To Houses | Highway Trans. Fund 6 | 18000 | 18000 | 2016-10-14 | 0% | 0% | 0 | 0 | 18000
54 | 118 | 199 | 16470401650 | Corpus Christi District Headquarters | Replace Roof | Highway Trans. Fund 6 | 225000 | 225000 | 2016-11-28 | 0% | 0% | 0 | 0 | 225000
166 | 129 | 200 | 16470401651 | Corpus Christi District Headquarters | Replace Roof On The District Hq Administration Bldg | Highway Trans. Fund 6 | 300000 | 300000 | 2016-11-28 | 0% | 0% | 0 | 0 | 300000
167 | 130 | 201 | 16470401652 | Corpus Christi District Headquarters | Replace Roof On The Lab Building | Highway Trans. Fund 6 | 35000 | 35000 | 2016-11-28 | 0% | 0% | 0 | 0 | 35000
168 | 135 | 202 | 16470401653 | Corpus Christi District Headquarters | Replace Roof On The Special Crews Office Building | Highway Trans. Fund 6 | 350000 | 350000 | 2017-02-03 | 0% | 0% | 0 | 0 | 350000
#N/A | #N/A | 203 | 14470403008 | Cedar Park | Cedar Park Generator & Electrical Upgrades | Highway Trans. Fund 6 | 0 | 505000 | TBD | 0% | 0% | 0 | 0 | 505000
628 | 638 | 204 | 17470402117 | Buffalo Maintenance Office | Upgrade HVAC System | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-19 | 0% | 0% | 0 | 0 | 20000
9 | 141 | 205 | 16470401496 | Rockport Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | 2017-01-02 | 0% | 0% | 0 | 0 | 300000
18 | 149 | 206 | 38470401507 | Camp Hubbard State Headquarters | Replace Roof (C.H. Bldg. 6) | Highway Trans. Fund 6 | 285000 | 285000 | 2016-08-22 | 0% | 0% | 0 | 0 | 285000
90 | 142 | 207 | 16470401730 | Nueces East | Replace Roof On The Maintenance Building | Highway Trans. Fund 6 | 250000 | 250000 | 2016-11-07 | 0% | 0% | 0 | 0 | 250000
183 | 152 | 208 | 04470401672 | Amarillo District Headquarters | Install Rooftop HVAC To Heat And Cool Shop | Highway Trans. Fund 6 | 50000 | 50000 | 2016-12-26 | 0% | 0% | 0 | 0 | 50000
919 | 927 | 209 | 17470402410 | Brenham Area Engineer & Maintenance Office | Replace Siding On A Wash Bay | Highway Trans. Fund 6 | 15000 | 15000 | 2016-10-07 | 0% | 0% | 0 | 0 | 15000
895 | 903 | 210 | 17470402386 | Huntsville Area Engineer & Maintenance Office | Paint Building | Highway Trans. Fund 6 | 20000 | 20000 | 2016-10-11 | 0% | 0% | 0 | 0 | 20000
#N/A | 199 | 211 | 14470402984 | San Marcos Maintenance Office | New Generator/Upgrade---Split off of 14470401613 | Highway Trans. Fund 6 | 0 | 75000 | 2016-09-27 | 0% | 0% | 0 | 0 | 75000 | Phase of Project ID: 14470401613
657 | 667 | 212 | 05470402146 | District Headquarters | Replace Stairs Going In To District Break Room | Highway Trans. Fund 6 | 5000 | 5000 | 2016-10-12 | 0% | 0% | 0 | 0 | 5000
889 | 897 | 213 | 08470402380 | Snyder Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-07 | 0% | 0% | 0 | 0 | 20000
#N/A | #N/A | 214 | 03470403021 | Seymour | Seymour Termite | Highway Trans. Fund 6 | 0 | 0 | 2016-08-17 | 0% | 0% | 0 | 0 | 0 | Project being scoped - estimate not available
1129 | 1137 | 215 | 17470402620 | Brenham Area Engineer & Maintenance Office | Enclose Two Bays Of Equipment Shed | Highway Trans. Fund 6 | 10000 | 10000 | 2016-10-03 | 0% | 0% | 0 | 0 | 10000
6 | 64 | 216 | 38470401493 | Camp Hubbard State Headquarters | Replace Or Rebuild Existing Generator | Highway Trans. Fund 6 | 75000 | 75000 | 2016-12-07 | 0% | 0% | 0 | 0 | 75000
1178 | 1186 | 217 | 17470402670 | District Headquarters | New Canopy And Lights | Highway Trans. Fund 6 | 12500 | 12500 | 2016-10-12 | 0% | 0% | 0 | 0 | 12500
172 | 162 | 218 | 11470401658 | Crockett Maintenance Office | Replace Emergency Generator | Highway Trans. Fund 6 | 38000 | 38000 | 2016-10-05 | 0% | 0% | 0 | 0 | 38000
842 | 850 | 219 | 11470402332 | Lufkin Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 15000 | 15000 | 2016-09-09 | 0% | 0% | 0 | 0 | 15000
935 | 943 | 220 | 04470402426 | Groom Maintenance Office | New Compressor/Relocate | Highway Trans. Fund 6 | 5000 | 5000 | 2016-07-01 | 0% | 0% | 0 | 0 | 5000
555 | 565 | 221 | 20470402044 | Woodville Maintenance Office | Install Additional Unit Heater | Highway Trans. Fund 6 | 3000 | 3000 | 2016-09-13 | 0% | 0% | 0 | 0 | 3000
159 | 101 | 222 | 04470401641 | Amarillo District Headquarters | Upgrade Generator | Highway Trans. Fund 6 | 400000 | 400000 | 2017-03-16 | 0% | 0% | 0 | 0 | 400000
312 | 324 | 223 | 19470401801 | District Headquarters | Replace 2 HVAC Systems | Highway Trans. Fund 6 | 35000 | 35000 | 2016-07-14 | 0% | 0% | 0 | 0 | 35000
704 | 714 | 224 | 08470402193 | District Headquarters | Add Wall, Lighting, And Ventilation | Highway Trans. Fund 6 | 7000 | 7000 | 2016-10-27 | 0% | 0% | 0 | 0 | 7000
727 | 735 | 225 | 05470402216 | Ralls Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 25000 | 25000 | 2016-09-15 | 0% | 0% | 0 | 0 | 25000
16 | 65 | 226 | 38470401505 | Camp Hubbard State Headquarters | Install Generator For Data Center (Camp Hubbard Bldg. 6) | Highway Trans. Fund 6 | 517000 | 517000 | 2017-01-06 | 0% | 0% | 0 | 0 | 517000
49 | 132 | 227 | 02470401585 | Fort Worth District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 2017-02-16 | 0% | 0% | 0 | 0 | 350000
135 | 63 | 228 | 14470401610 | Austin District Headquarters | Replace Generator | Highway Trans. Fund 6 | 250000 | 250000 | 2017-01-04 | 0% | 0% | 0 | 0 | 250000
198 | 157 | 229 | 23470402339 | Brownwood District Headquarters | Renovate Existing Facilities | Highway Trans. Fund 6 | 6000000 | 6350000 | 2018-05-18 | 0% | 0% | 0 | 0 | 6350000 | Ccure project #23470401667 cancelled and combined with this project. 04/14/16
542 | 552 | 230 | 11470402031 | District Headquarters | Replace Flooring | Highway Trans. Fund 6 | 8000 | 8000 | 2016-09-16 | 0% | 0% | 0 | 0 | 8000
868 | 876 | 231 | 05470402359 | Tahoka Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 15000 | 15000 | 2016-10-28 | 0% | 0% | 0 | 0 | 15000
1033 | 1041 | 232 | 20470402524 | Jasper Area Engineer & Maintenance Office | Paint Office Interior | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-16 | 0% | 0% | 0 | 0 | 20000
1099 | 1107 | 233 | 20470402590 | Liberty Area Engineer & Maintenance Office | Interior Lighting | Highway Trans. Fund 6 | 10000 | 10000 | 2016-09-16 | 0% | 0% | 0 | 0 | 10000
1140 | 1148 | 234 | 11470402631 | Hemphill Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | 2016-10-28 | 0% | 0% | 0 | 0 | 15000
380 | 392 | 235 | 05470401869 | Post RDC | Nw Side Of Long Building Dirt Work To Shed Water | Highway Trans. Fund 6 | 10000 | 10000 | 2016-09-19 | 0% | 0% | 0 | 0 | 10000
722 | 730 | 236 | 05470402211 | Bovina Maintenance Office | Repaint Exterior, Old Faded Peeling | Highway Trans. Fund 6 | 25000 | 25000 | 2016-09-19 | 0% | 0% | 0 | 0 | 25000
724 | 732 | 237 | 05470402213 | Brownfield Area Engineer & Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-19 | 0% | 0% | 0 | 0 | 20000
742 | 750 | 238 | 08470402231 | Big Spring Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-19 | 0% | 0% | 0 | 0 | 20000
744 | 752 | 239 | 08470402233 | Big Spring Maintenance Office | Repair Damage To Walls And Wood In Area Ofice | Highway Trans. Fund 6 | 8000 | 8000 | 2016-09-19 | 0% | 0% | 0 | 0 | 8000
844 | 852 | 240 | 11470402334 | Lufkin Maintenance Office | Underskirt Fuel Awning | Highway Trans. Fund 6 | 6000 | 6000 | 2016-09-19 | 0% | 0% | 0 | 0 | 6000
979 | 987 | 241 | 11470402470 | Center Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 15000 | 15000 | 2016-09-19 | 0% | 0% | 0 | 0 | 15000
981 | 989 | 242 | 11470402472 | Livingston Area Engineer & Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-19 | 0% | 0% | 0 | 0 | 20000
982 | 990 | 243 | 11470402473 | Livingston Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-19 | 0% | 0% | 0 | 0 | 20000
1072 | 1080 | 244 | 17470402563 | Hearne Area Engineer & Maintenance Office | Install Welding Ventilation Hood | Highway Trans. Fund 6 | 7500 | 7500 | 2016-10-31 | 0% | 0% | 0 | 0 | 7500
1152 | 1160 | 245 | 17470402643 | Brenham Area Engineer & Maintenance Office | Add Network Connections To Lab Area | Highway Trans. Fund 6 | 7500 | 7500 | 2016-10-31 | 0% | 0% | 0 | 0 | 7500
1161 | 1169 | 246 | 11470402652 | District Headquarters | Renovate Interior | Highway Trans. Fund 6 | 8000 | 8000 | 2016-09-19 | 0% | 0% | 0 | 0 | 8000
46 | 83 | 247 | 05470401553 | Lubbock District Headquarters | Replace Roof | Highway Trans. Fund 6 | 50000 | 50000 | 2016-12-13 | 0% | 0% | 0 | 0 | 50000
50 | 147 | 248 | 06470401587 | Odessa District Headquarters | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | 2017-01-24 | 0% | 0% | 0 | 0 | 300000
85 | 116 | 249 | 15470401724 | Uvalde Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2016-11-15 | 0% | 0% | 0 | 0 | 100000
86 | 148 | 250 | 06470401725 | Midland Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | 2016-11-15 | 0% | 0% | 0 | 0 | 65000
87 | 104 | 251 | 03470401726 | Vernon Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 120000 | 120000 | 2017-01-24 | 0% | 0% | 0 | 0 | 120000
94 | 105 | 252 | 04470401735 | Dalhart Maintenance Office | Roof | Highway Trans. Fund 6 | 175000 | 175000 | 2016-11-15 | 0% | 0% | 0 | 0 | 175000
97 | 97 | 253 | 05470401738 | Lubbock District Headquarters | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | 2016-11-29 | 0% | 0% | 0 | 0 | 65000
131 | 151 | 254 | 08470401604 | Abilene District Headquarters | Replace Generator | Highway Trans. Fund 6 | 58000 | 58000 | 2016-07-12 | 0% | 0% | 0 | 0 | 58000
148 | 106 | 255 | 04470401629 | Pampa Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 175000 | 225000 | 2017-01-24 | 0% | 0% | 0 | 0 | 225000
307 | 319 | 256 | 10470401796 | South Tyler Area Engineer & Maintenance Office | Upgrade HVAC In Maint &Area Office | Highway Trans. Fund 6 | 150000 | 150000 | 2016-07-19 | 0% | 0% | 0 | 0 | 150000
784 | 792 | 257 | 11470402273 | Crockett Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 15000 | 15000 | 2016-09-20 | 0% | 0% | 0 | 0 | 15000
995 | 1003 | 258 | 11470402486 | San Augustine Area Engineer & Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | 2016-09-20 | 0% | 0% | 0 | 0 | 15000
5 | 167 | 259 | 22470401492 | Del Rio Maintenance Office | Replace Generators (x2) | Highway Trans. Fund 6 | 50000 | 50000 | 2016-11-09 | 0% | 0% | 0 | 0 | 50000
15 | 80 | 260 | 38470401504 | Camp Hubbard State Headquarters | Demolish Existing Building and Convert To Parking | Highway Trans. Fund 6 | 200000 | 200000 | 2016-10-26 | 0% | 0% | 0 | 0 | 200000
26 | 81 | 261 | 09470401518 | Waco District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 300000 | 300000 | 2017-01-25 | 0% | 0% | 0 | 0 | 300000
56 | 158 | 262 | 13470401661 | Port Lavaca MNT - Calhoun Cty Maint. | Convert Flat Roof To Gable Style | Highway Trans. Fund 6 | 250000 | 250000 | 2017-02-22 | 0% | 0% | 0 | 0 | 250000
104 | 156 | 263 | 38470401570 | Camp Hubbard State Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 200000 | 200000 | 2016-11-30 | 0% | 0% | 0 | 0 | 200000
109 | 161 | 264 | 10470401575 | North Tyler Maintenance Office | Replace Roof At North Tyler Fuel Station | Highway Trans. Fund 6 | 85000 | 85000 | 2017-03-15 | 0% | 0% | 0 | 0 | 85000
191 | 164 | 265 | 21470401683 | Pharr District Headquarters | Replace Roof | Highway Trans. Fund 6 | 250000 | 250000 | 2017-02-22 | 0% | 0% | 0 | 0 | 250000
1035 | 1043 | 266 | 20470402526 | Jasper Area Engineer & Maintenance Office | Replace Carpet And VCT | Highway Trans. Fund 6 | 15000 | 15000 | 2016-09-21 | 0% | 0% | 0 | 0 | 15000
#N/A | 146 | 267 | 08470402982 | Baird Maintenance | Spalling Concrete hazard - Add approved 1/5/16 Soloman create schedule | Highway Trans. Fund 6 | 0 | 0 | 2016-12-21 | 0% | 0% | 0 | 0 | 0
#N/A | #N/A | 268 | 11470402989 | Livingston Area Engineer & Maintenance Office | SFMO Fire Wall | Highway Trans. Fund 6 | 0 | 50000 | 2016-10-07 | 0% | 0% | 0 | 0 | 50000
517 | 527 | 269 | 18470402006 | Waxahachie Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-03 | 0% | 0% | 0 | 0 | 10000
616 | 626 | 270 | 18470402105 | Ennis Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-03 | 0% | 0% | 0 | 0 | 10000
650 | 660 | 271 | 18470402139 | District Headquarters | Paint Exterior | Highway Trans. Fund 6 | 20000 | 20000 | 2016-11-03 | 0% | 0% | 0 | 0 | 20000
913 | 921 | 272 | 18470402404 | Hutchins Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-03 | 0% | 0% | 0 | 0 | 10000
1094 | 1102 | 273 | 18470402585 | District Headquarters | Paint Exterior | Highway Trans. Fund 6 | 15000 | 15000 | 2016-11-03 | 0% | 0% | 0 | 0 | 15000
151 | 69 | 274 | 20470401632 | Beaumont District Headquarters | Fence Repairs | Highway Trans. Fund 6 | 9000 | 9000 | 2016-09-23 | 0% | 0% | 0 | 0 | 9000
285 | 297 | 275 | 18470401773 | Denton Area Engineer & Maintenance Office | Install Gate - Electric W/Remote On Ih35 Service Road | Highway Trans. Fund 6 | 20000 | 20000 | 2016-11-04 | 0% | 0% | 0 | 0 | 20000
319 | 331 | 276 | 12470401808 | District Headquarters | Upgrade Site Lighting | Highway Trans. Fund 6 | 100000 | 100000 | 2016-11-04 | 0% | 0% | 0 | 0 | 100000
540 | 550 | 277 | 11470402029 | District Headquarters | Paint Interior | Highway Trans. Fund 6 | 8000 | 8000 | 2016-09-23 | 0% | 0% | 0 | 0 | 8000
622 | 632 | 278 | 20470402111 | Newton Maintenance Office | Interior Lighting | Highway Trans. Fund 6 | 10000 | 10000 | 2016-09-23 | 0% | 0% | 0 | 0 | 10000
843 | 851 | 279 | 11470402333 | Lufkin Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 15000 | 15000 | 2016-11-04 | 0% | 0% | 0 | 0 | 15000
990 | 998 | 280 | 11470402481 | San Augustine Area Engineer & Maintenance Office | Install Electric Baydoor Openers | Highway Trans. Fund 6 | 10000 | 10000 | 2016-09-23 | 0% | 0% | 0 | 0 | 10000
994 | 1002 | 281 | 11470402485 | San Augustine Area Engineer & Maintenance Office | Upgrade Exterior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | 2016-11-04 | 0% | 0% | 0 | 0 | 15000
1100 | 1108 | 282 | 20470402591 | Liberty Area Engineer & Maintenance Office | Paint Office Interior | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-23 | 0% | 0% | 0 | 0 | 20000
1142 | 1150 | 283 | 11470402633 | Groveton Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | 2016-09-23 | 0% | 0% | 0 | 0 | 15000
550 | 560 | 284 | 04470402039 | Dumas Maintenance Office | Remove Oh Door In Breakroom And Install Walk Door | Highway Trans. Fund 6 | 15000 | 15000 | 2016-07-25 | 0% | 0% | 0 | 0 | 15000
1081 | 1089 | 285 | 05470402572 | Littlefield Area Engineer & Maintenance Office | Replace Windows AE's Office | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-26 | 0% | 0% | 0 | 0 | 20000
#N/A | 205 | 286 | 24470402992 | El Paso District Headquarters | El Paso Generator Replacement | Highway Trans. Fund 6 | 0 | 0 | 2017-01-12 | 0% | 0% | 0 | 0 | 0
103 | 153 | 287 | 05470401568 | Post RDC | Replace Generator | Highway Trans. Fund 6 | 75000 | 75000 | 2016-10-13 | 0% | 0% | 0 | 0 | 75000
297 | 309 | 288 | 20470401786 | Liberty Area Engineer & Maintenance Office | Install/Repair Fence | Highway Trans. Fund 6 | 7000 | 7000 | 2016-09-30 | 0% | 0% | 0 | 0 | 7000
543 | 553 | 289 | 11470402032 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 6 | 8000 | 8000 | 2016-09-30 | 0% | 0% | 0 | 0 | 8000
787 | 795 | 290 | 11470402276 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 6 | 8000 | 8000 | 2016-09-30 | 0% | 0% | 0 | 0 | 8000
164 | 170 | 291 | 16470401648 | Corpus Christi District Headquarters | Modifications/Upgrade Electrical | Highway Trans. Fund 6 | 250000 | 450000 | 2017-02-06 | 0% | 0% | 0 | 0 | 450000
283 | 295 | 292 | 15470401771 | Bexar Metro Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 45000 | 45000 | 2016-10-18 | 0% | 0% | 0 | 0 | 45000
339 | 351 | 293 | 22470401828 | Del Rio Maintenance Office (US 90) | Parking Lot Lighting | Highway Trans. Fund 6 | 35000 | 35000 | 2016-11-15 | 0% | 0% | 0 | 0 | 35000
877 | 885 | 294 | 20470402368 | Kountze Maintenance Office | Install Overhead Doors | Highway Trans. Fund 6 | 20000 | 20000 | 2016-10-06 | 0% | 0% | 0 | 0 | 20000
922 | 930 | 295 | 17470402413 | Bryan Area Engineer & Maintenance Office | Install Automatic Gate On Rear Gate | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-17 | 0% | 0% | 0 | 0 | 10000
1146 | 1154 | 296 | 18470402637 | Corsicana Area Engineer & Maintenance Office | Floor Tile Removal - Corridors Only (Stain Concrete) | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-17 | 0% | 0% | 0 | 0 | 10000
1147 | 1155 | 297 | 18470402638 | Corsicana Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-17 | 0% | 0% | 0 | 0 | 10000
752 | 760 | 298 | 20470402241 | Districtwide | Flag Pole Lights | Highway Trans. Fund 6 | 12000 | 12000 | 2016-10-07 | 0% | 0% | 0 | 0 | 12000
848 | 856 | 299 | 20470402338 | District Headquarters | Paint Interior | Highway Trans. Fund 6 | 5000 | 5000 | 2016-10-10 | 0% | 0% | 0 | 0 | 5000
615 | 625 | 300 | 18470402104 | Ennis Maintenance Office | Floor Tile Abatement - Corridors Only (Stain Concrete) | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-21 | 0% | 0% | 0 | 0 | 10000
586 | 596 | 301 | 06470402075 | McCamey Maintenance Office | Paint Building Exterior | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-23 | 0% | 0% | 0 | 0 | 10000
587 | 597 | 302 | 06470402076 | McCamey Maintenance Office | Replace Linolium With Tile In Offices | Highway Trans. Fund 6 | 15000 | 15000 | 2016-11-23 | 0% | 0% | 0 | 0 | 15000
757 | 765 | 303 | 06470402246 | McCamey Maintenance Office | Repaint Exterior | Highway Trans. Fund 6 | 15000 | 15000 | 2016-11-23 | 0% | 0% | 0 | 0 | 15000
78 | 114 | 304 | 21470401713 | Mission Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | 2017-02-16 | 0% | 0% | 0 | 0 | 300000
544 | 554 | 305 | 16470402033 | Refugio Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 12000 | 12000 | 2016-11-25 | 0% | 0% | 0 | 0 | 12000
1139 | 1147 | 306 | 11470402630 | Hemphill Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 15000 | 15000 | 2016-10-14 | 0% | 0% | 0 | 0 | 15000
#N/A | #N/A | 307 | 38470403000 | Approved in Sr. Mgr Mtg 4/5/16 | 0 | Highway Trans. Fund 6 | 0 | 990000 | 2017-07-21 | 0% | 0% | 0 | 0 | 990000
#N/A | #N/A | 308 | 38470403002 | Approved in Sr. Mgr Mtg 4/5/16 | 0 | Highway Trans. Fund 6 | 0 | 115000 | 2017-03-17 | 0% | 0% | 0 | 0 | 115000
#N/A | #N/A | 309 | 01470402991 | Sulphur Springs | Fuel Canopy | Highway Trans. Fund 6 | 0 | 0 | 2016-12-27 | 0% | 0% | 0 | 0 | 0
334 | 346 | 310 | 01470401823 | District Headquarters | Resurface Parking Lot | Highway Trans. Fund 6 | 164000 | 164000 | 2017-01-18 | 0% | 0% | 0 | 0 | 164000
335 | 347 | 311 | 21470401824 | Pharr Area Engineer & Maintenance Office | Reconfigure Parking Lot | Highway Trans. Fund 6 | 41000 | 41000 | 2017-01-18 | 0% | 0% | 0 | 0 | 41000
35 | 137 | 312 | 21470401538 | Zapata Maintenance Office Sub-Section | Replace Generators | Highway Trans. Fund 6 | 20000 | 20000 | 2016-11-17 | 0% | 0% | 0 | 0 | 20000
621 | 631 | 313 | 20470402110 | Anahuac Maintenance Office | Install Storm Shutters | Highway Trans. Fund 6 | 14000 | 14000 | 2016-10-20 | 0% | 0% | 0 | 0 | 14000
845 | 853 | 314 | 11470402335 | Lufkin Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | 2016-10-20 | 0% | 0% | 0 | 0 | 15000
887 | 895 | 315 | 08470402378 | Snyder Maintenance Office | Convert Old Propane Gas Heaters In Shop To Natural Gas | Highway Trans. Fund 6 | 10000 | 10000 | 2016-12-01 | 0% | 0% | 0 | 0 | 10000
897 | 905 | 316 | 17470402388 | Huntsville Area Engineer & Maintenance Office | Repair Roof | Highway Trans. Fund 6 | 15000 | 15000 | 2016-12-01 | 0% | 0% | 0 | 0 | 15000
980 | 988 | 317 | 11470402471 | Center Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | 2016-10-20 | 0% | 0% | 0 | 0 | 15000
1022 | 1030 | 318 | 18470402513 | District Headquarters | Paint Exterior And Interior | Highway Trans. Fund 6 | 10000 | 10000 | 2016-12-01 | 0% | 0% | 0 | 0 | 10000
1080 | 1088 | 319 | 05470402571 | Littlefield Area Engineer & Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 30000 | 30000 | 2016-12-01 | 0% | 0% | 0 | 0 | 30000
1097 | 1105 | 320 | 20470402588 | Anahuac Maintenance Office | Install Roll-Up Door Opener | Highway Trans. Fund 6 | 3000 | 3000 | 2016-10-20 | 0% | 0% | 0 | 0 | 3000
75 | 122 | 321 | 21470401710 | Brownsville Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 40000 | 2016-11-04 | 0% | 0% | 0 | 0 | 40000
387 | 399 | 322 | 08470401876 | District Headquarters | Replace Water Cut Offs On The Complex For Various Buildings | Highway Trans. Fund 6 | 8500 | 8500 | 2016-12-16 | 0% | 0% | 0 | 0 | 8500
637 | 647 | 323 | 16470402126 | Goliad Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 12000 | 12000 | 2016-12-02 | 0% | 0% | 0 | 0 | 12000
806 | 814 | 324 | 20470402295 | Port Arthur Area Engineer & Maintenance Office | Asbestos Abatement | Highway Trans. Fund 6 | 5000 | 5000 | 2016-10-21 | 0% | 0% | 0 | 0 | 5000
864 | 872 | 325 | 16470402355 | Kingsville Maintenance Office | Replace Flooring At Maintenance - Kingsville MNT | Highway Trans. Fund 6 | 20000 | 20000 | 2016-12-02 | 0% | 0% | 0 | 0 | 20000
865 | 873 | 326 | 16470402356 | Kleburg Co. | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 6 | 25000 | 25000 | 2016-12-02 | 0% | 0% | 0 | 0 | 25000
958 | 966 | 327 | 16470402449 | Corpus Christi Area Engineer & Maintenance Office | Replace Flooring At Area Engineer And Maintenance - Corpus Christi AEM | Highway Trans. Fund 6 | 20000 | 20000 | 2016-12-02 | 0% | 0% | 0 | 0 | 20000
972 | 980 | 328 | 16470402463 | Rockport Maintenance Office | Replace Flooring At Maintenance - Rockport MNT | Highway Trans. Fund 6 | 15000 | 15000 | 2016-12-02 | 0% | 0% | 0 | 0 | 15000
987 | 995 | 329 | 11470402478 | Nacogdoches Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 20000 | 20000 | 2016-10-21 | 0% | 0% | 0 | 0 | 20000
1101 | 1109 | 330 | 20470402592 | Liberty Area Engineer & Maintenance Office | Replace Carpet And VCT | Highway Trans. Fund 6 | 15000 | 15000 | 2016-10-21 | 0% | 0% | 0 | 0 | 15000
818 | 826 | 331 | 11470402308 | District Headquarters | Paint Interior | Highway Trans. Fund 6 | 8000 | 8000 | 2016-10-24 | 0% | 0% | 0 | 0 | 8000
300 | 312 | 332 | 24470401789 | El Paso (East) Area Engineer & Maintenance Office | Upgrade Evaporative AC Unit In The Shop. Add Heaters And Double Door. | Highway Trans. Fund 6 | 35000 | 35000 | 2017-01-03 | 0% | 0% | 0 | 0 | 35000
1079 | 1087 | 333 | 18470402570 | Denton Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | 2016-12-08 | 0% | 0% | 0 | 0 | 10000
77 | 124 | 334 | 21470401712 | Mission Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 40000 | 2016-12-09 | 0% | 0% | 0 | 0 | 40000
649 | 659 | 335 | 25470402138 | Munday Maintenance Office | Replace Floor Tiles | Highway Trans. Fund 6 | 9500 | 9500 | 2016-08-26 | 0% | 0% | 0 | 0 | 9500
775 | 783 | 336 | 16470402264 | Karnes Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 12000 | 12000 | 2016-12-09 | 0% | 0% | 0 | 0 | 12000
900 | 908 | 337 | 25470402391 | Quanah Maintenance Office | Paint Interior & Exterior, Resurface Parking Area | Highway Trans. Fund 6 | 15000 | 15000 | 2016-08-26 | 0% | 0% | 0 | 0 | 15000
967 | 975 | 338 | 16470402458 | Sinton Area Engineer & Maintenance Office | Replace Flooring At Area Engineer And Maintenance - Sinton AEM | Highway Trans. Fund 6 | 20000 | 20000 | 2016-12-23 | 0% | 0% | 0 | 0 | 20000
1090 | 1098 | 339 | 20470402581 | Beaumont Area Engineer & Maintenance Office | Interior Lighting | Highway Trans. Fund 6 | 5000 | 5000 | 2016-10-28 | 0% | 0% | 0 | 0 | 5000
#N/A | 211 | 340 | 09470402991 | Waco District Headquarters | SMFO Fire Exit | Highway Trans. Fund 6 | 0 | 125000 | 2016-12-22 | 0% | 0% | 0 | 0 | 125000
3 | 198 | 341 | 01470401490 | Paris District Headquarters | Replace Roof And Walls | Highway Trans. Fund 6 | 50000 | 50000 | 2016-12-27 | 0% | 0% | 0 | 0 | 50000
69 | 120 | 342 | 15470401701 | Pearsall Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | 2017-03-07 | 0% | 0% | 0 | 0 | 65000
138 | 143 | 343 | 06470401615 | Odessa District Headquarters | Replace Main HVAC Multi-Zone Units | Highway Trans. Fund 6 | 160000 | 160000 | 2016-12-06 | 0% | 0% | 0 | 0 | 160000
140 | 176 | 344 | 15470401617 | Seguin Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2017-03-21 | 0% | 0% | 0 | 0 | 100000
143 | 177 | 345 | 08470401623 | Big Spring Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 60000 | 60000 | 2016-12-27 | 0% | 0% | 0 | 0 | 60000
287 | 299 | 346 | 21470401776 | District Headquarters | HVAC Upgrade In HQ Bldg. | Highway Trans. Fund 6 | 300000 | 300000 | 2016-12-06 | 0% | 0% | 0 | 0 | 300000
298 | 310 | 347 | 20470401787 | Liberty Area Engineer & Maintenance Office | Rehab Roof With Insulation | Highway Trans. Fund 6 | 95000 | 95000 | 2017-03-21 | 0% | 0% | 0 | 0 | 95000
299 | 311 | 348 | 24470401788 | El Paso (East) Area Engineer & Maintenance Office | Install/Repair Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2017-03-21 | 0% | 0% | 0 | 0 | 100000
325 | 337 | 349 | 15470401814 | West Bexar Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2017-03-21 | 0% | 0% | 0 | 0 | 100000
132 | 172 | 350 | 08470401605 | Abilene District Headquarters | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | 2016-12-28 | 0% | 0% | 0 | 0 | 65000
133 | 173 | 351 | 08470401606 | Abilene District Headquarters | Replace Roof (Warehouse) | Highway Trans. Fund 6 | 130000 | 130000 | 2016-12-28 | 0% | 0% | 0 | 0 | 130000
134 | 174 | 352 | 08470401607 | Abilene District Headquarters | Reroof Building Or Repatch In Areas | Highway Trans. Fund 6 | 10000 | 10000 | 2016-12-28 | 0% | 0% | 0 | 0 | 10000
157 | 168 | 353 | 03470401639 | Wichita Falls District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 2017-03-01 | 0% | 0% | 0 | 0 | 350000
261 | 273 | 354 | 22470401749 | Del Rio Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 50000 | 50000 | 2017-03-22 | 0% | 0% | 0 | 0 | 50000
263 | 275 | 355 | 22470401751 | Cotulla Maintenance Office | Roof Repairs | Highway Trans. Fund 6 | 50000 | 50000 | 2017-03-22 | 0% | 0% | 0 | 0 | 50000
281 | 293 | 356 | 05470401769 | District Headquarters | Replace Roof | Highway Trans. Fund 6 | 40000 | 40000 | 2017-03-22 | 0% | 0% | 0 | 0 | 40000
286 | 298 | 357 | 05470401774 | Littlefield Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 45000 | 45000 | 2017-03-22 | 0% | 0% | 0 | 0 | 45000
289 | 301 | 358 | 21470401778 | San Benito Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | 2017-06-07 | 0% | 0% | 0 | 0 | 300000
355 | 367 | 359 | 23470401844 | Breckenridge Maintenance Office | Demolish Old Structures On Adjacent Site | Highway Trans. Fund 6 | 39500 | 39500 | 2016-12-07 | 0% | 0% | 0 | 0 | 39500
841 | 849 | 360 | 11470402331 | Lufkin Maintenance Office | Replace Flooring | Highway Trans. Fund 6 | 12000 | 12000 | 2016-11-02 | 0% | 0% | 0 | 0 | 12000
274 | 286 | 361 | 22470401762 | Laredo Auto Shop | Furnish/Install HVAC | Highway Trans. Fund 6 | 100000 | 100000 | 2017-01-31 | 0% | 0% | 0 | 0 | 100000
659 | 669 | 362 | 06470402148 | Kermit Maintenance Office | Paint Exterior Walls & Re-Insulate Weldging Shop | Highway Trans. Fund 6 | 20000 | 20000 | 2017-01-26 | 0% | 0% | 0 | 0 | 20000
81 | 125 | 363 | 38470401720 | Riverside Annex II RA150-200 | Replacement of R22 to 410 HVAC System | Highway Trans. Fund 6 | 200000 | 200000 | 2017-03-17 | 0% | 0% | 0 | 0 | 200000
98 | 169 | 364 | 15470401739 | San Antonio District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 150000 | 150000 | 2017-05-18 | 0% | 0% | 0 | 0 | 150000
108 | 195 | 365 | 10470401574 | Tyler District Headquarters | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2017-07-28 | 0% | 0% | 0 | 0 | 100000
116 | 188 | 366 | 02470401583 | Fort Worth District Headquarters | Replace Roof (3 Buildings) | Highway Trans. Fund 6 | 492000 | 492000 | 2017-06-02 | 0% | 0% | 0 | 0 | 492000
117 | 180 | 367 | 02470401584 | Fort Worth District Headquarters | Roof Replacement and Interior upgrade | Highway Trans. Fund 6 | 480000 | 980000 | 2017-06-02 | 0% | 0% | 0 | 0 | 980000
124 | 189 | 368 | 15470401595 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 75000 | 75000 | 2017-09-22 | 0% | 0% | 0 | 0 | 75000
125 | 190 | 369 | 15470401596 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2017-09-22 | 0% | 0% | 0 | 0 | 100000
126 | 191 | 370 | 15470401597 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2017-09-22 | 0% | 0% | 0 | 0 | 100000
127 | 192 | 371 | 15470401598 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 125000 | 125000 | 2017-09-22 | 0% | 0% | 0 | 0 | 125000
128 | 193 | 372 | 15470401599 | San Antonio District Headquarters | Replace Roof - Buildings 1, 3 & 4 | Highway Trans. Fund 6 | 250000 | 250000 | 2017-09-22 | 0% | 0% | 0 | 0 | 250000
129 | 194 | 373 | 15470401600 | San Antonio District Headquarters | Replace Roof - Buildings 8 & 9 | Highway Trans. Fund 6 | 150000 | 150000 | 2017-09-22 | 0% | 0% | 0 | 0 | 150000
141 | 196 | 374 | 10470401621 | Tyler District Headquarters | Replace Roof On Old Lab | Highway Trans. Fund 6 | 200000 | 200000 | 2017-08-25 | 0% | 0% | 0 | 0 | 200000
253 | 265 | 375 | 15470401741 | District Headquarters | Replace All VAV and Upgrade To Electrical Control | Highway Trans. Fund 6 | 85000 | 85000 | 2017-05-18 | 0% | 0% | 0 | 0 | 85000
316 | 328 | 376 | 18470401805 | District Headquarters | Generator Backup Power Completed | Highway Trans. Fund 6 | 90000 | 90000 | 2017-05-16 | 0% | 0% | 0 | 0 | 90000
324 | 336 | 377 | 15470401813 | District Headquarters | Replace 3 Each 20 Ton Chillers For Backup | Highway Trans. Fund 6 | 125000 | 125000 | 2017-05-17 | 0% | 0% | 0 | 0 | 125000
326 | 338 | 378 | 38470401815 | Riverside Annex I RA118 | Replacement of R22 to 410 HVAC System | Highway Trans. Fund 6 | 200000 | 200000 | 2017-03-17 | 0% | 0% | 0 | 0 | 200000
329 | 341 | 379 | 38470401818 | Riverside Annex II RA150-200 | Replacement of R22 to 410 HVAC System | Highway Trans. Fund 6 | 360000 | 360000 | 2017-03-17 | 0% | 0% | 0 | 0 | 360000
514 | 524 | 380 | 09470402003 | Waco Area Engineer & Maintenance Office - Bagby | Site Drainage Improvements | Highway Trans. Fund 6 | 25200 | 25200 | 2018-03-15 | 0% | 0% | 0 | 0 | 25200
119 | 181 | 381 | 15470401590 | San Antonio District Headquarters | Install All New Hot And Chill Water Valves And Connect To New Control System | Highway Trans. Fund 6 | 150000 | 150000 | 2017-05-22 | 0% | 0% | 0 | 0 | 150000
120 | 109 | 382 | 15470401591 | San Antonio District Headquarters | New Boiler | Highway Trans. Fund 6 | 20000 | 20000 | 2017-05-18 | 0% | 0% | 0 | 0 | 20000
122 | 183 | 383 | 15470401593 | San Antonio District Headquarters | Replace 60 Ton Chiller | Highway Trans. Fund 6 | 150000 | 150000 | 2017-05-18 | 0% | 0% | 0 | 0 | 150000
123 | 184 | 384 | 15470401594 | San Antonio District Headquarters | Replace All VAV and Upgrade To Electrical Control | Highway Trans. Fund 6 | 100000 | 100000 | 2017-05-18 | 0% | 0% | 0 | 0 | 100000
279 | 291 | 385 | 15470401767 | San Antonio - Transguide | Replace 2 - 75 Ton Chillers And Add Chiller For (Backup) | Highway Trans. Fund 6 | 150000 | 150000 | 2017-05-18 | 0% | 0% | 0 | 0 | 150000
317 | 329 | 386 | 18470401806 | District Headquarters | HVAC Upgrade - Leibert System @ Server Room | Highway Trans. Fund 6 | 45000 | 45000 | 2017-05-17 | 0% | 0% | 0 | 0 | 45000
E5 | 84 | 387 | 10470402976 | Athens Regional Distribution Center | Fire supression system water line | Highway Trans. Fund 6 | 0 | 200000 | 2017-03-20 | 0% | 0% | 0 | 0 | 200000
362 | 374 | 388 | 20470401851 | Newton Maintenance Office | Reconfigure Parking Lot | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-17 | 0% | 0% | 0 | 0 | 10000
978 | 986 | 389 | 11470402469 | Center Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 6 | 20000 | 20000 | 2016-11-17 | 0% | 0% | 0 | 0 | 20000
983 | 991 | 390 | 11470402474 | Livingston Area Engineer & Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | 2016-11-17 | 0% | 0% | 0 | 0 | 15000
1098 | 1106 | 391 | 20470402589 | Liberty Area Engineer & Maintenance Office | Abate Floor Tile | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-17 | 0% | 0% | 0 | 0 | 10000
807 | 815 | 392 | 20470402296 | Port Arthur Area Engineer & Maintenance Office | Paint Interior Of Facility | Highway Trans. Fund 6 | 20000 | 20000 | 2016-11-18 | 0% | 0% | 0 | 0 | 20000
854 | 862 | 393 | 11470402345 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 6 | 8000 | 8000 | 2016-11-18 | 0% | 0% | 0 | 0 | 8000
984 | 992 | 394 | 11470402475 | Nacogdoches Area Engineer & Maintenance Office | Install Electric Baydoor Openers | Highway Trans. Fund 6 | 10000 | 10000 | 2016-11-18 | 0% | 0% | 0 | 0 | 10000
993 | 1001 | 395 | 11470402484 | San Augustine Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000
#N/A | #N/A | 396 | 11470402990 | Lufkin District Headquarters | SMFO Fire Exit | Highway Trans. Fund 6 | 0 | 150000 | 2016-11-25 | 0% | 0% | 0 | 0 | 150000
154 | 178 | 397 | 20470401635 | Beaumont District Headquarters | Replace Roof | Highway Trans. Fund 6 | 95000 | 95000 | 2016-12-20 | 0% | 0% | 0 | 0 | 95000
160 | 179 | 398 | 19470401643 | Atlanta District Headquarters | Building 300 Storage Needs Replace Roof | Highway Trans. Fund 6 | 200000 | 200000 | 2017-03-28 | 0% | 0% | 0 | 0 | 200000
256 | 268 | 399 | 13470401744 | Gonzales Maintenance Office | Roof Replacement | Highway Trans. Fund 6 | 200000 | 200000 | 2017-04-11 | 0% | 0% | 0 | 0 | 200000
267 | 279 | 400 | 12470401755 | Houston South Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 45000 | 45000 | 2017-04-11 | 0% | 0% | 0 | 0 | 45000
269 | 281 | 401 | 12470401757 | Rosenberg Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000
322 | 334 | 402 | 18470401811 | Ennis Maintenance Office | Roof - Coating Metal Roof Over Storage/Salt Shed | Highway Trans. Fund 6 | 40000 | 40000 | 2017-04-11 | 0% | 0% | 0 | 0 | 40000
139 | 175 | 403 | 12470401620 | Humble Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 87000 | 87000 | 2017-02-01 | 0% | 0% | 0 | 0 | 87000
328 | 340 | 404 | 38470401817 | Riverside Annex II RA150-200 | Replace Roof | Highway Trans. Fund 6 | 450000 | 450000 | 2017-07-12 | 0% | 0% | 0 | 0 | 450000
#N/A | #N/A | 405 | 24470402817 | 0 | Add Canopy | Highway Trans. Fund 6 | 0 | 25000 | 2017-02-03 | 0% | 0% | 0 | 0 | 25000
1111 | 1119 | 406 | 24470402602 | El Paso (West) Area Engineer & Maintenance Office | Install Truck Lift | Highway Trans. Fund 6 | 12500 | 12500 | 2017-01-24 | 0% | 0% | 0 | 0 | 12500
583 | 593 | 407 | 06470402072 | Andrews Maintenance Office | Repaint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | 2017-01-11 | 0% | 0% | 0 | 0 | 10000
110 | 165 | 408 | 10470401576 | Tyler District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 2017-04-25 | 0% | 0% | 0 | 0 | 350000
174 | 155 | 409 | 21470401660 | Pharr District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 2017-04-18 | 0% | 0% | 0 | 0 | 350000
8 | 150 | 410 | 11470401495 | Lufkin District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 2017-04-13 | 0% | 0% | 0 | 0 | 350000
197 | 197 | 411 | 18470402299 | Dallas District Headquarters | Remodel The District Main Office | Highway Trans. Fund 6 | 5653246 | 5653246 | 2018-07-19 | 0% | 0% | 0 | 0 | 5653246
882 | 890 | 412 | 24470402373 | Terlingua Sub-Section | Paint Interior Walls | Highway Trans. Fund 6 | 17500 | 17500 | 2017-01-30 | 0% | 0% | 0 | 0 | 17500
59 | 54 | 413 | 38470401689 | Camp Hubbard State Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 287500 | 1700000 | 2017-07-14 | 0% | 0% | 0 | 0 | 1700000
175 | 166 | 645 | 13470401662 | Yoakum District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 2017-06-13 | 0% | 0% | 0 | 0 | 350000
155 | 62 | 646 | 20470401636 | Beaumont District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 2017-03-28 | 0% | 0% | 0 | 0 | 350000
811 | 819 | 647 | 24470402301 | Dell City Maintenance Office | Install Bird Screens @ Truck Bays | Highway Trans. Fund 6 | 5500 | 5500 | 2017-02-24 | 0% | 0% | 0 | 0 | 5500
#N/A | 201 | 648 | 38470402977 | Riverside | ADA entrances and driveway | Highway Trans. Fund 6 | 0 | 0 | 2017-04-11 | 0% | 0% | 0 | 0 | 0
359 | 371 | 649 | 21470401848 | Zapata Maintenance Office Sub-Section | Repave Parking Lot | Highway Trans. Fund 6 | 19780 | 19780 | 2017-04-14 | 0% | 0% | 0 | 0 | 19780
1085 | 1093 | 650 | 21470402576 | District Headquarters | Flooring Replacement | Highway Trans. Fund 6 | 7000 | 7000 | 2017-04-14 | 0% | 0% | 0 | 0 | 7000
688 | 698 | 651 | 24470402177 | Fort Davis Maintenance Office | Insulate Interior Of Stock Room / Storage | Highway Trans. Fund 6 | 22500 | 22500 | 2016-11-22 | 0% | 0% | 0 | 0 | 22500
301 | 313 | 652 | 24470401790 | El Paso (East) Area Engineer & Maintenance Office | Upgrade Front/Rear Entrance Gates | Highway Trans. Fund 6 | 75000 | 75000 | 2016-10-19 | 0% | 0% | 0 | 0 | 75000
302 | 314 | 653 | 24470401791 | El Paso (West) Area Engineer & Maintenance Office | Secure The Lobby Area | Highway Trans. Fund 6 | 125000 | 125000 | 2017-03-22 | 0% | 0% | 0 | 0 | 125000
121 | 182 | 654 | 15470401592 | San Antonio District Headquarters | New HVAC In Shop Restrooms | Highway Trans. Fund 6 | 20000 | 20000 | 2017-03-13 | 0% | 0% | 0 | 0 | 20000
1089 | 1097 | 655 | 38470402580 | TxDOT Flight Services | Repair Drainage Issues Around Hangars Water Run Off Going Inside | Highway Trans. Fund 6 | 60000 | 125000 | 2242-03-27 | 0% | 0% | 0 | 0 | 125000
47 | 134 | 656 | 21470401559 | Hebbronville Area Engineer & Maintenance Office | Upgrade Lighting And Gates | Highway Trans. Fund 6 | 0 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000
#N/A | 85 | 657 | 08470402983 | Baird | Baird MNT slab repair - to be scope w/ Byron | Highway Trans. Fund 6 | 0 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000
#N/A | #N/A | 660 | 12470403017 | Angleton Area Engineer & Maintenance | Fuel System Repair | Highway Trans. Fund 6 | 0 | 0 | TBD | 0% | 0% | 0 | 0 | 0
#N/A | #N/A | 661 | 14470403018 | San Marcos Maintenance Office | Septic | Highway Trans. Fund 6 | 0 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000
#N/A | #N/A | 662 | 15470403020 | New Braunfels | Security | Highway Trans. Fund 7 | 0 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Phase I of Proj ID #15470401560 New Braunfels Security Gate
#N/A | #N/A | 663 | 08470402681 | Abilene District Headquarters | Add Canopy | Highway Trans. Fund 6 | 0 | 6500 | TBD | 0% | 0% | 0 | 0 | 6500
#N/A | #N/A | 664 | 18470402685 | Waxahachie Area Engineer & Maintenance Office | Add Canopy | Highway Trans. Fund 6 | 0 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000
#N/A | #N/A | 665 | 08470402690 | Sweetwater Maintenance Office | Add Canopy | Highway Trans. Fund 6 | 0 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000
#N/A | #N/A | 666 | 11470402692 | Center Maintenance Office | Add Canopy | Highway Trans. Fund 6 | 0 | 21000 | TBD | 0% | 0% | 0 | 0 | 21000
#N/A | #N/A | 667 | 24470402703 | Marfa Sub-Section | Add Canopy | Highway Trans. Fund 6 | 0 | 21500 | TBD | 0% | 0% | 0 | 0 | 21500
#N/A | #N/A | 668 | 24470402704 | Presidio Maintenance Office | Add Canopy | Highway Trans. Fund 6 | 0 | 21500 | TBD | 0% | 0% | 0 | 0 | 21500
#N/A | #N/A | 669 | 24470402705 | Terlingua Sub-Section | Add Canopy | Highway Trans. Fund 6 | 0 | 21500 | TBD | 0% | 0% | 0 | 0 | 21500
#N/A | #N/A | 670 | 24470402706 | Van Horn Maintenance Office | Add Canopy | Highway Trans. Fund 6 | 0 | 11500 | TBD | 0% | 0% | 0 | 0 | 11500
#N/A | #N/A | 671 | 11470402711 | Shepherd Maintenance Office | Add Canopy | Highway Trans. Fund 6 | 0 | 21000 | TBD | 0% | 0% | 0 | 0 | 21000
1185b | #NA | 672 | 38470402678 | Statewide | Emergency Repairs - Statewide | Highway Trans. Fund 6 | 0 | 9526514.31 | TBD | 0% | 0% | 0 | 0 | 9526514.31
PROJECTS CURRENTLY FUNDED $57.5M | [6 empty] | 41121926 | 57500000 |  |  |  | 5139553.74 | 481242.78 | 57500000
199 | 213 | 673 | 24470401509 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000
200 | 214 | 674 | 07470401516 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000
201 | 215 | 675 | 07470401520 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 224000 | 224000
202 | 216 | 676 | 25470401521 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 224000 | 224000
204 | 218 | 677 | 05470401523 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1680000 | 1680000
205 | 219 | 678 | 06470401524 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1120000 | 1120000
206 | 220 | 679 | 08470401528 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1120000 | 1120000
207 | 221 | 680 | 04470401529 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1680000 | 1680000
208 | 222 | 681 | 17470401531 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
209 | 223 | 682 | 16470401534 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 896000 | 896000
210 | 224 | 683 | 11470401537 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 784000 | 784000
211 | 225 | 684 | 02470401548 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000
212 | 226 | 685 | 15470401550 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000
213 | 227 | 686 | 18470401551 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000
214 | 228 | 687 | 05470401552 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000
215 | 229 | 688 | 01470401556 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
216 | 230 | 689 | 01470401557 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 672000 | 672000
203 | 217 | 690 | 25470401522 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1120000 | 1120000
218 | 232 | 691 | 15470401560 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000
219 | 233 | 692 | 10470401561 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000
220 | 234 | 693 | 10470401562 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000
221 | 235 | 694 | 09470401563 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000
222 | 236 | 695 | 03470401564 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
223 | 237 | 696 | 03470401565 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 784000 | 784000
224 | 238 | 697 | 13470401566 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000
225 | 239 | 698 | 21470401569 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000
226 | 240 | 699 | 22470401586 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000
227 | 241 | 700 | 09470401603 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000
228 | 242 | 701 | 19470401608 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
229 | 243 | 702 | 19470401609 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 672000 | 672000
217 | 231 | 703 | 21470401558 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
231 | 244 | 704 | 06470401614 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
233 | 245 | 705 | 13470401618 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
234 | 246 | 706 | 13470401622 | Austin Cty Maint. | Repair Leaking Metal Roofs | Highway Trans. Fund 6 | 50000 | 50000
235 | 247 | 707 | 04470401624 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
236 | 248 | 708 | 23470401637 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 784000 | 784000
237 | 249 | 709 | 17470401647 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 784000 | 784000
238 | 250 | 710 | 20470401666 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
239 | 251 | 711 | 18470401668 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000
240 | 252 | 712 | 02470401678 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 672000 | 672000
241 | 253 | 713 | 12470401679 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 784000 | 784000
242 | 254 | 714 | 11470401681 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
243 | 255 | 715 | 20470401706 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 672000 | 672000
244 | 256 | 716 | 23470401707 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 224000 | 224000
245 | 257 | 717 | 06470401709 | Iraan Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 6 | 1500 | 1500
246 | 258 | 718 | 12470401714 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000
247 | 259 | 719 | 24470401715 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
248 | 260 | 720 | 22470401716 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000
249 | 261 | 721 | 06470401717 | Balmorhea Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 6 | 1500 | 1500
250 | 262 | 722 | 14470401727 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000
251 | 263 | 723 | 16470401732 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000
252 | 264 | 724 | 15470401740 | District Headquarters | New Boiler | Highway Trans. Fund 6 | 20000 | 20000
254 | 266 | 725 | 10470401742 | Jacksonville Maintenance Office | Site Improvements | Highway Trans. Fund 6 | 12000 | 12000
255 | 267 | 726 | 13470401743 | Gonzales Cty Maint. | Convert Flat Roof To Gable Style | Highway Trans. Fund 6 | 250000 | 250000
258 | 270 | 727 | 04470401746 | Loop | New Generator | Highway Trans. Fund 6 | 12500 | 12500
262 | 274 | 728 | 22470401750 | Del Rio Maintenance Office (US 90) | Upgrade HVAC | Highway Trans. Fund 6 | 10000 | 10000
268 | 280 | 729 | 12470401756 | Humble Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 87000 | 87000
270 | 282 | 730 | 22470401758 | District Headquarters | New HVAC In Shop Restrooms | Highway Trans. Fund 6 | 20000 | 20000
271 | 283 | 731 | 22470401759 | District Headquarters | Replace Roof | Highway Trans. Fund 6 | 225000 | 225000
272 | 284 | 732 | 22470401760 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000
273 | 285 | 733 | 22470401761 | Laredo Area Engineer & Maintenance Office | Exterior Lighting | Highway Trans. Fund 6 | 40000 | 40000
275 | 287 | 734 | 22470401763 | Laredo Auto Shop | Restrooms HVAC | Highway Trans. Fund 6 | 20000 | 20000
276 | 288 | 735 | 22470401764 | Laredo District Headquarters | Repair MNT To Auto Shop Roof | Highway Trans. Fund 6 | 250000 | 250000
278 | 290 | 736 | 22470401766 | Laredo Traffic | Replace Computer/Storage Room HVAC | Highway Trans. Fund 6 | 15000 | 15000
280 | 292 | 737 | 24470401768 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000
282 | 294 | 738 | 15470401770 | Bexar Metro Area Engineer & Maintenance Office | HVAC Upgrade | Highway Trans. Fund 6 | 15000 | 15000
290 | 302 | 739 | 20470401779 | Beaumont Area Engineer & Maintenance Office | Install Card Reader Access | Highway Trans. Fund 6 | 16000 | 16000
291 | 303 | 740 | 25470401780 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000
293 | 305 | 741 | 18470401782 | District Headquarters | Fire/Sprinkler Upgrade (Obsolete Panels) | Highway Trans. Fund 6 | 25000 | 25000
294 | 306 | 742 | 13470401783 | Fayette Cty Maint. | Upgrade Apu To Supply Entire Maintenace Building | Highway Trans. Fund 6 | 125000 | 125000
295 | 307 | 743 | 20470401784 | Liberty Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 7500 | 7500
296 | 308 | 744 | 20470401785 | Liberty Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 18000 | 18000
304 | 316 | 745 | 22470401793 | Freer | HVAC Replacement | Highway Trans. Fund 6 | 17000 | 17000
305 | 317 | 746 | 05470401794 | District Headquarters | Replace Roof | Highway Trans. Fund 6 | 40000 | 40000
310 | 322 | 747 | 18470401799 | Cedar Hill Maintenance Office | Install Gates - Electric/Key Pad | Highway Trans. Fund 6 | 20000 | 20000
314 | 326 | 748 | 22470401803 | La Pryor on HWY 57 | Install Gate Operator And Key Pad | Highway Trans. Fund 6 | 5000 | 5000
315 | 327 | 749 | 18470401804 | Corsicana Area Engineer & Maintenance Office | Fire/Sprinkler Upgrade (Obsolete Panels) | Highway Trans. Fund 6 | 25000 | 25000
318 | 330 | 750 | 12470401807 | District Headquarters | Install CCTV Security Camera (Parking Garage) | Highway Trans. Fund 6 | 20000 | 20000
320 | 332 | 751 | 12470401809 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000
321 | 333 | 752 | 16470401810 | Aransas Co. | Replace Roof On The Maintenance Building | Highway Trans. Fund 6 | 250000 | 250000
323 | 335 | 753 | 06470401812 | Ft Stockton Area Engineer & Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 6 | 1500 | 1500
327 | 339 | 754 | 38470401816 | Riverside Annex II RA150-200 | Install Redundant UPS for Data Center | Highway Trans. Fund 6 | 250000 | 250000
330 | 342 | 755 | 38470401819 | Riverside Annex II RA150-200 | Roof and Weatherize Exterior | Highway Trans. Fund 6 | 350000 | 350000
332 | 344 | 756 | 21470401821 | Edcouch Maintenance Office | Add Exit Only Gate To East Side | Highway Trans. Fund 6 | 16000 | 16000
333 | 345 | 757 | 17470401822 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000
336 | 348 | 758 | 21470401825 | Pharr Area Engineer & Maintenance Office | Rework Concrete Drainage Structure | Highway Trans. Fund 6 | 11000 | 11000
337 | 349 | 759 | 22470401826 | Del Rio | Sprinkler System Repair & Upgrade | Highway Trans. Fund 6 | 20000 | 20000
338 | 350 | 760 | 22470401827 | Del Rio Maintenance Office | Furnish/Install Bollard | Highway Trans. Fund 6 | 5000 | 5000
342 | 354 | 761 | 07470401831 | Eden Maintenance Office | Install New 10,000 Gallon Brine Storge Tank | Highway Trans. Fund 6 | 6000 | 6000
343 | 355 | 762 | 07470401832 | Eden Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000
344 | 356 | 763 | 07470401833 | Eden Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000
345 | 357 | 764 | 24470401834 | Fort Hancock Sub-Section | Demolish Old Asphalt Storage Tank. | Highway Trans. Fund 6 | 8400 | 8400
346 | 358 | 765 | 24470401835 | Fort Hancock Sub-Section | Install Back Rockwall | Highway Trans. Fund 6 | 18000 | 18000
347 | 359 | 766 | 07470401836 | Leakey Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 15000 | 15000
348 | 360 | 767 | 07470401837 | Leakey Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000
349 | 361 | 768 | 07470401838 | Leakey Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000
351 | 363 | 769 | 07470401840 | Ballinger Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 30000 | 30000
352 | 364 | 770 | 07470401841 | Ballinger Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000
353 | 365 | 771 | 07470401842 | Ballinger Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 122000 | 122000
356 | 368 | 772 | 16470401845 | Jim Wells Co. | Add Additional Lateral Lines To Septic System At The Alice Ae Office | Highway Trans. Fund 6 | 15000 | 15000
357 | 369 | 773 | 18470401846 | Ennis Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 20000 | 20000
360 | 372 | 774 | 20470401849 | Anahuac Maintenance Office | Rehab Parking Lot And Drainage | Highway Trans. Fund 6 | 30000 | 30000
361 | 373 | 775 | 20470401850 | Anahuac Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 20000 | 20000
363 | 375 | 776 | 20470401852 | Newton Maintenance Office | Remove Out Of Service Emulsion, Linseed Oil & Asts | Highway Trans. Fund 6 | 55000 | 55000
364 | 376 | 777 | 20470401853 | Stowel Maintenance Office | Electric Service To Yard | Highway Trans. Fund 6 | 4000 | 4000
366 | 378 | 778 | 18470401855 | District Headquarters | Site Improvements | Highway Trans. Fund 6 | 207000 | 207000
367 | 379 | 779 | 18470401856 | District Headquarters | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 75000 | 75000
369 | 381 | 780 | 22470401858 | Brackettville | Fuel Pump Replacements | Highway Trans. Fund 6 | 15000 | 15000
370 | 382 | 781 | 22470401859 | Brackettville | Landscaping & Irrigation | Highway Trans. Fund 6 | 45000 | 45000
371 | 383 | 782 | 07470401860 | San Angelo Area Engineer & Maintenance Office | Overlay And Restripe Parking Lot | Highway Trans. Fund 6 | 25000 | 25000
372 | 384 | 783 | 07470401861 | San Angelo Maintenance Office | Install New Automated Vehicle Entry Gate | Highway Trans. Fund 6 | 25000 | 25000
373 | 385 | 784 | 07470401862 | San Angelo Maintenance Office | Pavement Seal Coat and Restripe | Highway Trans. Fund 6 | 25000 | 25000
374 | 386 | 785 | 07470401863 | San Angelo Maintenance Office | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 6 | 75000 | 75000
376 | 388 | 786 | 07470401865 | Sterling City Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000
377 | 389 | 787 | 07470401866 | Sterling City Maintenance Office | Replace Automated Swing Gate With Automated Sliding Gate | Highway Trans. Fund 6 | 25000 | 25000
378 | 390 | 788 | 07470401867 | Sterling City Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000
379 | 391 | 789 | 25470401868 | Munday Maintenance Office | Resurface Parking Lot | Highway Trans. Fund 6 | 25000 | 25000
381 | 393 | 790 | 05470401870 | Post RDC | Site Work And Concrete Flume | Highway Trans. Fund 6 | 50000 | 50000
382 | 394 | 791 | 21470401871 | Raymondville Maintenance Office | New Fire Proof Overhead Doors | Highway Trans. Fund 6 | 20000 | 20000
383 | 395 | 792 | 21470401872 | Raymondville Maintenance Office | Resurface Maintenance Yard | Highway Trans. Fund 6 | 134800 | 134800
384 | 396 | 793 | 10470401873 | District Headquarters | Modifications/Upgrade Site | Highway Trans. Fund 6 | 110000 | 110000
385 | 397 | 794 | 08470401874 | District Headquarters | Parking Lot Reconfiguration | Highway Trans. Fund 6 | 150000 | 150000
388 | 400 | 795 | 24470401877 | Fort Davis Maintenance Office | Demolish Old Emulsion Tank | Highway Trans. Fund 6 | 8500 | 8500
389 | 401 | 796 | 24470401878 | Fort Davis Maintenance Office | Install Sprinkler System | Highway Trans. Fund 6 | 20000 | 20000
390 | 402 | 797 | 02470401879 | District Headquarters | Site Improvements | Highway Trans. Fund 6 | 303000 | 303000
391 | 403 | 798 | 06470401880 | District Headquarters | Modifications/Upgrade Site | Highway Trans. Fund 6 | 150000 | 150000
392 | 404 | 799 | 06470401881 | District Headquarters | Xeroscape Grounds | Highway Trans. Fund 6 | 264000 | 264000
393 | 405 | 800 | 06470401882 | Odessa Maintenance Office | Reconfigure Parking In Front Of Office | Highway Trans. Fund 6 | 30000 | 30000
396 | 408 | 801 | 07470401885 | Junction Area Engineer & Maintenance Office | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 6 | 75000 | 75000
398 | 410 | 802 | 07470401887 | Junction Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000
399 | 411 | 803 | 07470401888 | Junction Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000
400 | 412 | 804 | 15470401889 | District Headquarters | Change Out Galvanized Water Main Piping | Highway Trans. Fund 6 | 25000 | 25000
401 | 413 | 805 | 15470401890 | District Headquarters | Change Out Galvanized Water Main Piping | Highway Trans. Fund 6 | 25000 | 25000
402 | 414 | 806 | 15470401891 | District Headquarters | Parking Lot Resurfacing & Reconfiguration | Highway Trans. Fund 6 | 200000 | 200000
403 | 415 | 807 | 06470401892 | Monahans Maintenance Office | Connect to City Sewer Utililty Line | Highway Trans. Fund 6 | 20000 | 20000
405 | 417 | 808 | 15470401894 | Seguin Area Engineer & Maintenance Office | Replace Radio Tower | Highway Trans. Fund 6 | 150000 | 150000
406 | 418 | 809 | 07470401895 | Sonora Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000
407 | 419 | 810 | 13470401896 | Austin Cty Maint. | Install Above Ground Fuel System/New Dispenser | Highway Trans. Fund 6 | 250000 | 250000
408 | 420 | 811 | 13470401897 | Colorado Cty Maint. | Install Above Ground Fuel System/New Dispenser | Highway Trans. Fund 6 | 250000 | 250000
409 | 421 | 812 | 20470401898 | Beaumont Area Engineer & Maintenance Office | Additional Sidewalks | Highway Trans. Fund 6 | 15000 | 15000
410 | 422 | 813 | 20470401899 | District Headquarters | Modifications/Upgrade Site Utilities | Highway Trans. Fund 6 | 101000 | 101000
411 | 423 | 814 | 20470401900 | District Headquarters | Rehab Parking Lot And Stripe | Highway Trans. Fund 6 | 450000 | 450000
414 | 426 | 815 | 20470401903 | Districtwide | Re-Stripe Parking Lots And Hc Spaces | Highway Trans. Fund 6 | 25000 | 25000
415 | 427 | 816 | 07470401904 | Rocksprings Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000
416 | 428 | 817 | 07470401905 | Rocksprings Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 122000 | 122000
417 | 429 | 818 | 03470401906 | District Headquarters | Construct In-Ground Storm Shelter | Highway Trans. Fund 6 | 45000 | 45000
418 | 430 | 819 | 03470401907 | District Headquarters | Modifications/Upgrade Site Utilities | Highway Trans. Fund 6 | 200000 | 200000
419 | 431 | 820 | 03470401908 | District Headquarters | Repave Parking Lot - Wichita Falls DHQ | Highway Trans. Fund 6 | 150000 | 150000
420 | 432 | 821 | 16470401909 | District Headquarters | Modifications/Upgrade Site | Highway Trans. Fund 6 | 100000 | 100000
421 | 433 | 822 | 16470401910 | District Headquarters | Modifications/Upgrade Site Utilities | Highway Trans. Fund 6 | 125000 | 125000
422 | 434 | 823 | 16470401911 | District Headquarters | Rehab Existing Parking Lots On Entire Campus | Highway Trans. Fund 6 | 200000 | 200000
423 | 435 | 824 | 16470401912 | District Headquarters | Repair Sidewalk Or Parking Lot - Corpus Christi DHQ | Highway Trans. Fund 6 | 25000 | 25000
425 | 437 | 825 | 16470401914 | District Headquarters | Replace Fuel Dispenser At Maintenance Special Jobs - Corpus Christi DHQ | Highway Trans. Fund 6 | 20000 | 20000
427 | 439 | 826 | 06470401916 | Crane Maintenance Office | Paint 10000 Gal Asphalt Tank & Insulate | Highway Trans. Fund 6 | 15000 | 15000
428 | 440 | 827 | 21470401917 | District Headquarters | Upgrade Landscaping to include Hike And Bike Trail | Highway Trans. Fund 6 | 100000 | 100000
429 | 441 | 828 | 21470401918 | District Headquarters | Increase Parking Area | Highway Trans. Fund 6 | 350000 | 350000
430 | 442 | 829 | 21470401919 | District Headquarters | Parking Lot Improvements | Highway Trans. Fund 6 | 400000 | 400000
432 | 444 | 830 | 07470401921 | Ozona Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000
433 | 445 | 831 | 07470401922 | Ozona Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000
434 | 446 | 832 | 13470401923 | District Headquarters | Install Above Ground Fuel System/New Dispenser | Highway Trans. Fund 6 | 250000 | 250000
435 | 447 | 833 | 13470401924 | District Headquarters | Replace Deteriorating Natural Gas Lines And Exterior Valves | Highway Trans. Fund 6 | 40000 | 40000
436 | 448 | 834 | 20470401925 | Port Arthur Area Engineer & Maintenance Office | Rehab Parking Lot And Stripe | Highway Trans. Fund 6 | 100000 | 100000
437 | 449 | 835 | 23470401926 | District Headquarters | Site Improvements | Highway Trans. Fund 6 | 155000 | 155000
438 | 450 | 836 | 18470401927 | Waxahachie Area Engineer & Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 40000 | 40000
440 | 452 | 837 | 18470401929 | Rockwall Maintenance Office | Asphalt Emulsion Tank Installation | Highway Trans. Fund 6 | 25000 | 25000
443 | 455 | 838 | 22470401932 | Carrizo Springs (Area Engineer & Maintenance Office & Lab) | Upgrade Sprinkler System | Highway Trans. Fund 6 | 5000 | 5000
444 | 456 | 839 | 07470401933 | District Headquarters | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 30000 | 30000
445 | 457 | 840 | 07470401934 | District Headquarters | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 6 | 75000 | 75000
447 | 458 | 841 | 20470401936 | Kountze Maintenance Office | Rehab Parking Lot And Stripe | Highway Trans. Fund 6 | 100000 | 100000
448 | 459 | 842 | 24470401937 | Terlingua Sub-Section | Resufacing of Parking Lot | Highway Trans. Fund 6 | 25000 | 25000
449 | 460 | 843 | 13470401938 | Wharton Cty Maint. | Build New Berm Around Asphalt Tanks | Highway Trans. Fund 6 | 40000 | 40000
452 | 462 | 844 | 18470401941 | Hutchins Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 40000 | 40000
453 | 463 | 845 | 18470401942 | Hutchins Maintenance Office | Parking Lot Striping | Highway Trans. Fund 6 | 10000 | 10000
454 | 464 | 846 | 18470401943 | NW Dallas Maintenance Office | Modular Building/Site Prep | Highway Trans. Fund 6 | 110000 | 110000
455 | 465 | 847 | 24470401944 | Alpine Area Engineer & Maintenance Office | Demolish Old Emulsion Tank | Highway Trans. Fund 6 | 8400 | 8400
457 | 467 | 848 | 21470401946 | San Benito Area Engineer & Maintenance Office | Fuel Tank Relocation | Highway Trans. Fund 6 | 125000 | 125000
458 | 468 | 849 | 21470401947 | San Benito Area Engineer & Maintenance Office | Improve Drainage | Highway Trans. Fund 6 | 150000 | 150000
459 | 469 | 850 | 21470401948 | San Benito Area Engineer & Maintenance Office | Repair Sewer Line At Rear Of Yard, Add Approx. 8 Manholes. | Highway Trans. Fund 6 | 50000 | 50000
460 | 470 | 851 | 21470401949 | San Benito Area Engineer & Maintenance Office | Resurface Parking Lot | Highway Trans. Fund 6 | 26200 | 26200
461 | 471 | 852 | 07470401950 | Robert Lee Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000
462 | 472 | 853 | 07470401951 | Rocksprings Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 30000 | 30000
464 | 474 | 854 | 21470401953 | Laguna Vista Maintenance Office Sub-Section | Repair Fuel Dispensing Pumps & Tanks | Highway Trans. Fund 6 | 12000 | 12000
465 | 475 | 855 | 15470401954 | Bandera Maintenance Office | Connect To City Water/Sewer | Highway Trans. Fund 6 | 350000 | 350000
466 | 476 | 856 | 24470401955 | Pine Springs Sub-Section | Demolish Old Emulsion Tank | Highway Trans. Fund 6 | 8500 | 8500
469 | 479 | 857 | 07470401958 | Big Lake Maintenance Office | Install New Above Ground Fuel Tanks | Highway Trans. Fund 6 | 50000 | 50000
470 | 480 | 858 | 07470401959 | Big Lake Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000
471 | 481 | 859 | 07470401960 | Big Lake Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000
472 | 482 | 860 | 14470401961 | Burnet Area Engineer & Maintenance Office | Parking Lot Overlay | Highway Trans. Fund 6 | 95000 | 95000
473 | 483 | 861 | 23470401962 | Goldthwaite Maintenance Office | Remove Underground Fuel Tanks And Install Above Ground Tanks | Highway Trans. Fund 6 | 75000 | 75000
474 | 484 | 862 | 07470401963 | Menard Maintenance Office | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 6 | 75000 | 75000
475 | 485 | 863 | 16470401964 | Corpus Christi Area Engineer & Maintenance Office | Repair Fuel Monitoring System - Corpus Christi AEM | Highway Trans. Fund 6 | 5000 | 5000
476 | 486 | 864 | 16470401965 | San Patricio Co | Replace Existing Sewage Line Running To Lift Station | Highway Trans. Fund 6 | 30000 | 30000
477 | 487 | 865 | 16470401966 | Sinton Area Engineer & Maintenance Office | Replace Sewer Line | Highway Trans. Fund 6 | 25000 | 25000
478 | 488 | 866 | 10470401967 | Jacksonville Maintenance Office | Parking Improvements | Highway Trans. Fund 6 | 120000 | 120000
479 | 489 | 867 | 22470401968 | Del Rio Maintenance Office | Irrigation Replacement | Highway Trans. Fund 6 | 15000 | 15000
480 | 490 | 868 | 05470401969 | Tulia Maintenance Office | New 2" Water Line Installation | Highway Trans. Fund 6 | 20000 | 20000
481 | 491 | 869 | 22470401970 | Cotulla Maintenance Office | Install French Drainage | Highway Trans. Fund 6 | 20000 | 20000
482 | 492 | 870 | 22470401971 | Cotulla Maintenance Office | Install Irrigation And Landscaping | Highway Trans. Fund 6 | 4250 | 4250
483 | 493 | 871 | 22470401972 | Cotulla Maintenance Office | Repave & Stripe Empl & Visitor Parking Lot | Highway Trans. Fund 6 | 105000 | 105000
484 | 494 | 872 | 20470401973 | Jasper Area Engineer & Maintenance Office | Add Connection To Public Supply For Water And Sanitary Sewer System | Highway Trans. Fund 6 | 150000 | 150000
485 | 495 | 873 | 20470401974 | Jasper Area Engineer & Maintenance Office | Remove Out Of Service Emulsion, Linseed Oil & Asts | Highway Trans. Fund 6 | 20000 | 20000
486 | 496 | 874 | 12470401975 | Conroe Area Engineer & Maintenance Office | Sitework Modifications (Drivewal And Visitor Parking) | Highway Trans. Fund 6 | 70000 | 70000
487 | 497 | 875 | 22470401976 | District Headquarters | Parking Lot Reconfiguration | Highway Trans. Fund 6 | 125000 | 125000
488 | 498 | 876 | 22470401977 | Laredo Administration & Area Engineer & Maintenance Office | Irrigation, Landscaping, Grass Seeds, Planting/Adding Trees | Highway Trans. Fund 6 | 225000 | 225000
489 | 499 | 877 | 22470401978 | Laredo District Headquarters | Reconfigure Landscaping For Walking Trail | Highway Trans. Fund 6 | 80000 | 80000
490 | 500 | 878 | 24470401979 | District Headquarters | Site Improvements | Highway Trans. Fund 6 | 318000 | 318000
491 | 501 | 879 | 13470401980 | District Headquarters | Replace Natural Gas Lines | Highway Trans. Fund 6 | 40000 | 40000
492 | 502 | 880 | 25470401981 | Clarendon Maintenance Office | Replace Fuel Station | Highway Trans. Fund 6 | 50000 | 50000
493 | 503 | 881 | 18470401982 | Denton Area Engineer & Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 40000 | 40000
496 | 506 | 882 | 20470401985 | Liberty Area Engineer & Maintenance Office | Regrade Parking And Drainage | Highway Trans. Fund 6 | 75000 | 75000
497 | 507 | 883 | 24470401986 | El Paso (East) Area Engineer & Maintenance Office | Install/Repair Rock Wall Front And Rear | Highway Trans. Fund 6 | 100000 | 100000
499 | 509 | 884 | 22470401988 | Freer | Irrigation And Landscaping | Highway Trans. Fund 6 | 10000 | 10000
500 | 510 | 885 | 38470401989 | CEDAR PARK Research and Technology Center | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 6 | 60000 | 60000
501 | 511 | 886 | 10470401990 | South Tyler Area Engineer & Maintenance Office | Sewer Connect To City - South Tyler Area Engineer And Maintenance Facility | Highway Trans. Fund 6 | 300000 | 300000
502 | 512 | 887 | 16470401991 | Beeville Maintenance Office | Repair Fuel Monitoring System - Beeville MNT | Highway Trans. Fund 6 | 5000 | 5000
503 | 513 | 888 | 16470401992 | Beeville Maintenance Office | Replace\New Fuel Dispenser/Fuel Pump At Maintenance - Beeville MNT | Highway Trans. Fund 6 | 20000 | 20000
504 | 514 | 889 | 08470401993 | Abilene Maintenance Office | Reroute Wash Bay Drain To City Sewer Drain | Highway Trans. Fund 6 | 10000 | 10000
505 | 515 | 890 | 22470401994 | La Pryor Maintenance Office | Resurface 2 Acres Of Parking Area In Yard & Strip Where Needed | Highway Trans. Fund 6 | 152000 | 152000
508 | 518 | 891 | 13470401997 | Fayette Cty Maint. | Eliminate Wash Rack Waste Water Recycle System And Convert To City Utilities | Highway Trans. Fund 6 | 75000 | 75000
509 | 519 | 892 | 18470401998 | Corsicana Area Engineer & Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 40000 | 40000
511 | 521 | 893 | 21470402000 | Laguna Vista Maintenance Office Sub-Section | Replace Fuel Pump Canopy | Highway Trans. Fund 6 | 13000 | 13000
512 | 522 | 894 | 15470402001 | New Braunfels Area Engineer & Maintenance Office | Parking Lot Reconfiguration | Highway Trans. Fund 6 | 50000 | 50000
513 | 523 | 895 | 10470402002 | Athens Area Engineer & Maintenance Office | Parking Improvements | Highway Trans. Fund 6 | 70000 | 70000
515 | 525 | 896 | 17470402004 | District Headquarters | Parking Area Pavement | Highway Trans. Fund 6 | 450000 | 450000
518 | 528 | 897 | 24470402007 | Marathon Sub-Section | Insulate Interior Roof And Walls, Spray Foam. | Highway Trans. Fund 6 | 50000 | 50000
519 | 529 | 898 | 16470402008 | District Headquarters | Replace Floor In Lab Building District | Highway Trans. Fund 6 | 75000 | 75000
520 | 530 | 899 | 16470402009 | George West Maintenance Office | Install Electrical - George West MNT | Highway Trans. Fund 6 | 40000 | 40000
521 | 531 | 900 | 16470402010 | Goliad Co. | Replace Metal Siding On Office Building With New Siding | Highway Trans. Fund 6 | 50000 | 50000
522 | 532 | 901 | 16470402011 | Goliad Co. | Replace Sliding Garage Doors With Overhead Doors | Highway Trans. Fund 6 | 15000 | 15000
524 | 534 | 902 | 19470402013 | District Headquarters | Remodel Inside Of Building | Highway Trans. Fund 6 | 90000 | 90000
525 | 535 | 903 | 19470402014 | District Headquarters | Window Replacement | Highway Trans. Fund 6 | 200000 | 200000
526 | 536 | 904 | 25470402015 | Guthrie Maintenance Office SS | Re-Skin Exterior, Insulate Bujilding, Install Windows, Roof, & Doors, Upgrade Rest Room | Highway Trans. Fund 6 | 300000 | 300000
527 | 537 | 905 | 01470402016 | District Headquarters | Abatement Of Roof And Walls (Monitoring) | Highway Trans. Fund 6 | 10000 | 10000
528 | 538 | 906 | 01470402017 | District Headquarters | Abatement Of Roof And Walls (Remediation) | Highway Trans. Fund 6 | 20000 | 20000
529 | 539 | 907 | 01470402018 | District Headquarters | Abatement Of Roof And Walls (Testing) | Highway Trans. Fund 6 | 10000 | 10000
530 | 540 | 908 | 01470402019 | District Headquarters | Boiler And Chiller Repairs | Highway Trans. Fund 6 | 100000 | 100000
532 | 542 | 909 | 01470402021 | District Headquarters | Renovate DHQ Campus | Highway Trans. Fund 6 | 1950000 | 1950000
533 | 543 | 910 | 21470402022 | Pharr Area Engineer & Maintenance Office | Add Office And Reconfigure Space | Highway Trans. Fund 6 | 4000 | 4000
534 | 544 | 911 | 21470402023 | Pharr Area Engineer & Maintenance Office | Add Vestibule | Highway Trans. Fund 6 | 10200 | 10200
535 | 545 | 912 | 22470402024 | Del Rio Maintenance Office | Convert 2Nd Floor Into Four Offices And Restroom Renovation | Highway Trans. Fund 6 | 75000 | 75000
536 | 546 | 913 | 22470402025 | Del Rio Maintenance Office | Replace Flooring In Mechanical Room | Highway Trans. Fund 6 | 30000 | 30000
537 | 547 | 914 | 22470402026 | Del Rio Maintenance Office | Roof & Exterior Painting | Highway Trans. Fund 6 | 70000 | 70000
541 | 551 | 915 | 11470402030 | District Headquarters | Renovate Baydoor Offices | Highway Trans. Fund 6 | 10000 | 10000
545 | 555 | 916 | 16470402034 | Refugio Co. | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 6 | 40000 | 40000
546 | 556 | 917 | 16470402035 | Refugio Co. | Replace Metal Siding On Office Building With New Siding | Highway Trans. Fund 6 | 50000 | 50000
547 | 557 | 918 | 16470402036 | Refugio Maintenance Office | Repair Structure At Maintenance - Refugio Maintenance | Highway Trans. Fund 6 | 10000 | 10000
548 | 558 | 919 | 06470402037 | Andrews Maintenance Office | Replace Garage Door W/Panel & Electric Open. | Highway Trans. Fund 6 | 8000 | 8000
549 | 559 | 920 | 06470402038 | Andrews Maintenance Office | Replace Metal Roof & Exterior Walls, Insulate | Highway Trans. Fund 6 | 22000 | 22000
551 | 561 | 921 | 03470402040 | Bowie Maintenance Office | Close In Front Of New Truck Shed And Add 4 Roll Up Doors | Highway Trans. Fund 6 | 80000 | 80000
552 | 562 | 922 | 10470402041 | District Headquarters | Replace Windows | Highway Trans. Fund 6 | 150000 | 150000
553 | 563 | 923 | 38470402042 | Camp Hubbard State Headquarters | Complete Renovation Of 5th Floor | Highway Trans. Fund 6 | 500000 | 500000
554 | 564 | 924 | 38470402043 | Camp Hubbard State Headquarters | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 6 | 150000 | 150000
557 | 567 | 925 | 20470402046 | Woodville Maintenance Office | Reskin, Replace Lighting And Reroof Bld | Highway Trans. Fund 6 | 95000 | 95000
558 | 568 | 926 | 25470402047 | Memphis Maintenance Office | Replace Floor Tiles, Upgrade Rest Room; Redesign Office Space | Highway Trans. Fund 6 | 75000 | 75000
559 | 569 | 927 | 25470402048 | Memphis Maintenance Office | Re-Skin Exterior, Install Roof, New Windows and Remove Sky Lights W/ Roof Replacement; Redesign Parking Area | Highway Trans. Fund 6 | 335000 | 335000
560 | 570 | 928 | 04470402049 | Canadian Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000
561 | 571 | 929 | 24470402050 | Fort Hancock Sub-Section | Add Rolling Doors To Existing Storage Bldg. | Highway Trans. Fund 6 | 6000 | 6000
562 | 572 | 930 | 24470402051 | Fort Hancock Sub-Section | Exterior Renovations | Highway Trans. Fund 6 | 100000 | 100000
563 | 573 | 931 | 24470402052 | Fort Hancock Sub-Section | Install Entrance Weather Canopy, Front Door. Add Rolling Doors To Existing Storage Bldg. | Highway Trans. Fund 6 | 8100 | 8100
564 | 574 | 932 | 04470402053 | Darouzett Maintenance Office | New Shop Heaters | Highway Trans. Fund 6 | 15000 | 15000
565 | 575 | 933 | 04470402054 | Darrouzett Maintenance Office | Abate and Remodel Office Area | Highway Trans. Fund 6 | 75000 | 75000
566 | 576 | 934 | 04470402055 | Gruver Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000
567 | 577 | 935 | 04470402056 | Channing Maintenance Office | Electrical Upgrades | Highway Trans. Fund 6 | 8000 | 8000
568 | 578 | 936 | 04470402057 | Channing Maintenance Office | New Unit Heaters | Highway Trans. Fund 6 | 15000 | 15000
569 | 579 | 937 | 04470402058 | Channing Maintenance Office | Replace Roof, Re-Skin Exterior, Install New Insulation And Windows | Highway Trans. Fund 6 | 175000 | 175000
570 | 580 | 938 | 04470402059 | Channing Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000
571 | 581 | 939 | 17470402060 | Brenham Area Engineer & Maintenance Office | Install Bathroom/Showers In Shop/Welding Shop | Highway Trans. Fund 6 | 25000 | 25000
572 | 582 | 940 | 05470402061 | Post Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000
573 | 583 | 941 | 05470402062 | Post Maintenance Office | Re-Skin Renovate Shop | Highway Trans. Fund 6 | 150000 | 150000
574 | 584 | 942 | 04470402063 | Panhandle Maintenance Office | Enlarge Supervisor Office And Breakroom | Highway Trans. Fund 6 | 50000 | 50000
575 | 585 | 943 | 04470402064 | Panhandle Maintenance Office | Install Overhead Doors And Openers | Highway Trans. Fund 6 | 25000 | 25000
576 | 586 | 944 | 04470402065 | Panhandle Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000
577 | 587 | 945 | 25470402066 | Munday Maintenance Office | Upgrade Electrical & Lights In Maintenance Barn | Highway Trans. Fund 6 | 30000 | 30000
578 | 588 | 946 | 16470402067 | Goliad Co. | Replace Metal Siding On Equipment Shed And Roof With New Siding And Roof | Highway Trans. Fund 6 | 60000 | 60000
579 | 589 | 947 | 16470402068 | Goliad Maintenance Office | Replace Exterior Door At Equipment Storage - Goliad MNT | Highway Trans. Fund 6 | 50000 | 50000
580 | 590 | 948 | 16470402069 | Goliad Maintenance Office | Replace Exterior Windows At Laboratory - Goliad MNT | Highway Trans. Fund 6 | 8000 | 8000
581 | 591 | 949 | 11470402070 | District Headquarters | Renovate Bathroom | Highway Trans. Fund 6 | 8000 | 8000
582 | 592 | 950 | 11470402071 | District Headquarters | Renovate Interior | Highway Trans. Fund 6 | 8000 | 8000
588 | 598 | 951 | 06470402077 | McCamey Maintenance Office | Upgrade Electrical Wiring & Lights In Shop Area | Highway Trans. Fund 6 | 7000 | 7000
589 | 599 | 952 | 07470402078 | Ballinger Maintenance Office | Erect Buildings Over Lifts | Highway Trans. Fund 6 | 50000 | 50000
590 | 600 | 953 | 09470402079 | District Headquarters | Replace Windows | Highway Trans. Fund 6 | 33450 | 33450
591 | 601 | 954 | 06470402080 | Sanderson Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 35000 | 35000
592 | 602 | 955 | 23470402081 | Comanche Maintenance Office | Renovate Facilities | Highway Trans. Fund 6 | 294000 | 294000
593 | 603 | 956 | 17470402082 | Brenham Area Engineer & Maintenance Office | Add Lighting And Catwalks To V-Box Area | Highway Trans. Fund 6 | 20000 | 20000
594 | 604 | 957 | 17470402083 | Brenham Area Engineer & Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 6 | 350000 | 350000
595 | 605 | 958 | 17470402084 | Brenham Area Engineer & Maintenance Office | New Sidewalk Lab To Parking Lot | Highway Trans. Fund 6 | 12500 | 12500
596 | 606 | 959 | 06470402085 | Stanton Maintenance Office | Install Shed Kit | Highway Trans. Fund 6 | 100000 | 100000
598 | 608 | 960 | 21470402087 | San Isidro Maintenance Office Sub-Section | Reconfigure Two Restrooms & Office | Highway Trans. Fund 6 | 50000 | 50000
599 | 609 | 961 | 15470402088 | Pearsall Maintenance Office | Refurbish Shop Building Skin And Roof | Highway Trans. Fund 6 | 95000 | 95000
600 | 610 | 962 | 38470402089 | Austin HQ | Austin HQ Campus Repairs | Highway Trans. Fund 6 | 5000000 | 5000000
601 | 611 | 963 | 09470402090 | District Headquarters | New Insulation & Replace Windows | Highway Trans. Fund 6 | 52200 | 52200
602 | 612 | 964 | 03470402091 | Bowie Maintenance Office | Replace Exterior Windows At Warehouse - Bowie Maintenance | Highway Trans. Fund 6 | 30000 | 30000
603 | 613 | 965 | 19470402092 | District Headquarters | Remodel Inside Of Building | Highway Trans. Fund 6 | 87000 | 87000
604 | 614 | 966 | 23470402093 | Brady Maintenance Office | Renovate Facilities | Highway Trans. Fund 6 | 317000 | 317000
605 | 615 | 967 | 17470402094 | Bryan Area Engineer & Maintenance Office | Reskin Shed | Highway Trans. Fund 6 | 20000 | 20000
606 | 616 | 968 | 17470402095 | Madisonville Maintenance Office | Fence/Gate Work | Highway Trans. Fund 6 | 10000 | 10000
607 | 617 | 969 | 17470402096 | Madisonville Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000
608 | 618 | 970 | 17470402097 | Madisonville Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 6 | 350000 | 350000
609 | 619 | 971 | 17470402098 | Madisonville Maintenance Office | Replace Fuel Canopy | Highway Trans. Fund 6 | 35000 | 35000
611 | 621 | 972 | 25470402100 | Crowell Maintenance Office | Rewire Office, New Lights; Heaters In Truck Barn | Highway Trans. Fund 6 | 45000 | 45000
612 | 622 | 973 | 25470402101 | Matador Maintenance Office | Re-Skin Exterior, Insulate Building, Install Windows, Roof and Lights; Redesign Office Space | Highway Trans. Fund 6 | 325000 | 325000
613 | 623 | 974 | 16470402102 | Nueces East | Install Redundant 2000 Gallon Diesel Tank To Existing Fuel Island | Highway Trans. Fund 6 | 35000 | 35000
614 | 624 | 975 | 18470402103 | Ennis Maintenance Office | Electrical Panel Upgrades | Highway Trans. Fund 6 | 20000 | 20000
618 | 628 | 976 | 21470402107 | Zapata Maintenance Office Sub-Section | Renovate Building Into Offices. Renovate Restrooms. | Highway Trans. Fund 6 | 200000 | 200000
623 | 633 | 977 | 20470402112 | Woodville Maintenance Office | Abate Transit Siding | Highway Trans. Fund 6 | 5000 | 5000
624 | 634 | 978 | 20470402113 | Woodville Maintenance Office | Replace Roof, Lighting & Siding | Highway Trans. Fund 6 | 40000 | 40000
625 | 635 | 979 | 23470402114 | Coleman Maintenance Office | Renovate Facilities | Highway Trans. Fund 6 | 350000 | 350000
627 | 637 | 980 | 17470402116 | Buffalo Maintenance Office | Restroom Remodels | Highway Trans. Fund 6 | 10000 | 10000
630 | 640 | 981 | 17470402119 | Cameron Maintenance Office | Replace Flooring (Carpet & Tile) | Highway Trans. Fund 6 | 25000 | 25000
631 | 641 | 982 | 17470402120 | Cameron Maintenance Office | Redo Walls In Office | Highway Trans. Fund 6 | 20000 | 20000
632 | 642 | 983 | 17470402121 | Cameron Maintenance Office | Reskin MNT Office Building | Highway Trans. Fund 6 | 50000 | 50000
634 | 644 | 984 | 25470402123 | Paducah Maintenance Office | Replace Restrooms | Highway Trans. Fund 6 | 30000 | 30000
635 | 645 | 985 | 25470402124 | Silverton Maintenance Office | Insulate, New Windows And Roof | Highway Trans. Fund 6 | 275000 | 275000
636 | 646 | 986 | 25470402125 | Silverton Maintenance Office | Re-Skin Exterior, Insulate Building,Install Windows and Roof | Highway Trans. Fund 6 | 175000 | 175000
638 | 648 | 987 | 16470402127 | Goliad Maintenance Office | Replace Exterior Door At Equipment Storage - Goliad MNT | Highway Trans. Fund 6 | 16000 | 16000
639 | 649 | 988 | 18470402128 | District Headquarters | Upgrade Lighting | Highway Trans. Fund 6 | 75000 | 75000
641 | 651 | 989 | 22470402130 | Brackettville | Deactivate Or Remove Mag Locks | Highway Trans. Fund 6 | 5000 | 5000
642 | 652 | 990 | 22470402131 | Brackettville | Furnish/Install Exterior Safety Lights | Highway Trans. Fund 6 | 1500 | 1500
643 | 653 | 991 | 22470402132 | Brackettville | Renovate Breakroom | Highway Trans. Fund 6 | 35000 | 35000
644 | 654 | 992 | 22470402133 | Brackettville | Restroom Renovations (Both Men and Women) | Highway Trans. Fund 6 | 40000 | 40000
645 | 655 | 993 | 22470402134 | Brackettville | Retrofit Bay Area Into Conference Room. (17'X28') 14' Ceiling. Tile Flooring, HVAC, Electrical, Communications, Removal Of Exiting Door. | Highway Trans. Fund 6 | 55000 | 55000
646 | 656 | 994 | 07470402135 | Sterling City Maintenance Office | Erect Buildings Over Lifts | Highway Trans. Fund 6 | 50000 | 50000
647 | 657 | 995 | 17470402136 | Navasota Maintenance Office | Restroom Remodels | Highway Trans. Fund 6 | 10000 | 10000
648 | 658 | 996 | 25470402137 | Munday Maintenance Office | New Partition Walls & Larger Break Room, Upgrade Rest Room, New Windows & Doors, Redesign Office Space | Highway Trans. Fund 6 | 200000 | 200000
653 | 663 | 997 | 05470402142 | District Headquarters | Campuswide Electrical Upgrade | Highway Trans. Fund 6 | 150000 | 150000
656 | 666 | 998 | 05470402145 | District Headquarters | New VCT Floor | Highway Trans. Fund 6 | 78000 | 78000
660 | 670 | 999 | 21470402149 | Hebbronville Area Engineer & Maintenance Office | Add Large Conference Room | Highway Trans. Fund 6 | 252000 | 252000
661 | 671 | 1000 | 21470402150 | Hebbronville Area Engineer & Maintenance Office | Restroom Renovation | Highway Trans. Fund 6 | 25000 | 25000
662 | 672 | 1001 | 21470402151 | Hebbronville Area Engineer & Maintenance Office | Locker Room With Showers | Highway Trans. Fund 6 | 0 | 0
663 | 673 | 1002 | 21470402152 | Hebbronville Area Engineer & Maintenance Office | Phone/Computer Access | Highway Trans. Fund 6 | 0 | 0
664 | 674 | 1003 | 21470402153 | Hebbronville Area Engineer & Maintenance Office | Ventilation Upgrade | Highway Trans. Fund 6 | 0 | 0
665 | 675 | 1004 | 09470402154 | Marlin Area Engineer & Maintenance Office | Remodel Office | Highway Trans. Fund 6 | 488000 | 488000
666 | 676 | 1005 | 03470402155 | Electra Maintenance Office | Building Renovation | Highway Trans. Fund 6 | 150000 | 150000
667 | 677 | 1006 | 03470402156 | Electra Maintenance Office | Reskin And Replace Windows | Highway Trans. Fund 6 | 90000 | 90000
668 | 678 | 1007 | 13470402157 | Edna Maintenance Office | Paint Metal On Shed | Highway Trans. Fund 6 | 12000 | 12000
669 | 679 | 1008 | 13470402158 | Jackson Cty Maint. | Paint Interior/Exterior Of Mechanic/Warehouse | Highway Trans. Fund 6 | 25000 | 25000
672 | 682 | 1009 | 17470402161 | Navasota Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 6 | 350000 | 350000
673 | 683 | 1010 | 16470402162 | Karnes City Area Engineer & Maintenance Office | Interior Renovations | Highway Trans. Fund 6 | 350000 | 350000
674 | 684 | 1011 | 16470402163 | Karnes City Area Engineer & Maintenance Office | Repair Plumbing System - Karnes City AEM | Highway Trans. Fund 6 | 15000 | 15000
675 | 685 | 1012 | 05470402164 | District Headquarters | Security System Upgrade - C-Cure | Highway Trans. Fund 6 | 40000 | 40000
676 | 686 | 1013 | 05470402165 | Post RDC | Add New Wall To Dock With Overhead Door Wk Door | Highway Trans. Fund 6 | 90000 | 90000
677 | 687 | 1014 | 38470402166 | Camp Hubbard State Headquarters | Replace Data Closet AC | Highway Trans. Fund 6 | 6000 | 6000
678 | 688 | 1015 | 10470402167 | District Headquarters | Demolish Abandoned Structure | Highway Trans. Fund 6 | 50000 | 50000
679 | 689 | 1016 | 10470402168 | District Headquarters | Exterior Renovations | Highway Trans. Fund 6 | 150000 | 150000
680 | 690 | 1017 | 10470402169 | District Headquarters | Replace Carpet In Administration Building | Highway Trans. Fund 6 | 75000 | 75000
681 | 691 | 1018 | 09470402170 | Mexia Maintenance Office | Renovate Maintenance Facility | Highway Trans. Fund 6 | 150000 | 150000
682 | 692 | 1019 | 08470402171 | District Headquarters | Construct Concrete Apron Around The District Headquarters | Highway Trans. Fund 6 | 35000 | 35000
683 | 693 | 1020 | 08470402172 | District Headquarters | Repair And Replace All Plumbing Fixtures | Highway Trans. Fund 6 | 100000 | 100000
684 | 694 | 1021 | 17470402173 | Caldwell Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000
685 | 695 | 1022 | 17470402174 | Caldwell Maintenance Office | New Fuel Canopy | Highway Trans. Fund 6 | 35000 | 35000
686 | 696 | 1023 | 17470402175 | Caldwell Maintenance Office | Repaving Of Parking Areas | Highway Trans. Fund 6 | 400000 | 400000
689 | 699 | 1024 | 02470402178 | District Headquarters | Convert Conference Room To EOC | Highway Trans. Fund 6 | 153000 | 153000
690 | 700 | 1025 | 02470402179 | District Headquarters | Electrical Upgrade For The Whole District Headquarters | Highway Trans. Fund 6 | 300000 | 300000
691 | 701 | 1026 | 02470402180 | District Headquarters | Install Interior Walls At Warehouse - Fort Worth DHQ Ware House Office | Highway Trans. Fund 6 | 150000 | 150000
692 | 702 | 1027 | 02470402181 | District Headquarters | Install Interiors At Shop - Fort Worth DHQ Locker Rooms | Highway Trans. Fund 6 | 100000 | 100000
693 | 703 | 1028 | 02470402182 | District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 125000 | 125000
695 | 705 | 1029 | 12470402184 | Rosenberg Area Engineer & Maintenance Office | Paint Exterior (5 Buildings) | Highway Trans. Fund 6 | 97000 | 97000
696 | 706 | 1030 | 12470402185 | Rosenberg Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 150000 | 150000
697 | 707 | 1031 | 12470402186 | Rosenberg Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 240000 | 240000
698 | 708 | 1032 | 05470402187 | Post Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
699 | 709 | 1033 | 06470402188 | District Headquarters | Repair/Replace Carpet In Tp&D Area | Highway Trans. Fund 6 | 25000 | 25000
700 | 710 | 1034 | 06470402189 | District Headquarters | Upgrade The District Complex Plumbing System | Highway Trans. Fund 6 | 280000 | 280000
701 | 711 | 1035 | 15470402190 | District Headquarters | Repair Foundation | Highway Trans. Fund 6 | 8000 | 8000
702 | 712 | 1036 | 15470402191 | District Headquarters | Repair Sidewalks | Highway Trans. Fund 6 | 8000 | 8000
703 | 713 | 1037 | 15470402192 | Seguin RDC | Restroom Renovation/Addition | Highway Trans. Fund 6 | 80000 | 80000
705 | 715 | 1038 | 08470402194 | District Headquarters | New Carpet | Highway Trans. Fund 6 | 40000 | 40000
707 | 717 | 1039 | 25470402196 | Wellington Maintenance Office | Re-Skin Exterior, Insulate Building, Install Windows and Roof, Redesign Office Space | Highway Trans. Fund 6 | 325000 | 325000
708 | 718 | 1040 | 02470402197 | District Headquarters | Lab Upgrades | Highway Trans. Fund 6 | 558500 | 558500
710 | 720 | 1041 | 12470402199 | Houston South Area Engineer & Maintenance Office | Renovate 3 Buildings Into One | Highway Trans. Fund 6 | 1200000 | 1200000
711 | 721 | 1042 | 12470402200 | Houston South Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 29000 | 29000
712 | 722 | 1043 | 12470402201 | Houston South Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 485000 | 485000
713 | 723 | 1044 | 12470402202 | Houston South Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 0 | 0
715 | 724 | 1045 | 06470402204 | District Headquarters | Replace/Repair Windows | Highway Trans. Fund 6 | 75000 | 75000
716 | 725 | 1046 | 15470402205 | Seguin Area Engineer & Maintenance Office | Exterior Paint | Highway Trans. Fund 6 | 15000 | 15000
718 | 726 | 1047 | 15470402207 | Seguin Area Engineer & Maintenance Office | Restroom Renovation/Addition | Highway Trans. Fund 6 | 25000 | 25000
719 | 727 | 1048 | 04470402208 | Canyon Maintenance Office | Abate Inside,Replace Windows And Replace Roof | Highway Trans. Fund 6 | 75000 | 75000
720 | 728 | 1049 | 05470402209 | Bovina Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
721 | 729 | 1050 | 05470402210 | Bovina Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000
723 | 731 | 1051 | 05470402212 | Brownfield Area Engineer & Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
725 | 733 | 1052 | 05470402214 | Brownfield Area Engineer & Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000
726 | 734 | 1053 | 05470402215 | Ralls Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
728 | 736 | 1054 | 05470402217 | Ralls Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000
729 | 737 | 1055 | 15470402218 | Tilden Maintenance Office | Carpet & Paint | Highway Trans. Fund 6 | 15000 | 15000
730 | 738 | 1056 | 15470402219 | Tilden Maintenance Office | Relocate Radio Tower | Highway Trans. Fund 6 | 0 | 0
731 | 739 | 1057 | 15470402220 | Tilden Maintenance Office | Upgrade Restrooms | Highway Trans. Fund 6 | 25000 | 25000
732 | 740 | 1058 | 38470402221 | Camp Hubbard State Headquarters | Renovate Interior Office Space, Include Abatement, New Lighting, New Windows, New Duct Work | Highway Trans. Fund 6 | 1000000 | 1000000
733 | 741 | 1059 | 10470402222 | North Tyler Maintenance Office | Elevated Water Storage | Highway Trans. Fund 6 | 30000 | 30000
734 | 742 | 1060 | 10470402223 | North Tyler Maintenance Office | Remodel Office & New Roof | Highway Trans. Fund 6 | 300000 | 300000
735 | 743 | 1061 | 13470402224 | Austin Cty Maint. | Paint Interior Structure Of Equip Shed | Highway Trans. Fund 6 | 15000 | 15000
736 | 744 | 1062 | 13470402225 | Austin Cty Maint. | Rehab. Of Mechanic Area (Front Wall W/ Door) | Highway Trans. Fund 6 | 20000 | 20000
737 | 745 | 1063 | 13470402226 | Colorado Cty Maint. | Level And Paint Interior Of Office Building | Highway Trans. Fund 6 | 50000 | 50000
739 | 747 | 1064 | 13470402228 | Columbus Maintenance Office | Level Building (Maintenance Bldg) | Highway Trans. Fund 6 | 50000 | 50000
740 | 748 | 1065 | 13470402229 | Columbus Maintenance Office | Paint Office & Warehouse Exterior | Highway Trans. Fund 6 | 15000 | 15000
741 | 749 | 1066 | 13470402230 | District Headquarters | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 6 | 5000 | 5000
743 | 751 | 1067 | 08470402232 | Big Spring Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 30000 | 30000
745 | 753 | 1068 | 20470402234 | District Headquarters | Install Rotary Lift & 2 Ton Overhead Crane And Trolley | Highway Trans. Fund 6 | 13000 | 13000
748 | 756 | 1069 | 20470402237 | District Headquarters | Interior Remodel | Highway Trans. Fund 6 | 6700 | 6700
749 | 757 | 1070 | 20470402238 | District Headquarters | Interior Remodel | Highway Trans. Fund 6 | 39000 | 39000
750 | 758 | 1071 | 20470402239 | District Headquarters | Repair ADA Ramps | Highway Trans. Fund 6 | 8000 | 8000
751 | 759 | 1072 | 20470402240 | District Headquarters | Replace 25 Infra-Red Heaters | Highway Trans. Fund 6 | 100000 | 100000
753 | 761 | 1073 | 20470402242 | Districtwide | Replace Fuel Dispensers Districtwide | Highway Trans. Fund 6 | 150000 | 150000
754 | 762 | 1074 | 25470402243 | Dickens Maintenance Office | Replace Windows & Locks | Highway Trans. Fund 6 | 20000 | 20000
755 | 763 | 1075 | 12470402244 | La Marque Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 300000 | 300000
756 | 764 | 1076 | 12470402245 | La Marque Area Engineer & Maintenance Office | Replace Siding (8 Buildings) | Highway Trans. Fund 6 | 640000 | 640000
758 | 766 | 1077 | 03470402247 | District Headquarters | Building Renovations | Highway Trans. Fund 6 | 112000 | 112000
759 | 767 | 1078 | 03470402248 | District Headquarters | Foundation And Cosmetic Repairs | Highway Trans. Fund 6 | 160000 | 160000
760 | 768 | 1079 | 13470402249 | Colorado Cty Maint. | Close Open Bay And Add To Sign Room | Highway Trans. Fund 6 | 25000 | 25000
#N/A | #N/A | 1080 | 08470402250 | Colorado Cty Maint. | Replace 5 Overhead Roll Up Doors And Paint 3 | Highway Trans. Fund 6 | 15000 | 15000
762 | 770 | 1081 | 13470402251 | Columbus Maintenance Office | Replace Oh Doors On Shed | Highway Trans. Fund 6 | 12000 | 12000
763 | 771 | 1082 | 13470402252 | Matagorda Cty Maint. | Bird Proof Underside Of Roof-Purlins | Highway Trans. Fund 6 | 6000 | 6000
764 | 772 | 1083 | 13470402253 | Matagorda Cty Maint. | Construct Elevated Platform For Wash Rack | Highway Trans. Fund 6 | 8000 | 8000
765 | 773 | 1084 | 19470402254 | District Headquarters | Renovation Of Warehouse | Highway Trans. Fund 6 | 515000 | 515000
766 | 774 | 1085 | 19470402255 | Texarkana Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 6 | 80000 | 80000
767 | 775 | 1086 | 19470402256 | Texarkana Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 6 | 111000 | 111000
769 | 777 | 1087 | 17470402258 | Brenham Area Engineer & Maintenance Office | Remove Fuel Awning/Install New Awning For Parking | Highway Trans. Fund 6 | 250000 | 250000
770 | 778 | 1088 | 16470402259 | District Headquarters | Repair Structure At Administration - Corpus Christi DHQ | Highway Trans. Fund 6 | 7500 | 7500
771 | 779 | 1089 | 16470402260 | District Headquarters | Replace Flooring At Administration - Corpus Christi DHQ | Highway Trans. Fund 6 | 40000 | 40000
773 | 781 | 1090 | 16470402262 | Goliad Maintenance Office | Replace\New Exterior Walls At Equipment Storage - Goliad MNT | Highway Trans. Fund 6 | 90000 | 90000
774 | 782 | 1091 | 16470402263 | Karnes Co. | Remodel Inside Office (Lights, Ceiling, Floor, Paint) | Highway Trans. Fund 6 | 75000 | 75000
776 | 784 | 1092 | 02470402265 | Mineral Wells Maintenance Office | Renovate Maintenance Facility | Highway Trans. Fund 6 | 500000 | 500000
777 | 785 | 1093 | 05470402266 | Plains Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
778 | 786 | 1094 | 05470402267 | Plains Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000
779 | 787 | 1095 | 05470402268 | Seminole Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
780 | 788 | 1096 | 05470402269 | Seminole Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 10000 | 10000
781 | 789 | 1097 | 05470402270 | Seminole Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000
782 | 790 | 1098 | 11470402271 | Crockett Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 6 | 40000 | 40000
783 | 791 | 1099 | 11470402272 | Crockett Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 15000 | 15000
785 | 793 | 1100 | 11470402274 | Crockett Maintenance Office | Upgrade Exterior Lighting | Highway Trans. Fund 6 | 15000 | 15000
786 | 794 | 1101 | 11470402275 | Crockett Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000
788 | 796 | 1102 | 06470402277 | Crane Maintenance Office | Paint Exterior And Interior | Highway Trans. Fund 6 | 25000 | 25000
789 | 797 | 1103 | 06470402278 | Crane Maintenance Office | Reconfigure Bay For Break Room Locker Room. New Kitchenette Lockers Flooring Walls Plumbing Electrical | Highway Trans. Fund 6 | 50000 | 50000
790 | 798 | 1104 | 06470402279 | Crane Maintenance Office | Remove & Replace Windows In Main Office | Highway Trans. Fund 6 | 10000 | 10000
791 | 799 | 1105 | 06470402280 | Crane Maintenance Office | Upgrade Electrical Wiring, Lights And Breakers | Highway Trans. Fund 6 | 4000 | 4000
793 | 801 | 1106 | 21470402282 | District Headquarters | Upgrade Conference Rooms | Highway Trans. Fund 6 | 51000 | 51000
794 | 802 | 1107 | 21470402283 | District Headquarters | Repair Plumbing Problems | Highway Trans. Fund 6 | 20000 | 20000
795 | 803 | 1108 | 21470402284 | Falfurrias Maintenance Office Sub-Section | Building Renovation | Highway Trans. Fund 6 | 163300 | 163300
796 | 804 | 1109 | 21470402285 | Falfurrias Maintenance Office Sub-Section | Upgrade Mechanic Shop | Highway Trans. Fund 6 | 190000 | 190000
797 | 805 | 1110 | 09470402286 | Meridian Maintenance Office | Retrofit Truck Bays To Conference Rooms and Meeting Space | Highway Trans. Fund 6 | 35000 | 35000
798 | 806 | 1111 | 09470402287 | Meridian Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 30000 | 30000
799 | 807 | 1112 | 03470402288 | District Headquarters | Retrofit Warehouse Space To Large Meeting Room | Highway Trans. Fund 6 | 28500 | 28500
800 | 808 | 1113 | 03470402289 | Nocona Maintenance Office | Building Remodel | Highway Trans. Fund 6 | 90000 | 90000
801 | 809 | 1114 | 13470402290 | Calhoun Cty Maint. | Interior Renovation (Floors & Walls) | Highway Trans. Fund 6 | 60000 | 60000
802 | 810 | 1115 | 13470402291 | Calhoun Cty Maint. | Paint Exterior Structure Of Canopy, Mechanci Shop, & Stock Room | Highway Trans. Fund 6 | 20000 | 20000
803 | 811 | 1116 | 13470402292 | Calhoun Cty Maint. | Paint Interior Structure Of Equip Shed | Highway Trans. Fund 6 | 25000 | 25000
804 | 812 | 1117 | 13470402293 | District Headquarters | Replace Shifting Concrete Pad Under Pad Mount Electrical Transformer | Highway Trans. Fund 6 | 15000 | 15000
805 | 813 | 1118 | 13470402294 | Port Lavaca Maintenance Office | Replace Flooring | Highway Trans. Fund 6 | 10000 | 10000 | [6 empty] | A Phase was broken out as Project #19470402979
809 | 817 | 1119 | 23470402298 | District Headquarters | Renovate Lab | Highway Trans. Fund 6 | 712000 | 712000
810 | 818 | 1120 | 18470402300 | Waxahachie Area Engineer & Maintenance Office | Electrical - Additional Service | Highway Trans. Fund 6 | 20000 | 20000
812 | 820 | 1121 | 12470402302 | Rosenberg Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 120000 | 120000
813 | 821 | 1122 | 22470402303 | Del Rio Maintenance Office | Exterior Warehouse Painting | Highway Trans. Fund 6 | 30000 | 30000
814 | 822 | 1123 | 05470402304 | Levelland Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
815 | 823 | 1124 | 05470402305 | Levelland Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000
816 | 824 | 1125 | 05470402306 | SE Maint. Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
819 | 827 | 1126 | 11470402309 | District Headquarters | Repair Dist Shop Parking Lot And Stripe Existing Lots At Dist HQ | Highway Trans. Fund 6 | 200000 | 200000
820 | 828 | 1127 | 11470402310 | District Headquarters | Replace Fuel Awning | Highway Trans. Fund 6 | 21000 | 21000
822 | 830 | 1128 | 11470402312 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 6 | 8000 | 8000
823 | 831 | 1129 | 04470402313 | District Headquarters | Abate Windows And Paint Exterior Of Shop | Highway Trans. Fund 6 | 100000 | 100000
824 | 832 | 1130 | 19470402314 | Mt Pleasant Area Engineer & Maintenance Office | Major Renovation | Highway Trans. Fund 6 | 767000 | 767000
825 | 833 | 1131 | 19470402315 | Mt Pleasant Area Engineer & Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 6 | 65000 | 65000
826 | 834 | 1132 | 19470402316 | Mt Pleasant Area Engineer & Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 6 | 128300 | 128300
827 | 835 | 1133 | 18470402317 | Rockwall Maintenance Office | Electrical Panel Upgrades | Highway Trans. Fund 6 | 15000 | 15000
829 | 837 | 1134 | 18470402319 | Rockwall Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 45000 | 45000
831 | 839 | 1135 | 22470402321 | Carrizo Springs | Replace Two Overhead Doors | Highway Trans. Fund 6 | 25000 | 25000
832 | 840 | 1136 | 22470402322 | Carrizo Springs | Restroom Renovation | Highway Trans. Fund 6 | 40000 | 40000
833 | 841 | 1137 | 22470402323 | Carrizo Springs | Retrofit Locker Room Into Storage/Supply Room | Highway Trans. Fund 6 | 5000 | 5000
834 | 842 | 1138 | 05470402324 | FloydADA Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
835 | 843 | 1139 | 05470402325 | Lamesa Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
836 | 844 | 1140 | 05470402326 | Lamesa Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 15000 | 15000
837 | 845 | 1141 | 05470402327 | Lamesa Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000
838 | 846 | 1142 | 11470402328 | Lufkin Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 6 | 40000 | 40000
840 | 848 | 1143 | 11470402330 | Lufkin Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 30000 | 30000
846 | 854 | 1144 | 07470402336 | District Headquarters | Modifications/Upgrade Electrical | Highway Trans. Fund 6 | 200000 | 200000
847 | 855 | 1145 | 07470402337 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 6 | 21500 | 21500
849 | 857 | 1146 | 12470402340 | Houston Northwest | Renovate Interior/Exterior (20K Sf Concrete Tilt Wall Aquired Building) | Highway Trans. Fund 6 | 2000000 | 2000000
850 | 858 | 1147 | 12470402341 | West Harris Maintenance Office | Renovation And Upgrade To AEM | Highway Trans. Fund 6 | 2000000 | 2000000
851 | 859 | 1148 | 05470402342 | District Headquarters-LBB AE's | New VCT Floor | Highway Trans. Fund 6 | 35000 | 35000
852 | 860 | 1149 | 05470402343 | District Headquarters-LBB AE's | Replace Roof | Highway Trans. Fund 6 | 50000 | 50000
853 | 861 | 1150 | 05470402344 | District Headquarters-LBB AE's | Replace Steps With ADA Ramp Back Door | Highway Trans. Fund 6 | 12000 | 12000
855 | 863 | 1151 | 04470402346 | Vega Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000
856 | 864 | 1152 | 04470402347 | Vega Maintenance Office | Upgrade Current Welding Shop | Highway Trans. Fund 6 | 100000 | 100000
857 | 865 | 1153 | 19470402348 | New Boston Maintenance Office | Remodel Inside Of Building Paint Floor And Ceiling | Highway Trans. Fund 6 | 80000 | 80000
858 | 866 | 1154 | 19470402349 | New Boston Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 6 | 99400 | 99400
859 | 867 | 1155 | 15470402350 | Devine Maintenance Office | Paint, Carpet Replacement | Highway Trans. Fund 6 | 15000 | 15000
860 | 868 | 1156 | 15470402351 | Devine Maintenance Office | Restroom Upgrades | Highway Trans. Fund 6 | 25000 | 25000
861 | 869 | 1157 | 13470402352 | District Headquarters | Replace All Exterior Roof Facial & Renovate All Exterior Entrances | Highway Trans. Fund 6 | 75000 | 75000
862 | 870 | 1158 | 16470402353 | Goliad Co. | Replace Metal Siding On Equipment Shed And Roof With New Siding And Roof | Highway Trans. Fund 6 | 75000 | 75000
863 | 871 | 1159 | 16470402354 | Kingsville Maintenance Office | Paint Interior Walls At Maintenance - Kingsville Maintenance | Highway Trans. Fund 6 | 7500 | 7500
866 | 874 | 1160 | 05470402357 | Plainview Area Engineer & Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
867 | 875 | 1161 | 05470402358 | Tahoka Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
869 | 877 | 1162 | 05470402360 | Tahoka Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000
870 | 878 | 1163 | 04470402361 | Canadian Maintenance Office | Foundation Repair | Highway Trans. Fund 6 | 0 | 0
872 | 880 | 1164 | 04470402363 | Canadian Maintenance Office | Renovation Of Building Exterior | Highway Trans. Fund 6 | 150000 | 150000
873 | 881 | 1165 | 04470402364 | Canadian Maintenance Office | Restroom Abatement And Remodel | Highway Trans. Fund 6 | 20000 | 20000
874 | 882 | 1166 | 04470402365 | E way | Lighting Upgrades | Highway Trans. Fund 6 | 25000 | 25000
875 | 883 | 1167 | 04470402366 | Hereford Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000
876 | 884 | 1168 | 14470402367 | Lockhart Maintenance Office | Foundation Repair | Highway Trans. Fund 6 | 350000 | 350000
878 | 886 | 1169 | 20470402369 | Kountze Maintenance Office | Paint Office Exterior | Highway Trans. Fund 6 | 30000 | 30000
879 | 887 | 1170 | 20470402370 | Liberty Area Engineer & Maintenance Office | Replace Electrical Panels And Upgrade Electrical Wiring. | Highway Trans. Fund 6 | 50000 | 50000
880 | 888 | 1171 | 24470402371 | Terlingua Sub-Section | Additional Outside LED Lighting For Houses. | Highway Trans. Fund 6 | 8000 | 8000
881 | 889 | 1172 | 24470402372 | Terlingua Sub-Section | Interior Renovation; Electrical, HVAC, Walls Finish, Framing, Floors And Kitchen | Highway Trans. Fund 6 | 36000 | 36000
884 | 892 | 1173 | 05470402375 | Muleshoe Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
885 | 893 | 1174 | 05470402376 | Muleshoe Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 20000 | 20000
886 | 894 | 1175 | 07470402377 | District Headquarters | Paint Interior Of Facility | Highway Trans. Fund 6 | 30000 | 30000
888 | 896 | 1176 | 08470402379 | Snyder Maintenance Office | Convert The Old Salt Bin Into A Sign And Traffic Control Room Storage | Highway Trans. Fund 6 | 10000 | 10000
890 | 898 | 1177 | 04470402381 | Perryton Maintenance Office | Replace Roof, Re-Skin Exterior, Install New Insulation And Windows | Highway Trans. Fund 6 | 175000 | 175000
891 | 899 | 1178 | 04470402382 | Perryton Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000
892 | 900 | 1179 | 08470402383 | Haskell Maintenance Office | Convert Old Shop Into Breakroom | Highway Trans. Fund 6 | 10000 | 10000
893 | 901 | 1180 | 23470402384 | Brownwood Area Engineer & Maintenance Office | Renovate Office | Highway Trans. Fund 6 | 311000 | 311000
894 | 902 | 1181 | 17470402385 | Huntsville Area Engineer & Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 6 | 350000 | 350000
896 | 904 | 1182 | 17470402387 | Huntsville Area Engineer & Maintenance Office | Repair Foundation/Porch/Walls | Highway Trans. Fund 6 | 50000 | 50000
898 | 906 | 1183 | 17470402389 | Huntsville Area Engineer & Maintenance Office | Replace Fuel Canopy | Highway Trans. Fund 6 | 35000 | 35000
899 | 907 | 1184 | 17470402390 | Huntsville Area Engineer & Maintenance Office | Replace Wiring In Building | Highway Trans. Fund 6 | 30000 | 30000
901 | 909 | 1185 | 25470402392 | Quanah Maintenance Office | Replace Floor Tiles; Upgrade Rest Rooms, Redesign Office Space | Highway Trans. Fund 6 | 45000 | 45000
902 | 910 | 1186 | 16470402393 | District Headquarters | Replace Electrical Panels At Right Of Way - Corpus Christi District Headquarters And Area Engineer And Maintenance Special Jobs | Highway Trans. Fund 6 | 15000 | 15000
904 | 912 | 1187 | 06470402395 | Iraan Maintenance Office | Enclose 3 Bays With Insulated Overhead Doors To Secure Equipment & Weather Protection | Highway Trans. Fund 6 | 20000 | 20000
906 | 914 | 1188 | 06470402397 | Iraan Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 35000 | 35000
907 | 915 | 1189 | 21470402398 | Mission Maintenance Office | New 4K Gallon Fuel Tanks/Replace Fuel Pumps | Highway Trans. Fund 6 | 300000 | 300000
908 | 916 | 1190 | 21470402399 | Mission Maintenance Office | New Heavy Equipment Overhead Doors | Highway Trans. Fund 6 | 57000 | 57000
909 | 917 | 1191 | 21470402400 | Mission Maintenance Office | New Heavy Equipment Pull Through Stalls | Highway Trans. Fund 6 | 21500 | 21500
910 | 918 | 1192 | 21470402401 | Mission Maintenance Office | Renovate Building | Highway Trans. Fund 6 | 112000 | 112000
911 | 919 | 1193 | 13470402402 | Jackson Cty Maint. | Interior Renovation (Floors & Walls) | Highway Trans. Fund 6 | 60000 | 60000
912 | 920 | 1194 | 18470402403 | Hutchins Maintenance Office | Electrical Panel Upgrades | Highway Trans. Fund 6 | 25000 | 25000
914 | 922 | 1195 | 24470402405 | Alpine Area Engineer & Maintenance Office | Remodel Bay For Maintenance Training And Breakroom, Add One Additional Office In Bay. | Highway Trans. Fund 6 | 30000 | 30000
915 | 923 | 1196 | 12470402406 | Houston NE Area Engineer & Maintenance Office | Renovate Restrooms (Locker Rooms) | Highway Trans. Fund 6 | 42000 | 42000
916 | 924 | 1197 | 12470402407 | Houston NE Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 20000 | 20000
917 | 925 | 1198 | 21470402408 | Hebbronville Area Engineer & Maintenance Office | Upgrade Mechanic Shop | Highway Trans. Fund 6 | 0 | 0
918 | 926 | 1199 | 17470402409 | Brenham Area Engineer & Maintenance Office | Upgrade Lighting In Washbay | Highway Trans. Fund 6 | 5000 | 5000
921 | 929 | 1200 | 17470402412 | Bryan Area Engineer & Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 6 | 350000 | 350000
925 | 933 | 1201 | 21470402416 | San Benito Area Engineer & Maintenance Office | Upgrade Ballasts | Highway Trans. Fund 6 | 30000 | 30000
926 | 934 | 1202 | 24470402417 | Presidio Maintenance Office | Convert Bay Into A Break Room | Highway Trans. Fund 6 | 19500 | 19500
927 | 935 | 1203 | 24470402418 | Presidio Maintenance Office | Extend Office Space Along Same Roof Line To The South 16 Feet | Highway Trans. Fund 6 | 80000 | 80000
928 | 936 | 1204 | 19470402419 | Daingerfield Maintenance Office | Install Overhead Door Operators & Gate | Highway Trans. Fund 6 | 32200 | 32200
929 | 937 | 1205 | 19470402420 | Daingerfield Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 6 | 45000 | 45000
930 | 938 | 1206 | 17470402421 | Buffalo Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000
931 | 939 | 1207 | 17470402422 | Buffalo Maintenance Office | Remove Undergrnd/Install Above Grnd Fuel Tanks | Highway Trans. Fund 6 | 350000 | 350000
932 | 940 | 1208 | 21470402423 | Laguna Vista Maintenance Office Sub-Section | Building Renovation | Highway Trans. Fund 6 | 200000 | 200000
933 | 941 | 1209 | 21470402424 | Laguna Vista Maintenance Office Sub-Section | Replace Overhead Doors | Highway Trans. Fund 6 | 12000 | 12000
934 | 942 | 1210 | 04470402425 | Groom Maintenance Office | Electrical Upgrades | Highway Trans. Fund 6 | 5000 | 5000
936 | 944 | 1211 | 04470402427 | Groom Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000
937 | 945 | 1212 | 15470402428 | Bandera Maintenance Office | Paint, Carpet Replacement | Highway Trans. Fund 6 | 15000 | 15000
938 | 946 | 1213 | 15470402429 | Bandera Maintenance Office | Restroom Upgrades | Highway Trans. Fund 6 | 0 | 0
939 | 947 | 1214 | 15470402430 | Bandera Maintenance Office | Window Replacement | Highway Trans. Fund 6 | 180000 | 180000
940 | 948 | 1215 | 15470402431 | Hondo Area Engineer & Maintenance Office | Asbestos Abatement, Carpet & Paint | Highway Trans. Fund 6 | 35000 | 35000
941 | 949 | 1216 | 15470402432 | Hondo Area Engineer & Maintenance Office | Restroom Upgrade | Highway Trans. Fund 6 | 25000 | 25000
942 | 950 | 1217 | 12470402433 | East Harris Maintenance Office | Locker Room Upgrades/Addition Of Showers | Highway Trans. Fund 6 | 42000 | 42000
944 | 952 | 1218 | 15470402435 | Uvalde Maintenance Office | Replace Irrigation System | Highway Trans. Fund 6 | 15000 | 15000
948 | 956 | 1219 | 08470402439 | Roby Maintenance Office | Repair Structural Damage to Columns | Highway Trans. Fund 6 | 25000 | 25000
950 | 958 | 1220 | 08470402441 | Taylor Co. Maintenance Office | Upgrade Wash Bay | Highway Trans. Fund 6 | 35000 | 35000
951 | 959 | 1221 | 24470402442 | Pine Springs Sub-Section | Additional Outside LED Lighting For Houses. | Highway Trans. Fund 6 | 8000 | 8000
953 | 961 | 1222 | 24470402444 | Pine Springs Sub-Section | Renovate Stock Area; Insulate Metal Walls, Ceiling | Highway Trans. Fund 6 | 11500 | 11500
954 | 962 | 1223 | 07470402445 | Big Lake Maintenance Office | Construct Buildings Over Lifts | Highway Trans. Fund 6 | 50000 | 50000
956 | 964 | 1224 | 14470402447 | East Travis Maintenance Office | Foundation Repair | Highway Trans. Fund 6 | 167200 | 167200
957 | 965 | 1225 | 17470402448 | Navasota Maintenance Office | Replace Fuel Canopy - Navasota MNT | Highway Trans. Fund 6 | 35000 | 35000
959 | 967 | 1226 | 16470402450 | Nueces East | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 6 | 25000 | 25000
960 | 968 | 1227 | 19470402451 | Carthage Maintenance Office | Install Overhead Door Operators & Gate | Highway Trans. Fund 6 | 82600 | 82600
961 | 969 | 1228 | 19470402452 | Carthage Maintenance Office | Remodel Inside Of Building Including Bathrooms | Highway Trans. Fund 6 | 75000 | 75000
964 | 972 | 1229 | 16470402455 | San Patricio Co | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 6 | 40000 | 40000
965 | 973 | 1230 | 16470402456 | Sinton Area Engineer & Maintenance Office | Paint Interior Walls At Area Engineer And Maintenance - Sinton AEM | Highway Trans. Fund 6 | 15000 | 15000
968 | 976 | 1231 | 16470402459 | Aransas Co. | Replace Existing Floor Tile And Paint Office | Highway Trans. Fund 6 | 17500 | 17500
969 | 977 | 1232 | 16470402460 | Aransas Co. | Install Storm Shutters On All Windows And Doors | Highway Trans. Fund 6 | 25000 | 25000
970 | 978 | 1233 | 16470402461 | Rockport Maintenance Office | Install Exteriors At Maintenance - Rockport MNT | Highway Trans. Fund 6 | 28000 | 28000
971 | 979 | 1234 | 16470402462 | Rockport Maintenance Office | Repair Exterior Windows At Maintenance - Rockport MNT | Highway Trans. Fund 6 | 20000 | 20000
973 | 981 | 1235 | 12470402464 | Humble Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 120000 | 120000
974 | 982 | 1236 | 12470402465 | Humble Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 320000 | 320000
975 | 983 | 1237 | 22470402466 | Del Rio Maintenance Office | Storage Shed Asbestos Testing & Abatement | Highway Trans. Fund 6 | 50000 | 50000
976 | 984 | 1238 | 22470402467 | Del Rio Maintenance Office | Storage Shed Repairs | Highway Trans. Fund 6 | 15000 | 15000
977 | 985 | 1239 | 11470402468 | Center Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 6 | 40000 | 40000
985 | 993 | 1240 | 11470402476 | Nacogdoches Area Engineer & Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 6 | 40000 | 40000
986 | 994 | 1241 | 11470402477 | Nacogdoches Area Engineer & Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 30000 | 30000
988 | 996 | 1242 | 11470402479 | Nacogdoches Area Engineer & Maintenance Office | Upgrade Exterior Lighting | Highway Trans. Fund 6 | 15000 | 15000
991 | 999 | 1243 | 11470402482 | San Augustine Area Engineer & Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 6 | 40000 | 40000
992 | 1000 | 1244 | 11470402483 | San Augustine Area Engineer & Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 30000 | 30000
997 | 1005 | 1245 | 06470402488 | Stanton Maintenance Office | Install Ladder Or Staircase | Highway Trans. Fund 6 | 5000 | 5000
998 | 1006 | 1246 | 06470402489 | Stanton Maintenance Office | Reinstall Evaporative Coolers In Wall | Highway Trans. Fund 6 | 8000 | 8000
999 | 1007 | 1247 | 21470402490 | District Headquarters | Exterior Facade Repairs To Warehouse, Shop & Teleconference Training Center | Highway Trans. Fund 6 | 35000 | 35000
1000 | 1008 | 1248 | 21470402491 | District Headquarters | Renovate Shop | Highway Trans. Fund 6 | 117000 | 117000
1001 | 1009 | 1249 | 21470402492 | District Headquarters/Area Engineer & Maintenance Office | Install Vehicle Exhaust System. Replace Existing Ceiling Fans. | Highway Trans. Fund 6 | 40000 | 40000
1002 | 1010 | 1250 | 21470402493 | District Headquarters/Area Engineer & Maintenance Office | Replace All Windows/Frames. | Highway Trans. Fund 6 | 85000 | 85000
1004 | 1012 | 1251 | 15470402495 | Pleasanton Area Engineer & Maintenance Office | Restroom Upgrade | Highway Trans. Fund 6 | 25000 | 25000
1005 | 1013 | 1252 | 04470402496 | Dalhart Maintenance Office | Electrical Upgrades | Highway Trans. Fund 6 | 8000 | 8000
1006 | 1014 | 1253 | 04470402497 | Dalhart Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000
1007 | 1015 | 1254 | 04470402498 | Dalhart Maintenance Office | Shop Lighting Upgrades | Highway Trans. Fund 6 | 15000 | 15000
1008 | 1016 | 1255 | 19470402499 | Jefferson Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 6 | 65000 | 65000
1009 | 1017 | 1256 | 19470402500 | Jefferson Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 6 | 113000 | 113000
1012 | 1020 | 1257 | 02470402503 | District Headquarters | Remodel Old Sign Shop Into A Fitness Center | Highway Trans. Fund 6 | 831000 | 831000
1013 | 1021 | 1258 | 06470402504 | Kermit Maintenance Office | Paint Exterior Walls | Highway Trans. Fund 6 | 21000 | 21000
1014 | 1022 | 1259 | 13470402505 | Gonzales Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 6 | 5000 | 5000
1015 | 1023 | 1260 | 04470402506 | Loop | Lighting Upgrades | Highway Trans. Fund 6 | 25000 | 25000
1016 | 1024 | 1261 | 04470402507 | Loop | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000
1017 | 1025 | 1262 | 19470402508 | Linden Maintenance Office | Install Overhead Door Operators & Gate | Highway Trans. Fund 6 | 83000 | 83000
1018 | 1026 | 1263 | 19470402509 | Linden Maintenance Office | Replace VCT Flooring And Paint Interior | Highway Trans. Fund 6 | 40000 | 40000
1019 | 1027 | 1264 | 18470402510 | District Headquarters | Modular Furniture Installation | Highway Trans. Fund 6 | 35000 | 35000
1020 | 1028 | 1265 | 18470402511 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 6 | 21500 | 21500
1023 | 1031 | 1266 | 22470402514 | Del Rio Maintenance Office | Relocate Generator From Freer | Highway Trans. Fund 6 | 25000 | 25000
1024 | 1032 | 1267 | 22470402515 | Del Rio Maintenance Office (US 90) | Men's Restroom Renovation | Highway Trans. Fund 6 | 20000 | 20000
1025 | 1033 | 1268 | 05470402516 | Morton Maintenance Office | Repaint Exterior, Old Faded Peeling | Highway Trans. Fund 6 | 30000 | 30000
1026 | 1034 | 1269 | 05470402517 | Tulia Maintenance Office | Repaint Exterior, Old Faded Peeling | Highway Trans. Fund 6 | 25000 | 25000
1027 | 1035 | 1270 | 13470402518 | Jackson Cty Maint. | Paint Interior Structure Of Equip Shed | Highway Trans. Fund 6 | 15000 | 15000
1028 | 1036 | 1271 | 22470402519 | Cotulla Maintenance Office | Men's Restroom Renovation | Highway Trans. Fund 6 | 24000 | 24000
1029 | 1037 | 1272 | 22470402520 | Cotulla Maintenance Office | Replace Breakroom Flooring | Highway Trans. Fund 6 | 15000 | 15000
1030 | 1038 | 1273 | 20470402521 | Jasper Area Engineer & Maintenance Office | Replace AV Electrical Circuit | Highway Trans. Fund 6 | 1500 | 1500
1034 | 1042 | 1274 | 20470402525 | Jasper Area Engineer & Maintenance Office | Remodel Rest Rooms & Wall Repair | Highway Trans. Fund 6 | 54000 | 54000
1036 | 1044 | 1275 | 20470402527 | Orange Maintenance Office | Replace Siding And Roofing | Highway Trans. Fund 6 | 65000 | 65000
1037 | 1045 | 1276 | 20470402528 | Orange Maintenance Office | Upgrade Electrical | Highway Trans. Fund 6 | 10000 | 10000
1038 | 1046 | 1277 | 12470402529 | Conroe Area Engineer & Maintenance Office | New Carpet/VCT | Highway Trans. Fund 6 | 15000 | 15000
1039 | 1047 | 1278 | 12470402530 | Conroe Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 15000 | 15000
1040 | 1048 | 1279 | 12470402531 | Conroe Area Engineer & Maintenance Office | Reconfigure Cubicles (Space Management) | Highway Trans. Fund 6 | 10000 | 10000
1042 | 1050 | 1280 | 22470402533 | Laredo Administration | Administration: Nail Down Spanish Tiles; Remove/Replace Broken Spanish Tiles | Highway Trans. Fund 6 | 120000 | 120000
1043 | 1051 | 1281 | 22470402534 | Laredo Area Engineer & Maintenance Office | Remove Worn Out Existing VCT Flooring & Replace Ceramic Tile | Highway Trans. Fund 6 | 20000 | 20000
1044 | 1052 | 1282 | 22470402535 | Laredo Area Engineer & Maintenance Office (Lilac/Conference room) | Retrofit To Video Teleconference Room | Highway Trans. Fund 6 | 10000 | 10000
1045 | 1053 | 1283 | 22470402536 | Laredo Auto Shop | Bat Issues (Clean Up And Resolution) | Highway Trans. Fund 6 | 300000 | 300000
1046 | 1054 | 1284 | 22470402537 | Laredo Auto Shop | Minor Restrooms Renovation | Highway Trans. Fund 6 | 5000 | 5000
1047 | 1055 | 1285 | 22470402538 | Laredo Compound facilities | Exterior Painting | Highway Trans. Fund 6 | 25000 | 25000
1048 | 1056 | 1286 | 22470402539 | Laredo District Headquarters | Carpet Replacement | Highway Trans. Fund 6 | 30000 | 30000
1049 | 1057 | 1287 | 22470402540 | Laredo FIN/Safety | Modular Unit (12) | Highway Trans. Fund 6 | 96000 | 96000
1050 | 1058 | 1288 | 15470402541 | Transguide | Proportionate Share Of 1St Floor Renovation | Highway Trans. Fund 6 | 1000000 | 1000000
1051 | 1059 | 1289 | 10470402542 | District Headquarters | Demo Warehouse Office | Highway Trans. Fund 6 | 40000 | 40000
1052 | 1060 | 1290 | 10470402543 | District Headquarters | Install New Elevator | Highway Trans. Fund 6 | 150000 | 150000
1053 | 1061 | 1291 | 10470402544 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 6 | 21500 | 21500
1054 | 1062 | 1292 | 13470402545 | Victoria A.O. | Paint Interior Office | Highway Trans. Fund 6 | 20000 | 20000
1055 | 1063 | 1293 | 13470402546 | Victoria A.O. | Sealing Exterior Block Walls | Highway Trans. Fund 6 | 15000 | 15000
1056 | 1064 | 1294 | 13470402547 | Victoria Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 6 | 5000 | 5000
1057 | 1065 | 1295 | 13470402548 | Victoria Cty Maint. | Replace Wash Rack Canopy | Highway Trans. Fund 6 | 50000 | 50000
1058 | 1066 | 1296 | 16470402549 | District Headquarters | Install Storm Shutters On All Windows And Doors | Highway Trans. Fund 6 | 15000 | 15000
1059 | 1067 | 1297 | 16470402550 | District Headquarters | Paint Exterior Walls At Shop - Corpus Christi DHQ | Highway Trans. Fund 6 | 27500 | 27500
1060 | 1068 | 1298 | 24470402551 | District Headquarters | Install LED Lighting In Wall Packs | Highway Trans. Fund 6 | 20000 | 20000
1061 | 1069 | 1299 | 24470402552 | District Headquarters | Install Vestabule / Canopy Near Breakroom | Highway Trans. Fund 6 | 36000 | 36000
1062 | 1070 | 1300 | 24470402553 | District Headquarters | Install Vestibule Front And Rear, Lobby Entries | Highway Trans. Fund 6 | 48000 | 48000
1065 | 1073 | 1301 | 05470402556 | District Headquarters-Division West Building | New VCT Floor | Highway Trans. Fund 6 | 50000 | 50000
1066 | 1074 | 1302 | 15470402557 | Bexar Metro Area Engineer & Maintenance Office | Interior LED Lighting Upgrade | Highway Trans. Fund 6 | 7500 | 7500
1067 | 1075 | 1303 | 15470402558 | Bexar Metro Area Engineer & Maintenance Office | Raise Truck Wash Canopy | Highway Trans. Fund 6 | 10000 | 10000
1068 | 1076 | 1304 | 15470402559 | Bexar Metro Area Engineer & Maintenance Office | Retrofit Equipment Bay For Enclosed Climate Control LED Storage | Highway Trans. Fund 6 | 2000 | 2000
1069 | 1077 | 1305 | 09470402560 | Gatesville Area Engineer & Maintenance Office | Upgrade Shop And Office | Highway Trans. Fund 6 | 50000 | 50000
1070 | 1078 | 1306 | 13470402561 | Yoakum A.O. | Level Building & Repair Exterior Cracks In Brick | Highway Trans. Fund 6 | 50000 | 50000
1071 | 1079 | 1307 | 13470402562 | Yoakum Area Engineer & Maintenance Office | Level Building (Area Engineers Bldg) | Highway Trans. Fund 6 | 50000 | 50000
1073 | 1081 | 1308 | 17470402564 | Hearne Area Engineer & Maintenance Office | Redo HVAC/Vent/Pipes | Highway Trans. Fund 6 | 15000 | 15000
1076 | 1084 | 1309 | 05470402567 | Dimmitt Maintenance Office | Repaint Exterior | Highway Trans. Fund 6 | 30000 | 30000
1077 | 1085 | 1310 | 03470402568 | Gainesville Area Engineer & Maintenance Office | Renovate Building For Storage | Highway Trans. Fund 6 | 30000 | 30000
1078 | 1086 | 1311 | 25470402569 | Shamrock Maintenance Office | Convert Truck Barn To Drive Thru, New Heaters In Truck Barn | Highway Trans. Fund 6 | 200000 | 200000
1082 | 1090 | 1312 | 05470402573 | NE Special Crews | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000
1084 | 1092 | 1313 | 05470402575 | NE Special Crews | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000
1086 | 1094 | 1314 | 15470402577 | Boerne Maintenance Office | Interior Paint | Highway Trans. Fund 6 | 30000 | 30000
1087 | 1095 | 1315 | 38470402578 | TxDOT Flight Services | Building Renovations | Highway Trans. Fund 6 | 430000 | 430000
1088 | 1096 | 1316 | 38470402579 | TxDOT Flight Services | New Epoxy Flooring In Hangars 2,3 And 4 | Highway Trans. Fund 6 | 210000 | 210000
1092 | 1100 | 1317 | 16470402583 | District Headquarters | Paint Interior Walls At Vehicle Titles And Registration - Corpus Christi DHQ | Highway Trans. Fund 6 | 5000 | 5000
1093 | 1101 | 1318 | 18470402584 | District Headquarters | Flooring Replaced - Remove VCT And Replace With VCT | Highway Trans. Fund 6 | 10000 | 10000
1096 | 1104 | 1319 | 13470402587 | Fayette Cty Maint. | Interior Renovation (Floors, Ceiling, & Ac Ducts) | Highway Trans. Fund 6 | 30000 | 30000
1103 | 1111 | 1320 | 20470402594 | Liberty Area Engineer & Maintenance Office | Rest Room/Shower/Ac/Water Heater | Highway Trans. Fund 6 | 9500 | 9500
1104 | 1112 | 1321 | 17470402595 | Bryan Area Engineer & Maintenance Office | Renovate Maintenance Building | Highway Trans. Fund 6 | 200000 | 200000
1105 | 1113 | 1322 | 17470402596 | Bryan Area Engineer & Maintenance Office | Replace Fuel Canopy - Bryan AEM | Highway Trans. Fund 6 | 35000 | 35000
1106 | 1114 | 1323 | 17470402597 | Bryan Area Engineer & Maintenance Office | Restroom Remodels, Training Building | Highway Trans. Fund 6 | 10000 | 10000
1107 | 1115 | 1324 | 25470402598 | Clarendon Maintenance Office | Convert Truck Barn To Drive Thru, New Heaters In Truck Barn | Highway Trans. Fund 6 | 200000 | 200000
1108 | 1116 | 1325 | 24470402599 | El Paso (East) Area Engineer & Maintenance Office | Install New Front Doors (Building ) And Secure The Lobby Area | Highway Trans. Fund 6 | 30000 | 30000
1109 | 1117 | 1326 | 24470402600 | El Paso (East) Area Engineer & Maintenance Office | Modify Interior Doorway, At Stockroom Forklift Access. | Highway Trans. Fund 6 | 5900 | 5900
1110 | 1118 | 1327 | 24470402601 | EL PASO (EAST) AREA Area Engineer & Maintenance Office | Building Renovations | Highway Trans. Fund 6 | 120000 | 120000
1112 | 1120 | 1328 | 24470402603 | El Paso (West) Area Engineer & Maintenance Office | Larger Restroom In Our Maintenance Section | Highway Trans. Fund 6 | 50000 | 50000
1113 | 1121 | 1329 | 02470402604 | District Headquarters | Emergency Generator At Intelligent Transportation Management Center - Fort Worth DHQ | Highway Trans. Fund 6 | 120000 | 120000
1114 | 1122 | 1330 | 22470402605 | Freer | Interior & Exterior Painting & Sheet Metal Painting | Highway Trans. Fund 6 | 30000 | 30000
1115 | 1123 | 1331 | 22470402606 | Freer | Overhead Projector & Electrical | Highway Trans. Fund 6 | 2500 | 2500
1116 | 1124 | 1332 | 38470402607 | CEDAR PARK Research and Technology Center | Interior Renovations | Highway Trans. Fund 6 | 180000 | 180000
1118 | 1126 | 1333 | 09470402609 | Hillsboro Area Engineer & Maintenance Office | Upgrade Lab | Highway Trans. Fund 6 | 35000 | 35000
1119 | 1127 | 1334 | 09470402610 | Hillsboro Area Engineer & Maintenance Office | Replace Plumbing | Highway Trans. Fund 6 | 12000 | 12000
1120 | 1128 | 1335 | 13470402611 | Colorado Cty Maint. | Painting Interior Structure Of Equip Shed | Highway Trans. Fund 6 | 15000 | 15000
1121 | 1129 | 1336 | 16470402612 | Bee Co. | Install Redundant 2000 Gallon Diesel Tank To Existing Fuel Island | Highway Trans. Fund 6 | 35000 | 35000
1122 | 1130 | 1337 | 18470402613 | Cedar Hill Maintenance Office | Upgrade Electrical | Highway Trans. Fund 6 | 40000 | 40000
1124 | 1132 | 1338 | 13470402615 | Lavaca Cty Maint | Replace Tin & Paint Exterior Struct Of Wash Rack | Highway Trans. Fund 6 | 10000 | 10000
1125 | 1133 | 1339 | 13470402616 | Lavaca Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 6 | 5000 | 5000
1126 | 1134 | 1340 | 13470402617 | Lavaca Cty Maint. | Repair Sheetrock And Paint Walls | Highway Trans. Fund 6 | 8000 | 8000
1127 | 1135 | 1341 | 19470402618 | District Headquarters | Remodel Inside Of Building | Highway Trans. Fund 6 | 50000 | 50000
1128 | 1136 | 1342 | 19470402619 | District Headquarters | Restroom Upgrades | Highway Trans. Fund 6 | 181000 | 181000
1134 | 1142 | 1343 | 17470402625 | Fairfield Maintenance Office | Close In Part Of Shed For Work Area | Highway Trans. Fund 6 | 35000 | 35000
1135 | 1143 | 1344 | 22470402626 | La Pryon on HWY 57 | Install Interior Lighting | Highway Trans. Fund 6 | 25000 | 25000
1136 | 1144 | 1345 | 22470402627 | La Pryor Maintenance Office | Renovation Conference Room | Highway Trans. Fund 6 | 150000 | 150000
1137 | 1145 | 1346 | 22470402628 | La Pryor Maintenance Office | Renovate Maintenance Facility | Highway Trans. Fund 6 | 125000 | 125000
1138 | 1146 | 1347 | 22470402629 | La Pryor Maintenance Office | Retrofit Existing Office Space | Highway Trans. Fund 6 | 50000 | 50000
1143 | 1151 | 1348 | 16470402634 | Kingsville Maintenance Office | Repair Plumbing System At Truck Wash Bay - Kingsville MNT | Highway Trans. Fund 6 | 40000 | 40000
1144 | 1152 | 1349 | 16470402635 | Robstown Maintenance Office | Repair Plumbing System At Truck Wash Bay - Robstown Maintenance | Highway Trans. Fund 6 | 40000 | 40000
1145 | 1153 | 1350 | 22470402636 | Laredo Auto Shop | Bay Wash Repairs | Highway Trans. Fund 6 | 40000 | 40000
1148 | 1156 | 1351 | 12470402639 | District Headquarters | Install Safety Flooring | Highway Trans. Fund 6 | 45000 | 45000
1149 | 1157 | 1352 | 12470402640 | District Headquarters | Renovate Restrooms (Locker Rooms) | Highway Trans. Fund 6 | 42000 | 42000
1150 | 1158 | 1353 | 12470402641 | District Headquarters | Replace Emergency Exit Signage | Highway Trans. Fund 6 | 45000 | 45000
1151 | 1159 | 1354 | 12470402642 | District Headquarters | Upgrade Lighting (LED) | Highway Trans. Fund 6 | 75000 | 75000
1154 | 1162 | 1355 | 17470402645 | Hearne Area Engineer & Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000
1155 | 1163 | 1356 | 17470402646 | Hearne Area Engineer & Maintenance Office | New Fuel Canopy - Hearne AEM | Highway Trans. Fund 6 | 35000 | 35000
1156 | 1164 | 1357 | 17470402647 | Huntsville Area Engineer & Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000
1157 | 1165 | 1358 | 16470402648 | Alice Area Engineer & Maintenance Office | Install Electrical Wiring - Alice AEM | Highway Trans. Fund 6 | 40000 | 40000
1158 | 1166 | 1359 | 16470402649 | Alice Area Engineer & Maintenance Office | Repair Sewer System - Alice AEM | Highway Trans. Fund 6 | 10000 | 10000
1159 | 1167 | 1360 | 12470402650 | Humble Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 500000 | 500000
1160 | 1168 | 1361 | 22470402651 | Del Rio Maintenance Office | Demo (D) And Install (I) Of 2 Lamp T8 Light Fixture (D-2 & I-6 @ Fueling Station; D-57 & I-45 @ Warehouse; And D-39 & I-31 @ MNT Vehicle | Highway Trans. Fund 6 | 18000 | 18000
1163 | 1171 | 1362 | 15470402654 | West Bexar Maintenance Office | Interior Paint | Highway Trans. Fund 6 | 15000 | 15000
1164 | 1172 | 1363 | 15470402655 | West Bexar Maintenance Office | Retrofit Shop Bay To Meeting Room | Highway Trans. Fund 6 | 50000 | 50000
1165 | 1173 | 1364 | 38470402656 | Riverside Annex I RA118 | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 6 | 15000 | 15000
1166 | 1174 | 1365 | 38470402657 | Riverside Annex II RA150-200 | EOC Technology Renovation (Electronics) | Highway Trans. Fund 6 | 60000 | 60000
1167 | 1175 | 1366 | 38470402658 | Riverside Annex II RA150-200 | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 6 | 35000 | 35000
1168 | 1176 | 1367 | 03470402659 | Bowie Maintenance Office | Upgrade Electrical | Highway Trans. Fund 6 | 80000 | 80000
1169 | 1177 | 1368 | 16470402660 | Nueces West | Install Storm Shutters On All Windows And Doors | Highway Trans. Fund 6 | 35000 | 35000
1170 | 1178 | 1369 | 11470402661 | Shepherd Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000
1174 | 1182 | 1370 | 17470402665 | District Headquarters | Add Awning To Shop Building | Highway Trans. Fund 6 | 35000 | 35000
1175 | 1183 | 1371 | 17470402666 | District Headquarters | Administration Bldg Foundation Repair | Highway Trans. Fund 6 | 50000 | 50000
1176 | 1184 | 1372 | 17470402667 | District Headquarters | Awnings Between Buildings W/ Lights | Highway Trans. Fund 6 | 30000 | 30000
1177 | 1185 | 1373 | 17470402669 | District Headquarters | Install A/C System To HQ Warehouse | Highway Trans. Fund 6 | 25000 | 25000
1179 | 1187 | 1374 | 17470402671 | District Headquarters | New Fuel Canopy | Highway Trans. Fund 6 | 45000 | 45000
1180 | 1188 | 1375 | 17470402672 | District Headquarters | Overhead Crane Shops | Highway Trans. Fund 6 | 75000 | 75000
1181 | 1189 | 1376 | 17470402673 | District Headquarters | Paint Signal Warehouse Walls | Highway Trans. Fund 6 | 10000 | 10000
1182 | 1190 | 1377 | 17470402674 | District Headquarters | Repair Admin Building Water Intrusion | Highway Trans. Fund 6 | 20000 | 20000
1184 | 1192 | 1378 | 21470402676 | Roma Area Engineer & Maintenance Office | Building Finish Out | Highway Trans. Fund 6 | 120000 | 120000
1185 | 1193 | 1379 | 38470402678 | Statewide | Emergency Repairs - Statewide | Highway Trans. Fund 236 | 50866849 | 57157025
PROJECTS PENDING FUNDING AVAILABILITY | [6 empty] | 147543949 | 153834125 | 0
Removed | R1 | R1 | 38470402968 | Condition AssessmentVarious |  | Highway Trans. Fund 6 | 5000000 | -5000000
Removed | R2 | R2 | 38470402969 | Condition Assessment SoftwareVarious |  | Highway Trans. Fund 6 | 1000000 | -1000000
2 | R3 | R3 | 19470401489 | Upgrade Security (C-CURE)Atlanta District Headquarters |  | Highway Trans. Fund 6 | 350000 | -350000
1 | 140 | R4 | 19470401488 | Install LED Parking Lot LightingAtlanta District Headquarters |  | Highway Trans. Fund 6 | 85000 | -85000
531 | 541 | R5 | 01470402020 | Demolish Existing Building District Headquarters |  | Highway Trans. Fund 6 | 29500 | -29500
156 | R17 | R6 | 03470401638 | In-Ground ShelterWichita Falls District Headquarters |  | Highway Trans. Fund 6 | 144125 | -144125
53 | R19 | R7 | 04470401642 | Upgrade Security (C-CURE)Amarillo District Headquarters |  | Highway Trans. Fund 6 | 350000 | -350000
340 | 352 | R8 | 04470401829 | Sprinkler System RepairsDumas Maintenance Office |  | Highway Trans. Fund 6 | 8000 | -8000
189 | 70 | R9 | 05470401680 | Retrofit Existing Gate Opener W/C-CureNE Maint. Office |  | Highway Trans. Fund 6 | 18000 | -18000
96 | 103 | R10 | 05470401737 | Install New Gate Opener To Existing GateLubbock District Headquarters |  | Highway Trans. Fund 6 | 6500 | -6500
654 | 664 | R11 | 05470402143 | Install Exit LoopsDistrict Headquarters |  | Highway Trans. Fund 6 | 2500 | -2500
Removed | R4 | R12 | 06470401497 | Install Motion Sensors On Install Automatic GateAndrews Maintenance Office |  | Highway Trans. Fund 6 | 1500 | -1500
Removed | R6 | R13 | 06470401515 | Install Motion Sensors On Install Automatic GateMcCamey Maintenance Office |  | Highway Trans. Fund 6 | 1500 | -1500
Removed | R8 | R14 | 06470401525 | Install Motion Sensors On Install Automatic GateStanton Maintenance Office |  | Highway Trans. Fund 6 | 1500 | -1500
Removed | R12 | R15 | 06470401555 | Install Motion Sensors On Install Automatic GateKermit Maintenance Office |  | Highway Trans. Fund 6 | 1500 | -1500
232 | R16 | R16 | 06470401616 | Install Motion Sensors On Install Automatic GateMonahans Maintenance Office |  | Highway Trans. Fund 6 | 1500 | -1500
350 | 362 | R17 | 06470401839 | Paint Asphalt Tank Bases And Hardware. Deteriorating Paint And Rusting SteelMcCamey Maintenance Office |  | Highway Trans. Fund 6 | 10000 | -10000
354 | 366 | R18 | 06470401843 | Repair Irrigation SystemsSanderson Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
395 | 407 | R19 | 06470401884 | Replace Irrigation System For New Yard DesignOdessa Maintenance Office |  | Highway Trans. Fund 6 | 10000 | -10000
404 | 416 | R20 | 06470401893 | Repair Irrigation SystemsMonahans Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
451 | 461 | R21 | 06470401940 | Repair Irrigation SystemsIraan Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
456 | 466 | R22 | 06470401945 | Repair Irrigation SystemsBalmorhea Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
467 | 477 | R23 | 06470401956 | Repair Irrigation SystemsMidland Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
584 | 594 | R24 | 06470402073 | Repair/Replace Atg System On Above Ground Fuel TanksAndrews Maintenance Office |  | Highway Trans. Fund 6 | 12000 | -12000
585 | 595 | R25 | 06470402074 | Seal Roof PenetrationsAndrews Maintenance Office |  | Highway Trans. Fund 6 | 3000 | -3000
714 | R29 | R26 | 06470402203 | Repair/Replace Atg System On Above Ground Fuel TanksDistrict Headquarters |  | Highway Trans. Fund 6 | 12000 | -12000
792 | 800 | R27 | 06470402281 | Upgrade Rain GuttersCrane Maintenance Office |  | Highway Trans. Fund 6 | 7000 | -7000
1162 | 1170 | R28 | 06470402653 | Paint Cat-WalkFt Stockton Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 10000 | -10000
341 | 353 | R29 | 07470401830 | Demolish Old Asphalt Storage TankEden Maintenance Office |  | Highway Trans. Fund 6 | 15000 | -15000
375 | 387 | R30 | 07470401864 | Demolish Old Asphalt Storage TankSterling City Maintenance Office |  | Highway Trans. Fund 6 | 15000 | -15000
397 | 409 | R31 | 07470401886 | Demolish Old Asphalt Storage TankJunction Maintenance Office |  | Highway Trans. Fund 6 | 15000 | -15000
431 | 443 | R32 | 07470401920 | Demolish Old Asphalt Storage TankOzona Maintenance Office |  | Highway Trans. Fund 6 | 15000 | -15000
468 | 478 | R33 | 07470401957 | Demolish Old Asphalt Storage TankBig Lake Maintenance Office |  | Highway Trans. Fund 6 | 15000 | -15000
112 | R13 | R34 | 08470401578 | Replace RoofColorado City Maintenance Office |  | Highway Trans. Fund 6 | 40000 | -40000
113 | R14 | R35 | 08470401579 | Modifications/Upgrade HVACAbilene District Headquarters |  | Highway Trans. Fund 6 | 120000 | -120000
48 | R15 | R36 | 08470401580 | Upgrade Security (C-CURE)Abilene District Headquarters |  | Highway Trans. Fund 6 | 350000 | -350000
945 | 953 | R37 | 08470402436 | Install Floor TileRoby Maintenance Office |  | Highway Trans. Fund 6 | 18000 | -18000
946 | 954 | R38 | 08470402437 | Level Wash BayRoby Maintenance Office |  | Highway Trans. Fund 6 | 1500 | -1500
949 | 957 | R39 | 08470402440 | Upgrade Power Washer BuildingRoby Maintenance Office |  | Highway Trans. Fund 6 | 2500 | -2500
1133 | 1141 | R40 | 08470402624 | Install Double Pane Glass Windows In Store Front Entry AreaAbilene Maintenance Office |  | Highway Trans. Fund 6 | 4500 | -4500
27 | R7 | R41 | 09470401519 | Upgrade Security (C-CURE)Waco District Headquarters |  | Highway Trans. Fund 6 | 350000 | -350000
284 | 296 | R42 | 09470401772 | Replace RoofGatesville Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 350000 | -350000
190 | R21 | R43 | 11470401682 | Replace Emergency GeneratorLufkin Maintenance Office |  | Highway Trans. Fund 6 | 38000 | -38000
1141 | 1149 | R44 | 11470402632 | Replace Fuel DispensersGroveton Maintenance Office |  | Highway Trans. Fund 6 | 20000 | -20000
1041 | 1049 | R45 | 12470402532 | Renovate Breakroom Conroe Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
158 | R18 | R46 | 13470401640 | Replace APU (Generator)Matagorda Cty Maint. |  | Highway Trans. Fund 6 | 10000 | -10000
495 | 505 | R47 | 13470401984 | Replace Asphalt Tank BermLa Grange Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 10000 | -10000
738 | 746 | R48 | 13470402227 | Paint Exterior Structure Of Fuel CanopyColorado Cty Maint. |  | Highway Trans. Fund 6 | 5000 | -5000
1123 | 1131 | R49 | 13470402614 | Replace Tin At Mechanic ShopHallettsville Maintenance Office |  | Highway Trans. Fund 6 | 7000 | -7000
60 | 87 | R50 | 15470401690 | Replace RoofDevine Maintenance Office |  | Highway Trans. Fund 6 | 100000 | -100000
1003 | 1011 | R51 | 15470402494 | Paint, Carpet ReplacementPleasanton Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 20000 | -20000
165 | 128 | R52 | 16470401649 | Replace Existing Security And Access Control System To C-CureCorpus Christi District Headquarters |  | Highway Trans. Fund 6 | 300000 | -300000
169 | 171 | R53 | 16470401654 | Upgrade HQ Campus Emergency GeneratorCorpus Christi District Headquarters |  | Highway Trans. Fund 6 | 200000 | -200000
74 | R24 | R54 | 16470401708 | Replace RoofCorpus Christi District Headquarters |  | Highway Trans. Fund 6 | 300000 | -300000
88 | R27 | R55 | 16470401728 | Replace Roof At Area Engineer And Maintenance - Corpus Christi AEMCorpus Christi Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 24000 | -24000
89 | R28 | R56 | 16470401729 | Replace\New Security Fence - Corpus Christi AEMCorpus Christi Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 17000 | -17000
903 | 911 | R57 | 16470402394 | Replace\New Electrical Panel At Right Of Way - Corpus Christi DHQDistrict Headquarters |  | Highway Trans. Fund 6 | 15000 | -15000
962 | 970 | R58 | 16470402453 | Replace Ceiling Tiles In Office BuildingSan Patricio Co |  | Highway Trans. Fund 6 | 7500 | -7500
966 | 974 | R59 | 16470402457 | Replace Ceilings At Area Engineer And Maintenance - Sinton AEMSinton Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 7500 | -7500
629 | 639 | R60 | 17470402118 | Improve Lighting In Yard/ShedCameron Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
670 | 680 | R61 | 17470402159 | Demolish Old Ae BuildingNavasota Maintenance Office |  | Highway Trans. Fund 6 | 12500 | -12500
671 | 681 | R62 | 17470402160 | Improve Lighting In Yard/ShedNavasota Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
687 | 697 | R63 | 17470402176 | Replace GuttersCaldwell Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
920 | 928 | R64 | 17470402411 | Improve Lighting In Yard/ShedBryan Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
1074 | 1082 | R65 | 17470402565 | Redo Lighting In WashbayHearne Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
1075 | 1083 | R66 | 17470402566 | Replace Ceiling TilesHearne Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 10000 | -10000
1130 | 1138 | R67 | 17470402621 | Improve Lighting In Yard/ShedBrenham Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
1131 | 1139 | R68 | 17470402622 | Install Electric Door Openers For Roll-Up DoorsBrenham Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 7500 | -7500
1132 | 1140 | R69 | 17470402623 | Replace Windows On Storage ShedBrenham Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
1183 | 1191 | R70 | 17470402675 | Upgrade Used Oil & Antifreeze ContainersDistrict Headquarters |  | Highway Trans. Fund 6 | 5000 | -5000
42 | R10 | R71 | 18470401545 | Relocate And Add HVAC To Break RoomDallas District Headquarters |  | Highway Trans. Fund 6 | 15000 | -15000
44 | R11 | R72 | 18470401547 | Fence - Repair Chain Link/Top Rail At EasementDallas District Headquarters |  | Highway Trans. Fund 6 | 10000 | -10000
187 | R20 | R73 | 18470401676 | New Generator - DieselRockwall Maintenance Office |  | Highway Trans. Fund 6 | 25000 | -25000
311 | 323 | R74 | 18470401800 | New Generator - DieselCedar Hill Maintenance Office |  | Highway Trans. Fund 6 | 15000 | -15000
358 | 370 | R75 | 18470401847 | Parking Lot StripingEnnis Maintenance Office |  | Highway Trans. Fund 6 | 5000 | -5000
368 | 380 | R76 | 18470401857 | Parking Lot StripingDistrict Headquarters |  | Highway Trans. Fund 6 | 20000 | -20000
439 | 451 | R77 | 18470401928 | Parking Lot StripingWaxahachie Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 10000 | -10000
494 | 504 | R78 | 18470401983 | Parking Lot StripingDenton Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 10000 | -10000
510 | 520 | R79 | 18470401999 | Parking Lot StripingCorsicana Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 10000 | -10000
610 | 620 | R80 | 25470402099 | Crowell Maintenance |  | Highway Trans. Fund 6 | 25000 | -25000
617 | 627 | R81 | 18470402106 | Restroom Partitions ReplacedEnnis Maintenance Office |  | Highway Trans. Fund 6 | 3000 | -3000
633 | 643 | R82 | 17470402122 | Cameron Maintenance Office |  | Highway Trans. Fund 6 | 25000 | -25000
651 | 661 | R83 | 18470402140 | Restroom Partitions Replacement - Men's RestroomDistrict Headquarters |  | Highway Trans. Fund 6 | 1500 | -1500
1010 | 1018 | R84 | 18470402501 | Analysis By Engineering ConsultantDistrict Headquarters |  | Highway Trans. Fund 6 | 45000 | -45000
1021 | 1029 | R85 | 18470402512 | Countertops - Restrooms On 4Th FloorDistrict Headquarters |  | Highway Trans. Fund 6 | 5000 | -5000
39 | R9 | R86 | 20470401542 | Install Card Reader AccessAnahuac Maintenance Office |  | Highway Trans. Fund 6 | 12000 | -12000
265 | 277 | R87 | 20470401753 | Rehab Metal RoofingOrange Maintenance Office |  | Highway Trans. Fund 6 | 95000 | -95000
365 | 377 | R88 | 20470401854 | Remove Out Of Service Emulsion, Linseed Oil & AstsWoodville Maintenance Office |  | Highway Trans. Fund 6 | 20000 | -20000
412 | 424 | R89 | 20470401901 | Remove Out Of Service Emulsion, Linseed Oil & AstsDistrict Headquarters |  | Highway Trans. Fund 6 | 20000 | -20000
746 | 754 | R90 | 20470402235 | Paint Flag PoleDistrict Headquarters |  | Highway Trans. Fund 6 | 3000 | -3000
747 | 755 | R91 | 20470402236 | Rebuild Overhead Door (10)District Headquarters |  | Highway Trans. Fund 6 | 4000 | -4000
1031 | 1039 | R92 | 20470402522 | Clean Fuel TanksJasper Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 4000 | -4000
1091 | 1099 | R93 | 20470402582 | Repair Heating SystemBeaumont Area Engineer & Maintenance Office |  | Highway Trans. Fund 6 | 7500 | -7500
82 | R26 | R94 | 21470401721 | Replace GeneratorLaguna Vista Maintenance Office Sub-Section |  | Highway Trans. Fund 6 | 15000 | -15000
1171 | 1179 | R95 | 21470402662 | Bird Net For Truck Wash And Equip. ShedEdcouch Maintenance Office |  | Highway Trans. Fund 6 | 1000 | -1000
1172 | 1180 | R96 | 21470402663 | Repaint GeneratorEdcouch Maintenance Office |  | Highway Trans. Fund 6 | 500 | -500
1173 | 1181 | R97 | 21470402664 | Repair Wall PacksEdcouch Maintenance Office |  | Highway Trans. Fund 6 | 2500 | -2500
498 | 508 | R98 | 22470401987 | Flag Pole LightingFreer |  | Highway Trans. Fund 6 | 3000 | -3000
516 | 526 | R99 | 22470402005 | Parking Lot StripingLaredo District Headquarters |  | Highway Trans. Fund 6 | 30000 | -30000
179 | 94 | R100 | 23470401667 | Upgrade Security (C-CURE)Brownwood District Headquarters |  | Highway Trans. Fund 6 | 350000 | -350000
65 | R23 | R101 | 24470401697 | Modifications/Upgrade ElectricalTerlingua Sub-Section |  | Highway Trans. Fund 6 | 150000 | -150000
79 | R25 | R102 | 24470401718 | Replace RoofPresidio Maintenance Office |  | Highway Trans. Fund 6 | 285000 | -285000
463 | 473 | R103 | 24470401952 | Demolish Old Emulsion TankPresidio Maintenance Office |  | Highway Trans. Fund 6 | 8500 | -8500
506 | 516 | R104 | 24470401995 | Demolish Old Emulsion TankMarfa Sub-Section |  | Highway Trans. Fund 6 | 8500 | -8500
507 | 517 | R105 | 24470401996 | Demolish Old Emulsion TankVan Horn Maintenance Office |  | Highway Trans. Fund 6 | 8500 | -8500
952 | 960 | R106 | 24470402443 | Install Garage Door OpenersPine Springs Sub-Section |  | Highway Trans. Fund 6 | 7000 | -7000
58 | R22 | R107 | 38470401688 | Modifications/Upgrade ElectricalCamp Hubbard State Headquarters |  | Highway Trans. Fund 6 | 517000 | -517000
#N/A | 206 | R108 | 03470402987 | Lift Station Grinder Pump ReplacementsHenrietta Maintenance Office |  | Highway Trans. Fund 7 | 0 | 0
[7 empty] | 11334125 | -11334125
[7 empty] | 200000000 | 200000000 |  |  |  | 5139554 | 481243 | 57500000
Note on C7: Diana Miller: Now Ordering based on Start Sheet Dates

## TxDOT 3.16
|  | Agency: | Texas Department of Transportation #601 |  |  | Legend: Used latest budget estimate available in order of 1. Contracted, 2 Start Estimate, 3 Current anticipated estimate. | Contracted Amt.
|  | Date: | 2016-02-29 |  |  |  | Start Estimate | Draft version: | 2016-02-29
|  | Prepared by: | Diana Miller |  |  |  | Current Estimate | Project 100% Complete
Q1JOC Priority |  | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q2 AY16) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
Q2JOC Priority
U6 | 1 | 15470402973 | NE Bexar Maintenance Office | Drainage Flume | Highway Trans. Fund 6 | 0 | 24120 | 2015-12-17 | 100% | 100% | 24120 | 24120 | 0
U3 | 2 | 03470402972 | District Headquarters | Foundation Repair at DHQ | Highway Trans. Fund 6 | 0 | 18000 | 2016-01-08 | 100% | 100% | 18000 | 18000 | 0
U4 | 3 | 03470402975 | Henrietta Maintenance Office | Stairs & Handicap Ramp for Mod Building | Highway Trans. Fund 6 | 0 | 24105 | 3/7/2016 | 100% | 50% | 24105 | 0 | 24105
U1 | 4 | 20470402970 | Beaumont District Headquarters | Remove and Install 10 and 8.5 ton Roof Top HVAC Units | Highway Trans. Fund 6 | 0 | 17650 | 2016-12-31 | 100% | 100% | 17650 | 17650 | 0
20 | 5 | 04470401510 | Darouzett Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 11483.33 | 2016-04-27 | 100% | 0% | 11483.33 | 0 | 11483.33
22 | 6 | 04470401512 | Gruver Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 12935.52 | 2016-04-27 | 100% | 0% | 12935.52 | 0 | 12935.52
11 | 7 | 04470401499 | Dumas Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 12935.51 | 2016-04-27 | 100% | 0% | 12935.51 | 0 | 12935.51
23 | 8 | 04470401513 | Panhandle Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 12000 | 12935.51 | 2016-04-27 | 100% | 100% | 12935.51 | 0 | 12935.51
10 | 9 | 08470401498 | Jayton Maintenance Office | New Perimeter Fence | Highway Trans. Fund 6 | 15000 | 22782 | 2016-04-13 | 100% | 0% | 22782 | 0 | 22782
40 | 10 | 20470401543 | Woodville Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 21177.75 | 7/20/2016 | 100% | 0% | 21177.75 | 0 | 21177.75
43 | 11 | 18470401546 | Dallas District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 8/23/2016 | 0% | 0% | 0 | 0 | 350000
12 | 12 | 10470401428 | Tyler District Headquarters | Replace Roof On Shop | Highway Trans. Fund 6 | 500000 | 763000 | 1/3/2017 | 100% | 0% | 763000 | 0 | 763000
21 | 13 | 04470401511 | Darouzett Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 11483.33 | 2016-06-08 | 100% | 0% | 11483.33 | 0 | 11483.33
24 | 14 | 04470401514 | Panhandle Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 11483.33 | 2016-06-08 | 100% | 0% | 11483.33 | 0 | 11483.33
37 | 15 | 04470401540 | Claude Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 11483.34 | 2016-06-08 | 100% | 0% | 11483.34 | 0 | 11483.34
U11 | 16 | 02470402980 | Fort Worth District Headquarters | Replace Fuel Station Gas Pipeline | Highway Trans. Fund 6 | 0 | 31340 | 2016-02-03 | 100% | 100% | 31340 | 31340 | 0
230A | 17 | 38470402984 | Maintenance Offices | Upgrade Security (C-CURE) Card Reader pedestals piece of this is now Proj ID #14470402984 | Highway Trans. Fund 6 | 0 | 100000 | 2016-06-02 | 100% | 0% | 0 | 0 | 100000 | This is part of Project ID 14470401612 or 230 and 230A
446 | 18 | 04470401935 | Pampa Area Engineer & Maintenance Office | Replace Fuel Pumps | Highway Trans. Fund 6 | 15000 | 17000 | 10/5/2016 | 100% | 0% | 17000 | 0 | 17000
450 | 19 | 04470401939 | Perryton Maintenance Office | Replace Fuel Pumps | Highway Trans. Fund 6 | 15000 | 17000 | 10/5/2016 | 100% | 0% | 17000 | 0 | 17000
230 | 20 | 14470401612 | Maintenance Offices | Card Reader Pedestals for the Upgrade Security (C-CURE). Part of Orig ID #14470401612 | Highway Trans. Fund 6 | 1120000 | 55000 | 9/6/2016 | 100% | 0% | 55000 | 0 | 55000 | This is part of Project ID 14470401612 or 230 and 230A
33 | 21 | 16470401535 | Nueces East | Replace Existing Secuity Fence Around Perimeter Of Property | Highway Trans. Fund 6 | 125000 | 54899 | 2016-07-22 | 100% | 0% | 54899 | 0 | 54899
34 | 22 | 16470401536 | San Patricio Co | Replace Existing Secuity Fence Around Perimeter Of Property | Highway Trans. Fund 6 | 150000 | 47998 | 2016-07-22 | 100% | 0% | 47998 | 0 | 47998
38 | 23 | 20470401541 | Anahuac Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 7500 | 7580 | 2016-01-25 | 100% | 100% | 7580 | 7580 | 0
U2 | 24 | 01470402967 | Paris District Headquarters | Shop Floor Replacement | Highway Trans. Fund 6 | 0 | 35000 | 9/15/2016 | 100% | 0% | 35000 | 0 | 35000
31 | 25 | 16470401532 | Jim Wells Co. | Install Yard Illumination In Back Yard Area | Highway Trans. Fund 6 | 40000 | 40000 | 6/9/2016 | 100% | 0% | 0 | 0 | 40000
32 | 26 | 16470401533 | Live Oak Co. | Install Exterior Lighting In Back Yard Area | Highway Trans. Fund 6 | 40000 | 40000 | 6/9/2016 | 100% | 0% | 0 | 0 | 40000
185 | 27 | 18470401674 | Rockwall Maintenance Office | Apply Ceramic Roof Coating | Highway Trans. Fund 6 | 120000 | 120000 | 6/9/2016 | 100% | 0% | 0 | 0 | 120000
52 | 28 | 15470401602 | San Antonio District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 10/25/2016 | 100% | 0% | 0 | 0 | 350000
51 | 29 | 06470401588 | Odessa District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 10/25/2016 | 100% | 0% | 0 | 0 | 350000
193 | 30 | 07470401686 | San Angelo District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 2/7/2017 | 100% | 0% | 0 | 0 | 350000
U9 | 31 | 18470402978 | Dallas District Headquarters | Replace Chiller, provide temporary unit until work complete | Highway Trans. Fund 6 | 0 | 247496 | 2016-05-23 | 100% | 0% | 247496 | 0 | 247496
14 | 32 | 08470401502 | Gail Maintenance Office | AC Unit Needs Replacing (Old R22 Unit) | Highway Trans. Fund 6 | 7500 | 9701 | 6/21/2016 | 100% | 0% | 9701 | 0 | 9701
180 | 33 | 18470401669 | Waxahachie Area Engineer & Maintenance Office | HVAC - Split Unit (Meeting & Stock Rooms) | Highway Trans. Fund 6 | 10000 | 17240.7 | 5/12/2016 | 100% | 0% | 17240.7 | 0 | 17240.7
188 | 34 | 18470401677 | Rockwall Maintenance Office | HVAC - Upgrade Existing System | Highway Trans. Fund 6 | 15000 | 19795.4 | 5/12/2016 | 100% | 0% | 19795.4 | 0 | 19795.4
U17 | 35 | 38470402989 | 0 | Riverside 150 Datacenter UPS | Highway Trans. Fund 6 | 0 | 795000 | 12/20/2016 | 100% | 0% | 0 | 0 | 795000
118 | 36 | 07470401589 | Junction Area Engineer & Maintenance Office | New Roof | Highway Trans. Fund 6 | 16200 | 46114 | 7/21/2016 | 100% | 0% | 0 | 0 | 46114
72 | 37 | 04470401704 | Perryton Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 15000 | 15000 | 7/8/2016 | 100% | 0% | 0 | 0 | 15000
93 | 38 | 04470401734 | Dalhart Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | 7/8/2016 | 100% | 0% | 0 | 0 | 10000
142 | 39 | 04470401619 | Canyon Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | 5/10/2016 | 100% | 0% | 0 | 0 | 10000
144 | 40 | 04470401625 | Borger Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | 5/10/2016 | 100% | 0% | 0 | 0 | 10000
196 | 41 | 04470401692 | Amarillo Area Engineer and Mainteannce Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | 2016-06-21 | 100% | 0% | 0 | 0 | 10000
146 | 42 | 04470401627 | Pampa Area Engineer & Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | 2016-06-21 | 100% | 0% | 0 | 0 | 10000
17 | 43 | 38470401506 | Camp Hubbard State Headquarters | Replace Fence Along Mopac With Standard Fence | Highway Trans. Fund 6 | 45000 | 73000 | 2016-10-24 | 100% | 0% | 0 | 0 | 73000
U10 | 44 | 38470402974 | Camp Hubbard State Headquarters | Paving Overlay Parking Lot | Highway Trans. Fund 6 | 0 | 785000 | 2016-09-27 | 0% | 0% | 0 | 0 | 785000 | Project pulled and will be rebid. Estimate is original estimate.
57 | 45 | 21470401684 | Pharr District Headquarters/Area Engineer & Maintenance Office | HVAC With Study/Assessment | Highway Trans. Fund 6 | 300000 | 300000 | 2016-08-15 | 0% | 0% | 0 | 0 | 300000
99 | 46 | 21470401775 | Pharr District Headquarters | Complete Power Project (Single, Electrical Power Upgrade Project, To Encompass All Of The Electrical Issues To Include Study/Assessment) | Highway Trans. Fund 6 | 300000 | 300000 | 2017-02-20 | 0% | 0% | 0 | 0 | 300000
19 | 47 | 38470401508 | Camp Hubbard State Headquarters | Upgrade Obsolete Johnson Control Panels | Highway Trans. Fund 6 | 30000 | 30000 | 2016-11-08 | 0% | 0% | 0 | 0 | 30000
4 | 48 | 01470401491 | Paris District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 9/27/2016 | 0% | 0% | 0 | 0 | 350000
73 | 49 | 04470401705 | Perryton Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | 6/14/2016 | 100% | 0% | 0 | 0 | 12500
U21 | 50 | 15470402986 | Bandera Maintenance Office | SFMO - add door in cmu wall at the Bandera Maintenance Building | Highway Trans. Fund 6 | 0 | 5000 | 5/31/2016 | 0% | 0% | 0 | 0 | 5000
61 | 51 | 04470401693 | Hereford Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | 6/14/2016 | 100% | 0% | 0 | 0 | 12500
30 | 52 | 19470401530 | Atlanta District Headquarters | Replace 1 HVAC System | Highway Trans. Fund 6 | 10000 | 10000 | 2016-06-14 | 0% | 0% | 0 | 0 | 10000
84 | 53 | 04470401723 | Groom Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | 6/14/2016 | 100% | 0% | 0 | 0 | 12500
59 | 54 | 38470401689 | Camp Hubbard State Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 287500 | 287500 | 2016-08-17 | 0% | 0% | 0 | 0 | 287500
62 | 55 | 20470401694 | Kountze Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 40000 | 2016-07-13 | 0% | 0% | 0 | 0 | 40000
149 | 56 | 20470401630 | Beaumont Area Engineer & Maintenance Office | Install Gates | Highway Trans. Fund 6 | 16000 | 16000 | 2016-05-18 | 100% | 0% | 0 | 0 | 16000
173 | 57 | 11470401659 | Lufkin District Headquarters | Replace HVAC Controls | Highway Trans. Fund 6 | 30000 | 30000 | 2016-05-18 | 0% | 0% | 0 | 0 | 30000
178 | 58 | 20470401665 | Port Arthur Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 80000 | 80000 | 2016-06-15 | 0% | 0% | 0 | 0 | 80000
29 | 59 | 08470401527 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | 11/2/2016 | 0% | 0% | 0 | 0 | 336000
136 | 60 | 14470401611 | Austin District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 11/2/2016 | 0% | 0% | 0 | 0 | 350000
7 | 61 | 11470401494 | Lufkin District Headquarters | Replace HVAC Units | Highway Trans. Fund 6 | 15000 | 15000 | 2016-06-15 | 0% | 0% | 0 | 0 | 15000
155 | 62 | 20470401636 | Beaumont District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 8/17/2016 | 0% | 0% | 0 | 0 | 350000
135 | 63 | 14470401610 | Austin District Headquarters | Replace Generator | Highway Trans. Fund 6 | 250000 | 250000 | 2016-07-18 | 0% | 0% | 0 | 0 | 250000
6 | 64 | 38470401493 | Camp Hubbard State Headquarters | Replace Or Rebuild Existing Generator | Highway Trans. Fund 6 | 75000 | 75000 | 2016-07-06 | 0% | 0% | 0 | 0 | 75000
16 | 65 | 38470401505 | Camp Hubbard State Headquarters | Install Generator For Data Center (Camp Hubbard Bldg. 6) | Highway Trans. Fund 6 | 517000 | 517000 | 10/12/2016 | 0% | 0% | 0 | 0 | 517000
111 | 66 | 08470401577 | Colorado City Maintenance Office | Replace AC Unit (R22 Unit) | Highway Trans. Fund 6 | 10000 | 10000 | 6/1/2016 | 0% | 0% | 0 | 0 | 10000
163 | 67 | 19470401646 | Atlanta District Headquarters | Replace HVAC System | Highway Trans. Fund 6 | 10000 | 10000 | 6/1/2016 | 0% | 0% | 0 | 0 | 10000
102 | 68 | 19470401567 | Atlanta District Headquarters | Replace 2 HVAC Systems | Highway Trans. Fund 6 | 20000 | 20000 | 6/1/2016 | 0% | 0% | 0 | 0 | 20000
151 | 69 | 20470401632 | Beaumont District Headquarters | Fence Repairs | Highway Trans. Fund 6 | 9000 | 9000 | 6/7/2016 | 0% | 0% | 0 | 0 | 9000
189 | 70 | 05470401680 | NE Maint. Office | Retrofit Existing Gate Opener W/C-Cure | Highway Trans. Fund 6 | 18000 | 18000 | 6/7/2016 | 0% | 0% | 0 | 0 | 18000
176 | 71 | 20470401663 | Port Arthur Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 8000 | 12000 | 6/7/2016 | 100% | 0% | 0 | 0 | 12000
177 | 72 | 20470401664 | Port Arthur Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 18000 | 16000 | 6/7/2016 | 100% | 0% | 0 | 0 | 16000
41 | 73 | 25470401544 | Paducah Maintenance Office | New Electronic Gate To Yard, Redesign Parking Area | Highway Trans. Fund 6 | 35000 | 35000 | 2016-08-02 | 0% | 0% | 0 | 0 | 35000
162 | 74 | 19470401645 | Atlanta District Headquarters | Replace Generator | Highway Trans. Fund 6 | 250000 | 250000 | 2016-10-04 | 0% | 0% | 0 | 0 | 250000
64 | 75 | 20470401696 | Liberty Area Engineer & Maintenance Office | Replace HVAC Units | Highway Trans. Fund 6 | 20000 | 22000 | 6/7/2016 | 100% | 0% | 0 | 0 | 22000
71 | 76 | 08470401703 | Snyder Maintenance Office | Replace AC Unit (Old R22 Unit) | Highway Trans. Fund 6 | 7500 | 7500 | 7/19/2016 | 0% | 0% | 0 | 0 | 7500
83 | 77 | 04470401722 | Groom Maintenance Office | HVAC Replacement | Highway Trans. Fund 6 | 8000 | 8000 | 6/21/2016 | 0% | 0% | 0 | 0 | 8000
152 | 78 | 20470401633 | Beaumont District Headquarters | Install Gates & Install/Repair Fencing | Highway Trans. Fund 6 | 24000 | 24000 | 6/7/2016 | 0% | 0% | 0 | 0 | 24000
100 | 79 | 17470402668 | Bryan District Headquarters | Improve Lab Ventilation | Highway Trans. Fund 6 | 5000 | 60000 | 9/27/2016 | 0% | 0% | 0 | 0 | 60000
15 | 80 | 38470401504 | Camp Hubbard State Headquarters | Demolish Existing Building and Convert To Parking | Highway Trans. Fund 6 | 200000 | 200000 | 2016-11-08 | 0% | 0% | 0 | 0 | 200000
26 | 81 | 09470401518 | Waco District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 300000 | 300000 | 2016-08-30 | 0% | 0% | 0 | 0 | 300000
45 | 82 | 22470401549 | Brackettville | 3-Ton Standalone Unit (Duct Work, Vents, Air Handler, Etc) | Highway Trans. Fund 6 | 8000 | 8000 | 8/16/2016 | 0% | 0% | 0 | 0 | 8000
46 | 83 | 05470401553 | Lubbock District Headquarters | Replace Roof | Highway Trans. Fund 6 | 50000 | 50000 | 2016-09-12 | 0% | 0% | 0 | 0 | 50000
U5 | 84 | 10470402976 | Athens Regional Distribution Center | Fire supression system water line | Highway Trans. Fund 6 | 0 | 200000 | 2016-08-30 | 0% | 0% | 0 | 0 | 200000
U14 | 85 | 08470402983 | Baird | Baird MNT slab repair - to be scope w/ Byron | Highway Trans. Fund 6 | 0 | 50000 | 2016-09-27 | 0% | 0% | 0 | 0 | 50000
13 | 86 | 03470401501 | Bowie Maintenance Office | New Fencing | Highway Trans. Fund 6 | 50000 | 50000 | 2016-08-02 | 0% | 0% | 0 | 0 | 50000
60 | 87 | 15470401690 | Devine Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2016-10-25 | 0% | 0% | 0 | 0 | 100000
115 | 88 | 02470401582 | Fort Worth District Headquarters | Exterior Lighting | Highway Trans. Fund 6 | 30000 | 30000 | 2016-06-21 | 0% | 0% | 0 | 0 | 30000
150 | 89 | 20470401631 | Beaumont District Headquarters | A/C Unit Replacement | Highway Trans. Fund 6 | 85000 | 85000 | 2016-06-21 | 100% | 0% | 0 | 0 | 85000
161 | 90 | 19470401644 | Atlanta District Headquarters | Replace 3 HVAC Systems | Highway Trans. Fund 6 | 30000 | 30000 | 2016-09-30 | 0% | 0% | 0 | 0 | 30000
181 | 91 | 22470401670 | Del Rio Maintenance Office | Replace HVAC For Sign Shop | Highway Trans. Fund 6 | 30000 | 30000 | 2016-06-21 | 0% | 0% | 0 | 0 | 30000
186 | 92 | 18470401675 | Rockwall Maintenance Office | Fence - Repair/Replace Chain Link/Rails | Highway Trans. Fund 6 | 25000 | 25000 | 2016-06-21 | 0% | 0% | 0 | 0 | 25000
55 | 93 | 16470401655 | Corpus Christi District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 12/6/2016 | 0% | 0% | 0 | 0 | 350000
179 | 94 | 23470401667 | Brownwood District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 12/6/2016 | 0% | 0% | 0 | 0 | 350000
92 | 95 | 08470401733 | Aspermont Maintenance Office | Replace AC Unit (R22 Unit) | Highway Trans. Fund 6 | 7500 | 7500 | 7/5/2016 | 0% | 0% | 0 | 0 | 7500
25 | 96 | 09470401517 | Waco District Headquarters | Fence in Front of Facility | Highway Trans. Fund 6 | 110000 | 110000 | 2016-08-03 | 0% | 0% | 0 | 0 | 110000
97 | 97 | 05470401738 | Lubbock District Headquarters | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | 2016-08-31 | 0% | 0% | 0 | 0 | 65000
170 | 98 | 05470401656 | Plains Maintenance Office | New HVAC Relocate From Roof | Highway Trans. Fund 6 | 25000 | 25000 | 2016-07-20 | 0% | 0% | 0 | 0 | 25000
171 | 99 | 05470401657 | Plains Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 50000 | 50000 | 2016-09-14 | 0% | 0% | 0 | 0 | 50000
1128A | 100 | 19470402979 | District Headquarters | Escalated $30K from Restroom Upgrades in Proj #19470402619 | Highway Trans. Fund 6 | 0 | 30000 | 8/3/2016 | 0% | 0% | 0 | 0 | 30000 | Escalated $30K from Restroom Upgrades in Proj #19470402619
159 | 101 | 04470401641 | Amarillo District Headquarters | Upgrade Generator | Highway Trans. Fund 6 | 400000 | 400000 | 11/18/2016 | 0% | 0% | 0 | 0 | 400000
U15 | 102 | 05470402987 | Lubbock District Headquarters | AE Office Mold Remediation | Highway Trans. Fund 6 | 0 | TBD | 11/18/2016 | 0% | 0% | 0 | 0 | 0
96 | 103 | 05470401737 | Lubbock District Headquarters | Install New Gate Opener To Existing Gate | Highway Trans. Fund 6 | 6500 | 6500 | 7/11/2016 | 0% | 0% | 0 | 0 | 6500
87 | 104 | 03470401726 | Vernon Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 120000 | 120000 | 2016-11-09 | 0% | 0% | 0 | 0 | 120000
94 | 105 | 04470401735 | Dalhart Maintenance Office | Roof | Highway Trans. Fund 6 | 175000 | 175000 | 2016-08-31 | 0% | 0% | 0 | 0 | 175000
148 | 106 | 04470401629 | Pampa Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 175000 | 175000 | 2016-11-09 | 0% | 0% | 0 | 0 | 175000
114 | 107 | 02470401581 | Fort Worth District Headquarters | Chiller Replacement | Highway Trans. Fund 6 | 200000 | 200000 | 2016-09-05 | 0% | 0% | 0 | 0 | 200000
153 | 108 | 20470401634 | Beaumont District Headquarters | Modifications/Upgrade Electrical | Highway Trans. Fund 6 | 60000 | 60000 | 2016-08-08 | 0% | 0% | 0 | 0 | 60000
120 | 109 | 15470401591 | San Antonio District Headquarters | New Boiler | Highway Trans. Fund 6 | 20000 | 20000 | 11/14/2016 | 0% | 0% | 0 | 0 | 20000
130 | 110 | 15470401601 | San Antonio District Headquarters | Replace Roof Top Package HVAC 10 Ton System | Highway Trans. Fund 6 | 15000 | 15000 | 11/14/2016 | 0% | 0% | 0 | 0 | 15000
184 | 111 | 19470401673 | Mt Pleasant Area Engineer & Maintenance Office | Replace 1 HVAC System | Highway Trans. Fund 6 | 10000 | 10000 | 9/6/2016 | 0% | 0% | 0 | 0 | 10000
80 | 112 | 19470401719 | Daingerfield Maintenance Office | Replaces HVAC System | Highway Trans. Fund 6 | 16000 | 16000 | 8/9/2016 | 0% | 0% | 0 | 0 | 16000
68 | 113 | 07470401700 | San Angelo District Headquarters | Replace Roof | Highway Trans. Fund 6 | 250000 | 250000 | 2016-11-18 | 0% | 0% | 0 | 0 | 250000
78 | 114 | 21470401713 | Mission Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | 2016-11-18 | 0% | 0% | 0 | 0 | 300000
192 | 115 | 07470401685 | San Angelo District Headquarters | Replace Roof | Highway Trans. Fund 6 | 125000 | 125000 | 2016-11-18 | 0% | 0% | 0 | 0 | 125000
85 | 116 | 15470401724 | Uvalde Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2016-09-14 | 0% | 0% | 0 | 0 | 100000
36 | 117 | 21470401539 | Zapata Maintenance Office Sub-Section | Security Fence | Highway Trans. Fund 6 | 39800 | 39800 | 2016-08-15 | 0% | 0% | 0 | 0 | 39800
54 | 118 | 16470401650 | Corpus Christi District Headquarters | Replace Roof | Highway Trans. Fund 6 | 225000 | 225000 | 2016-11-28 | 0% | 0% | 0 | 0 | 225000
63 | 119 | 20470401695 | Liberty Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 120000 | 120000 | 2016-09-19 | 0% | 0% | 0 | 0 | 120000
69 | 120 | 15470401701 | Pearsall Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | 2016-11-28 | 0% | 0% | 0 | 0 | 65000
70 | 121 | 13470401702 | Wharton Cty Maint. | Install ADA Into Time Room | Highway Trans. Fund 6 | 10000 | 10000 | 2016-10-17 | 0% | 0% | 0 | 0 | 10000
75 | 122 | 21470401710 | Brownsville Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 40000 | 2016-08-22 | 0% | 0% | 0 | 0 | 40000
76 | 123 | 21470401711 | Brownsville Maintenance Office | Upgrade Fencing | Highway Trans. Fund 6 | 39000 | 39000 | 2016-08-22 | 0% | 0% | 0 | 0 | 39000
77 | 124 | 21470401712 | Mission Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 40000 | 2016-09-19 | 0% | 0% | 0 | 0 | 40000
81 | 125 | 38470401720 | Riverside Annex II RA150-200 | Replacement of R22 to 410 HVAC System | Highway Trans. Fund 6 | 200000 | 200000 | 2016-09-19 | 0% | 0% | 0 | 0 | 200000
145 | 126 | 04470401626 | Borger Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | 2016-09-19 | 0% | 0% | 0 | 0 | 12500
147 | 127 | 04470401628 | Pampa Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | 2016-09-19 | 0% | 0% | 0 | 0 | 12500
165 | 128 | 16470401649 | Corpus Christi District Headquarters | Replace Existing Security And Access Control System To C-Cure | Highway Trans. Fund 6 | 300000 | 300000 | 2016-10-03 | 0% | 0% | 0 | 0 | 300000
166 | 129 | 16470401651 | Corpus Christi District Headquarters | Replace Roof On The District Hq Administration Bldg | Highway Trans. Fund 6 | 300000 | 300000 | 2016-11-28 | 0% | 0% | 0 | 0 | 300000
167 | 130 | 16470401652 | Corpus Christi District Headquarters | Replace Roof On The Lab Building | Highway Trans. Fund 6 | 35000 | 35000 | 2016-11-28 | 0% | 0% | 0 | 0 | 35000
195 | 131 | 04470401691 | Canadian Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | 2016-09-22 | 0% | 0% | 0 | 0 | 12500
49 | 132 | 02470401585 | Fort Worth District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 1/9/2017 | 0% | 0% | 0 | 0 | 350000
101 | 133 | 05470401554 | Lubbock District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 1/9/2017 | 0% | 0% | 0 | 0 | 350000
47 | 134 | 21470401559 | Hebbronville Area Engineer & Maintenance Office | Upgrade Lighting And Gates | Highway Trans. Fund 6 | 0 | 336000 | 11/7/2016 | 0% | 0% | 0 | 0 | 336000
168 | 135 | 16470401653 | Corpus Christi District Headquarters | Replace Roof On The Special Crews Office Building | Highway Trans. Fund 6 | 350000 | 350000 | 2/13/2017 | 0% | 0% | 0 | 0 | 350000
28 | 136 | 21470401526 | San Isidro Maintenance Office Sub-Section | Replace Existing Generator | Highway Trans. Fund 6 | 15000 | 15000 | 2016-09-06 | 0% | 0% | 0 | 0 | 15000
35 | 137 | 21470401538 | Zapata Maintenance Office Sub-Section | Replace Generators | Highway Trans. Fund 6 | 20000 | 20000 | 2016-09-06 | 0% | 0% | 0 | 0 | 20000
91 | 138 | 19470401731 | Carthage Maintenance Office | Replace HVAC Systems | Highway Trans. Fund 6 | 16000 | 16000 | 8/9/2016 | 0% | 0% | 0 | 0 | 16000
95 | 139 | 19470401736 | Jefferson Maintenance Office | Replace HVAC | Highway Trans. Fund 6 | 8500 | 8500 | 9/6/2016 | 0% | 0% | 0 | 0 | 8500
1 | 140 | 19470401488 | Atlanta District Headquarters | Install LED Parking Lot Lighting | Highway Trans. Fund 6 | 85000 | 85000 | TBD | 0% | 0% | 0 | 0 | 0
9 | 141 | 16470401496 | Rockport Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | 2016-12-21 | 0% | 0% | 0 | 0 | 300000
90 | 142 | 16470401730 | Nueces East | Replace Roof On The Maintenance Building | Highway Trans. Fund 6 | 250000 | 250000 | 2016-10-26 | 0% | 0% | 0 | 0 | 250000
138 | 143 | 06470401615 | Odessa District Headquarters | Replace Main HVAC Multi-Zone Units | Highway Trans. Fund 6 | 160000 | 160000 | 2016-11-14 | 0% | 0% | 0 | 0 | 160000
U12 | 144 | 11470402981 | Lufkin | Foundation repair - Project being scoped | Highway Trans. Fund 6 | 0 | TBD | 12/26/2016 | 0% | 0% | 0 | 0 | 0
137 | 145 | 14470401613 | Georgetown AE/M, Bastrop AE/M, Mason MNT, Austin DHQ | New Generators/Upgrades | Highway Trans. Fund 6 | 425000 | 150000 | 2016-12-05 | 0% | 0% | 0 | 0 | 150000
U13 | 146 | 08470402982 | Abilene | Spalling Concrete hazard | Highway Trans. Fund 6 | 0 | 50000 | 9/1/2016 | 0% | 0% | 0 | 0 | 50000
50 | 147 | 06470401587 | Odessa District Headquarters | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | 2016-12-19 | 0% | 0% | 0 | 0 | 300000
86 | 148 | 06470401725 | Midland Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | 2016-10-10 | 0% | 0% | 0 | 0 | 65000
18 | 149 | 38470401507 | Camp Hubbard State Headquarters | Replace Roof (C.H. Bldg. 6) | Highway Trans. Fund 6 | 285000 | 285000 | 2016-08-31 | 0% | 0% | 0 | 0 | 285000
8 | 150 | 11470401495 | Lufkin District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 2017-01-09 | 0% | 0% | 0 | 0 | 350000
131 | 151 | 08470401604 | Abilene District Headquarters | Replace Generator | Highway Trans. Fund 6 | 58000 | 58000 | 2016-10-31 | 0% | 0% | 0 | 0 | 58000
183 | 152 | 04470401672 | Amarillo District Headquarters | Install Rooftop HVAC To Heat And Cool Shop | Highway Trans. Fund 6 | 50000 | 50000 | 12/26/2016 | 0% | 0% | 0 | 0 | 50000
103 | 153 | 05470401568 | Post RDC | Replace Generator | Highway Trans. Fund 6 | 75000 | 75000 | 2016-09-06 | 0% | 0% | 0 | 0 | 75000
194 | 154 | 15470401687 | Kerrville Area Engineer & Maintenance Office | Install Gate Operator & Exterior Lighting | Highway Trans. Fund 6 | 45000 | 45000 | 2016-09-06 | 0% | 0% | 0 | 0 | 45000
174 | 155 | 21470401660 | Pharr District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 2/7/2017 | 0% | 0% | 0 | 0 | 350000
104 | 156 | 38470401570 | Camp Hubbard State Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 200000 | 200000 | 2017-02-08 | 0% | 0% | 0 | 0 | 200000
198 | 157 | 23470402339 | Brownwood District Headquarters | Renovate Existing Facilities | Highway Trans. Fund 6 | 6000000 | 6000000 | 2018-05-18 | 0% | 0% | 0 | 0 | 6000000
56 | 158 | 13470401661 | Calhoun Cty Maint. | Convert Flat Roof To Gable Style | Highway Trans. Fund 6 | 250000 | 250000 | 2017-02-23 | 0% | 0% | 0 | 0 | 250000
66 | 159 | 07470401698 | San Angelo District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 220000 | 220000 | 2016-12-01 | 0% | 0% | 0 | 0 | 220000
67 | 160 | 07470401699 | San Angelo District Headquarters | Replace 2 Penthouse Type HVAC Units | Highway Trans. Fund 6 | 300000 | 300000 | 2016-12-01 | 0% | 0% | 0 | 0 | 300000
109 | 161 | 10470401575 | North Tyler Maintenance Office | Replace Roof At North Tyler Fuel Station | Highway Trans. Fund 6 | 85000 | 85000 | 2017-03-16 | 0% | 0% | 0 | 0 | 85000
172 | 162 | 11470401658 | Crockett Maintenance Office | Replace Emergency Generator | Highway Trans. Fund 6 | 38000 | 38000 | 2016-10-06 | 0% | 0% | 0 | 0 | 38000
182 | 163 | 11470401671 | Lufkin District Headquarters | Replace Boiler At Warehouse | Highway Trans. Fund 6 | 45000 | 45000 | 2016-10-20 | 0% | 0% | 0 | 0 | 45000
191 | 164 | 21470401683 | Pharr District Headquarters | Replace Roof | Highway Trans. Fund 6 | 250000 | 250000 | 2017-02-23 | 0% | 0% | 0 | 0 | 250000
110 | 165 | 10470401576 | Tyler District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 3/9/2017 | 0% | 0% | 0 | 0 | 350000
175 | 166 | 13470401662 | Yoakum District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 3/9/2017 | 0% | 0% | 0 | 0 | 350000
5 | 167 | 22470401492 | Del Rio Maintenance Office | Replace Generators (x2) | Highway Trans. Fund 6 | 50000 | 50000 | 11/10/2016 | 0% | 0% | 0 | 0 | 50000
157 | 168 | 03470401639 | Wichita Falls District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | 3/9/2017 | 0% | 0% | 0 | 0 | 350000
98 | 169 | 15470401739 | San Antonio District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 150000 | 150000 | 2017-06-02 | 0% | 0% | 0 | 0 | 150000
164 | 170 | 16470401648 | Corpus Christi District Headquarters | Modifications/Upgrade Electrical | Highway Trans. Fund 6 | 250000 | 250000 | 2016-12-12 | 0% | 0% | 0 | 0 | 250000
169 | 171 | 16470401654 | Corpus Christi District Headquarters | Upgrade HQ Campus Emergency Generator | Highway Trans. Fund 6 | 200000 | 200000 | 2016-12-12 | 0% | 0% | 0 | 0 | 200000
132 | 172 | 08470401605 | Abilene District Headquarters | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | 2016-12-28 | 0% | 0% | 0 | 0 | 65000
133 | 173 | 08470401606 | Abilene District Headquarters | Replace Roof (Warehouse) | Highway Trans. Fund 6 | 130000 | 130000 | 2017-03-08 | 0% | 0% | 0 | 0 | 130000
134 | 174 | 08470401607 | Abilene District Headquarters | Reroof Building Or Repatch In Areas | Highway Trans. Fund 6 | 10000 | 10000 | 2016-12-28 | 0% | 0% | 0 | 0 | 10000
139 | 175 | 12470401620 | Humble Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 87000 | 87000 | 2017-01-11 | 0% | 0% | 0 | 0 | 87000
140 | 176 | 15470401617 | Seguin Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2017-03-22 | 0% | 0% | 0 | 0 | 100000
143 | 177 | 08470401623 | Big Spring Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 60000 | 60000 | 2016-12-28 | 0% | 0% | 0 | 0 | 60000
154 | 178 | 20470401635 | Beaumont District Headquarters | Replace Roof | Highway Trans. Fund 6 | 95000 | 95000 | 2016-11-30 | 0% | 0% | 0 | 0 | 95000
160 | 179 | 19470401643 | Atlanta District Headquarters | Building 300 Storage Needs Replace Roof | Highway Trans. Fund 6 | 200000 | 200000 | 2017-03-08 | 0% | 0% | 0 | 0 | 200000
117 | 180 | 02470401584 | Fort Worth District Headquarters | Roof Replacement and Interior upgrade | Highway Trans. Fund 6 | 480000 | 980000 | 2017-05-24 | 0% | 0% | 0 | 0 | 980000
119 | 181 | 15470401590 | San Antonio District Headquarters | Install All New Hot And Chill Water Valves And Connect To New Control System | Highway Trans. Fund 6 | 150000 | 150000 | 2017-03-13 | 0% | 0% | 0 | 0 | 150000
121 | 182 | 15470401592 | San Antonio District Headquarters | New HVAC In Shop Restrooms | Highway Trans. Fund 6 | 20000 | 20000 | 2017-03-13 | 0% | 0% | 0 | 0 | 20000
122 | 183 | 15470401593 | San Antonio District Headquarters | Replace 60 Ton Chiller | Highway Trans. Fund 6 | 150000 | 150000 | 2017-03-13 | 0% | 0% | 0 | 0 | 150000
123 | 184 | 15470401594 | San Antonio District Headquarters | Replace All VAV and Upgrade To Electrical Control | Highway Trans. Fund 6 | 100000 | 100000 | 2017-03-13 | 0% | 0% | 0 | 0 | 100000
105 | 185 | 10470401571 | Tyler District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 180000 | 180000 | 2017-03-14 | 0% | 0% | 0 | 0 | 180000
106 | 186 | 10470401572 | Tyler District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 300000 | 300000 | 2017-03-14 | 0% | 0% | 0 | 0 | 300000
107 | 187 | 10470401573 | Tyler District Headquarters | Replace 5 Air Handler Units | Highway Trans. Fund 6 | 85000 | 85000 | 2017-03-14 | 0% | 0% | 0 | 0 | 85000
116 | 188 | 02470401583 | Fort Worth District Headquarters | Replace Roof (3 Buildings) | Highway Trans. Fund 6 | 492000 | 492000 | 2017-06-02 | 0% | 0% | 0 | 0 | 492000
124 | 189 | 15470401595 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 75000 | 75000 | 2017-09-22 | 0% | 0% | 0 | 0 | 75000
125 | 190 | 15470401596 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2017-09-22 | 0% | 0% | 0 | 0 | 100000
126 | 191 | 15470401597 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2017-09-22 | 0% | 0% | 0 | 0 | 100000
127 | 192 | 15470401598 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 125000 | 125000 | 2017-09-22 | 0% | 0% | 0 | 0 | 125000
128 | 193 | 15470401599 | San Antonio District Headquarters | Replace Roof - Buildings 1, 3 & 4 | Highway Trans. Fund 6 | 250000 | 250000 | 2017-09-22 | 0% | 0% | 0 | 0 | 250000
129 | 194 | 15470401600 | San Antonio District Headquarters | Replace Roof - Buildings 8 & 9 | Highway Trans. Fund 6 | 150000 | 150000 | 2017-09-22 | 0% | 0% | 0 | 0 | 150000
108 | 195 | 10470401574 | Tyler District Headquarters | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | 2017-07-31 | 0% | 0% | 0 | 0 | 100000
141 | 196 | 10470401621 | Tyler District Headquarters | Replace Roof On Old Lab | Highway Trans. Fund 6 | 200000 | 200000 | 2017-08-28 | 0% | 0% | 0 | 0 | 200000
197 | 197 | 18470402299 | Dallas District Headquarters | Remodel The District Main Office | Highway Trans. Fund 6 | 5653246 | 5653246 | 2018-07-19 | 0% | 0% | 0 | 0 | 5653246
3 | 198 | 01470401490 | Paris District Headquarters | Replace Roof And Walls | Highway Trans. Fund 6 | 50000 | 50000 | 3/22/2018 | 0% | 0% | 0 | 0 | 50000
137A | 199 | 14470402984 | San Marcos Maintenance Office | New Generator/Upgrade---Split off of 14470401613 | Highway Trans. Fund 6 | 0 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | New Generator/Upgrade---Split off of 14470401613
U7 | 200 | 15470402985 | Seguin Warehouse and Seguin Mantenance Office | Fencing, gate operators, preliminarty asbestos testing. | Highway Trans. Fund 6 | 0 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000
U8 | 201 | 38470402977 | Riverside | ADA entrances and driveway | Highway Trans. Fund 6 | 0 | TBD | TBD | 0% | 0% | 0 | 0 | 0
U16 | 202 | 38470402988 | Cedar Park | New Discharge air temp sensors and HVAC | Highway Trans. Fund 6 | 0 | 133480 | TBD | 0% | 0% | 0 | 0 | 0
U18 | 203 | 38470402990 | 0 | Austin Dist. Elevator Project Addition | Highway Trans. Fund 6 | 0 | 298000 | TBD | 0% | 0% | 0 | 0 | 0
U19 | 204 | 18470402991 | Sulphur Springs | Fuel Canopy | Highway Trans. Fund 6 | 0 | TBD | TBD | 0% | 0% | 0 | 0 | 0
U20 | 205 | 24470402992 | 0 | El Paso Generator Replacement | Highway Trans. Fund 6 | 0 | TBD | TBD | 0% | 0% | 0 | 0 | 0
U23 | 206 | 03470402987 | Henrietta Maintenance Office | Lift Station Grinder Pump Replacements | Highway Trans. Fund 6 | 0 | TBD | TBD | 0% | 0% | 0 | 0 | 0
U24 | 207 | 16470402987 | Port Aransas Ferry Landing | Roof Repairs | Highway Trans. Fund 6 | 0 | 100000 | TBD | 0% | 0% | 0 | 0 | 0
U25 | 208 | 15470402988 | Bandera MNT | Bandera MNT Building structure | Highway Trans. Fund 6 | 0 | TBD | TBD | 0% | 0% | 0 | 0 | 0
U26 | 209 | 11470402989 | Livingston Area Engineer & Maintenance Office | SFMO Fire Wall | Highway Trans. Fund 6 | 0 | 50000 | TBD | 0% | 0% | 0 | 0 | 0
U27 | 210 | 11470402990 | Lufkin District Headquarters | SMFO Fire Exit | Highway Trans. Fund 6 | 0 | 150000 | TBD | 0% | 0% | 0 | 0 | 0
U28 | 211 | 09470402991 | Waco District Headquarters | SMFO Fire Exit | Highway Trans. Fund 6 | 0 | 125000 | TBD | 0% | 0% | 0 | 0 | 0
717 | 212 | 15470402206 | Seguin Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 0 | TBD | TBD | 0% | 0% | 0 | 0 | 0
[6 empty] | 35434246 | 38694764.72 |  |  |  | 1535624.72 | 98690 | 37654594.72
$57M FUNDED PROJECTS | [5 empty] | 35434246 | 38694764.72
199 | 213 | 24470401509 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000 | TBD | 0% | 0% | 0 | 0 | 1008000 | Pending Administrative Funding
200 | 214 | 07470401516 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000 | TBD | 0% | 0% | 0 | 0 | 1008000 | Pending Administrative Funding
201 | 215 | 07470401520 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 224000 | 224000 | TBD | 0% | 0% | 0 | 0 | 224000 | Pending Administrative Funding
202 | 216 | 25470401521 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 224000 | 224000 | TBD | 0% | 0% | 0 | 0 | 224000 | Pending Administrative Funding
203 | 217 | 25470401522 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1120000 | 1120000 | TBD | 0% | 0% | 0 | 0 | 1120000 | Pending Administrative Funding
204 | 218 | 05470401523 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1680000 | 1680000 | TBD | 0% | 0% | 0 | 0 | 1680000 | Pending Administrative Funding
205 | 219 | 06470401524 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1120000 | 1120000 | TBD | 0% | 0% | 0 | 0 | 1120000 | Pending Administrative Funding
206 | 220 | 08470401528 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1120000 | 1120000 | TBD | 0% | 0% | 0 | 0 | 1120000 | Pending Administrative Funding
207 | 221 | 04470401529 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1680000 | 1680000 | TBD | 0% | 0% | 0 | 0 | 1680000 | Pending Administrative Funding
208 | 222 | 17470401531 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
209 | 223 | 16470401534 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 896000 | 896000 | TBD | 0% | 0% | 0 | 0 | 896000 | Pending Administrative Funding
210 | 224 | 11470401537 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 784000 | 784000 | TBD | 0% | 0% | 0 | 0 | 784000 | Pending Administrative Funding
211 | 225 | 02470401548 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000 | TBD | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding
212 | 226 | 15470401550 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000 | TBD | 0% | 0% | 0 | 0 | 1008000 | Pending Administrative Funding
213 | 227 | 18470401551 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000 | TBD | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding
214 | 228 | 05470401552 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000 | TBD | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding
215 | 229 | 01470401556 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
216 | 230 | 01470401557 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 672000 | 672000 | TBD | 0% | 0% | 0 | 0 | 672000 | Pending Administrative Funding
217 | 231 | 21470401558 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
218 | 232 | 15470401560 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000 | TBD | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding
219 | 233 | 10470401561 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000 | TBD | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding
220 | 234 | 10470401562 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000 | TBD | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding
221 | 235 | 09470401563 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000 | TBD | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding
222 | 236 | 03470401564 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
223 | 237 | 03470401565 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 784000 | 784000 | TBD | 0% | 0% | 0 | 0 | 784000 | Pending Administrative Funding
224 | 238 | 13470401566 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000 | TBD | 0% | 0% | 0 | 0 | 1008000 | Pending Administrative Funding
225 | 239 | 21470401569 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000 | TBD | 0% | 0% | 0 | 0 | 1008000 | Pending Administrative Funding
226 | 240 | 22470401586 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000 | TBD | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding
227 | 241 | 09470401603 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000 | TBD | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding
228 | 242 | 19470401608 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
229 | 243 | 19470401609 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 672000 | 672000 | TBD | 0% | 0% | 0 | 0 | 672000 | Pending Administrative Funding
231 | 244 | 06470401614 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
233 | 245 | 13470401618 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
234 | 246 | 13470401622 | Austin Cty Maint. | Repair Leaking Metal Roofs | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
235 | 247 | 04470401624 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
236 | 248 | 23470401637 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 784000 | 784000 | TBD | 0% | 0% | 0 | 0 | 784000 | Pending Administrative Funding
237 | 249 | 17470401647 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 784000 | 784000 | TBD | 0% | 0% | 0 | 0 | 784000 | Pending Administrative Funding
238 | 250 | 20470401666 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
239 | 251 | 18470401668 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000 | TBD | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding
240 | 252 | 02470401678 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 672000 | 672000 | TBD | 0% | 0% | 0 | 0 | 672000 | Pending Administrative Funding
241 | 253 | 12470401679 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 784000 | 784000 | TBD | 0% | 0% | 0 | 0 | 784000 | Pending Administrative Funding
242 | 254 | 11470401681 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
243 | 255 | 20470401706 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 672000 | 672000 | TBD | 0% | 0% | 0 | 0 | 672000 | Pending Administrative Funding
244 | 256 | 23470401707 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 224000 | 224000 | TBD | 0% | 0% | 0 | 0 | 224000 | Pending Administrative Funding
245 | 257 | 06470401709 | Iraan Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 6 | 1500 | 1500 | TBD | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding
246 | 258 | 12470401714 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000 | TBD | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding
247 | 259 | 24470401715 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
248 | 260 | 22470401716 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | TBD | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding
249 | 261 | 06470401717 | Balmorhea Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 6 | 1500 | 1500 | TBD | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding
250 | 262 | 14470401727 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 560000 | 560000 | TBD | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding
251 | 263 | 16470401732 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 448000 | 448000 | TBD | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding
252 | 264 | 15470401740 | District Headquarters | New Boiler | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
253 | 265 | 15470401741 | District Headquarters | Replace All VAV and Upgrade To Electrical Control | Highway Trans. Fund 6 | 85000 | 85000 | TBD | 0% | 0% | 0 | 0 | 85000 | Pending Administrative Funding
254 | 266 | 10470401742 | Jacksonville Maintenance Office | Site Improvements | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
255 | 267 | 13470401743 | Gonzales Cty Maint. | Convert Flat Roof To Gable Style | Highway Trans. Fund 6 | 250000 | 250000 | TBD | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding
256 | 268 | 13470401744 | Gonzales Maintenance Office | Roof Replacement | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
257 | 269 | 04470401745 | Loop | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
258 | 270 | 04470401746 | Loop | New Generator | Highway Trans. Fund 6 | 12500 | 12500 | TBD | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding
259 | 271 | 19470401747 | Linden Maintenance Office | Replace 2 HVAC Systems Add 1 HVAC For Shop | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
260 | 272 | 18470401748 | District Headquarters | Generator Replaced With Diesel | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
261 | 273 | 22470401749 | Del Rio Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
262 | 274 | 22470401750 | Del Rio Maintenance Office (US 90) | Upgrade HVAC | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
263 | 275 | 22470401751 | Cotulla Maintenance Office | Roof Repairs | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
264 | 276 | 22470401752 | Cotulla Maintenance Office | Upgrade Propane Generator | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
265 | 277 | 20470401753 | Orange Maintenance Office | Rehab Metal Roofing | Highway Trans. Fund 6 | 95000 | 95000 | TBD | 0% | 0% | 0 | 0 | 95000 | Pending Administrative Funding
266 | 278 | 12470401754 | Brookshire Maintenance Office | Replace Emergency Generator | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
267 | 279 | 12470401755 | Houston South Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
268 | 280 | 12470401756 | Humble Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 87000 | 87000 | TBD | 0% | 0% | 0 | 0 | 87000 | Pending Administrative Funding
269 | 281 | 12470401757 | Rosenberg Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
270 | 282 | 22470401758 | District Headquarters | New HVAC In Shop Restrooms | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
271 | 283 | 22470401759 | District Headquarters | Replace Roof | Highway Trans. Fund 6 | 225000 | 225000 | TBD | 0% | 0% | 0 | 0 | 225000 | Pending Administrative Funding
272 | 284 | 22470401760 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
273 | 285 | 22470401761 | Laredo Area Engineer & Maintenance Office | Exterior Lighting | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
274 | 286 | 22470401762 | Laredo Auto Shop | Furnish/Install HVAC | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
275 | 287 | 22470401763 | Laredo Auto Shop | Restrooms HVAC | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
276 | 288 | 22470401764 | Laredo District Headquarters | Repair MNT To Auto Shop Roof | Highway Trans. Fund 6 | 250000 | 250000 | TBD | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding
277 | 289 | 22470401765 | Laredo Lab/FIN/Stratus | Replace 8 HVAC Units | Highway Trans. Fund 6 | 80000 | 80000 | TBD | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding
278 | 290 | 22470401766 | Laredo Traffic | Replace Computer/Storage Room HVAC | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
279 | 291 | 15470401767 | Transguide | Replace 2 - 75 Ton Chillers And Add Chiller For (Backup) | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
280 | 292 | 24470401768 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
281 | 293 | 05470401769 | District Headquarters | Replace Roof | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
282 | 294 | 15470401770 | Bexar Metro Area Engineer & Maintenance Office | HVAC Upgrade | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
283 | 295 | 15470401771 | Bexar Metro Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
284 | 296 | 09470401772 | Gatesville Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
285 | 297 | 18470401773 | Denton Area Engineer & Maintenance Office | Install Gate - Electric W/Remote On Ih35 Service Road | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
286 | 298 | 05470401774 | Littlefield Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
287 | 299 | 21470401776 | District Headquarters | HVAC Upgrade In HQ Bldg. | Highway Trans. Fund 6 | 300000 | 300000 | TBD | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding
288 | 300 | 21470401777 | San Benito Area Engineer & Maintenance Office | Replace HVAC Units | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
289 | 301 | 21470401778 | San Benito Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | TBD | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding
290 | 302 | 20470401779 | Beaumont Area Engineer & Maintenance Office | Install Card Reader Access | Highway Trans. Fund 6 | 16000 | 16000 | TBD | 0% | 0% | 0 | 0 | 16000 | Pending Administrative Funding
291 | 303 | 25470401780 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
292 | 304 | 16470401781 | District Headquarters | Replace HVAC Unit At Vehicle Titles And Registration - Corpus Christi DHQ | Highway Trans. Fund 6 | 18000 | 18000 | TBD | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding
293 | 305 | 18470401782 | District Headquarters | Fire/Sprinkler Upgrade (Obsolete Panels) | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
294 | 306 | 13470401783 | Fayette Cty Maint. | Upgrade Apu To Supply Entire Maintenace Building | Highway Trans. Fund 6 | 125000 | 125000 | TBD | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding
295 | 307 | 20470401784 | Liberty Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
296 | 308 | 20470401785 | Liberty Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 18000 | 18000 | TBD | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding
297 | 309 | 20470401786 | Liberty Area Engineer & Maintenance Office | Install/Repair Fence | Highway Trans. Fund 6 | 7000 | 7000 | TBD | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding
298 | 310 | 20470401787 | Liberty Area Engineer & Maintenance Office | Rehab Roof With Insulation | Highway Trans. Fund 6 | 95000 | 95000 | TBD | 0% | 0% | 0 | 0 | 95000 | Pending Administrative Funding
299 | 311 | 24470401788 | El Paso (East) Area Engineer & Maintenance Office | Install/Repair Roof | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
300 | 312 | 24470401789 | El Paso (East) Area Engineer & Maintenance Office | Upgrade Evaporative AC Unit In The Shop. Add Heaters And Double Door. | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
301 | 313 | 24470401790 | El Paso (East) Area Engineer & Maintenance Office | Upgrade Front/Rear Entrance Gates | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
302 | 314 | 24470401791 | El Paso (West) Area Engineer & Maintenance Office | Secure The Lobby Area | Highway Trans. Fund 6 | 125000 | 125000 | TBD | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding
303 | 315 | 02470401792 | District Headquarters | 9 Crac HVAC Units Transvision Building | Highway Trans. Fund 6 | 270000 | 270000 | TBD | 0% | 0% | 0 | 0 | 270000 | Pending Administrative Funding
304 | 316 | 22470401793 | Freer | HVAC Replacement | Highway Trans. Fund 6 | 17000 | 17000 | TBD | 0% | 0% | 0 | 0 | 17000 | Pending Administrative Funding
305 | 317 | 05470401794 | District Headquarters | Replace Roof | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
306 | 318 | 10470401795 | South Tyler Area Engineer & Maintenance Office | Replace HVAC In Bldg. B | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
307 | 319 | 10470401796 | South Tyler Area Engineer & Maintenance Office | Upgrade HVAC In Maint &Area Office | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
308 | 320 | 09470401797 | Hillsboro Area Engineer & Maintenance Office | Install Gate and Controls | Highway Trans. Fund 6 | 17000 | 17000 | TBD | 0% | 0% | 0 | 0 | 17000 | Pending Administrative Funding
309 | 321 | 16470401798 | Bee Co. | Replace HVAC System | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
310 | 322 | 18470401799 | Cedar Hill Maintenance Office | Install Gates - Electric/Key Pad | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
311 | 323 | 18470401800 | Cedar Hill Maintenance Office | New Generator - Diesel | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
312 | 324 | 19470401801 | District Headquarters | Replace 2 HVAC Systems | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
313 | 325 | 22470401802 | La Pryor Maintenance Office | Replace Two HVAC Units | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
314 | 326 | 22470401803 | La Pryor on HWY 57 | Install Gate Operator And Key Pad | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
315 | 327 | 18470401804 | Corsicana Area Engineer & Maintenance Office | Fire/Sprinkler Upgrade (Obsolete Panels) | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
316 | 328 | 18470401805 | District Headquarters | Generator Backup Power Completed | Highway Trans. Fund 6 | 90000 | 90000 | TBD | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding
317 | 329 | 18470401806 | District Headquarters | HVAC Upgrade - Leibert System @ Server Room | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
318 | 330 | 12470401807 | District Headquarters | Install CCTV Security Camera (Parking Garage) | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
319 | 331 | 12470401808 | District Headquarters | Upgrade Site Lighting | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
320 | 332 | 12470401809 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
321 | 333 | 16470401810 | Aransas Co. | Replace Roof On The Maintenance Building | Highway Trans. Fund 6 | 250000 | 250000 | TBD | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding
322 | 334 | 18470401811 | Ennis Maintenance Office | Roof - Coating Metal Roof Over Storage/Salt Shed | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
323 | 335 | 06470401812 | Ft Stockton Area Engineer & Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 6 | 1500 | 1500 | TBD | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding
324 | 336 | 15470401813 | District Headquarters | Replace 3 Each 20 Ton Chillers For Backup | Highway Trans. Fund 6 | 125000 | 125000 | TBD | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding
325 | 337 | 15470401814 | West Bexar Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
326 | 338 | 38470401815 | Riverside Annex I RA118 | Replacement of R22 to 410 HVAC System | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
327 | 339 | 38470401816 | Riverside Annex II RA150-200 | Install Redundant UPS for Data Center | Highway Trans. Fund 6 | 250000 | 250000 | TBD | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding
328 | 340 | 38470401817 | Riverside Annex II RA150-200 | Replace Roof | Highway Trans. Fund 6 | 450000 | 450000 | TBD | 0% | 0% | 0 | 0 | 450000 | Pending Administrative Funding
329 | 341 | 38470401818 | Riverside Annex II RA150-200 | Replacement of R22 to 410 HVAC System | Highway Trans. Fund 6 | 360000 | 360000 | TBD | 0% | 0% | 0 | 0 | 360000 | Pending Administrative Funding
330 | 342 | 38470401819 | Riverside Annex II RA150-200 | Roof and Weatherize Exterior | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
331 | 343 | 38470401820 | Riverside Annex II RA150-200 | Upgrade Obsolete Johnson Control Panels | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
332 | 344 | 21470401821 | Edcouch Maintenance Office | Add Exit Only Gate To East Side | Highway Trans. Fund 6 | 16000 | 16000 | TBD | 0% | 0% | 0 | 0 | 16000 | Pending Administrative Funding
333 | 345 | 17470401822 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
334 | 346 | 01470401823 | District Headquarters | Resurface Parking Lot | Highway Trans. Fund 6 | 164000 | 164000 | TBD | 0% | 0% | 0 | 0 | 164000 | Pending Administrative Funding
335 | 347 | 21470401824 | Pharr Area Engineer & Maintenance Office | Reconfigure Parking Lot | Highway Trans. Fund 6 | 41000 | 41000 | TBD | 0% | 0% | 0 | 0 | 41000 | Pending Administrative Funding
336 | 348 | 21470401825 | Pharr Area Engineer & Maintenance Office | Rework Concrete Drainage Structure | Highway Trans. Fund 6 | 11000 | 11000 | TBD | 0% | 0% | 0 | 0 | 11000 | Pending Administrative Funding
337 | 349 | 22470401826 | Del Rio | Sprinkler System Repair & Upgrade | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
338 | 350 | 22470401827 | Del Rio Maintenance Office | Furnish/Install Bollard | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
339 | 351 | 22470401828 | Del Rio Maintenance Office (US 90) | Parking Lot Lighting | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
340 | 352 | 04470401829 | Dumas Maintenance Office | Sprinkler System Repairs | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
341 | 353 | 07470401830 | Eden Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
342 | 354 | 07470401831 | Eden Maintenance Office | Install New 10,000 Gallon Brine Storge Tank | Highway Trans. Fund 6 | 6000 | 6000 | TBD | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding
343 | 355 | 07470401832 | Eden Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
344 | 356 | 07470401833 | Eden Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000 | TBD | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding
345 | 357 | 24470401834 | Fort Hancock Sub-Section | Demolish Old Asphalt Storage Tank. | Highway Trans. Fund 6 | 8400 | 8400 | TBD | 0% | 0% | 0 | 0 | 8400 | Pending Administrative Funding
346 | 358 | 24470401835 | Fort Hancock Sub-Section | Install Back Rockwall | Highway Trans. Fund 6 | 18000 | 18000 | TBD | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding
347 | 359 | 07470401836 | Leakey Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
348 | 360 | 07470401837 | Leakey Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
349 | 361 | 07470401838 | Leakey Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000 | TBD | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding
350 | 362 | 06470401839 | McCamey Maintenance Office | Paint Asphalt Tank Bases And Hardware. Deteriorating Paint And Rusting Steel | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
351 | 363 | 07470401840 | Ballinger Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
352 | 364 | 07470401841 | Ballinger Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
353 | 365 | 07470401842 | Ballinger Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 122000 | 122000 | TBD | 0% | 0% | 0 | 0 | 122000 | Pending Administrative Funding
354 | 366 | 06470401843 | Sanderson Maintenance Office | Repair Irrigation Systems | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
355 | 367 | 23470401844 | Breckenridge Maintenance Office | Demolish Old Structures On Adjacent Site | Highway Trans. Fund 6 | 39500 | 39500 | TBD | 0% | 0% | 0 | 0 | 39500 | Pending Administrative Funding
356 | 368 | 16470401845 | Jim Wells Co. | Add Additional Lateral Lines To Septic System At The Alice Ae Office | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
357 | 369 | 18470401846 | Ennis Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
358 | 370 | 18470401847 | Ennis Maintenance Office | Parking Lot Striping | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
359 | 371 | 21470401848 | Zapata Maintenance Office Sub-Section | Repave Parking Lot | Highway Trans. Fund 6 | 19780 | 19780 | TBD | 0% | 0% | 0 | 0 | 19780 | Pending Administrative Funding
360 | 372 | 20470401849 | Anahuac Maintenance Office | Rehab Parking Lot And Drainage | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
361 | 373 | 20470401850 | Anahuac Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
362 | 374 | 20470401851 | Newton Maintenance Office | Reconfigure Parking Lot | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
363 | 375 | 20470401852 | Newton Maintenance Office | Remove Out Of Service Emulsion, Linseed Oil & Asts | Highway Trans. Fund 6 | 55000 | 55000 | TBD | 0% | 0% | 0 | 0 | 55000 | Pending Administrative Funding
364 | 376 | 20470401853 | Stowel Maintenance Office | Electric Service To Yard | Highway Trans. Fund 6 | 4000 | 4000 | TBD | 0% | 0% | 0 | 0 | 4000 | Pending Administrative Funding
365 | 377 | 20470401854 | Woodville Maintenance Office | Remove Out Of Service Emulsion, Linseed Oil & Asts | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
366 | 378 | 18470401855 | District Headquarters | Site Improvements | Highway Trans. Fund 6 | 207000 | 207000 | TBD | 0% | 0% | 0 | 0 | 207000 | Pending Administrative Funding
367 | 379 | 18470401856 | District Headquarters | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
368 | 380 | 18470401857 | District Headquarters | Parking Lot Striping | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
369 | 381 | 22470401858 | Brackettville | Fuel Pump Replacements | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
370 | 382 | 22470401859 | Brackettville | Landscaping & Irrigation | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
371 | 383 | 07470401860 | San Angelo Area Engineer & Maintenance Office | Overlay And Restripe Parking Lot | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
372 | 384 | 07470401861 | San Angelo Maintenance Office | Install New Automated Vehicle Entry Gate | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
373 | 385 | 07470401862 | San Angelo Maintenance Office | Pavement Seal Coat and Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
374 | 386 | 07470401863 | San Angelo Maintenance Office | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
375 | 387 | 07470401864 | Sterling City Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
376 | 388 | 07470401865 | Sterling City Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
377 | 389 | 07470401866 | Sterling City Maintenance Office | Replace Automated Swing Gate With Automated Sliding Gate | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
378 | 390 | 07470401867 | Sterling City Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000 | TBD | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding
379 | 391 | 25470401868 | Munday Maintenance Office | Resurface Parking Lot | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
380 | 392 | 05470401869 | Post RDC | Nw Side Of Long Building Dirt Work To Shed Water | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
381 | 393 | 05470401870 | Post RDC | Site Work And Concrete Flume | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
382 | 394 | 21470401871 | Raymondville Maintenance Office | New Fire Proof Overhead Doors | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
383 | 395 | 21470401872 | Raymondville Maintenance Office | Resurface Maintenance Yard | Highway Trans. Fund 6 | 134800 | 134800 | TBD | 0% | 0% | 0 | 0 | 134800 | Pending Administrative Funding
384 | 396 | 10470401873 | District Headquarters | Modifications/Upgrade Site | Highway Trans. Fund 6 | 110000 | 110000 | TBD | 0% | 0% | 0 | 0 | 110000 | Pending Administrative Funding
385 | 397 | 08470401874 | District Headquarters | Parking Lot Reconfiguration | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
386 | 398 | 08470401875 | District Headquarters | Sidewalks at the DMV Building Need to be Cut Out and Replaced in Various Areas | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
387 | 399 | 08470401876 | District Headquarters | Replace Water Cut Offs On The Complex For Various Buildings | Highway Trans. Fund 6 | 8500 | 8500 | TBD | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding
388 | 400 | 24470401877 | Fort Davis Maintenance Office | Demolish Old Emulsion Tank | Highway Trans. Fund 6 | 8500 | 8500 | TBD | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding
389 | 401 | 24470401878 | Fort Davis Maintenance Office | Install Sprinkler System | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
390 | 402 | 02470401879 | District Headquarters | Site Improvements | Highway Trans. Fund 6 | 303000 | 303000 | TBD | 0% | 0% | 0 | 0 | 303000 | Pending Administrative Funding
391 | 403 | 06470401880 | District Headquarters | Modifications/Upgrade Site | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
392 | 404 | 06470401881 | District Headquarters | Xeroscape Grounds | Highway Trans. Fund 6 | 264000 | 264000 | TBD | 0% | 0% | 0 | 0 | 264000 | Pending Administrative Funding
393 | 405 | 06470401882 | Odessa Maintenance Office | Reconfigure Parking In Front Of Office | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
394 | 406 | 06470401883 | Odessa Maintenance Office | Repair/Replace ATG System On Above Ground Fuel Tanks | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
395 | 407 | 06470401884 | Odessa Maintenance Office | Replace Irrigation System For New Yard Design | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
396 | 408 | 07470401885 | Junction Area Engineer & Maintenance Office | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
397 | 409 | 07470401886 | Junction Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
398 | 410 | 07470401887 | Junction Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
399 | 411 | 07470401888 | Junction Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000 | TBD | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding
400 | 412 | 15470401889 | District Headquarters | Change Out Galvanized Water Main Piping | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
401 | 413 | 15470401890 | District Headquarters | Change Out Galvanized Water Main Piping | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
402 | 414 | 15470401891 | District Headquarters | Parking Lot Resurfacing & Reconfiguration | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
403 | 415 | 06470401892 | Monahans Maintenance Office | Connect to City Sewer Utililty Line | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
404 | 416 | 06470401893 | Monahans Maintenance Office | Repair Irrigation Systems | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
405 | 417 | 15470401894 | Seguin Area Engineer & Maintenance Office | Replace Radio Tower | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
406 | 418 | 07470401895 | Sonora Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
407 | 419 | 13470401896 | Austin Cty Maint. | Install Above Ground Fuel System/New Dispenser | Highway Trans. Fund 6 | 250000 | 250000 | TBD | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding
408 | 420 | 13470401897 | Colorado Cty Maint. | Install Above Ground Fuel System/New Dispenser | Highway Trans. Fund 6 | 250000 | 250000 | TBD | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding
409 | 421 | 20470401898 | Beaumont Area Engineer & Maintenance Office | Additional Sidewalks | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
410 | 422 | 20470401899 | District Headquarters | Modifications/Upgrade Site Utilities | Highway Trans. Fund 6 | 101000 | 101000 | TBD | 0% | 0% | 0 | 0 | 101000 | Pending Administrative Funding
411 | 423 | 20470401900 | District Headquarters | Rehab Parking Lot And Stripe | Highway Trans. Fund 6 | 450000 | 450000 | TBD | 0% | 0% | 0 | 0 | 450000 | Pending Administrative Funding
412 | 424 | 20470401901 | District Headquarters | Remove Out Of Service Emulsion, Linseed Oil & Asts | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
413 | 425 | 20470401902 | District Headquarters | Replace Fuel Dispensers | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
414 | 426 | 20470401903 | Districtwide | Re-Stripe Parking Lots And Hc Spaces | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
415 | 427 | 07470401904 | Rocksprings Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
416 | 428 | 07470401905 | Rocksprings Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 122000 | 122000 | TBD | 0% | 0% | 0 | 0 | 122000 | Pending Administrative Funding
417 | 429 | 03470401906 | District Headquarters | Construct In-Ground Storm Shelter | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
418 | 430 | 03470401907 | District Headquarters | Modifications/Upgrade Site Utilities | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
419 | 431 | 03470401908 | District Headquarters | Repave Parking Lot - Wichita Falls DHQ | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
420 | 432 | 16470401909 | District Headquarters | Modifications/Upgrade Site | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
421 | 433 | 16470401910 | District Headquarters | Modifications/Upgrade Site Utilities | Highway Trans. Fund 6 | 125000 | 125000 | TBD | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding
422 | 434 | 16470401911 | District Headquarters | Rehab Existing Parking Lots On Entire Campus | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
423 | 435 | 16470401912 | District Headquarters | Repair Sidewalk Or Parking Lot - Corpus Christi DHQ | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
424 | 436 | 16470401913 | District Headquarters | Replace 3 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
425 | 437 | 16470401914 | District Headquarters | Replace Fuel Dispenser At Maintenance Special Jobs - Corpus Christi DHQ | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
426 | 438 | 11470401915 | Crockett Maintenance Office | Replace Bathroom Sewer Dainage System | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
427 | 439 | 06470401916 | Crane Maintenance Office | Paint 10000 Gal Asphalt Tank & Insulate | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
428 | 440 | 21470401917 | District Headquarters | Upgrade Landscaping to include Hike And Bike Trail | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
429 | 441 | 21470401918 | District Headquarters | Increase Parking Area | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
430 | 442 | 21470401919 | District Headquarters | Parking Lot Improvements | Highway Trans. Fund 6 | 400000 | 400000 | TBD | 0% | 0% | 0 | 0 | 400000 | Pending Administrative Funding
431 | 443 | 07470401920 | Ozona Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
432 | 444 | 07470401921 | Ozona Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
433 | 445 | 07470401922 | Ozona Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000 | TBD | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding
434 | 446 | 13470401923 | District Headquarters | Install Above Ground Fuel System/New Dispenser | Highway Trans. Fund 6 | 250000 | 250000 | TBD | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding
435 | 447 | 13470401924 | District Headquarters | Replace Deteriorating Natural Gas Lines And Exterior Valves | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
436 | 448 | 20470401925 | Port Arthur Area Engineer & Maintenance Office | Rehab Parking Lot And Stripe | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
437 | 449 | 23470401926 | District Headquarters | Site Improvements | Highway Trans. Fund 6 | 155000 | 155000 | TBD | 0% | 0% | 0 | 0 | 155000 | Pending Administrative Funding
438 | 450 | 18470401927 | Waxahachie Area Engineer & Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
439 | 451 | 18470401928 | Waxahachie Area Engineer & Maintenance Office | Parking Lot Striping | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
440 | 452 | 18470401929 | Rockwall Maintenance Office | Asphalt Emulsion Tank Installation | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
441 | 453 | 18470401930 | Rockwall Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
442 | 454 | 18470401931 | Rockwall Maintenance Office | Parking Lot Striping | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
443 | 455 | 22470401932 | Carrizo Springs (Area Engineer & Maintenance Office & Lab) | Upgrade Sprinkler System | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
444 | 456 | 07470401933 | District Headquarters | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
445 | 457 | 07470401934 | District Headquarters | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
447 | 458 | 20470401936 | Kountze Maintenance Office | Rehab Parking Lot And Stripe | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
448 | 459 | 24470401937 | Terlingua Sub-Section | Resufacing of Parking Lot | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
449 | 460 | 13470401938 | Wharton Cty Maint. | Build New Berm Around Asphalt Tanks | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
451 | 461 | 06470401940 | Iraan Maintenance Office | Repair Irrigation Systems | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
452 | 462 | 18470401941 | Hutchins Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
453 | 463 | 18470401942 | Hutchins Maintenance Office | Parking Lot Striping | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
454 | 464 | 18470401943 | NW Dallas Maintenance Office | Modular Building/Site Prep | Highway Trans. Fund 6 | 110000 | 110000 | TBD | 0% | 0% | 0 | 0 | 110000 | Pending Administrative Funding
455 | 465 | 24470401944 | Alpine Area Engineer & Maintenance Office | Demolish Old Emulsion Tank | Highway Trans. Fund 6 | 8400 | 8400 | TBD | 0% | 0% | 0 | 0 | 8400 | Pending Administrative Funding
456 | 466 | 06470401945 | Balmorhea Maintenance Office | Repair Irrigation Systems | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
457 | 467 | 21470401946 | San Benito Area Engineer & Maintenance Office | Fuel Tank Relocation | Highway Trans. Fund 6 | 125000 | 125000 | TBD | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding
458 | 468 | 21470401947 | San Benito Area Engineer & Maintenance Office | Improve Drainage | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
459 | 469 | 21470401948 | San Benito Area Engineer & Maintenance Office | Repair Sewer Line At Rear Of Yard, Add Approx. 8 Manholes. | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
460 | 470 | 21470401949 | San Benito Area Engineer & Maintenance Office | Resurface Parking Lot | Highway Trans. Fund 6 | 26200 | 26200 | TBD | 0% | 0% | 0 | 0 | 26200 | Pending Administrative Funding
461 | 471 | 07470401950 | Robert Lee Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
462 | 472 | 07470401951 | Rocksprings Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
463 | 473 | 24470401952 | Presidio Maintenance Office | Demolish Old Emulsion Tank | Highway Trans. Fund 6 | 8500 | 8500 | TBD | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding
464 | 474 | 21470401953 | Laguna Vista Maintenance Office Sub-Section | Repair Fuel Dispensing Pumps & Tanks | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
465 | 475 | 15470401954 | Bandera Maintenance Office | Connect To City Water/Sewer | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
466 | 476 | 24470401955 | Pine Springs Sub-Section | Demolish Old Emulsion Tank | Highway Trans. Fund 6 | 8500 | 8500 | TBD | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding
467 | 477 | 06470401956 | Midland Area Engineer & Maintenance Office | Repair Irrigation Systems | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
468 | 478 | 07470401957 | Big Lake Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
469 | 479 | 07470401958 | Big Lake Maintenance Office | Install New Above Ground Fuel Tanks | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
470 | 480 | 07470401959 | Big Lake Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
471 | 481 | 07470401960 | Big Lake Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 6 | 61000 | 61000 | TBD | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding
472 | 482 | 14470401961 | Burnet Area Engineer & Maintenance Office | Parking Lot Overlay | Highway Trans. Fund 6 | 95000 | 95000 | TBD | 0% | 0% | 0 | 0 | 95000 | Pending Administrative Funding
473 | 483 | 23470401962 | Goldthwaite Maintenance Office | Remove Underground Fuel Tanks And Install Above Ground Tanks | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
474 | 484 | 07470401963 | Menard Maintenance Office | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
475 | 485 | 16470401964 | Corpus Christi Area Engineer & Maintenance Office | Repair Fuel Monitoring System - Corpus Christi AEM | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
476 | 486 | 16470401965 | San Patricio Co | Replace Existing Sewage Line Running To Lift Station | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
477 | 487 | 16470401966 | Sinton Area Engineer & Maintenance Office | Replace Sewer Line | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
478 | 488 | 10470401967 | Jacksonville Maintenance Office | Parking Improvements | Highway Trans. Fund 6 | 120000 | 120000 | TBD | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding
479 | 489 | 22470401968 | Del Rio Maintenance Office | Irrigation Replacement | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
480 | 490 | 05470401969 | Tulia Maintenance Office | New 2" Water Line Installation | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
481 | 491 | 22470401970 | Cotulla Maintenance Office | Install French Drainage | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
482 | 492 | 22470401971 | Cotulla Maintenance Office | Install Irrigation And Landscaping | Highway Trans. Fund 6 | 4250 | 4250 | TBD | 0% | 0% | 0 | 0 | 4250 | Pending Administrative Funding
483 | 493 | 22470401972 | Cotulla Maintenance Office | Repave & Stripe Empl & Visitor Parking Lot | Highway Trans. Fund 6 | 105000 | 105000 | TBD | 0% | 0% | 0 | 0 | 105000 | Pending Administrative Funding
484 | 494 | 20470401973 | Jasper Area Engineer & Maintenance Office | Add Connection To Public Supply For Water And Sanitary Sewer System | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
485 | 495 | 20470401974 | Jasper Area Engineer & Maintenance Office | Remove Out Of Service Emulsion, Linseed Oil & Asts | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
486 | 496 | 12470401975 | Conroe Area Engineer & Maintenance Office | Sitework Modifications (Drivewal And Visitor Parking) | Highway Trans. Fund 6 | 70000 | 70000 | TBD | 0% | 0% | 0 | 0 | 70000 | Pending Administrative Funding
487 | 497 | 22470401976 | District Headquarters | Parking Lot Reconfiguration | Highway Trans. Fund 6 | 125000 | 125000 | TBD | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding
488 | 498 | 22470401977 | Laredo Administration & Area Engineer & Maintenance Office | Irrigation, Landscaping, Grass Seeds, Planting/Adding Trees | Highway Trans. Fund 6 | 225000 | 225000 | TBD | 0% | 0% | 0 | 0 | 225000 | Pending Administrative Funding
489 | 499 | 22470401978 | Laredo District Headquarters | Reconfigure Landscaping For Walking Trail | Highway Trans. Fund 6 | 80000 | 80000 | TBD | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding
490 | 500 | 24470401979 | District Headquarters | Site Improvements | Highway Trans. Fund 6 | 318000 | 318000 | TBD | 0% | 0% | 0 | 0 | 318000 | Pending Administrative Funding
491 | 501 | 13470401980 | District Headquarters | Replace Natural Gas Lines | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
492 | 502 | 25470401981 | Clarendon Maintenance Office | Replace Fuel Station | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
493 | 503 | 18470401982 | Denton Area Engineer & Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
494 | 504 | 18470401983 | Denton Area Engineer & Maintenance Office | Parking Lot Striping | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
495 | 505 | 13470401984 | La Grange Area Engineer & Maintenance Office | Replace Asphalt Tank Berm | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
496 | 506 | 20470401985 | Liberty Area Engineer & Maintenance Office | Regrade Parking And Drainage | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
497 | 507 | 24470401986 | El Paso (East) Area Engineer & Maintenance Office | Install/Repair Rock Wall Front And Rear | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
498 | 508 | 22470401987 | Freer | Flag Pole Lighting | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
499 | 509 | 22470401988 | Freer | Irrigation And Landscaping | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
500 | 510 | 38470401989 | CEDAR PARK Research and Technology Center | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 6 | 60000 | 60000 | TBD | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding
501 | 511 | 10470401990 | South Tyler Area Engineer & Maintenance Office | Sewer Connect To City - South Tyler Area Engineer And Maintenance Facility | Highway Trans. Fund 6 | 300000 | 300000 | TBD | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding
502 | 512 | 16470401991 | Beeville Maintenance Office | Repair Fuel Monitoring System - Beeville MNT | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
503 | 513 | 16470401992 | Beeville Maintenance Office | Replace\New Fuel Dispenser/Fuel Pump At Maintenance - Beeville MNT | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
504 | 514 | 08470401993 | Abilene Maintenance Office | Reroute Wash Bay Drain To City Sewer Drain | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
505 | 515 | 22470401994 | La Pryor Maintenance Office | Resurface 2 Acres Of Parking Area In Yard & Strip Where Needed | Highway Trans. Fund 6 | 152000 | 152000 | TBD | 0% | 0% | 0 | 0 | 152000 | Pending Administrative Funding
506 | 516 | 24470401995 | Marfa Sub-Section | Demolish Old Emulsion Tank | Highway Trans. Fund 6 | 8500 | 8500 | TBD | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding
507 | 517 | 24470401996 | Van Horn Maintenance Office | Demolish Old Emulsion Tank | Highway Trans. Fund 6 | 8500 | 8500 | TBD | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding
508 | 518 | 13470401997 | Fayette Cty Maint. | Eliminate Wash Rack Waste Water Recycle System And Convert To City Utilities | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
509 | 519 | 18470401998 | Corsicana Area Engineer & Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
510 | 520 | 18470401999 | Corsicana Area Engineer & Maintenance Office | Parking Lot Striping | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
511 | 521 | 21470402000 | Laguna Vista Maintenance Office Sub-Section | Replace Fuel Pump Canopy | Highway Trans. Fund 6 | 13000 | 13000 | TBD | 0% | 0% | 0 | 0 | 13000 | Pending Administrative Funding
512 | 522 | 15470402001 | New Braunfels Area Engineer & Maintenance Office | Parking Lot Reconfiguration | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
513 | 523 | 10470402002 | Athens Area Engineer & Maintenance Office | Parking Improvements | Highway Trans. Fund 6 | 70000 | 70000 | TBD | 0% | 0% | 0 | 0 | 70000 | Pending Administrative Funding
514 | 524 | 09470402003 | Waco Area Engineer & Maintenance Office - Bagby | Site Drainage Improvements | Highway Trans. Fund 6 | 25200 | 25200 | TBD | 0% | 0% | 0 | 0 | 25200 | Pending Administrative Funding
515 | 525 | 17470402004 | District Headquarters | Parking Area Pavement | Highway Trans. Fund 6 | 450000 | 450000 | TBD | 0% | 0% | 0 | 0 | 450000 | Pending Administrative Funding
516 | 526 | 22470402005 | Laredo District Headquarters | Parking Lot Striping | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
517 | 527 | 18470402006 | Waxahachie Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
518 | 528 | 24470402007 | Marathon Sub-Section | Insulate Interior Roof And Walls, Spray Foam. | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
519 | 529 | 16470402008 | District Headquarters | Replace Floor In Lab Building District | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
520 | 530 | 16470402009 | George West Maintenance Office | Install Electrical - George West MNT | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
521 | 531 | 16470402010 | Goliad Co. | Replace Metal Siding On Office Building With New Siding | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
522 | 532 | 16470402011 | Goliad Co. | Replace Sliding Garage Doors With Overhead Doors | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
523 | 533 | 16470402012 | Kleburg Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
524 | 534 | 19470402013 | District Headquarters | Remodel Inside Of Building | Highway Trans. Fund 6 | 90000 | 90000 | TBD | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding
525 | 535 | 19470402014 | District Headquarters | Window Replacement | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
526 | 536 | 25470402015 | Guthrie Maintenance Office SS | Re-Skin Exterior, Insulate Bujilding, Install Windows, Roof, & Doors, Upgrade Rest Room | Highway Trans. Fund 6 | 300000 | 300000 | TBD | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding
527 | 537 | 01470402016 | District Headquarters | Abatement Of Roof And Walls (Monitoring) | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
528 | 538 | 01470402017 | District Headquarters | Abatement Of Roof And Walls (Remediation) | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
529 | 539 | 01470402018 | District Headquarters | Abatement Of Roof And Walls (Testing) | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
530 | 540 | 01470402019 | District Headquarters | Boiler And Chiller Repairs | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
531 | 541 | 01470402020 | District Headquarters | Demolish Existing Building | Highway Trans. Fund 6 | 29500 | 29500 | TBD | 0% | 0% | 0 | 0 | 29500 | Pending Administrative Funding
532 | 542 | 01470402021 | District Headquarters | Renovate DHQ Campus | Highway Trans. Fund 6 | 1950000 | 1950000 | TBD | 0% | 0% | 0 | 0 | 1950000 | Pending Administrative Funding
533 | 543 | 21470402022 | Pharr Area Engineer & Maintenance Office | Add Office And Reconfigure Space | Highway Trans. Fund 6 | 4000 | 4000 | TBD | 0% | 0% | 0 | 0 | 4000 | Pending Administrative Funding
534 | 544 | 21470402023 | Pharr Area Engineer & Maintenance Office | Add Vestibule | Highway Trans. Fund 6 | 10200 | 10200 | TBD | 0% | 0% | 0 | 0 | 10200 | Pending Administrative Funding
535 | 545 | 22470402024 | Del Rio Maintenance Office | Convert 2Nd Floor Into Four Offices And Restroom Renovation | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
536 | 546 | 22470402025 | Del Rio Maintenance Office | Replace Flooring In Mechanical Room | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
537 | 547 | 22470402026 | Del Rio Maintenance Office | Roof & Exterior Painting | Highway Trans. Fund 6 | 70000 | 70000 | TBD | 0% | 0% | 0 | 0 | 70000 | Pending Administrative Funding
538 | 548 | 11470402027 | District Headquarters | Install Vinyl Plank Flooring | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
539 | 549 | 11470402028 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
540 | 550 | 11470402029 | District Headquarters | Paint Interior | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
541 | 551 | 11470402030 | District Headquarters | Renovate Baydoor Offices | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
542 | 552 | 11470402031 | District Headquarters | Replace Flooring | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
543 | 553 | 11470402032 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
544 | 554 | 16470402033 | Refugio Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
545 | 555 | 16470402034 | Refugio Co. | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
546 | 556 | 16470402035 | Refugio Co. | Replace Metal Siding On Office Building With New Siding | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
547 | 557 | 16470402036 | Refugio Maintenance Office | Repair Structure At Maintenance - Refugio Maintenance | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
548 | 558 | 06470402037 | Andrews Maintenance Office | Replace Garage Door W/Panel & Electric Open. | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
549 | 559 | 06470402038 | Andrews Maintenance Office | Replace Metal Roof & Exterior Walls, Insulate | Highway Trans. Fund 6 | 22000 | 22000 | TBD | 0% | 0% | 0 | 0 | 22000 | Pending Administrative Funding
550 | 560 | 04470402039 | Dumas Maintenance Office | Remove Oh Door In Breakroom And Install Walk Door | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
551 | 561 | 03470402040 | Bowie Maintenance Office | Close In Front Of New Truck Shed And Add 4 Roll Up Doors | Highway Trans. Fund 6 | 80000 | 80000 | TBD | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding
552 | 562 | 10470402041 | District Headquarters | Replace Windows | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
553 | 563 | 38470402042 | Camp Hubbard State Headquarters | Complete Renovation Of 5th Floor | Highway Trans. Fund 6 | 500000 | 500000 | TBD | 0% | 0% | 0 | 0 | 500000 | Pending Administrative Funding
554 | 564 | 38470402043 | Camp Hubbard State Headquarters | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
555 | 565 | 20470402044 | Woodville Maintenance Office | Install Additional Unit Heater | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
556 | 566 | 20470402045 | Woodville Maintenance Office | Paint Interior of Facilities | Highway Trans. Fund 6 | 2500 | 2500 | TBD | 0% | 0% | 0 | 0 | 2500 | Pending Administrative Funding
557 | 567 | 20470402046 | Woodville Maintenance Office | Reskin, Replace Lighting And Reroof Bld | Highway Trans. Fund 6 | 95000 | 95000 | TBD | 0% | 0% | 0 | 0 | 95000 | Pending Administrative Funding
558 | 568 | 25470402047 | Memphis Maintenance Office | Replace Floor Tiles, Upgrade Rest Room; Redesign Office Space | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
559 | 569 | 25470402048 | Memphis Maintenance Office | Re-Skin Exterior, Install Roof, New Windows and Remove Sky Lights W/ Roof Replacement; Redesign Parking Area | Highway Trans. Fund 6 | 335000 | 335000 | TBD | 0% | 0% | 0 | 0 | 335000 | Pending Administrative Funding
560 | 570 | 04470402049 | Canadian Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
561 | 571 | 24470402050 | Fort Hancock Sub-Section | Add Rolling Doors To Existing Storage Bldg. | Highway Trans. Fund 6 | 6000 | 6000 | TBD | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding
562 | 572 | 24470402051 | Fort Hancock Sub-Section | Exterior Renovations | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
563 | 573 | 24470402052 | Fort Hancock Sub-Section | Install Entrance Weather Canopy, Front Door. Add Rolling Doors To Existing Storage Bldg. | Highway Trans. Fund 6 | 8100 | 8100 | TBD | 0% | 0% | 0 | 0 | 8100 | Pending Administrative Funding
564 | 574 | 04470402053 | Darouzett Maintenance Office | New Shop Heaters | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
565 | 575 | 04470402054 | Darrouzett Maintenance Office | Abate and Remodel Office Area | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
566 | 576 | 04470402055 | Gruver Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
567 | 577 | 04470402056 | Channing Maintenance Office | Electrical Upgrades | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
568 | 578 | 04470402057 | Channing Maintenance Office | New Unit Heaters | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
569 | 579 | 04470402058 | Channing Maintenance Office | Replace Roof, Re-Skin Exterior, Install New Insulation And Windows | Highway Trans. Fund 6 | 175000 | 175000 | TBD | 0% | 0% | 0 | 0 | 175000 | Pending Administrative Funding
570 | 580 | 04470402059 | Channing Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
571 | 581 | 17470402060 | Brenham Area Engineer & Maintenance Office | Install Bathroom/Showers In Shop/Welding Shop | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
572 | 582 | 05470402061 | Post Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
573 | 583 | 05470402062 | Post Maintenance Office | Re-Skin Renovate Shop | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
574 | 584 | 04470402063 | Panhandle Maintenance Office | Enlarge Supervisor Office And Breakroom | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
575 | 585 | 04470402064 | Panhandle Maintenance Office | Install Overhead Doors And Openers | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
576 | 586 | 04470402065 | Panhandle Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
577 | 587 | 25470402066 | Munday Maintenance Office | Upgrade Electrical & Lights In Maintenance Barn | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
578 | 588 | 16470402067 | Goliad Co. | Replace Metal Siding On Equipment Shed And Roof With New Siding And Roof | Highway Trans. Fund 6 | 60000 | 60000 | TBD | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding
579 | 589 | 16470402068 | Goliad Maintenance Office | Replace Exterior Door At Equipment Storage - Goliad MNT | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
580 | 590 | 16470402069 | Goliad Maintenance Office | Replace Exterior Windows At Laboratory - Goliad MNT | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
581 | 591 | 11470402070 | District Headquarters | Renovate Bathroom | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
582 | 592 | 11470402071 | District Headquarters | Renovate Interior | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
583 | 593 | 06470402072 | Andrews Maintenance Office | Repaint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
584 | 594 | 06470402073 | Andrews Maintenance Office | Repair/Replace Atg System On Above Ground Fuel Tanks | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
585 | 595 | 06470402074 | Andrews Maintenance Office | Seal Roof Penetrations | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
586 | 596 | 06470402075 | McCamey Maintenance Office | Paint Building Exterior | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
587 | 597 | 06470402076 | McCamey Maintenance Office | Replace Linolium With Tile In Offices | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
588 | 598 | 06470402077 | McCamey Maintenance Office | Upgrade Electrical Wiring & Lights In Shop Area | Highway Trans. Fund 6 | 7000 | 7000 | TBD | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding
589 | 599 | 07470402078 | Ballinger Maintenance Office | Erect Buildings Over Lifts | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
590 | 600 | 09470402079 | District Headquarters | Replace Windows | Highway Trans. Fund 6 | 33450 | 33450 | TBD | 0% | 0% | 0 | 0 | 33450 | Pending Administrative Funding
591 | 601 | 06470402080 | Sanderson Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
592 | 602 | 23470402081 | Comanche Maintenance Office | Renovate Facilities | Highway Trans. Fund 6 | 294000 | 294000 | TBD | 0% | 0% | 0 | 0 | 294000 | Pending Administrative Funding
593 | 603 | 17470402082 | Brenham Area Engineer & Maintenance Office | Add Lighting And Catwalks To V-Box Area | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
594 | 604 | 17470402083 | Brenham Area Engineer & Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
595 | 605 | 17470402084 | Brenham Area Engineer & Maintenance Office | New Sidewalk Lab To Parking Lot | Highway Trans. Fund 6 | 12500 | 12500 | TBD | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding
596 | 606 | 06470402085 | Stanton Maintenance Office | Install Shed Kit | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
597 | 607 | 06470402086 | Stanton Maintenance Office | Repair/Replace ATG System On Above Ground Fuel Tanks | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
598 | 608 | 21470402087 | San Isidro Maintenance Office Sub-Section | Reconfigure Two Restrooms & Office | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
599 | 609 | 15470402088 | Pearsall Maintenance Office | Refurbish Shop Building Skin And Roof | Highway Trans. Fund 6 | 95000 | 95000 | TBD | 0% | 0% | 0 | 0 | 95000 | Pending Administrative Funding
600 | 610 | 38470402089 | Austin HQ | Austin HQ Campus Repairs | Highway Trans. Fund 6 | 5000000 | 5000000 | TBD | 0% | 0% | 0 | 0 | 5000000 | Pending Administrative Funding
601 | 611 | 09470402090 | District Headquarters | New Insulation & Replace Windows | Highway Trans. Fund 6 | 52200 | 52200 | TBD | 0% | 0% | 0 | 0 | 52200 | Pending Administrative Funding
602 | 612 | 03470402091 | Bowie Maintenance Office | Replace Exterior Windows At Warehouse - Bowie Maintenance | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
603 | 613 | 19470402092 | District Headquarters | Remodel Inside Of Building | Highway Trans. Fund 6 | 87000 | 87000 | TBD | 0% | 0% | 0 | 0 | 87000 | Pending Administrative Funding
604 | 614 | 23470402093 | Brady Maintenance Office | Renovate Facilities | Highway Trans. Fund 6 | 317000 | 317000 | TBD | 0% | 0% | 0 | 0 | 317000 | Pending Administrative Funding
605 | 615 | 17470402094 | Bryan Area Engineer & Maintenance Office | Reskin Shed | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
606 | 616 | 17470402095 | Madisonville Maintenance Office | Fence/Gate Work | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
607 | 617 | 17470402096 | Madisonville Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
608 | 618 | 17470402097 | Madisonville Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
609 | 619 | 17470402098 | Madisonville Maintenance Office | Replace Fuel Canopy | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
610 | 620 | 25470402099 | Crowell Maintenance Office | Replace Floor Tiles, Windows, Doors, Locks | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
611 | 621 | 25470402100 | Crowell Maintenance Office | Rewire Office, New Lights; Heaters In Truck Barn | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
612 | 622 | 25470402101 | Matador Maintenance Office | Re-Skin Exterior, Insulate Building, Install Windows, Roof and Lights; Redesign Office Space | Highway Trans. Fund 6 | 325000 | 325000 | TBD | 0% | 0% | 0 | 0 | 325000 | Pending Administrative Funding
613 | 623 | 16470402102 | Nueces East | Install Redundant 2000 Gallon Diesel Tank To Existing Fuel Island | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
614 | 624 | 18470402103 | Ennis Maintenance Office | Electrical Panel Upgrades | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
615 | 625 | 18470402104 | Ennis Maintenance Office | Floor Tile Abatement - Corridors Only (Stain Concrete) | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
616 | 626 | 18470402105 | Ennis Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
617 | 627 | 18470402106 | Ennis Maintenance Office | Restroom Partitions Replaced | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
618 | 628 | 21470402107 | Zapata Maintenance Office Sub-Section | Renovate Building Into Offices. Renovate Restrooms. | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
619 | 629 | 04470402108 | Claude Maintenance Office | New Overhead Doors | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
620 | 630 | 04470402109 | Stratford Maintenance Office | Install Overhead Doors and Openers | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
621 | 631 | 20470402110 | Anahuac Maintenance Office | Install Storm Shutters | Highway Trans. Fund 6 | 14000 | 14000 | TBD | 0% | 0% | 0 | 0 | 14000 | Pending Administrative Funding
622 | 632 | 20470402111 | Newton Maintenance Office | Interior Lighting | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
623 | 633 | 20470402112 | Woodville Maintenance Office | Abate Transit Siding | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
624 | 634 | 20470402113 | Woodville Maintenance Office | Replace Roof, Lighting & Siding | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
625 | 635 | 23470402114 | Coleman Maintenance Office | Renovate Facilities | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
626 | 636 | 17470402115 | Buffalo Maintenance Office | Repair Roof | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
627 | 637 | 17470402116 | Buffalo Maintenance Office | Restroom Remodels | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
628 | 638 | 17470402117 | Buffalo Maintenance Office | Upgrade HVAC System | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
629 | 639 | 17470402118 | Cameron Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
630 | 640 | 17470402119 | Cameron Maintenance Office | Replace Flooring (Carpet & Tile) | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
631 | 641 | 17470402120 | Cameron Maintenance Office | Redo Walls In Office | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
632 | 642 | 17470402121 | Cameron Maintenance Office | Reskin MNT Office Building | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
633 | 643 | 17470402122 | Cameron Maintenance Office | Reskin Shed | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
634 | 644 | 25470402123 | Paducah Maintenance Office | Replace Restrooms | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
635 | 645 | 25470402124 | Silverton Maintenance Office | Insulate, New Windows And Roof | Highway Trans. Fund 6 | 275000 | 275000 | TBD | 0% | 0% | 0 | 0 | 275000 | Pending Administrative Funding
636 | 646 | 25470402125 | Silverton Maintenance Office | Re-Skin Exterior, Insulate Building,Install Windows and Roof | Highway Trans. Fund 6 | 175000 | 175000 | TBD | 0% | 0% | 0 | 0 | 175000 | Pending Administrative Funding
637 | 647 | 16470402126 | Goliad Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
638 | 648 | 16470402127 | Goliad Maintenance Office | Replace Exterior Door At Equipment Storage - Goliad MNT | Highway Trans. Fund 6 | 16000 | 16000 | TBD | 0% | 0% | 0 | 0 | 16000 | Pending Administrative Funding
639 | 649 | 18470402128 | District Headquarters | Upgrade Lighting | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
640 | 650 | 12470402129 | Angleton Area Engineer & Maintenance Office | New Carpet/VCT | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
641 | 651 | 22470402130 | Brackettville | Deactivate Or Remove Mag Locks | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
642 | 652 | 22470402131 | Brackettville | Furnish/Install Exterior Safety Lights | Highway Trans. Fund 6 | 1500 | 1500 | TBD | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding
643 | 653 | 22470402132 | Brackettville | Renovate Breakroom | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
644 | 654 | 22470402133 | Brackettville | Restroom Renovations (Both Men and Women) | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
645 | 655 | 22470402134 | Brackettville | Retrofit Bay Area Into Conference Room. (17'X28') 14' Ceiling. Tile Flooring, HVAC, Electrical, Communications, Removal Of Exiting Door. | Highway Trans. Fund 6 | 55000 | 55000 | TBD | 0% | 0% | 0 | 0 | 55000 | Pending Administrative Funding
646 | 656 | 07470402135 | Sterling City Maintenance Office | Erect Buildings Over Lifts | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
647 | 657 | 17470402136 | Navasota Maintenance Office | Restroom Remodels | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
648 | 658 | 25470402137 | Munday Maintenance Office | New Partition Walls & Larger Break Room, Upgrade Rest Room, New Windows & Doors, Redesign Office Space | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
649 | 659 | 25470402138 | Munday Maintenance Office | Replace Floor Tiles | Highway Trans. Fund 6 | 9500 | 9500 | TBD | 0% | 0% | 0 | 0 | 9500 | Pending Administrative Funding
650 | 660 | 18470402139 | District Headquarters | Paint Exterior | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
651 | 661 | 18470402140 | District Headquarters | Restroom Partitions Replacement - Men's Restroom | Highway Trans. Fund 6 | 1500 | 1500 | TBD | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding
652 | 662 | 18470402141 | District Headquarters | Window - Ceramic Coating (Warehouse/Facilities/Shop) | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
653 | 663 | 05470402142 | District Headquarters | Campuswide Electrical Upgrade | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
654 | 664 | 05470402143 | District Headquarters | Install Exit Loops | Highway Trans. Fund 6 | 2500 | 2500 | TBD | 0% | 0% | 0 | 0 | 2500 | Pending Administrative Funding
655 | 665 | 05470402144 | District Headquarters | New VCT Floor | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
656 | 666 | 05470402145 | District Headquarters | New VCT Floor | Highway Trans. Fund 6 | 78000 | 78000 | TBD | 0% | 0% | 0 | 0 | 78000 | Pending Administrative Funding
657 | 667 | 05470402146 | District Headquarters | Replace Stairs Going In To District Break Room | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
658 | 668 | 05470402147 | District Headquarters | Replace Stairs Going Into Maint. Office | Highway Trans. Fund 6 | 7000 | 7000 | TBD | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding
659 | 669 | 06470402148 | Kermit Maintenance Office | Paint Exterior Walls & Re-Insulate Weldging Shop | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
660 | 670 | 21470402149 | Hebbronville Area Engineer & Maintenance Office | Add Large Conference Room | Highway Trans. Fund 6 | 252000 | 252000 | TBD | 0% | 0% | 0 | 0 | 252000 | Pending Administrative Funding
661 | 671 | 21470402150 | Hebbronville Area Engineer & Maintenance Office | Restroom Renovation | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
662 | 672 | 21470402151 | Hebbronville Area Engineer & Maintenance Office | Locker Room With Showers | Highway Trans. Fund 6 | 0 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding
663 | 673 | 21470402152 | Hebbronville Area Engineer & Maintenance Office | Phone/Computer Access | Highway Trans. Fund 6 | 0 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding
664 | 674 | 21470402153 | Hebbronville Area Engineer & Maintenance Office | Ventilation Upgrade | Highway Trans. Fund 6 | 0 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding
665 | 675 | 09470402154 | Marlin Area Engineer & Maintenance Office | Remodel Office | Highway Trans. Fund 6 | 488000 | 488000 | TBD | 0% | 0% | 0 | 0 | 488000 | Pending Administrative Funding
666 | 676 | 03470402155 | Electra Maintenance Office | Building Renovation | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
667 | 677 | 03470402156 | Electra Maintenance Office | Reskin And Replace Windows | Highway Trans. Fund 6 | 90000 | 90000 | TBD | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding
668 | 678 | 13470402157 | Edna Maintenance Office | Paint Metal On Shed | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
669 | 679 | 13470402158 | Jackson Cty Maint. | Paint Interior/Exterior Of Mechanic/Warehouse | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
670 | 680 | 17470402159 | Navasota Maintenance Office | Demolish Old Ae Building | Highway Trans. Fund 6 | 12500 | 12500 | TBD | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding
671 | 681 | 17470402160 | Navasota Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
672 | 682 | 17470402161 | Navasota Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
673 | 683 | 16470402162 | Karnes City Area Engineer & Maintenance Office | Interior Renovations | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
674 | 684 | 16470402163 | Karnes City Area Engineer & Maintenance Office | Repair Plumbing System - Karnes City AEM | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
675 | 685 | 05470402164 | District Headquarters | Security System Upgrade - C-Cure | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
676 | 686 | 05470402165 | Post RDC | Add New Wall To Dock With Overhead Door Wk Door | Highway Trans. Fund 6 | 90000 | 90000 | TBD | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding
677 | 687 | 38470402166 | Camp Hubbard State Headquarters | Replace Data Closet AC | Highway Trans. Fund 6 | 6000 | 6000 | TBD | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding
678 | 688 | 10470402167 | District Headquarters | Demolish Abandoned Structure | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
679 | 689 | 10470402168 | District Headquarters | Exterior Renovations | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
680 | 690 | 10470402169 | District Headquarters | Replace Carpet In Administration Building | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
681 | 691 | 09470402170 | Mexia Maintenance Office | Renovate Maintenance Facility | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
682 | 692 | 08470402171 | District Headquarters | Construct Concrete Apron Around The District Headquarters | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
683 | 693 | 08470402172 | District Headquarters | Repair And Replace All Plumbing Fixtures | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
684 | 694 | 17470402173 | Caldwell Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
685 | 695 | 17470402174 | Caldwell Maintenance Office | New Fuel Canopy | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
686 | 696 | 17470402175 | Caldwell Maintenance Office | Repaving Of Parking Areas | Highway Trans. Fund 6 | 400000 | 400000 | TBD | 0% | 0% | 0 | 0 | 400000 | Pending Administrative Funding
687 | 697 | 17470402176 | Caldwell Maintenance Office | Replace Gutters | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
688 | 698 | 24470402177 | Fort Davis Maintenance Office | Insulate Interior Of Stock Room / Storage | Highway Trans. Fund 6 | 22500 | 22500 | TBD | 0% | 0% | 0 | 0 | 22500 | Pending Administrative Funding
689 | 699 | 02470402178 | District Headquarters | Convert Conference Room To EOC | Highway Trans. Fund 6 | 153000 | 153000 | TBD | 0% | 0% | 0 | 0 | 153000 | Pending Administrative Funding
690 | 700 | 02470402179 | District Headquarters | Electrical Upgrade For The Whole District Headquarters | Highway Trans. Fund 6 | 300000 | 300000 | TBD | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding
691 | 701 | 02470402180 | District Headquarters | Install Interior Walls At Warehouse - Fort Worth DHQ Ware House Office | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
692 | 702 | 02470402181 | District Headquarters | Install Interiors At Shop - Fort Worth DHQ Locker Rooms | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
693 | 703 | 02470402182 | District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 125000 | 125000 | TBD | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding
694 | 704 | 02470402183 | District Headquarters | Replace\New Windows At Laboratory - Fort Worth DHQ | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
695 | 705 | 12470402184 | Rosenberg Area Engineer & Maintenance Office | Paint Exterior (5 Buildings) | Highway Trans. Fund 6 | 97000 | 97000 | TBD | 0% | 0% | 0 | 0 | 97000 | Pending Administrative Funding
696 | 706 | 12470402185 | Rosenberg Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
697 | 707 | 12470402186 | Rosenberg Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 240000 | 240000 | TBD | 0% | 0% | 0 | 0 | 240000 | Pending Administrative Funding
698 | 708 | 05470402187 | Post Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
699 | 709 | 06470402188 | District Headquarters | Repair/Replace Carpet In Tp&D Area | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
700 | 710 | 06470402189 | District Headquarters | Upgrade The District Complex Plumbing System | Highway Trans. Fund 6 | 280000 | 280000 | TBD | 0% | 0% | 0 | 0 | 280000 | Pending Administrative Funding
701 | 711 | 15470402190 | District Headquarters | Repair Foundation | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
702 | 712 | 15470402191 | District Headquarters | Repair Sidewalks | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
703 | 713 | 15470402192 | Seguin RDC | Restroom Renovation/Addition | Highway Trans. Fund 6 | 80000 | 80000 | TBD | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding
704 | 714 | 08470402193 | District Headquarters | Add Wall, Lighting, And Ventilation | Highway Trans. Fund 6 | 7000 | 7000 | TBD | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding
705 | 715 | 08470402194 | District Headquarters | New Carpet | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
706 | 716 | 08470402195 | District Headquarters | Replace Flooring At The Special Crews Building | Highway Trans. Fund 6 | 16700 | 16700 | TBD | 0% | 0% | 0 | 0 | 16700 | Pending Administrative Funding
707 | 717 | 25470402196 | Wellington Maintenance Office | Re-Skin Exterior, Insulate Building, Install Windows and Roof, Redesign Office Space | Highway Trans. Fund 6 | 325000 | 325000 | TBD | 0% | 0% | 0 | 0 | 325000 | Pending Administrative Funding
708 | 718 | 02470402197 | District Headquarters | Lab Upgrades | Highway Trans. Fund 6 | 558500 | 558500 | TBD | 0% | 0% | 0 | 0 | 558500 | Pending Administrative Funding
709 | 719 | 02470402198 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 6 | 21500 | 21500 | TBD | 0% | 0% | 0 | 0 | 21500 | Pending Administrative Funding
710 | 720 | 12470402199 | Houston South Area Engineer & Maintenance Office | Renovate 3 Buildings Into One | Highway Trans. Fund 6 | 1200000 | 1200000 | TBD | 0% | 0% | 0 | 0 | 1200000 | Pending Administrative Funding
711 | 721 | 12470402200 | Houston South Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 29000 | 29000 | TBD | 0% | 0% | 0 | 0 | 29000 | Pending Administrative Funding
712 | 722 | 12470402201 | Houston South Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 485000 | 485000 | TBD | 0% | 0% | 0 | 0 | 485000 | Pending Administrative Funding
713 | 723 | 12470402202 | Houston South Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 0 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding
715 | 724 | 06470402204 | District Headquarters | Replace/Repair Windows | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
716 | 725 | 15470402205 | Seguin Area Engineer & Maintenance Office | Exterior Paint | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
718 | 726 | 15470402207 | Seguin Area Engineer & Maintenance Office | Restroom Renovation/Addition | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
719 | 727 | 04470402208 | Canyon Maintenance Office | Abate Inside,Replace Windows And Replace Roof | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
720 | 728 | 05470402209 | Bovina Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
721 | 729 | 05470402210 | Bovina Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
722 | 730 | 05470402211 | Bovina Maintenance Office | Repaint Exterior, Old Faded Peeling | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
723 | 731 | 05470402212 | Brownfield Area Engineer & Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
724 | 732 | 05470402213 | Brownfield Area Engineer & Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
725 | 733 | 05470402214 | Brownfield Area Engineer & Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
726 | 734 | 05470402215 | Ralls Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
727 | 735 | 05470402216 | Ralls Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
728 | 736 | 05470402217 | Ralls Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
729 | 737 | 15470402218 | Tilden Maintenance Office | Carpet & Paint | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
730 | 738 | 15470402219 | Tilden Maintenance Office | Relocate Radio Tower | Highway Trans. Fund 6 | 0 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding
731 | 739 | 15470402220 | Tilden Maintenance Office | Upgrade Restrooms | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
732 | 740 | 38470402221 | Camp Hubbard State Headquarters | Renovate Interior Office Space, Include Abatement, New Lighting, New Windows, New Duct Work | Highway Trans. Fund 6 | 1000000 | 1000000 | TBD | 0% | 0% | 0 | 0 | 1000000 | Pending Administrative Funding
733 | 741 | 10470402222 | North Tyler Maintenance Office | Elevated Water Storage | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
734 | 742 | 10470402223 | North Tyler Maintenance Office | Remodel Office & New Roof | Highway Trans. Fund 6 | 300000 | 300000 | TBD | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding
735 | 743 | 13470402224 | Austin Cty Maint. | Paint Interior Structure Of Equip Shed | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
736 | 744 | 13470402225 | Austin Cty Maint. | Rehab. Of Mechanic Area (Front Wall W/ Door) | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
737 | 745 | 13470402226 | Colorado Cty Maint. | Level And Paint Interior Of Office Building | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
738 | 746 | 13470402227 | Colorado Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
739 | 747 | 13470402228 | Columbus Maintenance Office | Level Building (Maintenance Bldg) | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
740 | 748 | 13470402229 | Columbus Maintenance Office | Paint Office & Warehouse Exterior | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
741 | 749 | 13470402230 | District Headquarters | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
742 | 750 | 08470402231 | Big Spring Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
743 | 751 | 08470402232 | Big Spring Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
744 | 752 | 08470402233 | Big Spring Maintenance Office | Repair Damage To Walls And Wood In Area Ofice | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
745 | 753 | 20470402234 | District Headquarters | Install Rotary Lift & 2 Ton Overhead Crane And Trolley | Highway Trans. Fund 6 | 13000 | 13000 | TBD | 0% | 0% | 0 | 0 | 13000 | Pending Administrative Funding
746 | 754 | 20470402235 | District Headquarters | Paint Flag Pole | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
747 | 755 | 20470402236 | District Headquarters | Rebuild Overhead Door (10) | Highway Trans. Fund 6 | 4000 | 4000 | TBD | 0% | 0% | 0 | 0 | 4000 | Pending Administrative Funding
748 | 756 | 20470402237 | District Headquarters | Interior Remodel | Highway Trans. Fund 6 | 6700 | 6700 | TBD | 0% | 0% | 0 | 0 | 6700 | Pending Administrative Funding
749 | 757 | 20470402238 | District Headquarters | Interior Remodel | Highway Trans. Fund 6 | 39000 | 39000 | TBD | 0% | 0% | 0 | 0 | 39000 | Pending Administrative Funding
750 | 758 | 20470402239 | District Headquarters | Repair ADA Ramps | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
751 | 759 | 20470402240 | District Headquarters | Replace 25 Infra-Red Heaters | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
752 | 760 | 20470402241 | Districtwide | Flag Pole Lights | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
753 | 761 | 20470402242 | Districtwide | Replace Fuel Dispensers Districtwide | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
754 | 762 | 25470402243 | Dickens Maintenance Office | Replace Windows & Locks | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
755 | 763 | 12470402244 | La Marque Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 300000 | 300000 | TBD | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding
756 | 764 | 12470402245 | La Marque Area Engineer & Maintenance Office | Replace Siding (8 Buildings) | Highway Trans. Fund 6 | 640000 | 640000 | TBD | 0% | 0% | 0 | 0 | 640000 | Pending Administrative Funding
757 | 765 | 06470402246 | McCamey Maintenance Office | Repaint Exterior | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
758 | 766 | 03470402247 | District Headquarters | Building Renovations | Highway Trans. Fund 6 | 112000 | 112000 | TBD | 0% | 0% | 0 | 0 | 112000 | Pending Administrative Funding
759 | 767 | 03470402248 | District Headquarters | Foundation And Cosmetic Repairs | Highway Trans. Fund 6 | 160000 | 160000 | TBD | 0% | 0% | 0 | 0 | 160000 | Pending Administrative Funding
760 | 768 | 13470402249 | Colorado Cty Maint. | Close Open Bay And Add To Sign Room | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
761 | 769 | 13470402250 | Colorado Cty Maint. | Replace 5 Overhead Roll Up Doors And Paint 3 | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
762 | 770 | 13470402251 | Columbus Maintenance Office | Replace Oh Doors On Shed | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
763 | 771 | 13470402252 | Matagorda Cty Maint. | Bird Proof Underside Of Roof-Purlins | Highway Trans. Fund 6 | 6000 | 6000 | TBD | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding
764 | 772 | 13470402253 | Matagorda Cty Maint. | Construct Elevated Platform For Wash Rack | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
765 | 773 | 19470402254 | District Headquarters | Renovation Of Warehouse | Highway Trans. Fund 6 | 515000 | 515000 | TBD | 0% | 0% | 0 | 0 | 515000 | Pending Administrative Funding
766 | 774 | 19470402255 | Texarkana Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 6 | 80000 | 80000 | TBD | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding
767 | 775 | 19470402256 | Texarkana Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 6 | 111000 | 111000 | TBD | 0% | 0% | 0 | 0 | 111000 | Pending Administrative Funding
768 | 776 | 17470402257 | Brenham Area Engineer & Maintenance Office | Paint Building | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
769 | 777 | 17470402258 | Brenham Area Engineer & Maintenance Office | Remove Fuel Awning/Install New Awning For Parking | Highway Trans. Fund 6 | 250000 | 250000 | TBD | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding
770 | 778 | 16470402259 | District Headquarters | Repair Structure At Administration - Corpus Christi DHQ | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
771 | 779 | 16470402260 | District Headquarters | Replace Flooring At Administration - Corpus Christi DHQ | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
772 | 780 | 16470402261 | District Headquarters | Replace Overhead Gas Heaters In Auto Shop | Highway Trans. Fund 6 | 24000 | 24000 | TBD | 0% | 0% | 0 | 0 | 24000 | Pending Administrative Funding
773 | 781 | 16470402262 | Goliad Maintenance Office | Replace\New Exterior Walls At Equipment Storage - Goliad MNT | Highway Trans. Fund 6 | 90000 | 90000 | TBD | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding
774 | 782 | 16470402263 | Karnes Co. | Remodel Inside Office (Lights, Ceiling, Floor, Paint) | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
775 | 783 | 16470402264 | Karnes Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
776 | 784 | 02470402265 | Mineral Wells Maintenance Office | Renovate Maintenance Facility | Highway Trans. Fund 6 | 500000 | 500000 | TBD | 0% | 0% | 0 | 0 | 500000 | Pending Administrative Funding
777 | 785 | 05470402266 | Plains Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
778 | 786 | 05470402267 | Plains Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
779 | 787 | 05470402268 | Seminole Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
780 | 788 | 05470402269 | Seminole Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
781 | 789 | 05470402270 | Seminole Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
782 | 790 | 11470402271 | Crockett Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
783 | 791 | 11470402272 | Crockett Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
784 | 792 | 11470402273 | Crockett Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
785 | 793 | 11470402274 | Crockett Maintenance Office | Upgrade Exterior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
786 | 794 | 11470402275 | Crockett Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
787 | 795 | 11470402276 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
788 | 796 | 06470402277 | Crane Maintenance Office | Paint Exterior And Interior | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
789 | 797 | 06470402278 | Crane Maintenance Office | Reconfigure Bay For Break Room Locker Room. New Kitchenette Lockers Flooring Walls Plumbing Electrical | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
790 | 798 | 06470402279 | Crane Maintenance Office | Remove & Replace Windows In Main Office | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
791 | 799 | 06470402280 | Crane Maintenance Office | Upgrade Electrical Wiring, Lights And Breakers | Highway Trans. Fund 6 | 4000 | 4000 | TBD | 0% | 0% | 0 | 0 | 4000 | Pending Administrative Funding
792 | 800 | 06470402281 | Crane Maintenance Office | Upgrade Rain Gutters | Highway Trans. Fund 6 | 7000 | 7000 | TBD | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding
793 | 801 | 21470402282 | District Headquarters | Upgrade Conference Rooms | Highway Trans. Fund 6 | 51000 | 51000 | TBD | 0% | 0% | 0 | 0 | 51000 | Pending Administrative Funding
794 | 802 | 21470402283 | District Headquarters | Repair Plumbing Problems | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
795 | 803 | 21470402284 | Falfurrias Maintenance Office Sub-Section | Building Renovation | Highway Trans. Fund 6 | 163300 | 163300 | TBD | 0% | 0% | 0 | 0 | 163300 | Pending Administrative Funding
796 | 804 | 21470402285 | Falfurrias Maintenance Office Sub-Section | Upgrade Mechanic Shop | Highway Trans. Fund 6 | 190000 | 190000 | TBD | 0% | 0% | 0 | 0 | 190000 | Pending Administrative Funding
797 | 805 | 09470402286 | Meridian Maintenance Office | Retrofit Truck Bays To Conference Rooms and Meeting Space | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
798 | 806 | 09470402287 | Meridian Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
799 | 807 | 03470402288 | District Headquarters | Retrofit Warehouse Space To Large Meeting Room | Highway Trans. Fund 6 | 28500 | 28500 | TBD | 0% | 0% | 0 | 0 | 28500 | Pending Administrative Funding
800 | 808 | 03470402289 | Nocona Maintenance Office | Building Remodel | Highway Trans. Fund 6 | 90000 | 90000 | TBD | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding
801 | 809 | 13470402290 | Calhoun Cty Maint. | Interior Renovation (Floors & Walls) | Highway Trans. Fund 6 | 60000 | 60000 | TBD | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding
802 | 810 | 13470402291 | Calhoun Cty Maint. | Paint Exterior Structure Of Canopy, Mechanci Shop, & Stock Room | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
803 | 811 | 13470402292 | Calhoun Cty Maint. | Paint Interior Structure Of Equip Shed | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
804 | 812 | 13470402293 | District Headquarters | Replace Shifting Concrete Pad Under Pad Mount Electrical Transformer | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
805 | 813 | 13470402294 | Port Lavaca Maintenance Office | Replace Flooring | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
806 | 814 | 20470402295 | Port Arthur Area Engineer & Maintenance Office | Asbestos Abatement | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
807 | 815 | 20470402296 | Port Arthur Area Engineer & Maintenance Office | Paint Interior Of Facility | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
808 | 816 | 20470402297 | Port Arthur Area Engineer & Maintenance Office | Replace Doors, Frames & Locksets | Highway Trans. Fund 6 | 6000 | 6000 | TBD | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding
809 | 817 | 23470402298 | District Headquarters | Renovate Lab | Highway Trans. Fund 6 | 712000 | 712000 | TBD | 0% | 0% | 0 | 0 | 712000 | Pending Administrative Funding
810 | 818 | 18470402300 | Waxahachie Area Engineer & Maintenance Office | Electrical - Additional Service | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
811 | 819 | 24470402301 | Dell City Maintenance Office | Install Bird Screens @ Truck Bays | Highway Trans. Fund 6 | 5500 | 5500 | TBD | 0% | 0% | 0 | 0 | 5500 | Pending Administrative Funding
812 | 820 | 12470402302 | Rosenberg Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 120000 | 120000 | TBD | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding
813 | 821 | 22470402303 | Del Rio Maintenance Office | Exterior Warehouse Painting | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
814 | 822 | 05470402304 | Levelland Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
815 | 823 | 05470402305 | Levelland Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
816 | 824 | 05470402306 | SE Maint. Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
817 | 825 | 11470402307 | District Headquarters | Foundation Repairs | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
818 | 826 | 11470402308 | District Headquarters | Paint Interior | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
819 | 827 | 11470402309 | District Headquarters | Repair Dist Shop Parking Lot And Stripe Existing Lots At Dist HQ | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
820 | 828 | 11470402310 | District Headquarters | Replace Fuel Awning | Highway Trans. Fund 6 | 21000 | 21000 | TBD | 0% | 0% | 0 | 0 | 21000 | Pending Administrative Funding
821 | 829 | 11470402311 | District Headquarters | Replace Fuel Dispensers | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
822 | 830 | 11470402312 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
823 | 831 | 04470402313 | District Headquarters | Abate Windows And Paint Exterior Of Shop | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
824 | 832 | 19470402314 | Mt Pleasant Area Engineer & Maintenance Office | Major Renovation | Highway Trans. Fund 6 | 767000 | 767000 | TBD | 0% | 0% | 0 | 0 | 767000 | Pending Administrative Funding
825 | 833 | 19470402315 | Mt Pleasant Area Engineer & Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 6 | 65000 | 65000 | TBD | 0% | 0% | 0 | 0 | 65000 | Pending Administrative Funding
826 | 834 | 19470402316 | Mt Pleasant Area Engineer & Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 6 | 128300 | 128300 | TBD | 0% | 0% | 0 | 0 | 128300 | Pending Administrative Funding
827 | 835 | 18470402317 | Rockwall Maintenance Office | Electrical Panel Upgrades | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
828 | 836 | 18470402318 | Rockwall Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
829 | 837 | 18470402319 | Rockwall Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
830 | 838 | 18470402320 | Rockwall Maintenance Office | Siding - Partial Replacement | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
831 | 839 | 22470402321 | Carrizo Springs | Replace Two Overhead Doors | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
832 | 840 | 22470402322 | Carrizo Springs | Restroom Renovation | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
833 | 841 | 22470402323 | Carrizo Springs | Retrofit Locker Room Into Storage/Supply Room | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
834 | 842 | 05470402324 | FloydADA Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
835 | 843 | 05470402325 | Lamesa Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
836 | 844 | 05470402326 | Lamesa Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
837 | 845 | 05470402327 | Lamesa Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
838 | 846 | 11470402328 | Lufkin Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
839 | 847 | 11470402329 | Lufkin Maintenance Office | Renovate Bathrooms | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
840 | 848 | 11470402330 | Lufkin Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
841 | 849 | 11470402331 | Lufkin Maintenance Office | Replace Flooring | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
842 | 850 | 11470402332 | Lufkin Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
843 | 851 | 11470402333 | Lufkin Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
844 | 852 | 11470402334 | Lufkin Maintenance Office | Underskirt Fuel Awning | Highway Trans. Fund 6 | 6000 | 6000 | TBD | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding
845 | 853 | 11470402335 | Lufkin Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
846 | 854 | 07470402336 | District Headquarters | Modifications/Upgrade Electrical | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
847 | 855 | 07470402337 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 6 | 21500 | 21500 | TBD | 0% | 0% | 0 | 0 | 21500 | Pending Administrative Funding
848 | 856 | 20470402338 | District Headquarters | Paint Interior | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
849 | 857 | 12470402340 | Houston Northwest | Renovate Interior/Exterior (20K Sf Concrete Tilt Wall Aquired Building) | Highway Trans. Fund 6 | 2000000 | 2000000 | TBD | 0% | 0% | 0 | 0 | 2000000 | Pending Administrative Funding
850 | 858 | 12470402341 | West Harris Maintenance Office | Renovation And Upgrade To AEM | Highway Trans. Fund 6 | 2000000 | 2000000 | TBD | 0% | 0% | 0 | 0 | 2000000 | Pending Administrative Funding
851 | 859 | 05470402342 | District Headquarters-LBB AE's | New VCT Floor | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
852 | 860 | 05470402343 | District Headquarters-LBB AE's | Replace Roof | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
853 | 861 | 05470402344 | District Headquarters-LBB AE's | Replace Steps With ADA Ramp Back Door | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
854 | 862 | 11470402345 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
855 | 863 | 04470402346 | Vega Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
856 | 864 | 04470402347 | Vega Maintenance Office | Upgrade Current Welding Shop | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
857 | 865 | 19470402348 | New Boston Maintenance Office | Remodel Inside Of Building Paint Floor And Ceiling | Highway Trans. Fund 6 | 80000 | 80000 | TBD | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding
858 | 866 | 19470402349 | New Boston Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 6 | 99400 | 99400 | TBD | 0% | 0% | 0 | 0 | 99400 | Pending Administrative Funding
859 | 867 | 15470402350 | Devine Maintenance Office | Paint, Carpet Replacement | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
860 | 868 | 15470402351 | Devine Maintenance Office | Restroom Upgrades | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
861 | 869 | 13470402352 | District Headquarters | Replace All Exterior Roof Facial & Renovate All Exterior Entrances | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
862 | 870 | 16470402353 | Goliad Co. | Replace Metal Siding On Equipment Shed And Roof With New Siding And Roof | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
863 | 871 | 16470402354 | Kingsville Maintenance Office | Paint Interior Walls At Maintenance - Kingsville Maintenance | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
864 | 872 | 16470402355 | Kingsville Maintenance Office | Replace Flooring At Maintenance - Kingsville MNT | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
865 | 873 | 16470402356 | Kleburg Co. | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
866 | 874 | 05470402357 | Plainview Area Engineer & Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
867 | 875 | 05470402358 | Tahoka Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
868 | 876 | 05470402359 | Tahoka Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
869 | 877 | 05470402360 | Tahoka Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
870 | 878 | 04470402361 | Canadian Maintenance Office | Foundation Repair | Highway Trans. Fund 6 | 0 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding
871 | 879 | 04470402362 | Canadian Maintenance Office | Install Overhead Doors And Openers | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
872 | 880 | 04470402363 | Canadian Maintenance Office | Renovation Of Building Exterior | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
873 | 881 | 04470402364 | Canadian Maintenance Office | Restroom Abatement And Remodel | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
874 | 882 | 04470402365 | E way | Lighting Upgrades | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
875 | 883 | 04470402366 | Hereford Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
876 | 884 | 14470402367 | Lockhart Maintenance Office | Foundation Repair | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
877 | 885 | 20470402368 | Kountze Maintenance Office | Install Overhead Doors | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
878 | 886 | 20470402369 | Kountze Maintenance Office | Paint Office Exterior | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
879 | 887 | 20470402370 | Liberty Area Engineer & Maintenance Office | Replace Electrical Panels And Upgrade Electrical Wiring. | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
880 | 888 | 24470402371 | Terlingua Sub-Section | Additional Outside LED Lighting For Houses. | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
881 | 889 | 24470402372 | Terlingua Sub-Section | Interior Renovation; Electrical, HVAC, Walls Finish, Framing, Floors And Kitchen | Highway Trans. Fund 6 | 36000 | 36000 | TBD | 0% | 0% | 0 | 0 | 36000 | Pending Administrative Funding
882 | 890 | 24470402373 | Terlingua Sub-Section | Paint Interior Walls | Highway Trans. Fund 6 | 17500 | 17500 | TBD | 0% | 0% | 0 | 0 | 17500 | Pending Administrative Funding
883 | 891 | 24470402374 | Terlingua Sub-Section | Repair / Replace Plumbing Lines Fro Meter To Houses | Highway Trans. Fund 6 | 18000 | 18000 | TBD | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding
884 | 892 | 05470402375 | Muleshoe Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
885 | 893 | 05470402376 | Muleshoe Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
886 | 894 | 07470402377 | District Headquarters | Paint Interior Of Facility | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
887 | 895 | 08470402378 | Snyder Maintenance Office | Convert Old Propane Gas Heaters In Shop To Natural Gas | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
888 | 896 | 08470402379 | Snyder Maintenance Office | Convert The Old Salt Bin Into A Sign And Traffic Control Room Storage | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
889 | 897 | 08470402380 | Snyder Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
890 | 898 | 04470402381 | Perryton Maintenance Office | Replace Roof, Re-Skin Exterior, Install New Insulation And Windows | Highway Trans. Fund 6 | 175000 | 175000 | TBD | 0% | 0% | 0 | 0 | 175000 | Pending Administrative Funding
891 | 899 | 04470402382 | Perryton Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
892 | 900 | 08470402383 | Haskell Maintenance Office | Convert Old Shop Into Breakroom | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
893 | 901 | 23470402384 | Brownwood Area Engineer & Maintenance Office | Renovate Office | Highway Trans. Fund 6 | 311000 | 311000 | TBD | 0% | 0% | 0 | 0 | 311000 | Pending Administrative Funding
894 | 902 | 17470402385 | Huntsville Area Engineer & Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
895 | 903 | 17470402386 | Huntsville Area Engineer & Maintenance Office | Paint Building | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
896 | 904 | 17470402387 | Huntsville Area Engineer & Maintenance Office | Repair Foundation/Porch/Walls | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
897 | 905 | 17470402388 | Huntsville Area Engineer & Maintenance Office | Repair Roof | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
898 | 906 | 17470402389 | Huntsville Area Engineer & Maintenance Office | Replace Fuel Canopy | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
899 | 907 | 17470402390 | Huntsville Area Engineer & Maintenance Office | Replace Wiring In Building | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
900 | 908 | 25470402391 | Quanah Maintenance Office | Paint Interior & Exterior, Resurface Parking Area | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
901 | 909 | 25470402392 | Quanah Maintenance Office | Replace Floor Tiles; Upgrade Rest Rooms, Redesign Office Space | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
902 | 910 | 16470402393 | District Headquarters | Replace Electrical Panels At Right Of Way - Corpus Christi District Headquarters And Area Engineer And Maintenance Special Jobs | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
903 | 911 | 16470402394 | District Headquarters | Replace\New Electrical Panel At Right Of Way - Corpus Christi DHQ | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
904 | 912 | 06470402395 | Iraan Maintenance Office | Enclose 3 Bays With Insulated Overhead Doors To Secure Equipment & Weather Protection | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
905 | 913 | 06470402396 | Iraan Maintenance Office | Repair/Replace ATG System On Above Ground Fuel Tanks | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
906 | 914 | 06470402397 | Iraan Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
907 | 915 | 21470402398 | Mission Maintenance Office | New 4K Gallon Fuel Tanks/Replace Fuel Pumps | Highway Trans. Fund 6 | 300000 | 300000 | TBD | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding
908 | 916 | 21470402399 | Mission Maintenance Office | New Heavy Equipment Overhead Doors | Highway Trans. Fund 6 | 57000 | 57000 | TBD | 0% | 0% | 0 | 0 | 57000 | Pending Administrative Funding
909 | 917 | 21470402400 | Mission Maintenance Office | New Heavy Equipment Pull Through Stalls | Highway Trans. Fund 6 | 21500 | 21500 | TBD | 0% | 0% | 0 | 0 | 21500 | Pending Administrative Funding
910 | 918 | 21470402401 | Mission Maintenance Office | Renovate Building | Highway Trans. Fund 6 | 112000 | 112000 | TBD | 0% | 0% | 0 | 0 | 112000 | Pending Administrative Funding
911 | 919 | 13470402402 | Jackson Cty Maint. | Interior Renovation (Floors & Walls) | Highway Trans. Fund 6 | 60000 | 60000 | TBD | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding
912 | 920 | 18470402403 | Hutchins Maintenance Office | Electrical Panel Upgrades | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
913 | 921 | 18470402404 | Hutchins Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
914 | 922 | 24470402405 | Alpine Area Engineer & Maintenance Office | Remodel Bay For Maintenance Training And Breakroom, Add One Additional Office In Bay. | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
915 | 923 | 12470402406 | Houston NE Area Engineer & Maintenance Office | Renovate Restrooms (Locker Rooms) | Highway Trans. Fund 6 | 42000 | 42000 | TBD | 0% | 0% | 0 | 0 | 42000 | Pending Administrative Funding
916 | 924 | 12470402407 | Houston NE Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
917 | 925 | 21470402408 | Hebbronville Area Engineer & Maintenance Office | Upgrade Mechanic Shop | Highway Trans. Fund 6 | 0 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding
918 | 926 | 17470402409 | Brenham Area Engineer & Maintenance Office | Upgrade Lighting In Washbay | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
919 | 927 | 17470402410 | Brenham Area Engineer & Maintenance Office | Replace Siding On A Wash Bay | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
920 | 928 | 17470402411 | Bryan Area Engineer & Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
921 | 929 | 17470402412 | Bryan Area Engineer & Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
922 | 930 | 17470402413 | Bryan Area Engineer & Maintenance Office | Install Automatic Gate On Rear Gate | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
923 | 931 | 06470402414 | Balmorhea Maintenance Office | Remove and Replace Existing Shower Floor Tile | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
924 | 932 | 06470402415 | Balmorhea Maintenance Office | Remove and Replace Floor Tile Main Office | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
925 | 933 | 21470402416 | San Benito Area Engineer & Maintenance Office | Upgrade Ballasts | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
926 | 934 | 24470402417 | Presidio Maintenance Office | Convert Bay Into A Break Room | Highway Trans. Fund 6 | 19500 | 19500 | TBD | 0% | 0% | 0 | 0 | 19500 | Pending Administrative Funding
927 | 935 | 24470402418 | Presidio Maintenance Office | Extend Office Space Along Same Roof Line To The South 16 Feet | Highway Trans. Fund 6 | 80000 | 80000 | TBD | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding
928 | 936 | 19470402419 | Daingerfield Maintenance Office | Install Overhead Door Operators & Gate | Highway Trans. Fund 6 | 32200 | 32200 | TBD | 0% | 0% | 0 | 0 | 32200 | Pending Administrative Funding
929 | 937 | 19470402420 | Daingerfield Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
930 | 938 | 17470402421 | Buffalo Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
931 | 939 | 17470402422 | Buffalo Maintenance Office | Remove Undergrnd/Install Above Grnd Fuel Tanks | Highway Trans. Fund 6 | 350000 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding
932 | 940 | 21470402423 | Laguna Vista Maintenance Office Sub-Section | Building Renovation | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
933 | 941 | 21470402424 | Laguna Vista Maintenance Office Sub-Section | Replace Overhead Doors | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
934 | 942 | 04470402425 | Groom Maintenance Office | Electrical Upgrades | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
935 | 943 | 04470402426 | Groom Maintenance Office | New Compressor/Relocate | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
936 | 944 | 04470402427 | Groom Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
937 | 945 | 15470402428 | Bandera Maintenance Office | Paint, Carpet Replacement | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
938 | 946 | 15470402429 | Bandera Maintenance Office | Restroom Upgrades | Highway Trans. Fund 6 | 0 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding
939 | 947 | 15470402430 | Bandera Maintenance Office | Window Replacement | Highway Trans. Fund 6 | 180000 | 180000 | TBD | 0% | 0% | 0 | 0 | 180000 | Pending Administrative Funding
940 | 948 | 15470402431 | Hondo Area Engineer & Maintenance Office | Asbestos Abatement, Carpet & Paint | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
941 | 949 | 15470402432 | Hondo Area Engineer & Maintenance Office | Restroom Upgrade | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
942 | 950 | 12470402433 | East Harris Maintenance Office | Locker Room Upgrades/Addition Of Showers | Highway Trans. Fund 6 | 42000 | 42000 | TBD | 0% | 0% | 0 | 0 | 42000 | Pending Administrative Funding
943 | 951 | 12470402434 | Houston NE Area Engineer & Maintenance Office | Replace Gutter System | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
944 | 952 | 15470402435 | Uvalde Maintenance Office | Replace Irrigation System | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
945 | 953 | 08470402436 | Roby Maintenance Office | Install Floor Tile | Highway Trans. Fund 6 | 18000 | 18000 | TBD | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding
946 | 954 | 08470402437 | Roby Maintenance Office | Level Wash Bay | Highway Trans. Fund 6 | 1500 | 1500 | TBD | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding
947 | 955 | 08470402438 | Roby Maintenance Office | Install Overhead Door Openers and Push Buttons in all Bay Door Openings. Total of 10 Door Openers. | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
948 | 956 | 08470402439 | Roby Maintenance Office | Repair Structural Damage to Columns | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
949 | 957 | 08470402440 | Roby Maintenance Office | Upgrade Power Washer Building | Highway Trans. Fund 6 | 2500 | 2500 | TBD | 0% | 0% | 0 | 0 | 2500 | Pending Administrative Funding
950 | 958 | 08470402441 | Taylor Co. Maintenance Office | Upgrade Wash Bay | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
951 | 959 | 24470402442 | Pine Springs Sub-Section | Additional Outside LED Lighting For Houses. | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
952 | 960 | 24470402443 | Pine Springs Sub-Section | Install Garage Door Openers | Highway Trans. Fund 6 | 7000 | 7000 | TBD | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding
953 | 961 | 24470402444 | Pine Springs Sub-Section | Renovate Stock Area; Insulate Metal Walls, Ceiling | Highway Trans. Fund 6 | 11500 | 11500 | TBD | 0% | 0% | 0 | 0 | 11500 | Pending Administrative Funding
954 | 962 | 07470402445 | Big Lake Maintenance Office | Construct Buildings Over Lifts | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
955 | 963 | 03470402446 | Vernon Area Engineer & Maintenance Office | Replace Flooring At Maintenance - Vernon Area Engineer And Maintenance | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
956 | 964 | 14470402447 | East Travis Maintenance Office | Foundation Repair | Highway Trans. Fund 6 | 167200 | 167200 | TBD | 0% | 0% | 0 | 0 | 167200 | Pending Administrative Funding
957 | 965 | 17470402448 | Navasota Maintenance Office | Replace Fuel Canopy - Navasota MNT | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
958 | 966 | 16470402449 | Corpus Christi Area Engineer & Maintenance Office | Replace Flooring At Area Engineer And Maintenance - Corpus Christi AEM | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
959 | 967 | 16470402450 | Nueces East | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
960 | 968 | 19470402451 | Carthage Maintenance Office | Install Overhead Door Operators & Gate | Highway Trans. Fund 6 | 82600 | 82600 | TBD | 0% | 0% | 0 | 0 | 82600 | Pending Administrative Funding
961 | 969 | 19470402452 | Carthage Maintenance Office | Remodel Inside Of Building Including Bathrooms | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
962 | 970 | 16470402453 | San Patricio Co | Replace Ceiling Tiles In Office Building | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
963 | 971 | 16470402454 | San Patricio Co | Replace 2 Existing Dual Product Fuel Dispensers At The Fuel Station | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
964 | 972 | 16470402455 | San Patricio Co | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
965 | 973 | 16470402456 | Sinton Area Engineer & Maintenance Office | Paint Interior Walls At Area Engineer And Maintenance - Sinton AEM | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
966 | 974 | 16470402457 | Sinton Area Engineer & Maintenance Office | Replace Ceilings At Area Engineer And Maintenance - Sinton AEM | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
967 | 975 | 16470402458 | Sinton Area Engineer & Maintenance Office | Replace Flooring At Area Engineer And Maintenance - Sinton AEM | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
968 | 976 | 16470402459 | Aransas Co. | Replace Existing Floor Tile And Paint Office | Highway Trans. Fund 6 | 17500 | 17500 | TBD | 0% | 0% | 0 | 0 | 17500 | Pending Administrative Funding
969 | 977 | 16470402460 | Aransas Co. | Install Storm Shutters On All Windows And Doors | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
970 | 978 | 16470402461 | Rockport Maintenance Office | Install Exteriors At Maintenance - Rockport MNT | Highway Trans. Fund 6 | 28000 | 28000 | TBD | 0% | 0% | 0 | 0 | 28000 | Pending Administrative Funding
971 | 979 | 16470402462 | Rockport Maintenance Office | Repair Exterior Windows At Maintenance - Rockport MNT | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
972 | 980 | 16470402463 | Rockport Maintenance Office | Replace Flooring At Maintenance - Rockport MNT | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
973 | 981 | 12470402464 | Humble Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 120000 | 120000 | TBD | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding
974 | 982 | 12470402465 | Humble Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 320000 | 320000 | TBD | 0% | 0% | 0 | 0 | 320000 | Pending Administrative Funding
975 | 983 | 22470402466 | Del Rio Maintenance Office | Storage Shed Asbestos Testing & Abatement | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
976 | 984 | 22470402467 | Del Rio Maintenance Office | Storage Shed Repairs | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
977 | 985 | 11470402468 | Center Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
978 | 986 | 11470402469 | Center Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
979 | 987 | 11470402470 | Center Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
980 | 988 | 11470402471 | Center Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
981 | 989 | 11470402472 | Livingston Area Engineer & Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
982 | 990 | 11470402473 | Livingston Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
983 | 991 | 11470402474 | Livingston Area Engineer & Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
984 | 992 | 11470402475 | Nacogdoches Area Engineer & Maintenance Office | Install Electric Baydoor Openers | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
985 | 993 | 11470402476 | Nacogdoches Area Engineer & Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
986 | 994 | 11470402477 | Nacogdoches Area Engineer & Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
987 | 995 | 11470402478 | Nacogdoches Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
988 | 996 | 11470402479 | Nacogdoches Area Engineer & Maintenance Office | Upgrade Exterior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
989 | 997 | 11470402480 | Nacogdoches Area Engineer & Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
990 | 998 | 11470402481 | San Augustine Area Engineer & Maintenance Office | Install Electric Baydoor Openers | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
991 | 999 | 11470402482 | San Augustine Area Engineer & Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
992 | 1000 | 11470402483 | San Augustine Area Engineer & Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
993 | 1001 | 11470402484 | San Augustine Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
994 | 1002 | 11470402485 | San Augustine Area Engineer & Maintenance Office | Upgrade Exterior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
995 | 1003 | 11470402486 | San Augustine Area Engineer & Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
996 | 1004 | 06470402487 | Stanton Maintenance Office | Enclose 3 Bays With Insulated Overhead Doors To Secure Equipment & Weather Protection | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
997 | 1005 | 06470402488 | Stanton Maintenance Office | Install Ladder Or Staircase | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
998 | 1006 | 06470402489 | Stanton Maintenance Office | Reinstall Evaporative Coolers In Wall | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
999 | 1007 | 21470402490 | District Headquarters | Exterior Facade Repairs To Warehouse, Shop & Teleconference Training Center | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
1000 | 1008 | 21470402491 | District Headquarters | Renovate Shop | Highway Trans. Fund 6 | 117000 | 117000 | TBD | 0% | 0% | 0 | 0 | 117000 | Pending Administrative Funding
1001 | 1009 | 21470402492 | District Headquarters/Area Engineer & Maintenance Office | Install Vehicle Exhaust System. Replace Existing Ceiling Fans. | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
1002 | 1010 | 21470402493 | District Headquarters/Area Engineer & Maintenance Office | Replace All Windows/Frames. | Highway Trans. Fund 6 | 85000 | 85000 | TBD | 0% | 0% | 0 | 0 | 85000 | Pending Administrative Funding
1003 | 1011 | 15470402494 | Pleasanton Area Engineer & Maintenance Office | Paint, Carpet Replacement | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1004 | 1012 | 15470402495 | Pleasanton Area Engineer & Maintenance Office | Restroom Upgrade | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
1005 | 1013 | 04470402496 | Dalhart Maintenance Office | Electrical Upgrades | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
1006 | 1014 | 04470402497 | Dalhart Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
1007 | 1015 | 04470402498 | Dalhart Maintenance Office | Shop Lighting Upgrades | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1008 | 1016 | 19470402499 | Jefferson Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 6 | 65000 | 65000 | TBD | 0% | 0% | 0 | 0 | 65000 | Pending Administrative Funding
1009 | 1017 | 19470402500 | Jefferson Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 6 | 113000 | 113000 | TBD | 0% | 0% | 0 | 0 | 113000 | Pending Administrative Funding
1010 | 1018 | 18470402501 | District Headquarters | Analysis By Engineering Consultant | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
1011 | 1019 | 18470402502 | District Headquarters | Countertops - Restrooms (Solid Surface) | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1012 | 1020 | 02470402503 | District Headquarters | Remodel Old Sign Shop Into A Fitness Center | Highway Trans. Fund 6 | 831000 | 831000 | TBD | 0% | 0% | 0 | 0 | 831000 | Pending Administrative Funding
1013 | 1021 | 06470402504 | Kermit Maintenance Office | Paint Exterior Walls | Highway Trans. Fund 6 | 21000 | 21000 | TBD | 0% | 0% | 0 | 0 | 21000 | Pending Administrative Funding
1014 | 1022 | 13470402505 | Gonzales Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1015 | 1023 | 04470402506 | Loop | Lighting Upgrades | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
1016 | 1024 | 04470402507 | Loop | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 6 | 100000 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding
1017 | 1025 | 19470402508 | Linden Maintenance Office | Install Overhead Door Operators & Gate | Highway Trans. Fund 6 | 83000 | 83000 | TBD | 0% | 0% | 0 | 0 | 83000 | Pending Administrative Funding
1018 | 1026 | 19470402509 | Linden Maintenance Office | Replace VCT Flooring And Paint Interior | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
1019 | 1027 | 18470402510 | District Headquarters | Modular Furniture Installation | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
1020 | 1028 | 18470402511 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 6 | 21500 | 21500 | TBD | 0% | 0% | 0 | 0 | 21500 | Pending Administrative Funding
1021 | 1029 | 18470402512 | District Headquarters | Countertops - Restrooms On 4Th Floor | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1022 | 1030 | 18470402513 | District Headquarters | Paint Exterior And Interior | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1023 | 1031 | 22470402514 | Del Rio Maintenance Office | Relocate Generator From Freer | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
1024 | 1032 | 22470402515 | Del Rio Maintenance Office (US 90) | Men's Restroom Renovation | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1025 | 1033 | 05470402516 | Morton Maintenance Office | Repaint Exterior, Old Faded Peeling | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
1026 | 1034 | 05470402517 | Tulia Maintenance Office | Repaint Exterior, Old Faded Peeling | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
1027 | 1035 | 13470402518 | Jackson Cty Maint. | Paint Interior Structure Of Equip Shed | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1028 | 1036 | 22470402519 | Cotulla Maintenance Office | Men's Restroom Renovation | Highway Trans. Fund 6 | 24000 | 24000 | TBD | 0% | 0% | 0 | 0 | 24000 | Pending Administrative Funding
1029 | 1037 | 22470402520 | Cotulla Maintenance Office | Replace Breakroom Flooring | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1030 | 1038 | 20470402521 | Jasper Area Engineer & Maintenance Office | Replace AV Electrical Circuit | Highway Trans. Fund 6 | 1500 | 1500 | TBD | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding
1031 | 1039 | 20470402522 | Jasper Area Engineer & Maintenance Office | Clean Fuel Tanks | Highway Trans. Fund 6 | 4000 | 4000 | TBD | 0% | 0% | 0 | 0 | 4000 | Pending Administrative Funding
1032 | 1040 | 20470402523 | Jasper Area Engineer & Maintenance Office | Interior Lighting | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1033 | 1041 | 20470402524 | Jasper Area Engineer & Maintenance Office | Paint Office Interior | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1034 | 1042 | 20470402525 | Jasper Area Engineer & Maintenance Office | Remodel Rest Rooms & Wall Repair | Highway Trans. Fund 6 | 54000 | 54000 | TBD | 0% | 0% | 0 | 0 | 54000 | Pending Administrative Funding
1035 | 1043 | 20470402526 | Jasper Area Engineer & Maintenance Office | Replace Carpet And VCT | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1036 | 1044 | 20470402527 | Orange Maintenance Office | Replace Siding And Roofing | Highway Trans. Fund 6 | 65000 | 65000 | TBD | 0% | 0% | 0 | 0 | 65000 | Pending Administrative Funding
1037 | 1045 | 20470402528 | Orange Maintenance Office | Upgrade Electrical | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1038 | 1046 | 12470402529 | Conroe Area Engineer & Maintenance Office | New Carpet/VCT | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1039 | 1047 | 12470402530 | Conroe Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1040 | 1048 | 12470402531 | Conroe Area Engineer & Maintenance Office | Reconfigure Cubicles (Space Management) | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1041 | 1049 | 12470402532 | Conroe Area Engineer & Maintenance Office | Renovate Breakroom | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1042 | 1050 | 22470402533 | Laredo Administration | Administration: Nail Down Spanish Tiles; Remove/Replace Broken Spanish Tiles | Highway Trans. Fund 6 | 120000 | 120000 | TBD | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding
1043 | 1051 | 22470402534 | Laredo Area Engineer & Maintenance Office | Remove Worn Out Existing VCT Flooring & Replace Ceramic Tile | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1044 | 1052 | 22470402535 | Laredo Area Engineer & Maintenance Office (Lilac/Conference room) | Retrofit To Video Teleconference Room | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1045 | 1053 | 22470402536 | Laredo Auto Shop | Bat Issues (Clean Up And Resolution) | Highway Trans. Fund 6 | 300000 | 300000 | TBD | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding
1046 | 1054 | 22470402537 | Laredo Auto Shop | Minor Restrooms Renovation | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1047 | 1055 | 22470402538 | Laredo Compound facilities | Exterior Painting | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
1048 | 1056 | 22470402539 | Laredo District Headquarters | Carpet Replacement | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
1049 | 1057 | 22470402540 | Laredo FIN/Safety | Modular Unit (12) | Highway Trans. Fund 6 | 96000 | 96000 | TBD | 0% | 0% | 0 | 0 | 96000 | Pending Administrative Funding
1050 | 1058 | 15470402541 | Transguide | Proportionate Share Of 1St Floor Renovation | Highway Trans. Fund 6 | 1000000 | 1000000 | TBD | 0% | 0% | 0 | 0 | 1000000 | Pending Administrative Funding
1051 | 1059 | 10470402542 | District Headquarters | Demo Warehouse Office | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
1052 | 1060 | 10470402543 | District Headquarters | Install New Elevator | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
1053 | 1061 | 10470402544 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 6 | 21500 | 21500 | TBD | 0% | 0% | 0 | 0 | 21500 | Pending Administrative Funding
1054 | 1062 | 13470402545 | Victoria A.O. | Paint Interior Office | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1055 | 1063 | 13470402546 | Victoria A.O. | Sealing Exterior Block Walls | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1056 | 1064 | 13470402547 | Victoria Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1057 | 1065 | 13470402548 | Victoria Cty Maint. | Replace Wash Rack Canopy | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
1058 | 1066 | 16470402549 | District Headquarters | Install Storm Shutters On All Windows And Doors | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1059 | 1067 | 16470402550 | District Headquarters | Paint Exterior Walls At Shop - Corpus Christi DHQ | Highway Trans. Fund 6 | 27500 | 27500 | TBD | 0% | 0% | 0 | 0 | 27500 | Pending Administrative Funding
1060 | 1068 | 24470402551 | District Headquarters | Install LED Lighting In Wall Packs | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1061 | 1069 | 24470402552 | District Headquarters | Install Vestabule / Canopy Near Breakroom | Highway Trans. Fund 6 | 36000 | 36000 | TBD | 0% | 0% | 0 | 0 | 36000 | Pending Administrative Funding
1062 | 1070 | 24470402553 | District Headquarters | Install Vestibule Front And Rear, Lobby Entries | Highway Trans. Fund 6 | 48000 | 48000 | TBD | 0% | 0% | 0 | 0 | 48000 | Pending Administrative Funding
1063 | 1071 | 24470402554 | District Headquarters | Lab Dock Storage, Install Soffit Filler To Close Off Gap At Top. | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1064 | 1072 | 12470402555 | Angleton Area Engineer & Maintenance Office | Replace Insulation (Laboratory) | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
1065 | 1073 | 05470402556 | District Headquarters-Division West Building | New VCT Floor | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
1066 | 1074 | 15470402557 | Bexar Metro Area Engineer & Maintenance Office | Interior LED Lighting Upgrade | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
1067 | 1075 | 15470402558 | Bexar Metro Area Engineer & Maintenance Office | Raise Truck Wash Canopy | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1068 | 1076 | 15470402559 | Bexar Metro Area Engineer & Maintenance Office | Retrofit Equipment Bay For Enclosed Climate Control LED Storage | Highway Trans. Fund 6 | 2000 | 2000 | TBD | 0% | 0% | 0 | 0 | 2000 | Pending Administrative Funding
1069 | 1077 | 09470402560 | Gatesville Area Engineer & Maintenance Office | Upgrade Shop And Office | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
1070 | 1078 | 13470402561 | Yoakum A.O. | Level Building & Repair Exterior Cracks In Brick | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
1071 | 1079 | 13470402562 | Yoakum Area Engineer & Maintenance Office | Level Building (Area Engineers Bldg) | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
1072 | 1080 | 17470402563 | Hearne Area Engineer & Maintenance Office | Install Welding Ventilation Hood | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
1073 | 1081 | 17470402564 | Hearne Area Engineer & Maintenance Office | Redo HVAC/Vent/Pipes | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1074 | 1082 | 17470402565 | Hearne Area Engineer & Maintenance Office | Redo Lighting In Washbay | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1075 | 1083 | 17470402566 | Hearne Area Engineer & Maintenance Office | Replace Ceiling Tiles | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1076 | 1084 | 05470402567 | Dimmitt Maintenance Office | Repaint Exterior | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
1077 | 1085 | 03470402568 | Gainesville Area Engineer & Maintenance Office | Renovate Building For Storage | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
1078 | 1086 | 25470402569 | Shamrock Maintenance Office | Convert Truck Barn To Drive Thru, New Heaters In Truck Barn | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
1079 | 1087 | 18470402570 | Denton Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1080 | 1088 | 05470402571 | Littlefield Area Engineer & Maintenance Office | New VCT Floor | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
1081 | 1089 | 05470402572 | Littlefield Area Engineer & Maintenance Office | Replace Windows AE's Office | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1082 | 1090 | 05470402573 | NE Special Crews | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
1083 | 1091 | 05470402574 | NE Special Crews | New VCT Floor | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1084 | 1092 | 05470402575 | NE Special Crews | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
1085 | 1093 | 21470402576 | District Headquarters | Flooring Replacement | Highway Trans. Fund 6 | 7000 | 7000 | TBD | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding
1086 | 1094 | 15470402577 | Boerne Maintenance Office | Interior Paint | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
1087 | 1095 | 38470402578 | TxDOT Flight Services | Building Renovations | Highway Trans. Fund 6 | 430000 | 430000 | TBD | 0% | 0% | 0 | 0 | 430000 | Pending Administrative Funding
1088 | 1096 | 38470402579 | TxDOT Flight Services | New Epoxy Flooring In Hangars 2,3 And 4 | Highway Trans. Fund 6 | 210000 | 210000 | TBD | 0% | 0% | 0 | 0 | 210000 | Pending Administrative Funding
1089 | 1097 | 38470402580 | TxDOT Flight Services | Repair Drainage Issues Around Hangars Water Run Off Going Inside | Highway Trans. Fund 6 | 60000 | 60000 | TBD | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding
1090 | 1098 | 20470402581 | Beaumont Area Engineer & Maintenance Office | Interior Lighting | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1091 | 1099 | 20470402582 | Beaumont Area Engineer & Maintenance Office | Repair Heating System | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
1092 | 1100 | 16470402583 | District Headquarters | Paint Interior Walls At Vehicle Titles And Registration - Corpus Christi DHQ | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1093 | 1101 | 18470402584 | District Headquarters | Flooring Replaced - Remove VCT And Replace With VCT | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1094 | 1102 | 18470402585 | District Headquarters | Paint Exterior | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1095 | 1103 | 02470402586 | Decatur Area Engineer & Maintenance Office | Replace Flooring At Area Engineer And Maintenance - Decatur Area Engineer And Maintenance | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1096 | 1104 | 13470402587 | Fayette Cty Maint. | Interior Renovation (Floors, Ceiling, & Ac Ducts) | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
1097 | 1105 | 20470402588 | Anahuac Maintenance Office | Install Roll-Up Door Opener | Highway Trans. Fund 6 | 3000 | 3000 | TBD | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding
1098 | 1106 | 20470402589 | Liberty Area Engineer & Maintenance Office | Abate Floor Tile | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1099 | 1107 | 20470402590 | Liberty Area Engineer & Maintenance Office | Interior Lighting | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1100 | 1108 | 20470402591 | Liberty Area Engineer & Maintenance Office | Paint Office Interior | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1101 | 1109 | 20470402592 | Liberty Area Engineer & Maintenance Office | Replace Carpet And VCT | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1102 | 1110 | 20470402593 | Liberty Area Engineer & Maintenance Office | Replace Electrical Panels | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1103 | 1111 | 20470402594 | Liberty Area Engineer & Maintenance Office | Rest Room/Shower/Ac/Water Heater | Highway Trans. Fund 6 | 9500 | 9500 | TBD | 0% | 0% | 0 | 0 | 9500 | Pending Administrative Funding
1104 | 1112 | 17470402595 | Bryan Area Engineer & Maintenance Office | Renovate Maintenance Building | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
1105 | 1113 | 17470402596 | Bryan Area Engineer & Maintenance Office | Replace Fuel Canopy - Bryan AEM | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
1106 | 1114 | 17470402597 | Bryan Area Engineer & Maintenance Office | Restroom Remodels, Training Building | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1107 | 1115 | 25470402598 | Clarendon Maintenance Office | Convert Truck Barn To Drive Thru, New Heaters In Truck Barn | Highway Trans. Fund 6 | 200000 | 200000 | TBD | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding
1108 | 1116 | 24470402599 | El Paso (East) Area Engineer & Maintenance Office | Install New Front Doors (Building ) And Secure The Lobby Area | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
1109 | 1117 | 24470402600 | El Paso (East) Area Engineer & Maintenance Office | Modify Interior Doorway, At Stockroom Forklift Access. | Highway Trans. Fund 6 | 5900 | 5900 | TBD | 0% | 0% | 0 | 0 | 5900 | Pending Administrative Funding
1110 | 1118 | 24470402601 | EL PASO (EAST) AREA Area Engineer & Maintenance Office | Building Renovations | Highway Trans. Fund 6 | 120000 | 120000 | TBD | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding
1111 | 1119 | 24470402602 | El Paso (West) Area Engineer & Maintenance Office | Install Truck Lift | Highway Trans. Fund 6 | 12500 | 12500 | TBD | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding
1112 | 1120 | 24470402603 | El Paso (West) Area Engineer & Maintenance Office | Larger Restroom In Our Maintenance Section | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
1113 | 1121 | 02470402604 | District Headquarters | Emergency Generator At Intelligent Transportation Management Center - Fort Worth DHQ | Highway Trans. Fund 6 | 120000 | 120000 | TBD | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding
1114 | 1122 | 22470402605 | Freer | Interior & Exterior Painting & Sheet Metal Painting | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
1115 | 1123 | 22470402606 | Freer | Overhead Projector & Electrical | Highway Trans. Fund 6 | 2500 | 2500 | TBD | 0% | 0% | 0 | 0 | 2500 | Pending Administrative Funding
1116 | 1124 | 38470402607 | CEDAR PARK Research and Technology Center | Interior Renovations | Highway Trans. Fund 6 | 180000 | 180000 | TBD | 0% | 0% | 0 | 0 | 180000 | Pending Administrative Funding
1117 | 1125 | 10470402608 | South Tyler Area Engineer & Maintenance Office | Repaint Bldg. B | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1118 | 1126 | 09470402609 | Hillsboro Area Engineer & Maintenance Office | Upgrade Lab | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
1119 | 1127 | 09470402610 | Hillsboro Area Engineer & Maintenance Office | Replace Plumbing | Highway Trans. Fund 6 | 12000 | 12000 | TBD | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding
1120 | 1128 | 13470402611 | Colorado Cty Maint. | Painting Interior Structure Of Equip Shed | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1121 | 1129 | 16470402612 | Bee Co. | Install Redundant 2000 Gallon Diesel Tank To Existing Fuel Island | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
1122 | 1130 | 18470402613 | Cedar Hill Maintenance Office | Upgrade Electrical | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
1123 | 1131 | 13470402614 | Hallettsville Maintenance Office | Replace Tin At Mechanic Shop | Highway Trans. Fund 6 | 7000 | 7000 | TBD | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding
1124 | 1132 | 13470402615 | Lavaca Cty Maint | Replace Tin & Paint Exterior Struct Of Wash Rack | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1125 | 1133 | 13470402616 | Lavaca Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1126 | 1134 | 13470402617 | Lavaca Cty Maint. | Repair Sheetrock And Paint Walls | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
1127 | 1135 | 19470402618 | District Headquarters | Remodel Inside Of Building | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
1128 | 1136 | 19470402619 | District Headquarters | Restroom Upgrades | Highway Trans. Fund 6 | 181000 | 181000 | TBD | 0% | 0% | 0 | 0 | 181000 | Pending Administrative Funding
1129 | 1137 | 17470402620 | Brenham Area Engineer & Maintenance Office | Enclose Two Bays Of Equipment Shed | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1130 | 1138 | 17470402621 | Brenham Area Engineer & Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1131 | 1139 | 17470402622 | Brenham Area Engineer & Maintenance Office | Install Electric Door Openers For Roll-Up Doors | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
1132 | 1140 | 17470402623 | Brenham Area Engineer & Maintenance Office | Replace Windows On Storage Shed | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1133 | 1141 | 08470402624 | Abilene Maintenance Office | Install Double Pane Glass Windows In Store Front Entry Area | Highway Trans. Fund 6 | 4500 | 4500 | TBD | 0% | 0% | 0 | 0 | 4500 | Pending Administrative Funding
1134 | 1142 | 17470402625 | Fairfield Maintenance Office | Close In Part Of Shed For Work Area | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
1135 | 1143 | 22470402626 | La Pryon on HWY 57 | Install Interior Lighting | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
1136 | 1144 | 22470402627 | La Pryor Maintenance Office | Renovation Conference Room | Highway Trans. Fund 6 | 150000 | 150000 | TBD | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding
1137 | 1145 | 22470402628 | La Pryor Maintenance Office | Renovate Maintenance Facility | Highway Trans. Fund 6 | 125000 | 125000 | TBD | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding
1138 | 1146 | 22470402629 | La Pryor Maintenance Office | Retrofit Existing Office Space | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
1139 | 1147 | 11470402630 | Hemphill Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1140 | 1148 | 11470402631 | Hemphill Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1141 | 1149 | 11470402632 | Groveton Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1142 | 1150 | 11470402633 | Groveton Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1143 | 1151 | 16470402634 | Kingsville Maintenance Office | Repair Plumbing System At Truck Wash Bay - Kingsville MNT | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
1144 | 1152 | 16470402635 | Robstown Maintenance Office | Repair Plumbing System At Truck Wash Bay - Robstown Maintenance | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
1145 | 1153 | 22470402636 | Laredo Auto Shop | Bay Wash Repairs | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
1146 | 1154 | 18470402637 | Corsicana Area Engineer & Maintenance Office | Floor Tile Removal - Corridors Only (Stain Concrete) | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1147 | 1155 | 18470402638 | Corsicana Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1148 | 1156 | 12470402639 | District Headquarters | Install Safety Flooring | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
1149 | 1157 | 12470402640 | District Headquarters | Renovate Restrooms (Locker Rooms) | Highway Trans. Fund 6 | 42000 | 42000 | TBD | 0% | 0% | 0 | 0 | 42000 | Pending Administrative Funding
1150 | 1158 | 12470402641 | District Headquarters | Replace Emergency Exit Signage | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
1151 | 1159 | 12470402642 | District Headquarters | Upgrade Lighting (LED) | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
1152 | 1160 | 17470402643 | Brenham Area Engineer & Maintenance Office | Add Network Connections To Lab Area | Highway Trans. Fund 6 | 7500 | 7500 | TBD | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding
1153 | 1161 | 17470402644 | Brenham Area Engineer & Maintenance Office | Replace Sidewalk Lab To Area Office | Highway Trans. Fund 6 | 12500 | 12500 | TBD | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding
1154 | 1162 | 17470402645 | Hearne Area Engineer & Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1155 | 1163 | 17470402646 | Hearne Area Engineer & Maintenance Office | New Fuel Canopy - Hearne AEM | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
1156 | 1164 | 17470402647 | Huntsville Area Engineer & Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1157 | 1165 | 16470402648 | Alice Area Engineer & Maintenance Office | Install Electrical Wiring - Alice AEM | Highway Trans. Fund 6 | 40000 | 40000 | TBD | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding
1158 | 1166 | 16470402649 | Alice Area Engineer & Maintenance Office | Repair Sewer System - Alice AEM | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1159 | 1167 | 12470402650 | Humble Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 6 | 500000 | 500000 | TBD | 0% | 0% | 0 | 0 | 500000 | Pending Administrative Funding
1160 | 1168 | 22470402651 | Del Rio Maintenance Office | Demo (D) And Install (I) Of 2 Lamp T8 Light Fixture (D-2 & I-6 @ Fueling Station; D-57 & I-45 @ Warehouse; And D-39 & I-31 @ MNT Vehicle | Highway Trans. Fund 6 | 18000 | 18000 | TBD | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding
1161 | 1169 | 11470402652 | District Headquarters | Renovate Interior | Highway Trans. Fund 6 | 8000 | 8000 | TBD | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding
1162 | 1170 | 06470402653 | Ft Stockton Area Engineer & Maintenance Office | Paint Cat-Walk | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1163 | 1171 | 15470402654 | West Bexar Maintenance Office | Interior Paint | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1164 | 1172 | 15470402655 | West Bexar Maintenance Office | Retrofit Shop Bay To Meeting Room | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
1165 | 1173 | 38470402656 | Riverside Annex I RA118 | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1166 | 1174 | 38470402657 | Riverside Annex II RA150-200 | EOC Technology Renovation (Electronics) | Highway Trans. Fund 6 | 60000 | 60000 | TBD | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding
1167 | 1175 | 38470402658 | Riverside Annex II RA150-200 | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
1168 | 1176 | 03470402659 | Bowie Maintenance Office | Upgrade Electrical | Highway Trans. Fund 6 | 80000 | 80000 | TBD | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding
1169 | 1177 | 16470402660 | Nueces West | Install Storm Shutters On All Windows And Doors | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
1170 | 1178 | 11470402661 | Shepherd Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 6 | 15000 | 15000 | TBD | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding
1171 | 1179 | 21470402662 | Edcouch Maintenance Office | Bird Net For Truck Wash And Equip. Shed | Highway Trans. Fund 6 | 1000 | 1000 | TBD | 0% | 0% | 0 | 0 | 1000 | Pending Administrative Funding
1172 | 1180 | 21470402663 | Edcouch Maintenance Office | Repaint Generator | Highway Trans. Fund 6 | 500 | 500 | TBD | 0% | 0% | 0 | 0 | 500 | Pending Administrative Funding
1173 | 1181 | 21470402664 | Edcouch Maintenance Office | Repair Wall Packs | Highway Trans. Fund 6 | 2500 | 2500 | TBD | 0% | 0% | 0 | 0 | 2500 | Pending Administrative Funding
1174 | 1182 | 17470402665 | District Headquarters | Add Awning To Shop Building | Highway Trans. Fund 6 | 35000 | 35000 | TBD | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding
1175 | 1183 | 17470402666 | District Headquarters | Administration Bldg Foundation Repair | Highway Trans. Fund 6 | 50000 | 50000 | TBD | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding
1176 | 1184 | 17470402667 | District Headquarters | Awnings Between Buildings W/ Lights | Highway Trans. Fund 6 | 30000 | 30000 | TBD | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding
1177 | 1185 | 17470402669 | District Headquarters | Install A/C System To HQ Warehouse | Highway Trans. Fund 6 | 25000 | 25000 | TBD | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding
1178 | 1186 | 17470402670 | District Headquarters | New Canopy And Lights | Highway Trans. Fund 6 | 12500 | 12500 | TBD | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding
1179 | 1187 | 17470402671 | District Headquarters | New Fuel Canopy | Highway Trans. Fund 6 | 45000 | 45000 | TBD | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding
1180 | 1188 | 17470402672 | District Headquarters | Overhead Crane Shops | Highway Trans. Fund 6 | 75000 | 75000 | TBD | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding
1181 | 1189 | 17470402673 | District Headquarters | Paint Signal Warehouse Walls | Highway Trans. Fund 6 | 10000 | 10000 | TBD | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding
1182 | 1190 | 17470402674 | District Headquarters | Repair Admin Building Water Intrusion | Highway Trans. Fund 6 | 20000 | 20000 | TBD | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding
1183 | 1191 | 17470402675 | District Headquarters | Upgrade Used Oil & Antifreeze Containers | Highway Trans. Fund 6 | 5000 | 5000 | TBD | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding
1184 | 1192 | 21470402676 | Roma Area Engineer & Maintenance Office | Building Finish Out | Highway Trans. Fund 6 | 120000 | 120000 | TBD | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding
1185 | 1193 | 38470402678 | Statewide | Emergency Repairs - Statewide | Highway Trans. Fund 6 | 50866849 | 56927954.98 | TBD | 0% | 0% | 0 | 0 | 56927954.98 | Pending Administrative Funding
PROJECTS PENDING FUNDING AVAILABILITY | [5 empty] | 155244129 | 161305234.98
REMOVED PROJECTS THAT WERE EITHER CANCELLED OR FUNDED WITH OTHER SOURCES
R1 | R1 | 38470402968 | Various | Condition Assessment |  | 5000000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | PM/MR funds
R2 | R2 | 38470402969 | Various | Condition Assessment Software |  | 1000000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | PM/MR funds
R3 | R3 | 19470401489 | Atlanta District Headquarters | Upgrade Security (C-CURE) |  | 350000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | FY15 Funds
R4 | R4 | 06470401497 | Andrews Maintenance Office | Install Motion Sensors On Install Automatic Gate |  | 1500 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | PM/MR funds
R5 | R5 | 10470401503 | Tyler District Headquarters | Replace Boilers at Administration Office |  | 180000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | PM/MR funds
R6 | R6 | 06470401515 | McCamey Maintenance Office | Install Motion Sensors On Install Automatic Gate |  | 1500 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | PM/MR funds
R7 | R7 | 09470401519 | Waco District Headquarters | Upgrade Security (C-CURE) |  | 350000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | FY15 Funds
R8 | R8 | 06470401525 | Stanton Maintenance Office | Install Motion Sensors On Install Automatic Gate |  | 1500 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | PM/MR funds
R9 | R9 | 20470401542 | Anahuac Maintenance Office | Install Card Reader Access |  | 12000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R10 | R10 | 18470401545 | Dallas District Headquarters | Relocate And Add HVAC To Break Room |  | 15000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R11 | R11 | 18470401547 | Dallas District Headquarters | Fence - Repair Chain Link/Top Rail At Easement |  | 10000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R12 | R12 | 06470401555 | Kermit Maintenance Office | Install Motion Sensors On Install Automatic Gate |  | 1500 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | PM/MR funds
R13 | R13 | 08470401578 | Colorado City Maintenance Office | Replace Roof |  | 40000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R14 | R14 | 08470401579 | Abilene District Headquarters | Modifications/Upgrade HVAC |  | 120000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R15 | R15 | 08470401580 | Abilene District Headquarters | Upgrade Security (C-CURE) |  | 350000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | FY15 Funds
R16 | R16 | 06470401616 | Monahans Maintenance Office | Install Motion Sensors On Install Automatic Gate |  | 1500 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | PM/MR funds
R17 | R17 | 03470401638 | Wichita Falls District Headquarters | In-Ground Shelter |  | 144125 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R18 | R18 | 13470401640 | Matagorda Cty Maint. | Replace APU (Generator) |  | 10000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R19 | R19 | 04470401642 | Amarillo District Headquarters | Upgrade Security (C-CURE) |  | 350000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | FY15 Funds
R20 | R20 | 18470401676 | Rockwall Maintenance Office | New Generator - Diesel |  | 25000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R21 | R21 | 11470401682 | Lufkin Maintenance Office | Replace Emergency Generator |  | 38000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R22 | R22 | 38470401688 | Camp Hubbard State Headquarters | Modifications/Upgrade Electrical |  | 517000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R23 | R23 | 24470401697 | Terlingua Sub-Section | Modifications/Upgrade Electrical |  | 150000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R24 | R24 | 16470401708 | Corpus Christi District Headquarters | Replace Roof |  | 300000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R25 | R25 | 24470401718 | Presidio Maintenance Office | Replace Roof |  | 285000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R26 | R26 | 21470401721 | Laguna Vista Maintenance Office Sub-Section | Replace Generator |  | 15000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R27 | R27 | 16470401728 | Corpus Christi Area Engineer & Maintenance Office | Replace Roof At Area Engineer And Maintenance - Corpus Christi AEM |  | 24000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R28 | R28 | 16470401729 | Corpus Christi Area Engineer & Maintenance Office | Replace\New Security Fence - Corpus Christi AEM |  | 17000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
R29 | R29 | 06470402203 | District Headquarters | Repair/Replace Atg System On Above Ground Fuel Tanks |  | 12000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | Cancelled
PROJECTS CANCELLED OR FUNDED WITH OTHER SOURCES | [5 empty] | 9321625 | 0
TOTAL OF ORIGINAL VS. CURRENT ESTIMATES | [5 empty] | 200000000 | 199999999.7
Note on B7: Diana Miller: Now Ordering based on Start Sheet Dates

## TxDOT 12.15
| Agency: | Texas Department of Transportation #601
| Date: | 2015-12-01 |  |  |  |  | Draft version: | 2015-12-01
| Prepared by: | Diana Miller
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q1 AY16) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
ORIG #
E1 | 20470402970 | Beaumont District Headquarters | Remove and Install 10 and 8.5 ton Roof Top HVAC Units | Highway Trans. Fund 6 | 0 | 21000 | 2015-12-23 | 0% | 0% | 21000 | 0 | 0 | Unplanned Emergency - Funded out of existing operating fund to be transferred to this program once funds have been released. | 0
E2 | 01470402967 | Paris District Headquarters | Shop Floor Replacement | Highway Trans. Fund 6 | 0 | 50000 | 2015-12-31 | 100% | 0% | 50000 | 0 | 0 | Unplanned Emergency - Funded out of existing operating fund to be transferred to this program once funds have been released. | 0
E3 | 03470402972 | Wichita Falls Admin Bldg | Foundation Repair at DHQ | Highway Trans. Fund 6 | 0 | 18000 | 2015-12-18 | 100% | 50% | 18000 | 0 | 0 | Unplanned Emergency - Funded out of existing operating fund to be transferred to this program once funds have been released. | 0
E4 | 03470402975 | Henrietta Maintenance Office | Stairs & Handicap Ramp for Mod Building | Highway Trans. Fund 6 | 0 | 24105 | 2015-12-23 | 0% | 0% | 24105 | 0 | 0 | Unplanned Emergency - Funded out of existing operating fund to be transferred to this program once funds have been released. | 0
E5 | 10470402976 | Athens Regional Distribution Center | Fire supression system water line | Highway Trans. Fund 6 | 0 | 200000 | 2016-06-30 | 50% | 0% | 200000 | 0 | 0 | Unplanned Emergency - Funded out of existing operating fund to be transferred to this program once funds have been released. | 0
1 | 19470401488 | Atlanta District Headquarters | Install LED Parking Lot Lighting | Highway Trans. Fund 6 | 85000 | 85000 | mm/dd/yy | 0% | 0% | 0 | 0 | 85000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 3
2 | 19470401489 | Atlanta District Headquarters | Exterior lighting and fencing | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Partially completed with FY15 Funds | 4
3 | 01470401490 | Paris District Headquarters | Replace Roof And Walls | Highway Trans. Fund 6 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 5
4 | 01470401491 | Paris District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 6
5 | 22470401492 | Del Rio Maintenance Office | Replace Generators (x2) | Highway Trans. Fund 6 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 7
6 | 38470401493 | Camp Hubbard State Headquarters | Replace Or Rebuild Existing Generator | Highway Trans. Fund 6 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 8
7 | 11470401494 | Lufkin District Headquarters | Replace HVAC Units | Highway Trans. Fund 6 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 9
8 | 11470401495 | Lufkin District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 10
9 | 16470401496 | Rockport Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 11
10 | 08470401498 | Jayton Maintenance Office | New Perimeter Fence | Highway Trans. Fund 6 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 13
11 | 04470401499 | Dumas Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 14
12 | 10470401500 | Tyler District Headquarters | Replace Roof On Shop | Highway Trans. Fund 6 | 500000 | 500000 | mm/dd/yy | 0% | 0% | 0 | 0 | 500000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 15
13 | 03470401501 | Bowie Maintenance Office | New Fencing | Highway Trans. Fund 6 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 16
14 | 08470401502 | Gail Maintenance Office | AC Unit Needs Replacing (Old R22 Unit) | Highway Trans. Fund 6 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 17
15 | 38470401504 | Camp Hubbard State Headquarters | Demolish Existing Building and Convert To Parking | Highway Trans. Fund 6 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 19
16 | 38470401505 | Camp Hubbard State Headquarters | Install Generator For Data Center (Camp Hubbard Bldg. 6) | Highway Trans. Fund 6 | 517000 | 517000 | mm/dd/yy | 0% | 0% | 0 | 0 | 517000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 20
17 | 38470401506 | Camp Hubbard State Headquarters | Replace Fence Along Mopac With Standard Fence | Highway Trans. Fund 6 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 21
18 | 38470401507 | Camp Hubbard State Headquarters | Replace Roof (C.H. Bldg. 6) | Highway Trans. Fund 6 | 285000 | 285000 | mm/dd/yy | 0% | 0% | 0 | 0 | 285000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 22
19 | 38470401508 | Camp Hubbard State Headquarters | Upgrade Obsolete Johnson Control Panels | Highway Trans. Fund 6 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 23
20 | 04470401510 | Darouzett Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 25
21 | 04470401511 | Darouzett Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 26
22 | 04470401512 | Gruver Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 27
23 | 04470401513 | Panhandle Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 28
24 | 04470401514 | Panhandle Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 29
25 | 09470401517 | Waco District Headquarters | Fence in Front of Facility | Highway Trans. Fund 6 | 110000 | 110000 | mm/dd/yy | 0% | 0% | 0 | 0 | 110000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 32
26 | 09470401518 | Waco District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 33
27 | 09470401519 | Waco District Headquarters | Exterior lighting and fencing | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Partially completed with FY15 Funds | 34
28 | 21470401526 | San Isidro Maintenance Office Sub-Section | Replace Existing Generator | Highway Trans. Fund 6 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 41
29 | 08470401527 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 42
30 | 19470401530 | Atlanta District Headquarters | Replace 1 HVAC System | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 45
31 | 16470401532 | Jim Wells Co. | Install Yard Illumination In Back Yard Area | Highway Trans. Fund 6 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 47
32 | 16470401533 | Live Oak Co. | Install Exterior Lighting In Back Yard Area | Highway Trans. Fund 6 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 48
33 | 16470401535 | Nueces East | Replace Existing Secuity Fence Around Perimeter Of Property | Highway Trans. Fund 6 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 50
34 | 16470401536 | San Patricio Co | Replace Existing Secuity Fence Around Perimeter Of Property | Highway Trans. Fund 6 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 51
35 | 21470401538 | Zapata Maintenance Office Sub-Section | Replace Generators | Highway Trans. Fund 6 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 53
36 | 21470401539 | Zapata Maintenance Office Sub-Section | Security Fence | Highway Trans. Fund 6 | 39800 | 39800 | mm/dd/yy | 0% | 0% | 0 | 0 | 39800 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 54
37 | 04470401540 | Claude Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 55
38 | 20470401541 | Anahuac Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 56
39 | 20470401542 | Anahuac Maintenance Office | Install Card Reader Access | Highway Trans. Fund 6 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 57
40 | 20470401543 | Woodville Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 58
41 | 25470401544 | Paducah Maintenance Office | New Electronic Gate To Yard, Redesign Parking Area | Highway Trans. Fund 6 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 59
42 | 18470401545 | Dallas District Headquarters | Relocate And Add HVAC To Break Room | Highway Trans. Fund 6 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 60
43 | 18470401546 | Dallas District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 61
44 | 18470401547 | Dallas District Headquarters | Fence - Repair Chain Link/Top Rail At Easement | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 62
45 | 22470401549 | Brackettville | 3-Ton Standalone Unit (Duct Work, Vents, Air Handler, Etc) | Highway Trans. Fund 6 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 64
46 | 05470401553 | Lubbock District Headquarters | Replace Roof | Highway Trans. Fund 6 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 68
47 | 21470401559 | Hebbronville Area Engineer & Maintenance Office | Upgrade Lighting And Gates | Highway Trans. Fund 6 | 0 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 74
48 | 08470401580 | Abilene District Headquarters | Exterior lighting and fencing | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Partially completed with FY15 Funds | 95
49 | 02470401585 | Fort Worth District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 100
50 | 06470401587 | Odessa District Headquarters | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 102
51 | 06470401588 | Odessa District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 103
52 | 15470401602 | San Antonio District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 117
53 | 04470401642 | Amarillo District Headquarters | Exterior lighting and fencing | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Partially completed with FY15 Funds | 157
54 | 16470401650 | Corpus Christi District Headquarters | Replace Roof | Highway Trans. Fund 6 | 225000 | 225000 | mm/dd/yy | 0% | 0% | 0 | 0 | 225000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 165
55 | 16470401655 | Corpus Christi District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 170
56 | 13470401661 | Calhoun Cty Maint. | Convert Flat Roof To Gable Style | Highway Trans. Fund 6 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 176
57 | 21470401684 | Pharr District Headquarters/Area Engineer & Maintenance Office | HVAC With Study/Assessment | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 199
58 | 38470401688 | Camp Hubbard State Headquarters | Modifications/Upgrade Electrical | Highway Trans. Fund 6 | 517000 | 517000 | mm/dd/yy | 0% | 0% | 0 | 0 | 517000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 203
59 | 38470401689 | Camp Hubbard State Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 287500 | 287500 | mm/dd/yy | 0% | 0% | 0 | 0 | 287500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 204
60 | 15470401690 | Devine Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 205
61 | 04470401693 | Hereford Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 208
62 | 20470401694 | Kountze Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 209
63 | 20470401695 | Liberty Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 210
64 | 20470401696 | Liberty Area Engineer & Maintenance Office | Replace HVAC Units | Highway Trans. Fund 6 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 211
65 | 24470401697 | Terlingua Sub-Section | Modifications/Upgrade Electrical | Highway Trans. Fund 6 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 212
66 | 07470401698 | San Angelo District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 220000 | 220000 | mm/dd/yy | 0% | 0% | 0 | 0 | 220000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 213
67 | 07470401699 | San Angelo District Headquarters | Replace 2 Penthouse Type HVAC Units | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 214
68 | 07470401700 | San Angelo District Headquarters | Replace Roof | Highway Trans. Fund 6 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 215
69 | 15470401701 | Pearsall Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | mm/dd/yy | 0% | 0% | 0 | 0 | 65000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 216
70 | 13470401702 | Wharton Cty Maint. | Install ADA Into Time Room | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 217
71 | 08470401703 | Snyder Maintenance Office | Replace AC Unit (Old R22 Unit) | Highway Trans. Fund 6 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 218
72 | 04470401704 | Perryton Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 219
73 | 04470401705 | Perryton Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 220
74 | 16470401708 | Corpus Christi District Headquarters | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 223
75 | 21470401710 | Brownsville Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 225
76 | 21470401711 | Brownsville Maintenance Office | Upgrade Fencing | Highway Trans. Fund 6 | 39000 | 39000 | mm/dd/yy | 0% | 0% | 0 | 0 | 39000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 226
77 | 21470401712 | Mission Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 227
78 | 21470401713 | Mission Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 228
79 | 24470401718 | Presidio Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 285000 | 285000 | mm/dd/yy | 0% | 0% | 0 | 0 | 285000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 233
80 | 19470401719 | Daingerfield Maintenance Office | Replaces HVAC System | Highway Trans. Fund 6 | 16000 | 16000 | mm/dd/yy | 0% | 0% | 0 | 0 | 16000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 234
81 | 38470401720 | Riverside Annex II RA150-200 | Replacement of R22 to 410 HVAC System | Highway Trans. Fund 6 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 235
82 | 21470401721 | Laguna Vista Maintenance Office Sub-Section | Replace Generator | Highway Trans. Fund 6 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 236
83 | 04470401722 | Groom Maintenance Office | HVAC Replacement | Highway Trans. Fund 6 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 237
84 | 04470401723 | Groom Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 238
85 | 15470401724 | Uvalde Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 239
86 | 06470401725 | Midland Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | mm/dd/yy | 0% | 0% | 0 | 0 | 65000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 240
87 | 03470401726 | Vernon Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 241
88 | 16470401728 | Corpus Christi Area Engineer & Maintenance Office | Replace Roof At Area Engineer And Maintenance - Corpus Christi AEM | Highway Trans. Fund 6 | 24000 | 24000 | mm/dd/yy | 0% | 0% | 0 | 0 | 24000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 243
89 | 16470401729 | Corpus Christi Area Engineer & Maintenance Office | Replace\New Security Fence - Corpus Christi AEM | Highway Trans. Fund 6 | 17000 | 17000 | mm/dd/yy | 0% | 0% | 0 | 0 | 17000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 244
90 | 16470401730 | Nueces East | Replace Roof On The Maintenance Building | Highway Trans. Fund 6 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 245
91 | 19470401731 | Carthage Maintenance Office | Replace HVAC Systems | Highway Trans. Fund 6 | 16000 | 16000 | mm/dd/yy | 0% | 0% | 0 | 0 | 16000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 246
92 | 08470401733 | Aspermont Maintenance Office | Replace AC Unit (R22 Unit) | Highway Trans. Fund 6 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 248
93 | 04470401734 | Dalhart Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 249
94 | 04470401735 | Dalhart Maintenance Office | Roof | Highway Trans. Fund 6 | 175000 | 175000 | mm/dd/yy | 0% | 0% | 0 | 0 | 175000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 250
95 | 19470401736 | Jefferson Maintenance Office | Replace HVAC | Highway Trans. Fund 6 | 8500 | 8500 | mm/dd/yy | 0% | 0% | 0 | 0 | 8500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 251
96 | 05470401737 | Lubbock District Headquarters | Install New Gate Opener To Existing Gate | Highway Trans. Fund 6 | 6500 | 6500 | mm/dd/yy | 0% | 0% | 0 | 0 | 6500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 252
97 | 05470401738 | Lubbock District Headquarters | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | mm/dd/yy | 0% | 0% | 0 | 0 | 65000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 253
98 | 15470401739 | San Antonio District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 254
99 | 21470401775 | Pharr District Headquarters | Complete Power Project (Single, Electrical Power Upgrade Project, To Encompass All Of The Electrical Issues To Include Study/Assessment) | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 290
100 | 17470402668 | Bryan District Headquarters | Improve Lab Ventilation | Highway Trans. Fund 6 | 5000 | 60000 | mm/dd/yy | 0% | 0% | 0 | 0 | 60000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 1183
Phase I $15,000,000 | [13 empty] | 0
101 | 05470401554 | Lubbock District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 69
102 | 19470401567 | Atlanta District Headquarters | Replace 2 HVAC Systems | Highway Trans. Fund 6 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 82
103 | 05470401568 | Post RDC | Replace Generator | Highway Trans. Fund 6 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 83
104 | 38470401570 | Camp Hubbard State Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 85
105 | 10470401571 | Tyler District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 180000 | 180000 | mm/dd/yy | 0% | 0% | 0 | 0 | 180000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 86
106 | 10470401572 | Tyler District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 87
107 | 10470401573 | Tyler District Headquarters | Replace 5 Air Handler Units | Highway Trans. Fund 6 | 85000 | 85000 | mm/dd/yy | 0% | 0% | 0 | 0 | 85000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 88
108 | 10470401574 | Tyler District Headquarters | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 89
109 | 10470401575 | North Tyler Maintenance Office | Replace Roof At North Tyler Fuel Station | Highway Trans. Fund 6 | 85000 | 85000 | mm/dd/yy | 0% | 0% | 0 | 0 | 85000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 90
110 | 10470401576 | Tyler District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 91
111 | 08470401577 | Colorado City Maintenance Office | Replace AC Unit (R22 Unit) | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 92
112 | 08470401578 | Colorado City Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 93
113 | 08470401579 | Abilene District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 6 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 94
114 | 02470401581 | Fort Worth District Headquarters | Chiller Replacement | Highway Trans. Fund 6 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 96
115 | 02470401582 | Fort Worth District Headquarters | Exterior Lighting | Highway Trans. Fund 6 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 97
116 | 02470401583 | Fort Worth District Headquarters | Replace Roof (3 Buildings) | Highway Trans. Fund 6 | 492000 | 492000 | mm/dd/yy | 0% | 0% | 0 | 0 | 492000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 98
117 | 02470401584 | Fort Worth District Headquarters | Roof Replacement and Interior upgrade | Highway Trans. Fund 6 | 480000 | 980000 | mm/dd/yy | 0% | 0% | 0 | 0 | 980000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 99
118 | 07470401589 | Junction Area Engineer & Maintenance Office | New Roof | Highway Trans. Fund 6 | 16200 | 16200 | mm/dd/yy | 0% | 0% | 0 | 0 | 16200 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 104
119 | 15470401590 | San Antonio District Headquarters | Install All New Hot And Chill Water Valves And Connect To New Control System | Highway Trans. Fund 6 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 105
120 | 15470401591 | San Antonio District Headquarters | New Boiler | Highway Trans. Fund 6 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 106
121 | 15470401592 | San Antonio District Headquarters | New HVAC In Shop Restrooms | Highway Trans. Fund 6 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 107
122 | 15470401593 | San Antonio District Headquarters | Replace 60 Ton Chiller | Highway Trans. Fund 6 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 108
123 | 15470401594 | San Antonio District Headquarters | Replace All VAV and Upgrade To Electrical Control | Highway Trans. Fund 6 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 109
124 | 15470401595 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 110
125 | 15470401596 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 111
126 | 15470401597 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 112
127 | 15470401598 | San Antonio District Headquarters | Replace Roof | Highway Trans. Fund 6 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 113
128 | 15470401599 | San Antonio District Headquarters | Replace Roof - Buildings 1, 3 & 4 | Highway Trans. Fund 6 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 114
129 | 15470401600 | San Antonio District Headquarters | Replace Roof - Buildings 8 & 9 | Highway Trans. Fund 6 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 115
130 | 15470401601 | San Antonio District Headquarters | Replace Roof Top Package HVAC 10 Ton System | Highway Trans. Fund 6 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 116
131 | 08470401604 | Abilene District Headquarters | Replace Generator | Highway Trans. Fund 6 | 58000 | 58000 | mm/dd/yy | 0% | 0% | 0 | 0 | 58000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 119
132 | 08470401605 | Abilene District Headquarters | Replace Roof | Highway Trans. Fund 6 | 65000 | 65000 | mm/dd/yy | 0% | 0% | 0 | 0 | 65000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 120
133 | 08470401606 | Abilene District Headquarters | Replace Roof (Warehouse) | Highway Trans. Fund 6 | 130000 | 130000 | mm/dd/yy | 0% | 0% | 0 | 0 | 130000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 121
134 | 08470401607 | Special Crews Building | Reroof Building Or Repatch In Areas | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 122
135 | 14470401610 | Austin District Headquarters | Replace Generator | Highway Trans. Fund 6 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 125
136 | 14470401611 | Austin District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 126
137 | 14470401613 | to be determined | New Generators/Upgrades | Highway Trans. Fund 6 | 425000 | 425000 | mm/dd/yy | 0% | 0% | 0 | 0 | 425000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 128
138 | 06470401615 | Odessa District Headquarters | Replace Main HVAC Multi-Zone Units | Highway Trans. Fund 6 | 160000 | 160000 | mm/dd/yy | 0% | 0% | 0 | 0 | 160000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 130
139 | 12470401620 | Humble Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 87000 | 87000 | mm/dd/yy | 0% | 0% | 0 | 0 | 87000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 135
140 | 15470401617 | Seguin Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 132
141 | 10470401621 | Tyler District Headquarters | Replace Roof On Old Lab | Highway Trans. Fund 6 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 136
142 | 04470401619 | Canyon Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 134
143 | 08470401623 | Big Spring Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 60000 | 60000 | mm/dd/yy | 0% | 0% | 0 | 0 | 60000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 138
144 | 04470401625 | Borger Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 140
145 | 04470401626 | Borger Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 141
146 | 04470401627 | Pampa Area Engineer & Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 142
147 | 04470401628 | Pampa Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 143
148 | 04470401629 | Pampa Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 175000 | 175000 | mm/dd/yy | 0% | 0% | 0 | 0 | 175000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 144
149 | 20470401630 | Beaumont Area Engineer & Maintenance Office | Install Gates | Highway Trans. Fund 6 | 16000 | 16000 | mm/dd/yy | 0% | 0% | 0 | 0 | 16000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 145
150 | 20470401631 | Beaumont District Headquarters | A/C Unit Replacement | Highway Trans. Fund 6 | 85000 | 85000 | mm/dd/yy | 0% | 0% | 0 | 0 | 85000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 146
151 | 20470401632 | Beaumont District Headquarters | Fence Repairs | Highway Trans. Fund 6 | 9000 | 9000 | mm/dd/yy | 0% | 0% | 0 | 0 | 9000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 147
152 | 20470401633 | Beaumont District Headquarters | Install Gates & Install/Repair Fencing | Highway Trans. Fund 6 | 24000 | 24000 | mm/dd/yy | 0% | 0% | 0 | 0 | 24000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 148
153 | 20470401634 | Beaumont District Headquarters | Modifications/Upgrade Electrical | Highway Trans. Fund 6 | 60000 | 60000 | mm/dd/yy | 0% | 0% | 0 | 0 | 60000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 149
154 | 20470401635 | Beaumont District Headquarters | Replace Roof | Highway Trans. Fund 6 | 95000 | 95000 | mm/dd/yy | 0% | 0% | 0 | 0 | 95000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 150
155 | 20470401636 | Beaumont District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 151
156 | 03470401638 | Wichita Falls District Headquarters | In-Ground Shelter | Highway Trans. Fund 6 | 144125 | 144125 | mm/dd/yy | 0% | 0% | 0 | 0 | 144125 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 153
157 | 03470401639 | Wichita Falls District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 154
158 | 13470401640 | Matagorda Cty Maint. | Replace APU (Generator) | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 155
159 | 04470401641 | Amarillo District Headquarters | Upgrade Generator | Highway Trans. Fund 6 | 400000 | 400000 | mm/dd/yy | 0% | 0% | 0 | 0 | 400000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 156
160 | 19470401643 | Atlanta District Headquarters | Building 300 Storage Needs Replace Roof | Highway Trans. Fund 6 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 158
161 | 19470401644 | Atlanta District Headquarters | Replace 3 HVAC Systems | Highway Trans. Fund 6 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 159
162 | 19470401645 | Atlanta District Headquarters | Replace Generator | Highway Trans. Fund 6 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 160
163 | 19470401646 | Atlanta District Headquarters | Replace HVAC System | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 161
164 | 16470401648 | Corpus Christi District Headquarters | Modifications/Upgrade Electrical | Highway Trans. Fund 6 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 163
165 | 16470401649 | Corpus Christi District Headquarters | Replace Existing Security And Access Control System To C-Cure | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 164
166 | 16470401651 | Corpus Christi District Headquarters | Replace Roof On The District Hq Administration Bldg | Highway Trans. Fund 6 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 166
167 | 16470401652 | Corpus Christi District Headquarters | Replace Roof On The Lab Building | Highway Trans. Fund 6 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 167
168 | 16470401653 | Corpus Christi District Headquarters | Replace Roof On The Special Crews Office Building | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 168
169 | 16470401654 | Corpus Christi District Headquarters | Upgrade HQ Campus Emergency Generator | Highway Trans. Fund 6 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 169
170 | 05470401656 | Plains Maintenance Office | New HVAC Relocate From Roof | Highway Trans. Fund 6 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 171
171 | 05470401657 | Plains Maintenance Office | Replace Roof | Highway Trans. Fund 6 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 172
172 | 11470401658 | Crockett Maintenance Office | Replace Emergency Generator | Highway Trans. Fund 6 | 38000 | 38000 | mm/dd/yy | 0% | 0% | 0 | 0 | 38000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 173
173 | 11470401659 | Lufkin District Headquarters | Replace HVAC Controls | Highway Trans. Fund 6 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 174
174 | 21470401660 | Pharr District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 175
175 | 13470401662 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 177
176 | 20470401663 | Port Arthur Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 178
177 | 20470401664 | Port Arthur Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 6 | 18000 | 18000 | mm/dd/yy | 0% | 0% | 0 | 0 | 18000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 179
178 | 20470401665 | Port Arthur Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 80000 | 80000 | mm/dd/yy | 0% | 0% | 0 | 0 | 80000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 180
179 | 23470401667 | Brownwood District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 182
180 | 18470401669 | Waxahachie Area Engineer & Maintenance Office | HVAC - Split Unit (Meeting & Stock Rooms) | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 184
181 | 22470401670 | Del Rio Maintenance Office | Replace HVAC For Sign Shop | Highway Trans. Fund 6 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 185
182 | 11470401671 | Lufkin District Headquarters | Replace Boiler At Warehouse | Highway Trans. Fund 6 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 186
183 | 04470401672 | Amarillo District Headquarters | Install Rooftop HVAC To Heat And Cool Shop | Highway Trans. Fund 6 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 187
184 | 19470401673 | Mt Pleasant Area Engineer & Maintenance Office | Replace 1 HVAC System | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 188
185 | 18470401674 | Rockwall Maintenance Office | Apply Ceramic Roof Coating | Highway Trans. Fund 6 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 189
186 | 18470401675 | Rockwall Maintenance Office | Fence - Repair/Replace Chain Link/Rails | Highway Trans. Fund 6 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 190
187 | 18470401676 | Rockwall Maintenance Office | New Generator - Diesel | Highway Trans. Fund 6 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 191
188 | 18470401677 | Rockwall Maintenance Office | HVAC - Upgrade Existing System | Highway Trans. Fund 6 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 192
189 | 05470401680 | NE Maint. Office | Retrofit Existing Gate Opener W/C-Cure | Highway Trans. Fund 6 | 18000 | 18000 | mm/dd/yy | 0% | 0% | 0 | 0 | 18000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 195
190 | 11470401682 | Lufkin Maintenance Office | Replace Emergency Generator | Highway Trans. Fund 6 | 38000 | 38000 | mm/dd/yy | 0% | 0% | 0 | 0 | 38000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 197
191 | 21470401683 | Pharr District Headquarters | Replace Roof | Highway Trans. Fund 6 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 198
192 | 07470401685 | San Angelo District Headquarters | Replace Roof | Highway Trans. Fund 6 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 200
193 | 07470401686 | San Angelo District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 201
194 | 15470401687 | Kerrville Area Engineer & Maintenance Office | Install Gate Operator & Exterior Lighting | Highway Trans. Fund 6 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 202
195 | 04470401691 | Canadian Maintenance Office | Replace Generator | Highway Trans. Fund 6 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 206
196 | 04470401692 | Amarillo Area Engineer and Maintenance Office | Install Automatic Gate | Highway Trans. Fund 6 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 207
197 | 18470402299 | Dallas District Headquarters | Remodel The District Main Office | Highway Trans. Fund 6 | 5653246 | 5653246 | mm/dd/yy | 0% | 0% | 0 | 0 | 5653246 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 814
198 | 23470402339 | Brownwood District Headquarters | Renovate Existing Facilities | Highway Trans. Fund 6 | 6000000 | 6000000 | mm/dd/yy | 0% | 0% | 0 | 0 | 6000000 | Funding authorized on 11/25/15. Schedules will be reported next Quarter. | 854
Phase II - $42,500,000 | [13 empty] | 0
199 | 24470401509 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 6 | 1008000 | 1008000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1008000 | Pending Administrative Funding | 24
200 | 07470401516 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 7 | 1008000 | 1008000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1008000 | Pending Administrative Funding | 31
201 | 07470401520 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 8 | 224000 | 224000 | mm/dd/yy | 0% | 0% | 0 | 0 | 224000 | Pending Administrative Funding | 35
202 | 25470401521 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 9 | 224000 | 224000 | mm/dd/yy | 0% | 0% | 0 | 0 | 224000 | Pending Administrative Funding | 36
203 | 25470401522 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 10 | 1120000 | 1120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1120000 | Pending Administrative Funding | 37
204 | 05470401523 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 11 | 1680000 | 1680000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1680000 | Pending Administrative Funding | 38
205 | 06470401524 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 12 | 1120000 | 1120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1120000 | Pending Administrative Funding | 39
206 | 08470401528 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 13 | 1120000 | 1120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1120000 | Pending Administrative Funding | 43
207 | 04470401529 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 14 | 1680000 | 1680000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1680000 | Pending Administrative Funding | 44
208 | 17470401531 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 15 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 46
209 | 16470401534 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 16 | 896000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 49
210 | 11470401537 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 17 | 784000 | 784000 | mm/dd/yy | 0% | 0% | 0 | 0 | 784000 | Pending Administrative Funding | 52
211 | 02470401548 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 18 | 448000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 63
212 | 15470401550 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 19 | 1008000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 65
213 | 18470401551 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 20 | 448000 | 448000 | mm/dd/yy | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding | 66
214 | 05470401552 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 21 | 448000 | 448000 | mm/dd/yy | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding | 67
215 | 01470401556 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 22 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 71
216 | 01470401557 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 23 | 672000 | 672000 | mm/dd/yy | 0% | 0% | 0 | 0 | 672000 | Pending Administrative Funding | 72
217 | 21470401558 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 24 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 73
218 | 15470401560 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 25 | 560000 | 560000 | mm/dd/yy | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding | 75
219 | 10470401561 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 26 | 560000 | 560000 | mm/dd/yy | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding | 76
220 | 10470401562 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 27 | 448000 | 448000 | mm/dd/yy | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding | 77
221 | 09470401563 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 28 | 448000 | 448000 | mm/dd/yy | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding | 78
222 | 03470401564 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 29 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 79
223 | 03470401565 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 30 | 784000 | 784000 | mm/dd/yy | 0% | 0% | 0 | 0 | 784000 | Pending Administrative Funding | 80
224 | 13470401566 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 31 | 1008000 | 1008000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1008000 | Pending Administrative Funding | 81
225 | 21470401569 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 32 | 1008000 | 1008000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1008000 | Pending Administrative Funding | 84
226 | 22470401586 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 33 | 560000 | 560000 | mm/dd/yy | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding | 101
227 | 09470401603 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 34 | 448000 | 448000 | mm/dd/yy | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding | 118
228 | 19470401608 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 35 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 123
229 | 19470401609 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 36 | 672000 | 672000 | mm/dd/yy | 0% | 0% | 0 | 0 | 672000 | Pending Administrative Funding | 124
230 | 14470401612 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 37 | 1120000 | 1120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1120000 | Pending Administrative Funding | 127
231 | 06470401614 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 38 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 129
232 | 06470401616 | Monahans Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 39 | 1500 | 0 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding | 133
233 | 13470401618 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 40 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Partially completed with FY15 Funds | 137
234 | 13470401622 | Austin Cty Maint. | Repair Leaking Metal Roofs | Highway Trans. Fund 41 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 139
235 | 04470401624 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 42 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 152
236 | 23470401637 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 43 | 784000 | 784000 | mm/dd/yy | 0% | 0% | 0 | 0 | 784000 | Pending Administrative Funding | 162
237 | 17470401647 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 44 | 784000 | 784000 | mm/dd/yy | 0% | 0% | 0 | 0 | 784000 | Pending Administrative Funding | 181
238 | 20470401666 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 45 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 183
239 | 18470401668 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 46 | 560000 | 560000 | mm/dd/yy | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding | 193
240 | 02470401678 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 47 | 672000 | 672000 | mm/dd/yy | 0% | 0% | 0 | 0 | 672000 | Pending Administrative Funding | 194
241 | 12470401679 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 48 | 784000 | 784000 | mm/dd/yy | 0% | 0% | 0 | 0 | 784000 | Pending Administrative Funding | 196
242 | 11470401681 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 49 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 221
243 | 20470401706 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 50 | 672000 | 672000 | mm/dd/yy | 0% | 0% | 0 | 0 | 672000 | Pending Administrative Funding | 222
244 | 23470401707 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 51 | 224000 | 224000 | mm/dd/yy | 0% | 0% | 0 | 0 | 224000 | Pending Administrative Funding | 224
245 | 06470401709 | Iraan Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 52 | 1500 | 1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding | 229
246 | 12470401714 | Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 53 | 560000 | 560000 | mm/dd/yy | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding | 230
247 | 24470401715 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 54 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 231
248 | 22470401716 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 55 | 336000 | 336000 | mm/dd/yy | 0% | 0% | 0 | 0 | 336000 | Pending Administrative Funding | 232
249 | 06470401717 | Balmorhea Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 56 | 1500 | 1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding | 242
250 | 14470401727 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 57 | 560000 | 560000 | mm/dd/yy | 0% | 0% | 0 | 0 | 560000 | Pending Administrative Funding | 247
251 | 16470401732 | Area Engineer and Maintenance Offices | Upgrade Security (C-CURE) | Highway Trans. Fund 58 | 448000 | 448000 | mm/dd/yy | 0% | 0% | 0 | 0 | 448000 | Pending Administrative Funding | 255
252 | 15470401740 | District Headquarters | New Boiler | Highway Trans. Fund 59 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 256
253 | 15470401741 | District Headquarters | Replace All VAV and Upgrade To Electrical Control | Highway Trans. Fund 60 | 85000 | 85000 | mm/dd/yy | 0% | 0% | 0 | 0 | 85000 | Pending Administrative Funding | 257
254 | 10470401742 | Jacksonville Maintenance Office | Site Improvements | Highway Trans. Fund 61 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 258
255 | 13470401743 | Gonzales Cty Maint. | Convert Flat Roof To Gable Style | Highway Trans. Fund 62 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding | 259
256 | 13470401744 | Gonzales Maintenance Office | Roof Replacement | Highway Trans. Fund 63 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 260
257 | 04470401745 | Loop | Install Automatic Gate | Highway Trans. Fund 64 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 261
258 | 04470401746 | Loop | New Generator | Highway Trans. Fund 65 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding | 262
259 | 19470401747 | Linden Maintenance Office | Replace 2 HVAC Systems Add 1 HVAC For Shop | Highway Trans. Fund 66 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 263
260 | 18470401748 | District Headquarters | Generator Replaced With Diesel | Highway Trans. Fund 67 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 264
261 | 22470401749 | Del Rio Maintenance Office | Replace Roof | Highway Trans. Fund 68 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 265
262 | 22470401750 | Del Rio Maintenance Office (US 90) | Upgrade HVAC | Highway Trans. Fund 69 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 266
263 | 22470401751 | Cotulla Maintenance Office | Roof Repairs | Highway Trans. Fund 70 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 267
264 | 22470401752 | Cotulla Maintenance Office | Upgrade Propane Generator | Highway Trans. Fund 71 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 268
265 | 20470401753 | Orange Maintenance Office | Rehab Metal Roofing | Highway Trans. Fund 72 | 95000 | 95000 | mm/dd/yy | 0% | 0% | 0 | 0 | 95000 | Pending Administrative Funding | 269
266 | 12470401754 | Brookshire Maintenance Office | Replace Emergency Generator | Highway Trans. Fund 73 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 270
267 | 12470401755 | Houston South Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 74 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 271
268 | 12470401756 | Humble Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 75 | 87000 | 87000 | mm/dd/yy | 0% | 0% | 0 | 0 | 87000 | Pending Administrative Funding | 272
269 | 12470401757 | Rosenberg Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 76 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 273
270 | 22470401758 | District Headquarters | New HVAC In Shop Restrooms | Highway Trans. Fund 77 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 274
271 | 22470401759 | District Headquarters | Replace Roof | Highway Trans. Fund 78 | 225000 | 225000 | mm/dd/yy | 0% | 0% | 0 | 0 | 225000 | Pending Administrative Funding | 275
272 | 22470401760 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 79 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 276
273 | 22470401761 | Laredo Area Engineer & Maintenance Office | Exterior Lighting | Highway Trans. Fund 80 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 277
274 | 22470401762 | Laredo Auto Shop | Furnish/Install HVAC | Highway Trans. Fund 81 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 278
275 | 22470401763 | Laredo Auto Shop | Restrooms HVAC | Highway Trans. Fund 82 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 279
276 | 22470401764 | Laredo District Headquarters | Repair MNT To Auto Shop Roof | Highway Trans. Fund 83 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding | 280
277 | 22470401765 | Laredo Lab/FIN/Stratus | Replace 8 HVAC Units | Highway Trans. Fund 84 | 80000 | 80000 | mm/dd/yy | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding | 281
278 | 22470401766 | Laredo Traffic | Replace Computer/Storage Room HVAC | Highway Trans. Fund 85 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 282
279 | 15470401767 | Transguide | Replace 2 - 75 Ton Chillers And Add Chiller For (Backup) | Highway Trans. Fund 86 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 283
280 | 24470401768 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 87 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 284
281 | 05470401769 | District Headquarters | Replace Roof | Highway Trans. Fund 88 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 285
282 | 15470401770 | Bexar Metro Area Engineer & Maintenance Office | HVAC Upgrade | Highway Trans. Fund 89 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 286
283 | 15470401771 | Bexar Metro Area Engineer & Maintenance Office | Replace Generator | Highway Trans. Fund 90 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 287
284 | 09470401772 | Gatesville Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 91 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 288
285 | 18470401773 | Denton Area Engineer & Maintenance Office | Install Gate - Electric W/Remote On Ih35 Service Road | Highway Trans. Fund 92 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 289
286 | 05470401774 | Littlefield Maintenance Office | Replace Roof | Highway Trans. Fund 93 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 291
287 | 21470401776 | District Headquarters | HVAC Upgrade In HQ Bldg. | Highway Trans. Fund 94 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding | 292
288 | 21470401777 | San Benito Area Engineer & Maintenance Office | Replace HVAC Units | Highway Trans. Fund 95 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 293
289 | 21470401778 | San Benito Area Engineer & Maintenance Office | Replace Roof | Highway Trans. Fund 96 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding | 294
290 | 20470401779 | Beaumont Area Engineer & Maintenance Office | Install Card Reader Access | Highway Trans. Fund 97 | 16000 | 16000 | mm/dd/yy | 0% | 0% | 0 | 0 | 16000 | Pending Administrative Funding | 295
291 | 25470401780 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 98 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 296
292 | 16470401781 | District Headquarters | Replace HVAC Unit At Vehicle Titles And Registration - Corpus Christi DHQ | Highway Trans. Fund 99 | 18000 | 18000 | mm/dd/yy | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding | 297
293 | 18470401782 | District Headquarters | Fire/Sprinkler Upgrade (Obsolete Panels) | Highway Trans. Fund 100 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 298
294 | 13470401783 | Fayette Cty Maint. | Upgrade Apu To Supply Entire Maintenace Building | Highway Trans. Fund 101 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding | 299
295 | 20470401784 | Liberty Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 102 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 300
296 | 20470401785 | Liberty Area Engineer & Maintenance Office | A/C Unit Replacement | Highway Trans. Fund 103 | 18000 | 18000 | mm/dd/yy | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding | 301
297 | 20470401786 | Liberty Area Engineer & Maintenance Office | Install/Repair Fence | Highway Trans. Fund 104 | 7000 | 7000 | mm/dd/yy | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding | 302
298 | 20470401787 | Liberty Area Engineer & Maintenance Office | Rehab Roof With Insulation | Highway Trans. Fund 105 | 95000 | 95000 | mm/dd/yy | 0% | 0% | 0 | 0 | 95000 | Pending Administrative Funding | 303
299 | 24470401788 | El Paso (East) Area Engineer & Maintenance Office | Install/Repair Roof | Highway Trans. Fund 106 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 304
300 | 24470401789 | El Paso (East) Area Engineer & Maintenance Office | Upgrade Evaporative AC Unit In The Shop. Add Heaters And Double Door. | Highway Trans. Fund 107 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 305
301 | 24470401790 | El Paso (East) Area Engineer & Maintenance Office | Upgrade Front/Rear Entrance Gates | Highway Trans. Fund 108 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 306
302 | 24470401791 | El Paso (West) Area Engineer & Maintenance Office | Secure The Lobby Area | Highway Trans. Fund 109 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding | 307
303 | 02470401792 | District Headquarters | 9 Crac HVAC Units Transvision Building | Highway Trans. Fund 110 | 270000 | 270000 | mm/dd/yy | 0% | 0% | 0 | 0 | 270000 | Pending Administrative Funding | 308
304 | 22470401793 | Freer | HVAC Replacement | Highway Trans. Fund 111 | 17000 | 17000 | mm/dd/yy | 0% | 0% | 0 | 0 | 17000 | Pending Administrative Funding | 309
305 | 05470401794 | District Headquarters | Replace Roof | Highway Trans. Fund 112 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 310
306 | 10470401795 | South Tyler Area Engineer & Maintenance Office | Replace HVAC In Bldg. B | Highway Trans. Fund 113 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 311
307 | 10470401796 | South Tyler Area Engineer & Maintenance Office | Upgrade HVAC In Maint &Area Office | Highway Trans. Fund 114 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 312
308 | 09470401797 | Hillsboro Area Engineer & Maintenance Office | Install Gate and Controls | Highway Trans. Fund 115 | 17000 | 17000 | mm/dd/yy | 0% | 0% | 0 | 0 | 17000 | Pending Administrative Funding | 313
309 | 16470401798 | Bee Co. | Replace HVAC System | Highway Trans. Fund 116 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 314
310 | 18470401799 | Cedar Hill Maintenance Office | Install Gates - Electric/Key Pad | Highway Trans. Fund 117 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 315
311 | 18470401800 | Cedar Hill Maintenance Office | New Generator - Diesel | Highway Trans. Fund 118 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 316
312 | 19470401801 | District Headquarters | Replace 2 HVAC Systems | Highway Trans. Fund 119 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 317
313 | 22470401802 | La Pryor Maintenance Office | Replace Two HVAC Units | Highway Trans. Fund 120 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 318
314 | 22470401803 | La Pryor on HWY 57 | Install Gate Operator And Key Pad | Highway Trans. Fund 121 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 319
315 | 18470401804 | Corsicana Area Engineer & Maintenance Office | Fire/Sprinkler Upgrade (Obsolete Panels) | Highway Trans. Fund 122 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 320
316 | 18470401805 | District Headquarters | Generator Backup Power Completed | Highway Trans. Fund 123 | 90000 | 90000 | mm/dd/yy | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding | 321
317 | 18470401806 | District Headquarters | HVAC Upgrade - Leibert System @ Server Room | Highway Trans. Fund 124 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 322
318 | 12470401807 | District Headquarters | Install CCTV Security Camera (Parking Garage) | Highway Trans. Fund 125 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 323
319 | 12470401808 | District Headquarters | Upgrade Site Lighting | Highway Trans. Fund 126 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 324
320 | 12470401809 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 127 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 325
321 | 16470401810 | Aransas Co. | Replace Roof On The Maintenance Building | Highway Trans. Fund 128 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding | 326
322 | 18470401811 | Ennis Maintenance Office | Roof - Coating Metal Roof Over Storage/Salt Shed | Highway Trans. Fund 129 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 327
323 | 06470401812 | Ft Stockton Area Engineer & Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 130 | 1500 | 1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding | 328
324 | 15470401813 | District Headquarters | Replace 3 Each 20 Ton Chillers For Backup | Highway Trans. Fund 131 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding | 329
325 | 15470401814 | West Bexar Maintenance Office | Replace Roof | Highway Trans. Fund 132 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 330
326 | 38470401815 | Riverside Annex I RA118 | Replacement of R22 to 410 HVAC System | Highway Trans. Fund 133 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 331
327 | 38470401816 | Riverside Annex II RA150-200 | Install Redundant UPS for Data Center | Highway Trans. Fund 134 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding | 332
328 | 38470401817 | Riverside Annex II RA150-200 | Replace Roof | Highway Trans. Fund 135 | 450000 | 450000 | mm/dd/yy | 0% | 0% | 0 | 0 | 450000 | Pending Administrative Funding | 333
329 | 38470401818 | Riverside Annex II RA150-200 | Replacement of R22 to 410 HVAC System | Highway Trans. Fund 136 | 360000 | 360000 | mm/dd/yy | 0% | 0% | 0 | 0 | 360000 | Pending Administrative Funding | 334
330 | 38470401819 | Riverside Annex II RA150-200 | Roof and Weatherize Exterior | Highway Trans. Fund 137 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 335
331 | 38470401820 | Riverside Annex II RA150-200 | Upgrade Obsolete Johnson Control Panels | Highway Trans. Fund 138 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 336
332 | 21470401821 | Edcouch Maintenance Office | Add Exit Only Gate To East Side | Highway Trans. Fund 139 | 16000 | 16000 | mm/dd/yy | 0% | 0% | 0 | 0 | 16000 | Pending Administrative Funding | 337
333 | 17470401822 | District Headquarters | Upgrade Security (C-CURE) | Highway Trans. Fund 140 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 338
334 | 01470401823 | District Headquarters | Resurface Parking Lot | Highway Trans. Fund 141 | 164000 | 164000 | mm/dd/yy | 0% | 0% | 0 | 0 | 164000 | Pending Administrative Funding | 339
335 | 21470401824 | Pharr Area Engineer & Maintenance Office | Reconfigure Parking Lot | Highway Trans. Fund 142 | 41000 | 41000 | mm/dd/yy | 0% | 0% | 0 | 0 | 41000 | Pending Administrative Funding | 340
336 | 21470401825 | Pharr Area Engineer & Maintenance Office | Rework Concrete Drainage Structure | Highway Trans. Fund 143 | 11000 | 11000 | mm/dd/yy | 0% | 0% | 0 | 0 | 11000 | Pending Administrative Funding | 341
337 | 22470401826 | Del Rio | Sprinkler System Repair & Upgrade | Highway Trans. Fund 144 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 342
338 | 22470401827 | Del Rio Maintenance Office | Furnish/Install Bollard | Highway Trans. Fund 145 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 343
339 | 22470401828 | Del Rio Maintenance Office (US 90) | Parking Lot Lighting | Highway Trans. Fund 146 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 344
340 | 04470401829 | Dumas Maintenance Office | Sprinkler System Repairs | Highway Trans. Fund 147 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 345
341 | 07470401830 | Eden Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 148 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 346
342 | 07470401831 | Eden Maintenance Office | Install New 10,000 Gallon Brine Storge Tank | Highway Trans. Fund 149 | 6000 | 6000 | mm/dd/yy | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding | 347
343 | 07470401832 | Eden Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 150 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 348
344 | 07470401833 | Eden Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 151 | 61000 | 61000 | mm/dd/yy | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding | 349
345 | 24470401834 | Fort Hancock Sub-Section | Demolish Old Asphalt Storage Tank. | Highway Trans. Fund 152 | 8400 | 8400 | mm/dd/yy | 0% | 0% | 0 | 0 | 8400 | Pending Administrative Funding | 350
346 | 24470401835 | Fort Hancock Sub-Section | Install Back Rockwall | Highway Trans. Fund 153 | 18000 | 18000 | mm/dd/yy | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding | 351
347 | 07470401836 | Leakey Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 154 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 352
348 | 07470401837 | Leakey Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 155 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 353
349 | 07470401838 | Leakey Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 156 | 61000 | 61000 | mm/dd/yy | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding | 354
350 | 06470401839 | McCamey Maintenance Office | Paint Asphalt Tank Bases And Hardware. Deteriorating Paint And Rusting Steel | Highway Trans. Fund 157 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 355
351 | 07470401840 | Ballinger Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 158 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 356
352 | 07470401841 | Ballinger Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 159 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 357
353 | 07470401842 | Ballinger Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 160 | 122000 | 122000 | mm/dd/yy | 0% | 0% | 0 | 0 | 122000 | Pending Administrative Funding | 358
354 | 06470401843 | Sanderson Maintenance Office | Repair Irrigation Systems | Highway Trans. Fund 161 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 359
355 | 23470401844 | Breckenridge Maintenance Office | Demolish Old Structures On Adjacent Site | Highway Trans. Fund 162 | 39500 | 39500 | mm/dd/yy | 0% | 0% | 0 | 0 | 39500 | Pending Administrative Funding | 360
356 | 16470401845 | Jim Wells Co. | Add Additional Lateral Lines To Septic System At The Alice Ae Office | Highway Trans. Fund 163 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 361
357 | 18470401846 | Ennis Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 164 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 362
358 | 18470401847 | Ennis Maintenance Office | Parking Lot Striping | Highway Trans. Fund 165 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 363
359 | 21470401848 | Zapata Maintenance Office Sub-Section | Repave Parking Lot | Highway Trans. Fund 166 | 19780 | 19780 | mm/dd/yy | 0% | 0% | 0 | 0 | 19780 | Pending Administrative Funding | 364
360 | 20470401849 | Anahuac Maintenance Office | Rehab Parking Lot And Drainage | Highway Trans. Fund 167 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 365
361 | 20470401850 | Anahuac Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 168 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 366
362 | 20470401851 | Newton Maintenance Office | Reconfigure Parking Lot | Highway Trans. Fund 169 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 367
363 | 20470401852 | Newton Maintenance Office | Remove Out Of Service Emulsion, Linseed Oil & Asts | Highway Trans. Fund 170 | 55000 | 55000 | mm/dd/yy | 0% | 0% | 0 | 0 | 55000 | Pending Administrative Funding | 368
364 | 20470401853 | Stowel Maintenance Office | Electric Service To Yard | Highway Trans. Fund 171 | 4000 | 4000 | mm/dd/yy | 0% | 0% | 0 | 0 | 4000 | Pending Administrative Funding | 369
365 | 20470401854 | Woodville Maintenance Office | Remove Out Of Service Emulsion, Linseed Oil & Asts | Highway Trans. Fund 172 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 370
366 | 18470401855 | District Headquarters | Site Improvements | Highway Trans. Fund 173 | 207000 | 207000 | mm/dd/yy | 0% | 0% | 0 | 0 | 207000 | Pending Administrative Funding | 371
367 | 18470401856 | District Headquarters | Asphalt Overlay Parking Lot | Highway Trans. Fund 174 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 372
368 | 18470401857 | District Headquarters | Parking Lot Striping | Highway Trans. Fund 175 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 373
369 | 22470401858 | Brackettville | Fuel Pump Replacements | Highway Trans. Fund 176 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 374
370 | 22470401859 | Brackettville | Landscaping & Irrigation | Highway Trans. Fund 177 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 375
371 | 07470401860 | San Angelo Area Engineer & Maintenance Office | Overlay And Restripe Parking Lot | Highway Trans. Fund 178 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 376
372 | 07470401861 | San Angelo Maintenance Office | Install New Automated Vehicle Entry Gate | Highway Trans. Fund 179 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 377
373 | 07470401862 | San Angelo Maintenance Office | Pavement Seal Coat and Restripe | Highway Trans. Fund 180 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 378
374 | 07470401863 | San Angelo Maintenance Office | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 181 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 379
375 | 07470401864 | Sterling City Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 182 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 380
376 | 07470401865 | Sterling City Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 183 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 381
377 | 07470401866 | Sterling City Maintenance Office | Replace Automated Swing Gate With Automated Sliding Gate | Highway Trans. Fund 184 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 382
378 | 07470401867 | Sterling City Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 185 | 61000 | 61000 | mm/dd/yy | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding | 383
379 | 25470401868 | Munday Maintenance Office | Resurface Parking Lot | Highway Trans. Fund 186 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 384
380 | 05470401869 | Post RDC | Nw Side Of Long Building Dirt Work To Shed Water | Highway Trans. Fund 187 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 385
381 | 05470401870 | Post RDC | Site Work And Concrete Flume | Highway Trans. Fund 188 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 386
382 | 21470401871 | Raymondville Maintenance Office | New Fire Proof Overhead Doors | Highway Trans. Fund 189 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 387
383 | 21470401872 | Raymondville Maintenance Office | Resurface Maintenance Yard | Highway Trans. Fund 190 | 134800 | 134800 | mm/dd/yy | 0% | 0% | 0 | 0 | 134800 | Pending Administrative Funding | 388
384 | 10470401873 | District Headquarters | Modifications/Upgrade Site | Highway Trans. Fund 191 | 110000 | 110000 | mm/dd/yy | 0% | 0% | 0 | 0 | 110000 | Pending Administrative Funding | 389
385 | 08470401874 | District Headquarters | Parking Lot Reconfiguration | Highway Trans. Fund 192 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 390
386 | 08470401875 | District Headquarters | Sidewalks at the DMV Building Need to be Cut Out and Replaced in Various Areas | Highway Trans. Fund 193 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 391
387 | 08470401876 | District Headquarters | Replace Water Cut Offs On The Complex For Various Buildings | Highway Trans. Fund 194 | 8500 | 8500 | mm/dd/yy | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding | 392
388 | 24470401877 | Fort Davis Maintenance Office | Demolish Old Emulsion Tank | Highway Trans. Fund 195 | 8500 | 8500 | mm/dd/yy | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding | 393
389 | 24470401878 | Fort Davis Maintenance Office | Install Sprinkler System | Highway Trans. Fund 196 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 394
390 | 02470401879 | District Headquarters | Site Improvements | Highway Trans. Fund 197 | 303000 | 303000 | mm/dd/yy | 0% | 0% | 0 | 0 | 303000 | Pending Administrative Funding | 395
391 | 06470401880 | District Headquarters | Modifications/Upgrade Site | Highway Trans. Fund 198 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 396
392 | 06470401881 | District Headquarters | Xeroscape Grounds | Highway Trans. Fund 199 | 264000 | 264000 | mm/dd/yy | 0% | 0% | 0 | 0 | 264000 | Pending Administrative Funding | 397
393 | 06470401882 | Odessa Maintenance Office | Reconfigure Parking In Front Of Office | Highway Trans. Fund 200 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 398
394 | 06470401883 | Odessa Maintenance Office | Repair/Replace ATG System On Above Ground Fuel Tanks | Highway Trans. Fund 201 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 399
395 | 06470401884 | Odessa Maintenance Office | Replace Irrigation System For New Yard Design | Highway Trans. Fund 202 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 400
396 | 07470401885 | Junction Area Engineer & Maintenance Office | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 203 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 401
397 | 07470401886 | Junction Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 204 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 402
398 | 07470401887 | Junction Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 205 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 403
399 | 07470401888 | Junction Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 206 | 61000 | 61000 | mm/dd/yy | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding | 404
400 | 15470401889 | District Headquarters | Change Out Galvanized Water Main Piping | Highway Trans. Fund 207 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 405
401 | 15470401890 | District Headquarters | Change Out Galvanized Water Main Piping | Highway Trans. Fund 208 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 406
402 | 15470401891 | District Headquarters | Parking Lot Resurfacing & Reconfiguration | Highway Trans. Fund 209 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 407
403 | 06470401892 | Monahans Maintenance Office | Connect to City Sewer Utililty Line | Highway Trans. Fund 210 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 408
404 | 06470401893 | Monahans Maintenance Office | Repair Irrigation Systems | Highway Trans. Fund 211 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 409
405 | 15470401894 | Seguin Area Engineer & Maintenance Office | Replace Radio Tower | Highway Trans. Fund 212 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 410
406 | 07470401895 | Sonora Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 213 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 411
407 | 13470401896 | Austin Cty Maint. | Install Above Ground Fuel System/New Dispenser | Highway Trans. Fund 214 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding | 412
408 | 13470401897 | Colorado Cty Maint. | Install Above Ground Fuel System/New Dispenser | Highway Trans. Fund 215 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding | 413
409 | 20470401898 | Beaumont Area Engineer & Maintenance Office | Additional Sidewalks | Highway Trans. Fund 216 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 414
410 | 20470401899 | District Headquarters | Modifications/Upgrade Site Utilities | Highway Trans. Fund 217 | 101000 | 101000 | mm/dd/yy | 0% | 0% | 0 | 0 | 101000 | Pending Administrative Funding | 415
411 | 20470401900 | District Headquarters | Rehab Parking Lot And Stripe | Highway Trans. Fund 218 | 450000 | 450000 | mm/dd/yy | 0% | 0% | 0 | 0 | 450000 | Pending Administrative Funding | 416
412 | 20470401901 | District Headquarters | Remove Out Of Service Emulsion, Linseed Oil & Asts | Highway Trans. Fund 219 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 417
413 | 20470401902 | District Headquarters | Replace Fuel Dispensers | Highway Trans. Fund 220 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 418
414 | 20470401903 | Districtwide | Re-Stripe Parking Lots And Hc Spaces | Highway Trans. Fund 221 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 419
415 | 07470401904 | Rocksprings Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 222 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 420
416 | 07470401905 | Rocksprings Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 223 | 122000 | 122000 | mm/dd/yy | 0% | 0% | 0 | 0 | 122000 | Pending Administrative Funding | 421
417 | 03470401906 | District Headquarters | Construct In-Ground Storm Shelter | Highway Trans. Fund 224 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 422
418 | 03470401907 | District Headquarters | Modifications/Upgrade Site Utilities | Highway Trans. Fund 225 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 423
419 | 03470401908 | District Headquarters | Repave Parking Lot - Wichita Falls DHQ | Highway Trans. Fund 226 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 424
420 | 16470401909 | District Headquarters | Modifications/Upgrade Site | Highway Trans. Fund 227 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 425
421 | 16470401910 | District Headquarters | Modifications/Upgrade Site Utilities | Highway Trans. Fund 228 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding | 426
422 | 16470401911 | District Headquarters | Rehab Existing Parking Lots On Entire Campus | Highway Trans. Fund 229 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 427
423 | 16470401912 | District Headquarters | Repair Sidewalk Or Parking Lot - Corpus Christi DHQ | Highway Trans. Fund 230 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 428
424 | 16470401913 | District Headquarters | Replace 3 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 231 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 429
425 | 16470401914 | District Headquarters | Replace Fuel Dispenser At Maintenance Special Jobs - Corpus Christi DHQ | Highway Trans. Fund 232 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 430
426 | 11470401915 | Crockett Maintenance Office | Replace Bathroom Sewer Dainage System | Highway Trans. Fund 233 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 431
427 | 06470401916 | Crane Maintenance Office | Paint 10000 Gal Asphalt Tank & Insulate | Highway Trans. Fund 234 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 432
428 | 21470401917 | District Headquarters | Upgrade Landscaping to include Hike And Bike Trail | Highway Trans. Fund 235 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 433
429 | 21470401918 | District Headquarters | Increase Parking Area | Highway Trans. Fund 236 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 434
430 | 21470401919 | District Headquarters | Parking Lot Improvements | Highway Trans. Fund 237 | 400000 | 400000 | mm/dd/yy | 0% | 0% | 0 | 0 | 400000 | Pending Administrative Funding | 435
431 | 07470401920 | Ozona Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 238 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 436
432 | 07470401921 | Ozona Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 239 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 437
433 | 07470401922 | Ozona Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 240 | 61000 | 61000 | mm/dd/yy | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding | 438
434 | 13470401923 | District Headquarters | Install Above Ground Fuel System/New Dispenser | Highway Trans. Fund 241 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding | 439
435 | 13470401924 | District Headquarters | Replace Deteriorating Natural Gas Lines And Exterior Valves | Highway Trans. Fund 242 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 440
436 | 20470401925 | Port Arthur Area Engineer & Maintenance Office | Rehab Parking Lot And Stripe | Highway Trans. Fund 243 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 441
437 | 23470401926 | District Headquarters | Site Improvements | Highway Trans. Fund 244 | 155000 | 155000 | mm/dd/yy | 0% | 0% | 0 | 0 | 155000 | Pending Administrative Funding | 442
438 | 18470401927 | Waxahachie Area Engineer & Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 245 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 443
439 | 18470401928 | Waxahachie Area Engineer & Maintenance Office | Parking Lot Striping | Highway Trans. Fund 246 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 444
440 | 18470401929 | Rockwall Maintenance Office | Asphalt Emulsion Tank Installation | Highway Trans. Fund 247 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 445
441 | 18470401930 | Rockwall Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 248 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 446
442 | 18470401931 | Rockwall Maintenance Office | Parking Lot Striping | Highway Trans. Fund 249 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 447
443 | 22470401932 | Carrizo Springs (Area Engineer & Maintenance Office & Lab) | Upgrade Sprinkler System | Highway Trans. Fund 250 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 448
444 | 07470401933 | District Headquarters | Pavement Seal Coat And Restripe | Highway Trans. Fund 251 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 449
445 | 07470401934 | District Headquarters | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 252 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 450
446 | 04470401935 | Pampa Area Engineer & Maintenance Office | Replace Fuel Pumps | Highway Trans. Fund 253 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 451
447 | 20470401936 | Kountze Maintenance Office | Rehab Parking Lot And Stripe | Highway Trans. Fund 254 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 452
448 | 24470401937 | Terlingua Sub-Section | Resufacing of Parking Lot | Highway Trans. Fund 255 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 453
449 | 13470401938 | Wharton Cty Maint. | Build New Berm Around Asphalt Tanks | Highway Trans. Fund 256 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 454
450 | 04470401939 | Perryton Maintenance Office | Replace Fuel Pumps | Highway Trans. Fund 257 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 455
451 | 06470401940 | Iraan Maintenance Office | Repair Irrigation Systems | Highway Trans. Fund 258 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 456
452 | 18470401941 | Hutchins Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 259 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 457
453 | 18470401942 | Hutchins Maintenance Office | Parking Lot Striping | Highway Trans. Fund 260 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 458
454 | 18470401943 | NW Dallas Maintenance Office | Modular Building/Site Prep | Highway Trans. Fund 261 | 110000 | 110000 | mm/dd/yy | 0% | 0% | 0 | 0 | 110000 | Pending Administrative Funding | 459
455 | 24470401944 | Alpine Area Engineer & Maintenance Office | Demolish Old Emulsion Tank | Highway Trans. Fund 262 | 8400 | 8400 | mm/dd/yy | 0% | 0% | 0 | 0 | 8400 | Pending Administrative Funding | 460
456 | 06470401945 | Balmorhea Maintenance Office | Repair Irrigation Systems | Highway Trans. Fund 263 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 461
457 | 21470401946 | San Benito Area Engineer & Maintenance Office | Fuel Tank Relocation | Highway Trans. Fund 264 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding | 462
458 | 21470401947 | San Benito Area Engineer & Maintenance Office | Improve Drainage | Highway Trans. Fund 265 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 463
459 | 21470401948 | San Benito Area Engineer & Maintenance Office | Repair Sewer Line At Rear Of Yard, Add Approx. 8 Manholes. | Highway Trans. Fund 266 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 464
460 | 21470401949 | San Benito Area Engineer & Maintenance Office | Resurface Parking Lot | Highway Trans. Fund 267 | 26200 | 26200 | mm/dd/yy | 0% | 0% | 0 | 0 | 26200 | Pending Administrative Funding | 465
461 | 07470401950 | Robert Lee Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 268 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 466
462 | 07470401951 | Rocksprings Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 269 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 467
463 | 24470401952 | Presidio Maintenance Office | Demolish Old Emulsion Tank | Highway Trans. Fund 270 | 8500 | 8500 | mm/dd/yy | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding | 468
464 | 21470401953 | Laguna Vista Maintenance Office Sub-Section | Repair Fuel Dispensing Pumps & Tanks | Highway Trans. Fund 271 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 469
465 | 15470401954 | Bandera Maintenance Office | Connect To City Water/Sewer | Highway Trans. Fund 272 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 470
466 | 24470401955 | Pine Springs Sub-Section | Demolish Old Emulsion Tank | Highway Trans. Fund 273 | 8500 | 8500 | mm/dd/yy | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding | 471
467 | 06470401956 | Midland Area Engineer & Maintenance Office | Repair Irrigation Systems | Highway Trans. Fund 274 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 472
468 | 07470401957 | Big Lake Maintenance Office | Demolish Old Asphalt Storage Tank | Highway Trans. Fund 275 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 473
469 | 07470401958 | Big Lake Maintenance Office | Install New Above Ground Fuel Tanks | Highway Trans. Fund 276 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 474
470 | 07470401959 | Big Lake Maintenance Office | Pavement Seal Coat And Restripe | Highway Trans. Fund 277 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 475
471 | 07470401960 | Big Lake Maintenance Office | Replace Old Asphalt Storage Tank | Highway Trans. Fund 278 | 61000 | 61000 | mm/dd/yy | 0% | 0% | 0 | 0 | 61000 | Pending Administrative Funding | 476
472 | 14470401961 | Burnet Area Engineer & Maintenance Office | Parking Lot Overlay | Highway Trans. Fund 279 | 95000 | 95000 | mm/dd/yy | 0% | 0% | 0 | 0 | 95000 | Pending Administrative Funding | 477
473 | 23470401962 | Goldthwaite Maintenance Office | Remove Underground Fuel Tanks And Install Above Ground Tanks | Highway Trans. Fund 280 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 478
474 | 07470401963 | Menard Maintenance Office | Replace Underground Fuel Tanks With New Above Ground Tanks | Highway Trans. Fund 281 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 479
475 | 16470401964 | Corpus Christi Area Engineer & Maintenance Office | Repair Fuel Monitoring System - Corpus Christi AEM | Highway Trans. Fund 282 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 480
476 | 16470401965 | San Patricio Co | Replace Existing Sewage Line Running To Lift Station | Highway Trans. Fund 283 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 481
477 | 16470401966 | Sinton Area Engineer & Maintenance Office | Replace Sewer Line | Highway Trans. Fund 284 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 482
478 | 10470401967 | Jacksonville Maintenance Office | Parking Improvements | Highway Trans. Fund 285 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding | 483
479 | 22470401968 | Del Rio Maintenance Office | Irrigation Replacement | Highway Trans. Fund 286 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 484
480 | 05470401969 | Tulia Maintenance Office | New 2" Water Line Installation | Highway Trans. Fund 287 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 485
481 | 22470401970 | Cotulla Maintenance Office | Install French Drainage | Highway Trans. Fund 288 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 486
482 | 22470401971 | Cotulla Maintenance Office | Install Irrigation And Landscaping | Highway Trans. Fund 289 | 4250 | 4250 | mm/dd/yy | 0% | 0% | 0 | 0 | 4250 | Pending Administrative Funding | 487
483 | 22470401972 | Cotulla Maintenance Office | Repave & Stripe Empl & Visitor Parking Lot | Highway Trans. Fund 290 | 105000 | 105000 | mm/dd/yy | 0% | 0% | 0 | 0 | 105000 | Pending Administrative Funding | 488
484 | 20470401973 | Jasper Area Engineer & Maintenance Office | Add Connection To Public Supply For Water And Sanitary Sewer System | Highway Trans. Fund 291 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 489
485 | 20470401974 | Jasper Area Engineer & Maintenance Office | Remove Out Of Service Emulsion, Linseed Oil & Asts | Highway Trans. Fund 292 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 490
486 | 12470401975 | Conroe Area Engineer & Maintenance Office | Sitework Modifications (Drivewal And Visitor Parking) | Highway Trans. Fund 293 | 70000 | 70000 | mm/dd/yy | 0% | 0% | 0 | 0 | 70000 | Pending Administrative Funding | 491
487 | 22470401976 | District Headquarters | Parking Lot Reconfiguration | Highway Trans. Fund 294 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding | 492
488 | 22470401977 | Laredo Administration & Area Engineer & Maintenance Office | Irrigation, Landscaping, Grass Seeds, Planting/Adding Trees | Highway Trans. Fund 295 | 225000 | 225000 | mm/dd/yy | 0% | 0% | 0 | 0 | 225000 | Pending Administrative Funding | 493
489 | 22470401978 | Laredo District Headquarters | Reconfigure Landscaping For Walking Trail | Highway Trans. Fund 296 | 80000 | 80000 | mm/dd/yy | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding | 494
490 | 24470401979 | District Headquarters | Site Improvements | Highway Trans. Fund 297 | 318000 | 318000 | mm/dd/yy | 0% | 0% | 0 | 0 | 318000 | Pending Administrative Funding | 495
491 | 13470401980 | District Headquarters | Replace Natural Gas Lines | Highway Trans. Fund 298 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 496
492 | 25470401981 | Clarendon Maintenance Office | Replace Fuel Station | Highway Trans. Fund 299 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 497
493 | 18470401982 | Denton Area Engineer & Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 300 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 498
494 | 18470401983 | Denton Area Engineer & Maintenance Office | Parking Lot Striping | Highway Trans. Fund 301 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 499
495 | 13470401984 | La Grange Area Engineer & Maintenance Office | Replace Asphalt Tank Berm | Highway Trans. Fund 302 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 500
496 | 20470401985 | Liberty Area Engineer & Maintenance Office | Regrade Parking And Drainage | Highway Trans. Fund 303 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 501
497 | 24470401986 | El Paso (East) Area Engineer & Maintenance Office | Install/Repair Rock Wall Front And Rear | Highway Trans. Fund 304 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 502
498 | 22470401987 | Freer | Flag Pole Lighting | Highway Trans. Fund 305 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 503
499 | 22470401988 | Freer | Irrigation And Landscaping | Highway Trans. Fund 306 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 504
500 | 38470401989 | CEDAR PARK Research and Technology Center | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 307 | 60000 | 60000 | mm/dd/yy | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding | 505
501 | 10470401990 | South Tyler Area Engineer & Maintenance Office | Sewer Connect To City - South Tyler Area Engineer And Maintenance Facility | Highway Trans. Fund 308 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding | 506
502 | 16470401991 | Beeville Maintenance Office | Repair Fuel Monitoring System - Beeville MNT | Highway Trans. Fund 309 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 507
503 | 16470401992 | Beeville Maintenance Office | Replace\New Fuel Dispenser/Fuel Pump At Maintenance - Beeville MNT | Highway Trans. Fund 310 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 508
504 | 08470401993 | Abilene Maintenance Office | Reroute Wash Bay Drain To City Sewer Drain | Highway Trans. Fund 311 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 509
505 | 22470401994 | La Pryor Maintenance Office | Resurface 2 Acres Of Parking Area In Yard & Strip Where Needed | Highway Trans. Fund 312 | 152000 | 152000 | mm/dd/yy | 0% | 0% | 0 | 0 | 152000 | Pending Administrative Funding | 510
506 | 24470401995 | Marfa Sub-Section | Demolish Old Emulsion Tank | Highway Trans. Fund 313 | 8500 | 8500 | mm/dd/yy | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding | 511
507 | 24470401996 | Van Horn Maintenance Office | Demolish Old Emulsion Tank | Highway Trans. Fund 314 | 8500 | 8500 | mm/dd/yy | 0% | 0% | 0 | 0 | 8500 | Pending Administrative Funding | 512
508 | 13470401997 | Fayette Cty Maint. | Eliminate Wash Rack Waste Water Recycle System And Convert To City Utilities | Highway Trans. Fund 315 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 513
509 | 18470401998 | Corsicana Area Engineer & Maintenance Office | Asphalt Overlay Parking Lot | Highway Trans. Fund 316 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 514
510 | 18470401999 | Corsicana Area Engineer & Maintenance Office | Parking Lot Striping | Highway Trans. Fund 317 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 515
511 | 21470402000 | Laguna Vista Maintenance Office Sub-Section | Replace Fuel Pump Canopy | Highway Trans. Fund 318 | 13000 | 13000 | mm/dd/yy | 0% | 0% | 0 | 0 | 13000 | Pending Administrative Funding | 516
512 | 15470402001 | New Braunfels Area Engineer & Maintenance Office | Parking Lot Reconfiguration | Highway Trans. Fund 319 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 517
513 | 10470402002 | Athens Area Engineer & Maintenance Office | Parking Improvements | Highway Trans. Fund 320 | 70000 | 70000 | mm/dd/yy | 0% | 0% | 0 | 0 | 70000 | Pending Administrative Funding | 518
514 | 09470402003 | Waco Area Engineer & Maintenance Office - Bagby | Site Drainage Improvements | Highway Trans. Fund 321 | 25200 | 25200 | mm/dd/yy | 0% | 0% | 0 | 0 | 25200 | Pending Administrative Funding | 519
515 | 17470402004 | District Headquarters | Parking Area Pavement | Highway Trans. Fund 322 | 450000 | 450000 | mm/dd/yy | 0% | 0% | 0 | 0 | 450000 | Pending Administrative Funding | 520
516 | 22470402005 | Laredo District Headquarters | Parking Lot Striping | Highway Trans. Fund 323 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 521
517 | 18470402006 | Waxahachie Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 324 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 522
518 | 24470402007 | Marathon Sub-Section | Insulate Interior Roof And Walls, Spray Foam. | Highway Trans. Fund 325 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 523
519 | 16470402008 | District Headquarters | Replace Floor In Lab Building District | Highway Trans. Fund 326 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 524
520 | 16470402009 | George West Maintenance Office | Install Electrical - George West MNT | Highway Trans. Fund 327 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 525
521 | 16470402010 | Goliad Co. | Replace Metal Siding On Office Building With New Siding | Highway Trans. Fund 328 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 526
522 | 16470402011 | Goliad Co. | Replace Sliding Garage Doors With Overhead Doors | Highway Trans. Fund 329 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 527
523 | 16470402012 | Kleburg Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 330 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 528
524 | 19470402013 | District Headquarters | Remodel Inside Of Building | Highway Trans. Fund 331 | 90000 | 90000 | mm/dd/yy | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding | 529
525 | 19470402014 | District Headquarters | Window Replacement | Highway Trans. Fund 332 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 530
526 | 25470402015 | Guthrie Maintenance Office SS | Re-Skin Exterior, Insulate Bujilding, Install Windows, Roof, & Doors, Upgrade Rest Room | Highway Trans. Fund 333 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding | 531
527 | 01470402016 | District Headquarters | Abatement Of Roof And Walls (Monitoring) | Highway Trans. Fund 334 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 532
528 | 01470402017 | District Headquarters | Abatement Of Roof And Walls (Remediation) | Highway Trans. Fund 335 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 533
529 | 01470402018 | District Headquarters | Abatement Of Roof And Walls (Testing) | Highway Trans. Fund 336 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 534
530 | 01470402019 | District Headquarters | Boiler And Chiller Repairs | Highway Trans. Fund 337 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 535
531 | 01470402020 | District Headquarters | Demolish Existing Building | Highway Trans. Fund 338 | 29500 | 29500 | mm/dd/yy | 0% | 0% | 0 | 0 | 29500 | Pending Administrative Funding | 536
532 | 01470402021 | District Headquarters | Renovate DHQ Campus | Highway Trans. Fund 339 | 1950000 | 1950000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1950000 | Pending Administrative Funding | 537
533 | 21470402022 | Pharr Area Engineer & Maintenance Office | Add Office And Reconfigure Space | Highway Trans. Fund 340 | 4000 | 4000 | mm/dd/yy | 0% | 0% | 0 | 0 | 4000 | Pending Administrative Funding | 538
534 | 21470402023 | Pharr Area Engineer & Maintenance Office | Add Vestibule | Highway Trans. Fund 341 | 10200 | 10200 | mm/dd/yy | 0% | 0% | 0 | 0 | 10200 | Pending Administrative Funding | 539
535 | 22470402024 | Del Rio Maintenance Office | Convert 2Nd Floor Into Four Offices And Restroom Renovation | Highway Trans. Fund 342 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 540
536 | 22470402025 | Del Rio Maintenance Office | Replace Flooring In Mechanical Room | Highway Trans. Fund 343 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 541
537 | 22470402026 | Del Rio Maintenance Office | Roof & Exterior Painting | Highway Trans. Fund 344 | 70000 | 70000 | mm/dd/yy | 0% | 0% | 0 | 0 | 70000 | Pending Administrative Funding | 542
538 | 11470402027 | District Headquarters | Install Vinyl Plank Flooring | Highway Trans. Fund 345 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 543
539 | 11470402028 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 346 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 544
540 | 11470402029 | District Headquarters | Paint Interior | Highway Trans. Fund 347 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 545
541 | 11470402030 | District Headquarters | Renovate Baydoor Offices | Highway Trans. Fund 348 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 546
542 | 11470402031 | District Headquarters | Replace Flooring | Highway Trans. Fund 349 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 547
543 | 11470402032 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 350 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 548
544 | 16470402033 | Refugio Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 351 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 549
545 | 16470402034 | Refugio Co. | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 352 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 550
546 | 16470402035 | Refugio Co. | Replace Metal Siding On Office Building With New Siding | Highway Trans. Fund 353 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 551
547 | 16470402036 | Refugio Maintenance Office | Repair Structure At Maintenance - Refugio Maintenance | Highway Trans. Fund 354 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 552
548 | 06470402037 | Andrews Maintenance Office | Replace Garage Door W/Panel & Electric Open. | Highway Trans. Fund 355 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 553
549 | 06470402038 | Andrews Maintenance Office | Replace Metal Roof & Exterior Walls, Insulate | Highway Trans. Fund 356 | 22000 | 22000 | mm/dd/yy | 0% | 0% | 0 | 0 | 22000 | Pending Administrative Funding | 554
550 | 04470402039 | Dumas Maintenance Office | Remove Oh Door In Breakroom And Install Walk Door | Highway Trans. Fund 357 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 555
551 | 03470402040 | Bowie Maintenance Office | Close In Front Of New Truck Shed And Add 4 Roll Up Doors | Highway Trans. Fund 358 | 80000 | 80000 | mm/dd/yy | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding | 556
552 | 10470402041 | District Headquarters | Replace Windows | Highway Trans. Fund 359 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 557
553 | 38470402042 | Camp Hubbard State Headquarters | Complete Renovation Of 5th Floor | Highway Trans. Fund 360 | 500000 | 500000 | mm/dd/yy | 0% | 0% | 0 | 0 | 500000 | Pending Administrative Funding | 558
554 | 38470402043 | Camp Hubbard State Headquarters | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 361 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 559
555 | 20470402044 | Woodville Maintenance Office | Install Additional Unit Heater | Highway Trans. Fund 362 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 560
556 | 20470402045 | Woodville Maintenance Office | Paint Interior of Facilities | Highway Trans. Fund 363 | 2500 | 2500 | mm/dd/yy | 0% | 0% | 0 | 0 | 2500 | Pending Administrative Funding | 561
557 | 20470402046 | Woodville Maintenance Office | Reskin, Replace Lighting And Reroof Bld | Highway Trans. Fund 364 | 95000 | 95000 | mm/dd/yy | 0% | 0% | 0 | 0 | 95000 | Pending Administrative Funding | 562
558 | 25470402047 | Memphis Maintenance Office | Replace Floor Tiles, Upgrade Rest Room; Redesign Office Space | Highway Trans. Fund 365 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 563
559 | 25470402048 | Memphis Maintenance Office | Re-Skin Exterior, Install Roof, New Windows and Remove Sky Lights W/ Roof Replacement; Redesign Parking Area | Highway Trans. Fund 366 | 335000 | 335000 | mm/dd/yy | 0% | 0% | 0 | 0 | 335000 | Pending Administrative Funding | 564
560 | 04470402049 | Canadian Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 367 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 565
561 | 24470402050 | Fort Hancock Sub-Section | Add Rolling Doors To Existing Storage Bldg. | Highway Trans. Fund 368 | 6000 | 6000 | mm/dd/yy | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding | 566
562 | 24470402051 | Fort Hancock Sub-Section | Exterior Renovations | Highway Trans. Fund 369 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 567
563 | 24470402052 | Fort Hancock Sub-Section | Install Entrance Weather Canopy, Front Door. Add Rolling Doors To Existing Storage Bldg. | Highway Trans. Fund 370 | 8100 | 8100 | mm/dd/yy | 0% | 0% | 0 | 0 | 8100 | Pending Administrative Funding | 568
564 | 04470402053 | Darouzett Maintenance Office | New Shop Heaters | Highway Trans. Fund 371 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 569
565 | 04470402054 | Darrouzett Maintenance Office | Abate and Remodel Office Area | Highway Trans. Fund 372 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 570
566 | 04470402055 | Gruver Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 373 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 571
567 | 04470402056 | Channing Maintenance Office | Electrical Upgrades | Highway Trans. Fund 374 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 572
568 | 04470402057 | Channing Maintenance Office | New Unit Heaters | Highway Trans. Fund 375 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 573
569 | 04470402058 | Channing Maintenance Office | Replace Roof, Re-Skin Exterior, Install New Insulation And Windows | Highway Trans. Fund 376 | 175000 | 175000 | mm/dd/yy | 0% | 0% | 0 | 0 | 175000 | Pending Administrative Funding | 574
570 | 04470402059 | Channing Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 377 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 575
571 | 17470402060 | Brenham Area Engineer & Maintenance Office | Install Bathroom/Showers In Shop/Welding Shop | Highway Trans. Fund 378 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 576
572 | 05470402061 | Post Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 379 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 577
573 | 05470402062 | Post Maintenance Office | Re-Skin Renovate Shop | Highway Trans. Fund 380 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 578
574 | 04470402063 | Panhandle Maintenance Office | Enlarge Supervisor Office And Breakroom | Highway Trans. Fund 381 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 579
575 | 04470402064 | Panhandle Maintenance Office | Install Overhead Doors And Openers | Highway Trans. Fund 382 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 580
576 | 04470402065 | Panhandle Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 383 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 581
577 | 25470402066 | Munday Maintenance Office | Upgrade Electrical & Lights In Maintenance Barn | Highway Trans. Fund 384 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 582
578 | 16470402067 | Goliad Co. | Replace Metal Siding On Equipment Shed And Roof With New Siding And Roof | Highway Trans. Fund 385 | 60000 | 60000 | mm/dd/yy | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding | 583
579 | 16470402068 | Goliad Maintenance Office | Replace Exterior Door At Equipment Storage - Goliad MNT | Highway Trans. Fund 386 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 584
580 | 16470402069 | Goliad Maintenance Office | Replace Exterior Windows At Laboratory - Goliad MNT | Highway Trans. Fund 387 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 585
581 | 11470402070 | District Headquarters | Renovate Bathroom | Highway Trans. Fund 388 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 586
582 | 11470402071 | District Headquarters | Renovate Interior | Highway Trans. Fund 389 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 587
583 | 06470402072 | Andrews Maintenance Office | Repaint Exterior | Highway Trans. Fund 390 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 588
584 | 06470402073 | Andrews Maintenance Office | Repair/Replace Atg System On Above Ground Fuel Tanks | Highway Trans. Fund 391 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 589
585 | 06470402074 | Andrews Maintenance Office | Seal Roof Penetrations | Highway Trans. Fund 392 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 590
586 | 06470402075 | McCamey Maintenance Office | Paint Building Exterior | Highway Trans. Fund 393 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 591
587 | 06470402076 | McCamey Maintenance Office | Replace Linolium With Tile In Offices | Highway Trans. Fund 394 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 592
588 | 06470402077 | McCamey Maintenance Office | Upgrade Electrical Wiring & Lights In Shop Area | Highway Trans. Fund 395 | 7000 | 7000 | mm/dd/yy | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding | 593
589 | 07470402078 | Ballinger Maintenance Office | Erect Buildings Over Lifts | Highway Trans. Fund 396 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 594
590 | 09470402079 | District Headquarters | Replace Windows | Highway Trans. Fund 397 | 33450 | 33450 | mm/dd/yy | 0% | 0% | 0 | 0 | 33450 | Pending Administrative Funding | 595
591 | 06470402080 | Sanderson Maintenance Office | Replace Windows | Highway Trans. Fund 398 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 596
592 | 23470402081 | Comanche Maintenance Office | Renovate Facilities | Highway Trans. Fund 399 | 294000 | 294000 | mm/dd/yy | 0% | 0% | 0 | 0 | 294000 | Pending Administrative Funding | 597
593 | 17470402082 | Brenham Area Engineer & Maintenance Office | Add Lighting And Catwalks To V-Box Area | Highway Trans. Fund 400 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 598
594 | 17470402083 | Brenham Area Engineer & Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 401 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 599
595 | 17470402084 | Brenham Area Engineer & Maintenance Office | New Sidewalk Lab To Parking Lot | Highway Trans. Fund 402 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding | 600
596 | 06470402085 | Stanton Maintenance Office | Install Shed Kit | Highway Trans. Fund 403 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 601
597 | 06470402086 | Stanton Maintenance Office | Repair/Replace ATG System On Above Ground Fuel Tanks | Highway Trans. Fund 404 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 602
598 | 21470402087 | San Isidro Maintenance Office Sub-Section | Reconfigure Two Restrooms & Office | Highway Trans. Fund 405 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 603
599 | 15470402088 | Pearsall Maintenance Office | Refurbish Shop Building Skin And Roof | Highway Trans. Fund 406 | 95000 | 95000 | mm/dd/yy | 0% | 0% | 0 | 0 | 95000 | Pending Administrative Funding | 604
600 | 38470402089 | Austin HQ | Austin HQ Campus Repairs | Highway Trans. Fund 407 | 5000000 | 5000000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000000 | Pending Administrative Funding | 605
601 | 09470402090 | District Headquarters | New Insulation & Replace Windows | Highway Trans. Fund 408 | 52200 | 52200 | mm/dd/yy | 0% | 0% | 0 | 0 | 52200 | Pending Administrative Funding | 606
602 | 03470402091 | Bowie Maintenance Office | Replace Exterior Windows At Warehouse - Bowie Maintenance | Highway Trans. Fund 409 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 607
603 | 19470402092 | District Headquarters | Remodel Inside Of Building | Highway Trans. Fund 410 | 87000 | 87000 | mm/dd/yy | 0% | 0% | 0 | 0 | 87000 | Pending Administrative Funding | 608
604 | 23470402093 | Brady Maintenance Office | Renovate Facilities | Highway Trans. Fund 411 | 317000 | 317000 | mm/dd/yy | 0% | 0% | 0 | 0 | 317000 | Pending Administrative Funding | 609
605 | 17470402094 | Bryan Area Engineer & Maintenance Office | Reskin Shed | Highway Trans. Fund 412 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 610
606 | 17470402095 | Madisonville Maintenance Office | Fence/Gate Work | Highway Trans. Fund 413 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 611
607 | 17470402096 | Madisonville Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 414 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 612
608 | 17470402097 | Madisonville Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 415 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 613
609 | 17470402098 | Madisonville Maintenance Office | Replace Fuel Canopy | Highway Trans. Fund 416 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 614
610 | 25470402099 | Crowell Maintenance Office | Replace Floor Tiles, Windows, Doors, Locks | Highway Trans. Fund 417 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 615
611 | 25470402100 | Crowell Maintenance Office | Rewire Office, New Lights; Heaters In Truck Barn | Highway Trans. Fund 418 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 616
612 | 25470402101 | Matador Maintenance Office | Re-Skin Exterior, Insulate Building, Install Windows, Roof and Lights; Redesign Office Space | Highway Trans. Fund 419 | 325000 | 325000 | mm/dd/yy | 0% | 0% | 0 | 0 | 325000 | Pending Administrative Funding | 617
613 | 16470402102 | Nueces East | Install Redundant 2000 Gallon Diesel Tank To Existing Fuel Island | Highway Trans. Fund 420 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 618
614 | 18470402103 | Ennis Maintenance Office | Electrical Panel Upgrades | Highway Trans. Fund 421 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 619
615 | 18470402104 | Ennis Maintenance Office | Floor Tile Abatement - Corridors Only (Stain Concrete) | Highway Trans. Fund 422 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 620
616 | 18470402105 | Ennis Maintenance Office | Paint Exterior | Highway Trans. Fund 423 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 621
617 | 18470402106 | Ennis Maintenance Office | Restroom Partitions Replaced | Highway Trans. Fund 424 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 622
618 | 21470402107 | Zapata Maintenance Office Sub-Section | Renovate Building Into Offices. Renovate Restrooms. | Highway Trans. Fund 425 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 623
619 | 04470402108 | Claude Maintenance Office | New Overhead Doors | Highway Trans. Fund 426 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 624
620 | 04470402109 | Stratford Maintenance Office | Install Overhead Doors and Openers | Highway Trans. Fund 427 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 625
621 | 20470402110 | Anahuac Maintenance Office | Install Storm Shutters | Highway Trans. Fund 428 | 14000 | 14000 | mm/dd/yy | 0% | 0% | 0 | 0 | 14000 | Pending Administrative Funding | 626
622 | 20470402111 | Newton Maintenance Office | Interior Lighting | Highway Trans. Fund 429 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 627
623 | 20470402112 | Woodville Maintenance Office | Abate Transit Siding | Highway Trans. Fund 430 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 628
624 | 20470402113 | Woodville Maintenance Office | Replace Roof, Lighting & Siding | Highway Trans. Fund 431 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 629
625 | 23470402114 | Coleman Maintenance Office | Renovate Facilities | Highway Trans. Fund 432 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 630
626 | 17470402115 | Buffalo Maintenance Office | Repair Roof | Highway Trans. Fund 433 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 631
627 | 17470402116 | Buffalo Maintenance Office | Restroom Remodels | Highway Trans. Fund 434 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 632
628 | 17470402117 | Buffalo Maintenance Office | Upgrade HVAC System | Highway Trans. Fund 435 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 633
629 | 17470402118 | Cameron Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 436 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 634
630 | 17470402119 | Cameron Maintenance Office | Replace Flooring (Carpet & Tile) | Highway Trans. Fund 437 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 635
631 | 17470402120 | Cameron Maintenance Office | Redo Walls In Office | Highway Trans. Fund 438 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 636
632 | 17470402121 | Cameron Maintenance Office | Reskin MNT Office Building | Highway Trans. Fund 439 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 637
633 | 17470402122 | Cameron Maintenance Office | Reskin Shed | Highway Trans. Fund 440 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 638
634 | 25470402123 | Paducah Maintenance Office | Replace Restrooms | Highway Trans. Fund 441 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 639
635 | 25470402124 | Silverton Maintenance Office | Insulate, New Windows And Roof | Highway Trans. Fund 442 | 275000 | 275000 | mm/dd/yy | 0% | 0% | 0 | 0 | 275000 | Pending Administrative Funding | 640
636 | 25470402125 | Silverton Maintenance Office | Re-Skin Exterior, Insulate Building,Install Windows and Roof | Highway Trans. Fund 443 | 175000 | 175000 | mm/dd/yy | 0% | 0% | 0 | 0 | 175000 | Pending Administrative Funding | 641
637 | 16470402126 | Goliad Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 444 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 642
638 | 16470402127 | Goliad Maintenance Office | Replace Exterior Door At Equipment Storage - Goliad MNT | Highway Trans. Fund 445 | 16000 | 16000 | mm/dd/yy | 0% | 0% | 0 | 0 | 16000 | Pending Administrative Funding | 643
639 | 18470402128 | District Headquarters | Upgrade Lighting | Highway Trans. Fund 446 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 644
640 | 12470402129 | Angleton Area Engineer & Maintenance Office | New Carpet/VCT | Highway Trans. Fund 447 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 645
641 | 22470402130 | Brackettville | Deactivate Or Remove Mag Locks | Highway Trans. Fund 448 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 646
642 | 22470402131 | Brackettville | Furnish/Install Exterior Safety Lights | Highway Trans. Fund 449 | 1500 | 1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding | 647
643 | 22470402132 | Brackettville | Renovate Breakroom | Highway Trans. Fund 450 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 648
644 | 22470402133 | Brackettville | Restroom Renovations (Both Men and Women) | Highway Trans. Fund 451 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 649
645 | 22470402134 | Brackettville | Retrofit Bay Area Into Conference Room. (17'X28') 14' Ceiling. Tile Flooring, HVAC, Electrical, Communications, Removal Of Exiting Door. | Highway Trans. Fund 452 | 55000 | 55000 | mm/dd/yy | 0% | 0% | 0 | 0 | 55000 | Pending Administrative Funding | 650
646 | 07470402135 | Sterling City Maintenance Office | Erect Buildings Over Lifts | Highway Trans. Fund 453 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 651
647 | 17470402136 | Navasota Maintenance Office | Restroom Remodels | Highway Trans. Fund 454 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 652
648 | 25470402137 | Munday Maintenance Office | New Partition Walls & Larger Break Room, Upgrade Rest Room, New Windows & Doors, Redesign Office Space | Highway Trans. Fund 455 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 653
649 | 25470402138 | Munday Maintenance Office | Replace Floor Tiles | Highway Trans. Fund 456 | 9500 | 9500 | mm/dd/yy | 0% | 0% | 0 | 0 | 9500 | Pending Administrative Funding | 654
650 | 18470402139 | District Headquarters | Paint Exterior | Highway Trans. Fund 457 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 655
651 | 18470402140 | District Headquarters | Restroom Partitions Replacement - Men's Restroom | Highway Trans. Fund 458 | 1500 | 1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding | 656
652 | 18470402141 | District Headquarters | Window - Ceramic Coating (Warehouse/Facilities/Shop) | Highway Trans. Fund 459 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 657
653 | 05470402142 | District Headquarters | Campuswide Electrical Upgrade | Highway Trans. Fund 460 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 658
654 | 05470402143 | District Headquarters | Install Exit Loops | Highway Trans. Fund 461 | 2500 | 2500 | mm/dd/yy | 0% | 0% | 0 | 0 | 2500 | Pending Administrative Funding | 659
655 | 05470402144 | District Headquarters | New VCT Floor | Highway Trans. Fund 462 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 660
656 | 05470402145 | District Headquarters | New VCT Floor | Highway Trans. Fund 463 | 78000 | 78000 | mm/dd/yy | 0% | 0% | 0 | 0 | 78000 | Pending Administrative Funding | 661
657 | 05470402146 | District Headquarters | Replace Stairs Going In To District Break Room | Highway Trans. Fund 464 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 662
658 | 05470402147 | District Headquarters | Replace Stairs Going Into Maint. Office | Highway Trans. Fund 465 | 7000 | 7000 | mm/dd/yy | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding | 663
659 | 06470402148 | Kermit Maintenance Office | Paint Exterior Walls & Re-Insulate Weldging Shop | Highway Trans. Fund 466 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 664
660 | 21470402149 | Hebbronville Area Engineer & Maintenance Office | Add Large Conference Room | Highway Trans. Fund 467 | 252000 | 252000 | mm/dd/yy | 0% | 0% | 0 | 0 | 252000 | Pending Administrative Funding | 665
661 | 21470402150 | Hebbronville Area Engineer & Maintenance Office | Restroom Renovation | Highway Trans. Fund 468 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 666
662 | 21470402151 | Hebbronville Area Engineer & Maintenance Office | Locker Room With Showers | Highway Trans. Fund 469 | 0 | 0 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding | 667
663 | 21470402152 | Hebbronville Area Engineer & Maintenance Office | Phone/Computer Access | Highway Trans. Fund 470 | 0 | 0 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding | 668
664 | 21470402153 | Hebbronville Area Engineer & Maintenance Office | Ventilation Upgrade | Highway Trans. Fund 471 | 0 | 0 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding | 669
665 | 09470402154 | Marlin Area Engineer & Maintenance Office | Remodel Office | Highway Trans. Fund 472 | 488000 | 488000 | mm/dd/yy | 0% | 0% | 0 | 0 | 488000 | Pending Administrative Funding | 670
666 | 03470402155 | Electra Maintenance Office | Building Renovation | Highway Trans. Fund 473 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 671
667 | 03470402156 | Electra Maintenance Office | Reskin And Replace Windows | Highway Trans. Fund 474 | 90000 | 90000 | mm/dd/yy | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding | 672
668 | 13470402157 | Edna Maintenance Office | Paint Metal On Shed | Highway Trans. Fund 475 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 673
669 | 13470402158 | Jackson Cty Maint. | Paint Interior/Exterior Of Mechanic/Warehouse | Highway Trans. Fund 476 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 674
670 | 17470402159 | Navasota Maintenance Office | Demolish Old Ae Building | Highway Trans. Fund 477 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding | 675
671 | 17470402160 | Navasota Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 478 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 676
672 | 17470402161 | Navasota Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 479 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 677
673 | 16470402162 | Karnes City Area Engineer & Maintenance Office | Interior Renovations | Highway Trans. Fund 480 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 678
674 | 16470402163 | Karnes City Area Engineer & Maintenance Office | Repair Plumbing System - Karnes City AEM | Highway Trans. Fund 481 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 679
675 | 05470402164 | District Headquarters | Security System Upgrade - C-Cure | Highway Trans. Fund 482 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 680
676 | 05470402165 | Post RDC | Add New Wall To Dock With Overhead Door Wk Door | Highway Trans. Fund 483 | 90000 | 90000 | mm/dd/yy | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding | 681
677 | 38470402166 | Camp Hubbard State Headquarters | Replace Data Closet AC | Highway Trans. Fund 484 | 6000 | 6000 | mm/dd/yy | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding | 682
678 | 10470402167 | District Headquarters | Demolish Abandoned Structure | Highway Trans. Fund 485 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 683
679 | 10470402168 | District Headquarters | Exterior Renovations | Highway Trans. Fund 486 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 684
680 | 10470402169 | District Headquarters | Replace Carpet In Administration Building | Highway Trans. Fund 487 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 685
681 | 09470402170 | Mexia Maintenance Office | Renovate Maintenance Facility | Highway Trans. Fund 488 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 686
682 | 08470402171 | District Headquarters | Construct Concrete Apron Around The District Headquarters | Highway Trans. Fund 489 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 687
683 | 08470402172 | District Headquarters | Repair And Replace All Plumbing Fixtures | Highway Trans. Fund 490 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 688
684 | 17470402173 | Caldwell Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 491 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 689
685 | 17470402174 | Caldwell Maintenance Office | New Fuel Canopy | Highway Trans. Fund 492 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 690
686 | 17470402175 | Caldwell Maintenance Office | Repaving Of Parking Areas | Highway Trans. Fund 493 | 400000 | 400000 | mm/dd/yy | 0% | 0% | 0 | 0 | 400000 | Pending Administrative Funding | 691
687 | 17470402176 | Caldwell Maintenance Office | Replace Gutters | Highway Trans. Fund 494 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 692
688 | 24470402177 | Fort Davis Maintenance Office | Insulate Interior Of Stock Room / Storage | Highway Trans. Fund 495 | 22500 | 22500 | mm/dd/yy | 0% | 0% | 0 | 0 | 22500 | Pending Administrative Funding | 693
689 | 02470402178 | District Headquarters | Convert Conference Room To EOC | Highway Trans. Fund 496 | 153000 | 153000 | mm/dd/yy | 0% | 0% | 0 | 0 | 153000 | Pending Administrative Funding | 694
690 | 02470402179 | District Headquarters | Electrical Upgrade For The Whole District Headquarters | Highway Trans. Fund 497 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding | 695
691 | 02470402180 | District Headquarters | Install Interior Walls At Warehouse - Fort Worth DHQ Ware House Office | Highway Trans. Fund 498 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 696
692 | 02470402181 | District Headquarters | Install Interiors At Shop - Fort Worth DHQ Locker Rooms | Highway Trans. Fund 499 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 697
693 | 02470402182 | District Headquarters | Modifications/Upgrade HVAC | Highway Trans. Fund 500 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding | 698
694 | 02470402183 | District Headquarters | Replace\New Windows At Laboratory - Fort Worth DHQ | Highway Trans. Fund 501 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 699
695 | 12470402184 | Rosenberg Area Engineer & Maintenance Office | Paint Exterior (5 Buildings) | Highway Trans. Fund 502 | 97000 | 97000 | mm/dd/yy | 0% | 0% | 0 | 0 | 97000 | Pending Administrative Funding | 700
696 | 12470402185 | Rosenberg Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 503 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 701
697 | 12470402186 | Rosenberg Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 504 | 240000 | 240000 | mm/dd/yy | 0% | 0% | 0 | 0 | 240000 | Pending Administrative Funding | 702
698 | 05470402187 | Post Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 505 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 703
699 | 06470402188 | District Headquarters | Repair/Replace Carpet In Tp&D Area | Highway Trans. Fund 506 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 704
700 | 06470402189 | District Headquarters | Upgrade The District Complex Plumbing System | Highway Trans. Fund 507 | 280000 | 280000 | mm/dd/yy | 0% | 0% | 0 | 0 | 280000 | Pending Administrative Funding | 705
701 | 15470402190 | District Headquarters | Repair Foundation | Highway Trans. Fund 508 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 706
702 | 15470402191 | District Headquarters | Repair Sidewalks | Highway Trans. Fund 509 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 707
703 | 15470402192 | Seguin RDC | Restroom Renovation/Addition | Highway Trans. Fund 510 | 80000 | 80000 | mm/dd/yy | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding | 708
704 | 08470402193 | District Headquarters | Add Wall, Lighting, And Ventilation | Highway Trans. Fund 511 | 7000 | 7000 | mm/dd/yy | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding | 709
705 | 08470402194 | District Headquarters | New Carpet | Highway Trans. Fund 512 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 710
706 | 08470402195 | District Headquarters | Replace Flooring At The Special Crews Building | Highway Trans. Fund 513 | 16700 | 16700 | mm/dd/yy | 0% | 0% | 0 | 0 | 16700 | Pending Administrative Funding | 711
707 | 25470402196 | Wellington Maintenance Office | Re-Skin Exterior, Insulate Building, Install Windows and Roof, Redesign Office Space | Highway Trans. Fund 514 | 325000 | 325000 | mm/dd/yy | 0% | 0% | 0 | 0 | 325000 | Pending Administrative Funding | 712
708 | 02470402197 | District Headquarters | Lab Upgrades | Highway Trans. Fund 515 | 558500 | 558500 | mm/dd/yy | 0% | 0% | 0 | 0 | 558500 | Pending Administrative Funding | 713
709 | 02470402198 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 516 | 21500 | 21500 | mm/dd/yy | 0% | 0% | 0 | 0 | 21500 | Pending Administrative Funding | 714
710 | 12470402199 | Houston South Area Engineer & Maintenance Office | Renovate 3 Buildings Into One | Highway Trans. Fund 517 | 1200000 | 1200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1200000 | Pending Administrative Funding | 715
711 | 12470402200 | Houston South Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 518 | 29000 | 29000 | mm/dd/yy | 0% | 0% | 0 | 0 | 29000 | Pending Administrative Funding | 716
712 | 12470402201 | Houston South Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 519 | 485000 | 485000 | mm/dd/yy | 0% | 0% | 0 | 0 | 485000 | Pending Administrative Funding | 717
713 | 12470402202 | Houston South Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 520 | 0 | 0 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding | 718
714 | 06470402203 | District Headquarters | Repair/Replace Atg System On Above Ground Fuel Tanks | Highway Trans. Fund 521 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 719
715 | 06470402204 | District Headquarters | Replace/Repair Windows | Highway Trans. Fund 522 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 720
716 | 15470402205 | Seguin Area Engineer & Maintenance Office | Exterior Paint | Highway Trans. Fund 523 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 721
717 | 15470402206 | Seguin Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 524 | 0 | 0 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding | 722
718 | 15470402207 | Seguin Area Engineer & Maintenance Office | Restroom Renovation/Addition | Highway Trans. Fund 525 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 723
719 | 04470402208 | Canyon Maintenance Office | Abate Inside,Replace Windows And Replace Roof | Highway Trans. Fund 526 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 724
720 | 05470402209 | Bovina Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 527 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 725
721 | 05470402210 | Bovina Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 528 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 726
722 | 05470402211 | Bovina Maintenance Office | Repaint Exterior, Old Faded Peeling | Highway Trans. Fund 529 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 727
723 | 05470402212 | Brownfield Area Engineer & Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 530 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 728
724 | 05470402213 | Brownfield Area Engineer & Maintenance Office | New VCT Floor | Highway Trans. Fund 531 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 729
725 | 05470402214 | Brownfield Area Engineer & Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 532 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 730
726 | 05470402215 | Ralls Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 533 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 731
727 | 05470402216 | Ralls Maintenance Office | Paint Exterior | Highway Trans. Fund 534 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 732
728 | 05470402217 | Ralls Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 535 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 733
729 | 15470402218 | Tilden Maintenance Office | Carpet & Paint | Highway Trans. Fund 536 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 734
730 | 15470402219 | Tilden Maintenance Office | Relocate Radio Tower | Highway Trans. Fund 537 | 0 | 0 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding | 735
731 | 15470402220 | Tilden Maintenance Office | Upgrade Restrooms | Highway Trans. Fund 538 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 736
732 | 38470402221 | Camp Hubbard State Headquarters | Renovate Interior Office Space, Include Abatement, New Lighting, New Windows, New Duct Work | Highway Trans. Fund 539 | 1000000 | 1000000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1000000 | Pending Administrative Funding | 737
733 | 10470402222 | North Tyler Maintenance Office | Elevated Water Storage | Highway Trans. Fund 540 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 738
734 | 10470402223 | North Tyler Maintenance Office | Remodel Office & New Roof | Highway Trans. Fund 541 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding | 739
735 | 13470402224 | Austin Cty Maint. | Paint Interior Structure Of Equip Shed | Highway Trans. Fund 542 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 740
736 | 13470402225 | Austin Cty Maint. | Rehab. Of Mechanic Area (Front Wall W/ Door) | Highway Trans. Fund 543 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 741
737 | 13470402226 | Colorado Cty Maint. | Level And Paint Interior Of Office Building | Highway Trans. Fund 544 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 742
738 | 13470402227 | Colorado Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 545 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 743
739 | 13470402228 | Columbus Maintenance Office | Level Building (Maintenance Bldg) | Highway Trans. Fund 546 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 744
740 | 13470402229 | Columbus Maintenance Office | Paint Office & Warehouse Exterior | Highway Trans. Fund 547 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 745
741 | 13470402230 | District Headquarters | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 548 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 746
742 | 08470402231 | Big Spring Maintenance Office | New VCT Floor | Highway Trans. Fund 549 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 747
743 | 08470402232 | Big Spring Maintenance Office | Paint Exterior | Highway Trans. Fund 550 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 748
744 | 08470402233 | Big Spring Maintenance Office | Repair Damage To Walls And Wood In Area Ofice | Highway Trans. Fund 551 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 749
745 | 20470402234 | District Headquarters | Install Rotary Lift & 2 Ton Overhead Crane And Trolley | Highway Trans. Fund 552 | 13000 | 13000 | mm/dd/yy | 0% | 0% | 0 | 0 | 13000 | Pending Administrative Funding | 750
746 | 20470402235 | District Headquarters | Paint Flag Pole | Highway Trans. Fund 553 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 751
747 | 20470402236 | District Headquarters | Rebuild Overhead Door (10) | Highway Trans. Fund 554 | 4000 | 4000 | mm/dd/yy | 0% | 0% | 0 | 0 | 4000 | Pending Administrative Funding | 752
748 | 20470402237 | District Headquarters | Interior Remodel | Highway Trans. Fund 555 | 6700 | 6700 | mm/dd/yy | 0% | 0% | 0 | 0 | 6700 | Pending Administrative Funding | 753
749 | 20470402238 | District Headquarters | Interior Remodel | Highway Trans. Fund 556 | 39000 | 39000 | mm/dd/yy | 0% | 0% | 0 | 0 | 39000 | Pending Administrative Funding | 754
750 | 20470402239 | District Headquarters | Repair ADA Ramps | Highway Trans. Fund 557 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 755
751 | 20470402240 | District Headquarters | Replace 25 Infra-Red Heaters | Highway Trans. Fund 558 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 756
752 | 20470402241 | Districtwide | Flag Pole Lights | Highway Trans. Fund 559 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 757
753 | 20470402242 | Districtwide | Replace Fuel Dispensers Districtwide | Highway Trans. Fund 560 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 758
754 | 25470402243 | Dickens Maintenance Office | Replace Windows & Locks | Highway Trans. Fund 561 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 759
755 | 12470402244 | La Marque Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 562 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding | 760
756 | 12470402245 | La Marque Area Engineer & Maintenance Office | Replace Siding (8 Buildings) | Highway Trans. Fund 563 | 640000 | 640000 | mm/dd/yy | 0% | 0% | 0 | 0 | 640000 | Pending Administrative Funding | 761
757 | 06470402246 | McCamey Maintenance Office | Repaint Exterior | Highway Trans. Fund 564 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 762
758 | 03470402247 | District Headquarters | Building Renovations | Highway Trans. Fund 565 | 112000 | 112000 | mm/dd/yy | 0% | 0% | 0 | 0 | 112000 | Pending Administrative Funding | 763
759 | 03470402248 | District Headquarters | Foundation And Cosmetic Repairs | Highway Trans. Fund 566 | 160000 | 160000 | mm/dd/yy | 0% | 0% | 0 | 0 | 160000 | Pending Administrative Funding | 764
760 | 13470402249 | Colorado Cty Maint. | Close Open Bay And Add To Sign Room | Highway Trans. Fund 567 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 765
761 | 13470402250 | Colorado Cty Maint. | Replace 5 Overhead Roll Up Doors And Paint 3 | Highway Trans. Fund 568 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 766
762 | 13470402251 | Columbus Maintenance Office | Replace Oh Doors On Shed | Highway Trans. Fund 569 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 767
763 | 13470402252 | Matagorda Cty Maint. | Bird Proof Underside Of Roof-Purlins | Highway Trans. Fund 570 | 6000 | 6000 | mm/dd/yy | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding | 768
764 | 13470402253 | Matagorda Cty Maint. | Construct Elevated Platform For Wash Rack | Highway Trans. Fund 571 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 769
765 | 19470402254 | District Headquarters | Renovation Of Warehouse | Highway Trans. Fund 572 | 515000 | 515000 | mm/dd/yy | 0% | 0% | 0 | 0 | 515000 | Pending Administrative Funding | 770
766 | 19470402255 | Texarkana Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 573 | 80000 | 80000 | mm/dd/yy | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding | 771
767 | 19470402256 | Texarkana Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 574 | 111000 | 111000 | mm/dd/yy | 0% | 0% | 0 | 0 | 111000 | Pending Administrative Funding | 772
768 | 17470402257 | Brenham Area Engineer & Maintenance Office | Paint Building | Highway Trans. Fund 575 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 773
769 | 17470402258 | Brenham Area Engineer & Maintenance Office | Remove Fuel Awning/Install New Awning For Parking | Highway Trans. Fund 576 | 250000 | 250000 | mm/dd/yy | 0% | 0% | 0 | 0 | 250000 | Pending Administrative Funding | 774
770 | 16470402259 | District Headquarters | Repair Structure At Administration - Corpus Christi DHQ | Highway Trans. Fund 577 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 775
771 | 16470402260 | District Headquarters | Replace Flooring At Administration - Corpus Christi DHQ | Highway Trans. Fund 578 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 776
772 | 16470402261 | District Headquarters | Replace Overhead Gas Heaters In Auto Shop | Highway Trans. Fund 579 | 24000 | 24000 | mm/dd/yy | 0% | 0% | 0 | 0 | 24000 | Pending Administrative Funding | 777
773 | 16470402262 | Goliad Maintenance Office | Replace\New Exterior Walls At Equipment Storage - Goliad MNT | Highway Trans. Fund 580 | 90000 | 90000 | mm/dd/yy | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding | 778
774 | 16470402263 | Karnes Co. | Remodel Inside Office (Lights, Ceiling, Floor, Paint) | Highway Trans. Fund 581 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 779
775 | 16470402264 | Karnes Co. | Replace 2 Existing Fuel Dispensers At The Fuel Station | Highway Trans. Fund 582 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 780
776 | 02470402265 | Mineral Wells Maintenance Office | Renovate Maintenance Facility | Highway Trans. Fund 583 | 500000 | 500000 | mm/dd/yy | 0% | 0% | 0 | 0 | 500000 | Pending Administrative Funding | 781
777 | 05470402266 | Plains Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 584 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 782
778 | 05470402267 | Plains Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 585 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 783
779 | 05470402268 | Seminole Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 586 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 784
780 | 05470402269 | Seminole Maintenance Office | New VCT Floor | Highway Trans. Fund 587 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 785
781 | 05470402270 | Seminole Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 588 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 786
782 | 11470402271 | Crockett Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 589 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 787
783 | 11470402272 | Crockett Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 590 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 788
784 | 11470402273 | Crockett Maintenance Office | Replace Windows | Highway Trans. Fund 591 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 789
785 | 11470402274 | Crockett Maintenance Office | Upgrade Exterior Lighting | Highway Trans. Fund 592 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 790
786 | 11470402275 | Crockett Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 593 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 791
787 | 11470402276 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 594 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 792
788 | 06470402277 | Crane Maintenance Office | Paint Exterior And Interior | Highway Trans. Fund 595 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 793
789 | 06470402278 | Crane Maintenance Office | Reconfigure Bay For Break Room Locker Room. New Kitchenette Lockers Flooring Walls Plumbing Electrical | Highway Trans. Fund 596 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 794
790 | 06470402279 | Crane Maintenance Office | Remove & Replace Windows In Main Office | Highway Trans. Fund 597 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 795
791 | 06470402280 | Crane Maintenance Office | Upgrade Electrical Wiring, Lights And Breakers | Highway Trans. Fund 598 | 4000 | 4000 | mm/dd/yy | 0% | 0% | 0 | 0 | 4000 | Pending Administrative Funding | 796
792 | 06470402281 | Crane Maintenance Office | Upgrade Rain Gutters | Highway Trans. Fund 599 | 7000 | 7000 | mm/dd/yy | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding | 797
793 | 21470402282 | District Headquarters | Upgrade Conference Rooms | Highway Trans. Fund 600 | 51000 | 51000 | mm/dd/yy | 0% | 0% | 0 | 0 | 51000 | Pending Administrative Funding | 798
794 | 21470402283 | District Headquarters | Repair Plumbing Problems | Highway Trans. Fund 601 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 799
795 | 21470402284 | Falfurrias Maintenance Office Sub-Section | Building Renovation | Highway Trans. Fund 602 | 163300 | 163300 | mm/dd/yy | 0% | 0% | 0 | 0 | 163300 | Pending Administrative Funding | 800
796 | 21470402285 | Falfurrias Maintenance Office Sub-Section | Upgrade Mechanic Shop | Highway Trans. Fund 603 | 190000 | 190000 | mm/dd/yy | 0% | 0% | 0 | 0 | 190000 | Pending Administrative Funding | 801
797 | 09470402286 | Meridian Maintenance Office | Retrofit Truck Bays To Conference Rooms and Meeting Space | Highway Trans. Fund 604 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 802
798 | 09470402287 | Meridian Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 605 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 803
799 | 03470402288 | District Headquarters | Retrofit Warehouse Space To Large Meeting Room | Highway Trans. Fund 606 | 28500 | 28500 | mm/dd/yy | 0% | 0% | 0 | 0 | 28500 | Pending Administrative Funding | 804
800 | 03470402289 | Nocona Maintenance Office | Building Remodel | Highway Trans. Fund 607 | 90000 | 90000 | mm/dd/yy | 0% | 0% | 0 | 0 | 90000 | Pending Administrative Funding | 805
801 | 13470402290 | Calhoun Cty Maint. | Interior Renovation (Floors & Walls) | Highway Trans. Fund 608 | 60000 | 60000 | mm/dd/yy | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding | 806
802 | 13470402291 | Calhoun Cty Maint. | Paint Exterior Structure Of Canopy, Mechanci Shop, & Stock Room | Highway Trans. Fund 609 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 807
803 | 13470402292 | Calhoun Cty Maint. | Paint Interior Structure Of Equip Shed | Highway Trans. Fund 610 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 808
804 | 13470402293 | District Headquarters | Replace Shifting Concrete Pad Under Pad Mount Electrical Transformer | Highway Trans. Fund 611 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 809
805 | 13470402294 | Port Lavaca Maintenance Office | Replace Flooring | Highway Trans. Fund 612 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 810
806 | 20470402295 | Port Arthur Area Engineer & Maintenance Office | Asbestos Abatement | Highway Trans. Fund 613 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 811
807 | 20470402296 | Port Arthur Area Engineer & Maintenance Office | Paint Interior Of Facility | Highway Trans. Fund 614 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 812
808 | 20470402297 | Port Arthur Area Engineer & Maintenance Office | Replace Doors, Frames & Locksets | Highway Trans. Fund 615 | 6000 | 6000 | mm/dd/yy | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding | 813
809 | 23470402298 | District Headquarters | Renovate Lab | Highway Trans. Fund 616 | 712000 | 712000 | mm/dd/yy | 0% | 0% | 0 | 0 | 712000 | Pending Administrative Funding | 815
810 | 18470402300 | Waxahachie Area Engineer & Maintenance Office | Electrical - Additional Service | Highway Trans. Fund 617 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 816
811 | 24470402301 | Dell City Maintenance Office | Install Bird Screens @ Truck Bays | Highway Trans. Fund 618 | 5500 | 5500 | mm/dd/yy | 0% | 0% | 0 | 0 | 5500 | Pending Administrative Funding | 817
812 | 12470402302 | Rosenberg Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 619 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding | 818
813 | 22470402303 | Del Rio Maintenance Office | Exterior Warehouse Painting | Highway Trans. Fund 620 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 819
814 | 05470402304 | Levelland Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 621 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 820
815 | 05470402305 | Levelland Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 622 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 821
816 | 05470402306 | SE Maint. Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 623 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 822
817 | 11470402307 | District Headquarters | Foundation Repairs | Highway Trans. Fund 624 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 823
818 | 11470402308 | District Headquarters | Paint Interior | Highway Trans. Fund 625 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 824
819 | 11470402309 | District Headquarters | Repair Dist Shop Parking Lot And Stripe Existing Lots At Dist HQ | Highway Trans. Fund 626 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 825
820 | 11470402310 | District Headquarters | Replace Fuel Awning | Highway Trans. Fund 627 | 21000 | 21000 | mm/dd/yy | 0% | 0% | 0 | 0 | 21000 | Pending Administrative Funding | 826
821 | 11470402311 | District Headquarters | Replace Fuel Dispensers | Highway Trans. Fund 628 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 827
822 | 11470402312 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 629 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 828
823 | 04470402313 | District Headquarters | Abate Windows And Paint Exterior Of Shop | Highway Trans. Fund 630 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 829
824 | 19470402314 | Mt Pleasant Area Engineer & Maintenance Office | Major Renovation | Highway Trans. Fund 631 | 767000 | 767000 | mm/dd/yy | 0% | 0% | 0 | 0 | 767000 | Pending Administrative Funding | 830
825 | 19470402315 | Mt Pleasant Area Engineer & Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 632 | 65000 | 65000 | mm/dd/yy | 0% | 0% | 0 | 0 | 65000 | Pending Administrative Funding | 831
826 | 19470402316 | Mt Pleasant Area Engineer & Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 633 | 128300 | 128300 | mm/dd/yy | 0% | 0% | 0 | 0 | 128300 | Pending Administrative Funding | 832
827 | 18470402317 | Rockwall Maintenance Office | Electrical Panel Upgrades | Highway Trans. Fund 634 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 833
828 | 18470402318 | Rockwall Maintenance Office | Paint Exterior | Highway Trans. Fund 635 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 834
829 | 18470402319 | Rockwall Maintenance Office | Renovate Interior | Highway Trans. Fund 636 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 835
830 | 18470402320 | Rockwall Maintenance Office | Siding - Partial Replacement | Highway Trans. Fund 637 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 836
831 | 22470402321 | Carrizo Springs | Replace Two Overhead Doors | Highway Trans. Fund 638 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 837
832 | 22470402322 | Carrizo Springs | Restroom Renovation | Highway Trans. Fund 639 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 838
833 | 22470402323 | Carrizo Springs | Retrofit Locker Room Into Storage/Supply Room | Highway Trans. Fund 640 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 839
834 | 05470402324 | FloydADA Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 641 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 840
835 | 05470402325 | Lamesa Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 642 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 841
836 | 05470402326 | Lamesa Maintenance Office | New VCT Floor | Highway Trans. Fund 643 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 842
837 | 05470402327 | Lamesa Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 644 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 843
838 | 11470402328 | Lufkin Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 645 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 844
839 | 11470402329 | Lufkin Maintenance Office | Renovate Bathrooms | Highway Trans. Fund 646 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 845
840 | 11470402330 | Lufkin Maintenance Office | Renovate Interior | Highway Trans. Fund 647 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 846
841 | 11470402331 | Lufkin Maintenance Office | Replace Flooring | Highway Trans. Fund 648 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 847
842 | 11470402332 | Lufkin Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 649 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 848
843 | 11470402333 | Lufkin Maintenance Office | Replace Windows | Highway Trans. Fund 650 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 849
844 | 11470402334 | Lufkin Maintenance Office | Underskirt Fuel Awning | Highway Trans. Fund 651 | 6000 | 6000 | mm/dd/yy | 0% | 0% | 0 | 0 | 6000 | Pending Administrative Funding | 850
845 | 11470402335 | Lufkin Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 652 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 851
846 | 07470402336 | District Headquarters | Modifications/Upgrade Electrical | Highway Trans. Fund 653 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 852
847 | 07470402337 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 654 | 21500 | 21500 | mm/dd/yy | 0% | 0% | 0 | 0 | 21500 | Pending Administrative Funding | 853
848 | 20470402338 | District Headquarters | Paint Interior | Highway Trans. Fund 655 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 855
849 | 12470402340 | Houston Northwest | Renovate Interior/Exterior (20K Sf Concrete Tilt Wall Aquired Building) | Highway Trans. Fund 656 | 2000000 | 2000000 | mm/dd/yy | 0% | 0% | 0 | 0 | 2000000 | Pending Administrative Funding | 856
850 | 12470402341 | West Harris Maintenance Office | Renovation And Upgrade To AEM | Highway Trans. Fund 657 | 2000000 | 2000000 | mm/dd/yy | 0% | 0% | 0 | 0 | 2000000 | Pending Administrative Funding | 857
851 | 05470402342 | District Headquarters-LBB AE's | New VCT Floor | Highway Trans. Fund 658 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 858
852 | 05470402343 | District Headquarters-LBB AE's | Replace Roof | Highway Trans. Fund 659 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 859
853 | 05470402344 | District Headquarters-LBB AE's | Replace Steps With ADA Ramp Back Door | Highway Trans. Fund 660 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 860
854 | 11470402345 | District Headquarters | Upgrade Interior Lighting | Highway Trans. Fund 661 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 861
855 | 04470402346 | Vega Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 662 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 862
856 | 04470402347 | Vega Maintenance Office | Upgrade Current Welding Shop | Highway Trans. Fund 663 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 863
857 | 19470402348 | New Boston Maintenance Office | Remodel Inside Of Building Paint Floor And Ceiling | Highway Trans. Fund 664 | 80000 | 80000 | mm/dd/yy | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding | 864
858 | 19470402349 | New Boston Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 665 | 99400 | 99400 | mm/dd/yy | 0% | 0% | 0 | 0 | 99400 | Pending Administrative Funding | 865
859 | 15470402350 | Devine Maintenance Office | Paint, Carpet Replacement | Highway Trans. Fund 666 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 866
860 | 15470402351 | Devine Maintenance Office | Restroom Upgrades | Highway Trans. Fund 667 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 867
861 | 13470402352 | District Headquarters | Replace All Exterior Roof Facial & Renovate All Exterior Entrances | Highway Trans. Fund 668 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 868
862 | 16470402353 | Goliad Co. | Replace Metal Siding On Equipment Shed And Roof With New Siding And Roof | Highway Trans. Fund 669 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 869
863 | 16470402354 | Kingsville Maintenance Office | Paint Interior Walls At Maintenance - Kingsville Maintenance | Highway Trans. Fund 670 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 870
864 | 16470402355 | Kingsville Maintenance Office | Replace Flooring At Maintenance - Kingsville MNT | Highway Trans. Fund 671 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 871
865 | 16470402356 | Kleburg Co. | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 672 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 872
866 | 05470402357 | Plainview Area Engineer & Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 673 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 873
867 | 05470402358 | Tahoka Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 674 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 874
868 | 05470402359 | Tahoka Maintenance Office | New VCT Floor | Highway Trans. Fund 675 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 875
869 | 05470402360 | Tahoka Maintenance Office | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 676 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 876
870 | 04470402361 | Canadian Maintenance Office | Foundation Repair | Highway Trans. Fund 677 | 0 | 0 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding | 877
871 | 04470402362 | Canadian Maintenance Office | Install Overhead Doors And Openers | Highway Trans. Fund 678 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 878
872 | 04470402363 | Canadian Maintenance Office | Renovation Of Building Exterior | Highway Trans. Fund 679 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 879
873 | 04470402364 | Canadian Maintenance Office | Restroom Abatement And Remodel | Highway Trans. Fund 680 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 880
874 | 04470402365 | E way | Lighting Upgrades | Highway Trans. Fund 681 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 881
875 | 04470402366 | Hereford Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 682 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 882
876 | 14470402367 | Lockhart Maintenance Office | Foundation Repair | Highway Trans. Fund 683 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 883
877 | 20470402368 | Kountze Maintenance Office | Install Overhead Doors | Highway Trans. Fund 684 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 884
878 | 20470402369 | Kountze Maintenance Office | Paint Office Exterior | Highway Trans. Fund 685 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 885
879 | 20470402370 | Liberty Area Engineer & Maintenance Office | Replace Electrical Panels And Upgrade Electrical Wiring. | Highway Trans. Fund 686 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 886
880 | 24470402371 | Terlingua Sub-Section | Additional Outside LED Lighting For Houses. | Highway Trans. Fund 687 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 887
881 | 24470402372 | Terlingua Sub-Section | Interior Renovation; Electrical, HVAC, Walls Finish, Framing, Floors And Kitchen | Highway Trans. Fund 688 | 36000 | 36000 | mm/dd/yy | 0% | 0% | 0 | 0 | 36000 | Pending Administrative Funding | 888
882 | 24470402373 | Terlingua Sub-Section | Paint Interior Walls | Highway Trans. Fund 689 | 17500 | 17500 | mm/dd/yy | 0% | 0% | 0 | 0 | 17500 | Pending Administrative Funding | 889
883 | 24470402374 | Terlingua Sub-Section | Repair / Replace Plumbing Lines Fro Meter To Houses | Highway Trans. Fund 690 | 18000 | 18000 | mm/dd/yy | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding | 890
884 | 05470402375 | Muleshoe Maintenance Office | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 691 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 891
885 | 05470402376 | Muleshoe Maintenance Office | New VCT Floor | Highway Trans. Fund 692 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 892
886 | 07470402377 | District Headquarters | Paint Interior Of Facility | Highway Trans. Fund 693 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 893
887 | 08470402378 | Snyder Maintenance Office | Convert Old Propane Gas Heaters In Shop To Natural Gas | Highway Trans. Fund 694 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 894
888 | 08470402379 | Snyder Maintenance Office | Convert The Old Salt Bin Into A Sign And Traffic Control Room Storage | Highway Trans. Fund 695 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 895
889 | 08470402380 | Snyder Maintenance Office | New VCT Floor | Highway Trans. Fund 696 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 896
890 | 04470402381 | Perryton Maintenance Office | Replace Roof, Re-Skin Exterior, Install New Insulation And Windows | Highway Trans. Fund 697 | 175000 | 175000 | mm/dd/yy | 0% | 0% | 0 | 0 | 175000 | Pending Administrative Funding | 897
891 | 04470402382 | Perryton Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 698 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 898
892 | 08470402383 | Haskell Maintenance Office | Convert Old Shop Into Breakroom | Highway Trans. Fund 699 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 899
893 | 23470402384 | Brownwood Area Engineer & Maintenance Office | Renovate Office | Highway Trans. Fund 700 | 311000 | 311000 | mm/dd/yy | 0% | 0% | 0 | 0 | 311000 | Pending Administrative Funding | 900
894 | 17470402385 | Huntsville Area Engineer & Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 701 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 901
895 | 17470402386 | Huntsville Area Engineer & Maintenance Office | Paint Building | Highway Trans. Fund 702 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 902
896 | 17470402387 | Huntsville Area Engineer & Maintenance Office | Repair Foundation/Porch/Walls | Highway Trans. Fund 703 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 903
897 | 17470402388 | Huntsville Area Engineer & Maintenance Office | Repair Roof | Highway Trans. Fund 704 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 904
898 | 17470402389 | Huntsville Area Engineer & Maintenance Office | Replace Fuel Canopy | Highway Trans. Fund 705 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 905
899 | 17470402390 | Huntsville Area Engineer & Maintenance Office | Replace Wiring In Building | Highway Trans. Fund 706 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 906
900 | 25470402391 | Quanah Maintenance Office | Paint Interior & Exterior, Resurface Parking Area | Highway Trans. Fund 707 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 907
901 | 25470402392 | Quanah Maintenance Office | Replace Floor Tiles; Upgrade Rest Rooms, Redesign Office Space | Highway Trans. Fund 708 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 908
902 | 16470402393 | District Headquarters | Replace Electrical Panels At Right Of Way - Corpus Christi District Headquarters And Area Engineer And Maintenance Special Jobs | Highway Trans. Fund 709 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 909
903 | 16470402394 | District Headquarters | Replace\New Electrical Panel At Right Of Way - Corpus Christi DHQ | Highway Trans. Fund 710 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 910
904 | 06470402395 | Iraan Maintenance Office | Enclose 3 Bays With Insulated Overhead Doors To Secure Equipment & Weather Protection | Highway Trans. Fund 711 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 911
905 | 06470402396 | Iraan Maintenance Office | Repair/Replace ATG System On Above Ground Fuel Tanks | Highway Trans. Fund 712 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 912
906 | 06470402397 | Iraan Maintenance Office | Replace Windows | Highway Trans. Fund 713 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 913
907 | 21470402398 | Mission Maintenance Office | New 4K Gallon Fuel Tanks/Replace Fuel Pumps | Highway Trans. Fund 714 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding | 914
908 | 21470402399 | Mission Maintenance Office | New Heavy Equipment Overhead Doors | Highway Trans. Fund 715 | 57000 | 57000 | mm/dd/yy | 0% | 0% | 0 | 0 | 57000 | Pending Administrative Funding | 915
909 | 21470402400 | Mission Maintenance Office | New Heavy Equipment Pull Through Stalls | Highway Trans. Fund 716 | 21500 | 21500 | mm/dd/yy | 0% | 0% | 0 | 0 | 21500 | Pending Administrative Funding | 916
910 | 21470402401 | Mission Maintenance Office | Renovate Building | Highway Trans. Fund 717 | 112000 | 112000 | mm/dd/yy | 0% | 0% | 0 | 0 | 112000 | Pending Administrative Funding | 917
911 | 13470402402 | Jackson Cty Maint. | Interior Renovation (Floors & Walls) | Highway Trans. Fund 718 | 60000 | 60000 | mm/dd/yy | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding | 918
912 | 18470402403 | Hutchins Maintenance Office | Electrical Panel Upgrades | Highway Trans. Fund 719 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 919
913 | 18470402404 | Hutchins Maintenance Office | Paint Exterior | Highway Trans. Fund 720 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 920
914 | 24470402405 | Alpine Area Engineer & Maintenance Office | Remodel Bay For Maintenance Training And Breakroom, Add One Additional Office In Bay. | Highway Trans. Fund 721 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 921
915 | 12470402406 | Houston NE Area Engineer & Maintenance Office | Renovate Restrooms (Locker Rooms) | Highway Trans. Fund 722 | 42000 | 42000 | mm/dd/yy | 0% | 0% | 0 | 0 | 42000 | Pending Administrative Funding | 922
916 | 12470402407 | Houston NE Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 723 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 923
917 | 21470402408 | Hebbronville Area Engineer & Maintenance Office | Upgrade Mechanic Shop | Highway Trans. Fund 724 | 0 | 0 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding | 924
918 | 17470402409 | Brenham Area Engineer & Maintenance Office | Upgrade Lighting In Washbay | Highway Trans. Fund 725 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 925
919 | 17470402410 | Brenham Area Engineer & Maintenance Office | Replace Siding On A Wash Bay | Highway Trans. Fund 726 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 926
920 | 17470402411 | Bryan Area Engineer & Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 727 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 927
921 | 17470402412 | Bryan Area Engineer & Maintenance Office | Install Above Ground Fuel Tank | Highway Trans. Fund 728 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 928
922 | 17470402413 | Bryan Area Engineer & Maintenance Office | Install Automatic Gate On Rear Gate | Highway Trans. Fund 729 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 929
923 | 06470402414 | Balmorhea Maintenance Office | Remove and Replace Existing Shower Floor Tile | Highway Trans. Fund 730 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 930
924 | 06470402415 | Balmorhea Maintenance Office | Remove and Replace Floor Tile Main Office | Highway Trans. Fund 731 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 931
925 | 21470402416 | San Benito Area Engineer & Maintenance Office | Upgrade Ballasts | Highway Trans. Fund 732 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 932
926 | 24470402417 | Presidio Maintenance Office | Convert Bay Into A Break Room | Highway Trans. Fund 733 | 19500 | 19500 | mm/dd/yy | 0% | 0% | 0 | 0 | 19500 | Pending Administrative Funding | 933
927 | 24470402418 | Presidio Maintenance Office | Extend Office Space Along Same Roof Line To The South 16 Feet | Highway Trans. Fund 734 | 80000 | 80000 | mm/dd/yy | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding | 934
928 | 19470402419 | Daingerfield Maintenance Office | Install Overhead Door Operators & Gate | Highway Trans. Fund 735 | 32200 | 32200 | mm/dd/yy | 0% | 0% | 0 | 0 | 32200 | Pending Administrative Funding | 935
929 | 19470402420 | Daingerfield Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 736 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 936
930 | 17470402421 | Buffalo Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 737 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 937
931 | 17470402422 | Buffalo Maintenance Office | Remove Undergrnd/Install Above Grnd Fuel Tanks | Highway Trans. Fund 738 | 350000 | 350000 | mm/dd/yy | 0% | 0% | 0 | 0 | 350000 | Pending Administrative Funding | 938
932 | 21470402423 | Laguna Vista Maintenance Office Sub-Section | Building Renovation | Highway Trans. Fund 739 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 939
933 | 21470402424 | Laguna Vista Maintenance Office Sub-Section | Replace Overhead Doors | Highway Trans. Fund 740 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 940
934 | 04470402425 | Groom Maintenance Office | Electrical Upgrades | Highway Trans. Fund 741 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 941
935 | 04470402426 | Groom Maintenance Office | New Compressor/Relocate | Highway Trans. Fund 742 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 942
936 | 04470402427 | Groom Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 743 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 943
937 | 15470402428 | Bandera Maintenance Office | Paint, Carpet Replacement | Highway Trans. Fund 744 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 944
938 | 15470402429 | Bandera Maintenance Office | Restroom Upgrades | Highway Trans. Fund 745 | 0 | 0 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Pending Administrative Funding | 945
939 | 15470402430 | Bandera Maintenance Office | Window Replacement | Highway Trans. Fund 746 | 180000 | 180000 | mm/dd/yy | 0% | 0% | 0 | 0 | 180000 | Pending Administrative Funding | 946
940 | 15470402431 | Hondo Area Engineer & Maintenance Office | Asbestos Abatement, Carpet & Paint | Highway Trans. Fund 747 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 947
941 | 15470402432 | Hondo Area Engineer & Maintenance Office | Restroom Upgrade | Highway Trans. Fund 748 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 948
942 | 12470402433 | East Harris Maintenance Office | Locker Room Upgrades/Addition Of Showers | Highway Trans. Fund 749 | 42000 | 42000 | mm/dd/yy | 0% | 0% | 0 | 0 | 42000 | Pending Administrative Funding | 949
943 | 12470402434 | Houston NE Area Engineer & Maintenance Office | Replace Gutter System | Highway Trans. Fund 750 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 950
944 | 15470402435 | Uvalde Maintenance Office | Replace Irrigation System | Highway Trans. Fund 751 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 951
945 | 08470402436 | Roby Maintenance Office | Install Floor Tile | Highway Trans. Fund 752 | 18000 | 18000 | mm/dd/yy | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding | 952
946 | 08470402437 | Roby Maintenance Office | Level Wash Bay | Highway Trans. Fund 753 | 1500 | 1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding | 953
947 | 08470402438 | Roby Maintenance Office | Install Overhead Door Openers and Push Buttons in all Bay Door Openings. Total of 10 Door Openers. | Highway Trans. Fund 754 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 954
948 | 08470402439 | Roby Maintenance Office | Repair Structural Damage to Columns | Highway Trans. Fund 755 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 955
949 | 08470402440 | Roby Maintenance Office | Upgrade Power Washer Building | Highway Trans. Fund 756 | 2500 | 2500 | mm/dd/yy | 0% | 0% | 0 | 0 | 2500 | Pending Administrative Funding | 956
950 | 08470402441 | Taylor Co. Maintenance Office | Upgrade Wash Bay | Highway Trans. Fund 757 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 957
951 | 24470402442 | Pine Springs Sub-Section | Additional Outside LED Lighting For Houses. | Highway Trans. Fund 758 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 958
952 | 24470402443 | Pine Springs Sub-Section | Install Garage Door Openers | Highway Trans. Fund 759 | 7000 | 7000 | mm/dd/yy | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding | 959
953 | 24470402444 | Pine Springs Sub-Section | Renovate Stock Area; Insulate Metal Walls, Ceiling | Highway Trans. Fund 760 | 11500 | 11500 | mm/dd/yy | 0% | 0% | 0 | 0 | 11500 | Pending Administrative Funding | 960
954 | 07470402445 | Big Lake Maintenance Office | Construct Buildings Over Lifts | Highway Trans. Fund 761 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 961
955 | 03470402446 | Vernon Area Engineer & Maintenance Office | Replace Flooring At Maintenance - Vernon Area Engineer And Maintenance | Highway Trans. Fund 762 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 962
956 | 14470402447 | East Travis Maintenance Office | Foundation Repair | Highway Trans. Fund 763 | 167200 | 167200 | mm/dd/yy | 0% | 0% | 0 | 0 | 167200 | Pending Administrative Funding | 963
957 | 17470402448 | Navasota Maintenance Office | Replace Fuel Canopy - Navasota MNT | Highway Trans. Fund 764 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 964
958 | 16470402449 | Corpus Christi Area Engineer & Maintenance Office | Replace Flooring At Area Engineer And Maintenance - Corpus Christi AEM | Highway Trans. Fund 765 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 965
959 | 16470402450 | Nueces East | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 766 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 966
960 | 19470402451 | Carthage Maintenance Office | Install Overhead Door Operators & Gate | Highway Trans. Fund 767 | 82600 | 82600 | mm/dd/yy | 0% | 0% | 0 | 0 | 82600 | Pending Administrative Funding | 967
961 | 19470402452 | Carthage Maintenance Office | Remodel Inside Of Building Including Bathrooms | Highway Trans. Fund 768 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 968
962 | 16470402453 | San Patricio Co | Replace Ceiling Tiles In Office Building | Highway Trans. Fund 769 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 969
963 | 16470402454 | San Patricio Co | Replace 2 Existing Dual Product Fuel Dispensers At The Fuel Station | Highway Trans. Fund 770 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 970
964 | 16470402455 | San Patricio Co | Replace Flooring In Office Building And Paint Walls | Highway Trans. Fund 771 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 971
965 | 16470402456 | Sinton Area Engineer & Maintenance Office | Paint Interior Walls At Area Engineer And Maintenance - Sinton AEM | Highway Trans. Fund 772 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 972
966 | 16470402457 | Sinton Area Engineer & Maintenance Office | Replace Ceilings At Area Engineer And Maintenance - Sinton AEM | Highway Trans. Fund 773 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 973
967 | 16470402458 | Sinton Area Engineer & Maintenance Office | Replace Flooring At Area Engineer And Maintenance - Sinton AEM | Highway Trans. Fund 774 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 974
968 | 16470402459 | Aransas Co. | Replace Existing Floor Tile And Paint Office | Highway Trans. Fund 775 | 17500 | 17500 | mm/dd/yy | 0% | 0% | 0 | 0 | 17500 | Pending Administrative Funding | 975
969 | 16470402460 | Aransas Co. | Install Storm Shutters On All Windows And Doors | Highway Trans. Fund 776 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 976
970 | 16470402461 | Rockport Maintenance Office | Install Exteriors At Maintenance - Rockport MNT | Highway Trans. Fund 777 | 28000 | 28000 | mm/dd/yy | 0% | 0% | 0 | 0 | 28000 | Pending Administrative Funding | 977
971 | 16470402462 | Rockport Maintenance Office | Repair Exterior Windows At Maintenance - Rockport MNT | Highway Trans. Fund 778 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 978
972 | 16470402463 | Rockport Maintenance Office | Replace Flooring At Maintenance - Rockport MNT | Highway Trans. Fund 779 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 979
973 | 12470402464 | Humble Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 780 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding | 980
974 | 12470402465 | Humble Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 781 | 320000 | 320000 | mm/dd/yy | 0% | 0% | 0 | 0 | 320000 | Pending Administrative Funding | 981
975 | 22470402466 | Del Rio Maintenance Office | Storage Shed Asbestos Testing & Abatement | Highway Trans. Fund 782 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 982
976 | 22470402467 | Del Rio Maintenance Office | Storage Shed Repairs | Highway Trans. Fund 783 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 983
977 | 11470402468 | Center Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 784 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 984
978 | 11470402469 | Center Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 785 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 985
979 | 11470402470 | Center Maintenance Office | Replace Windows | Highway Trans. Fund 786 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 986
980 | 11470402471 | Center Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 787 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 987
981 | 11470402472 | Livingston Area Engineer & Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 788 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 988
982 | 11470402473 | Livingston Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 789 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 989
983 | 11470402474 | Livingston Area Engineer & Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 790 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 990
984 | 11470402475 | Nacogdoches Area Engineer & Maintenance Office | Install Electric Baydoor Openers | Highway Trans. Fund 791 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 991
985 | 11470402476 | Nacogdoches Area Engineer & Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 792 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 992
986 | 11470402477 | Nacogdoches Area Engineer & Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 793 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 993
987 | 11470402478 | Nacogdoches Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 794 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 994
988 | 11470402479 | Nacogdoches Area Engineer & Maintenance Office | Upgrade Exterior Lighting | Highway Trans. Fund 795 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 995
989 | 11470402480 | Nacogdoches Area Engineer & Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 796 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 996
990 | 11470402481 | San Augustine Area Engineer & Maintenance Office | Install Electric Baydoor Openers | Highway Trans. Fund 797 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 997
991 | 11470402482 | San Augustine Area Engineer & Maintenance Office | Paint Entire Facility Interior And Exterior | Highway Trans. Fund 798 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 998
992 | 11470402483 | San Augustine Area Engineer & Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 799 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 999
993 | 11470402484 | San Augustine Area Engineer & Maintenance Office | Replace Windows | Highway Trans. Fund 800 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1000
994 | 11470402485 | San Augustine Area Engineer & Maintenance Office | Upgrade Exterior Lighting | Highway Trans. Fund 801 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1001
995 | 11470402486 | San Augustine Area Engineer & Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 802 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1002
996 | 06470402487 | Stanton Maintenance Office | Enclose 3 Bays With Insulated Overhead Doors To Secure Equipment & Weather Protection | Highway Trans. Fund 803 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1003
997 | 06470402488 | Stanton Maintenance Office | Install Ladder Or Staircase | Highway Trans. Fund 804 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1004
998 | 06470402489 | Stanton Maintenance Office | Reinstall Evaporative Coolers In Wall | Highway Trans. Fund 805 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 1005
999 | 21470402490 | District Headquarters | Exterior Facade Repairs To Warehouse, Shop & Teleconference Training Center | Highway Trans. Fund 806 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 1006
1000 | 21470402491 | District Headquarters | Renovate Shop | Highway Trans. Fund 807 | 117000 | 117000 | mm/dd/yy | 0% | 0% | 0 | 0 | 117000 | Pending Administrative Funding | 1007
1001 | 21470402492 | District Headquarters/Area Engineer & Maintenance Office | Install Vehicle Exhaust System. Replace Existing Ceiling Fans. | Highway Trans. Fund 808 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 1008
1002 | 21470402493 | District Headquarters/Area Engineer & Maintenance Office | Replace All Windows/Frames. | Highway Trans. Fund 809 | 85000 | 85000 | mm/dd/yy | 0% | 0% | 0 | 0 | 85000 | Pending Administrative Funding | 1009
1003 | 15470402494 | Pleasanton Area Engineer & Maintenance Office | Paint, Carpet Replacement | Highway Trans. Fund 810 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1010
1004 | 15470402495 | Pleasanton Area Engineer & Maintenance Office | Restroom Upgrade | Highway Trans. Fund 811 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 1011
1005 | 04470402496 | Dalhart Maintenance Office | Electrical Upgrades | Highway Trans. Fund 812 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 1012
1006 | 04470402497 | Dalhart Maintenance Office | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 813 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 1013
1007 | 04470402498 | Dalhart Maintenance Office | Shop Lighting Upgrades | Highway Trans. Fund 814 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1014
1008 | 19470402499 | Jefferson Maintenance Office | Remodel Inside Of Building | Highway Trans. Fund 815 | 65000 | 65000 | mm/dd/yy | 0% | 0% | 0 | 0 | 65000 | Pending Administrative Funding | 1015
1009 | 19470402500 | Jefferson Maintenance Office | Replace Overhead Doors | Highway Trans. Fund 816 | 113000 | 113000 | mm/dd/yy | 0% | 0% | 0 | 0 | 113000 | Pending Administrative Funding | 1016
1010 | 18470402501 | District Headquarters | Analysis By Engineering Consultant | Highway Trans. Fund 817 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 1017
1011 | 18470402502 | District Headquarters | Countertops - Restrooms (Solid Surface) | Highway Trans. Fund 818 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1018
1012 | 02470402503 | District Headquarters | Remodel Old Sign Shop Into A Fitness Center | Highway Trans. Fund 819 | 831000 | 831000 | mm/dd/yy | 0% | 0% | 0 | 0 | 831000 | Pending Administrative Funding | 1019
1013 | 06470402504 | Kermit Maintenance Office | Paint Exterior Walls | Highway Trans. Fund 820 | 21000 | 21000 | mm/dd/yy | 0% | 0% | 0 | 0 | 21000 | Pending Administrative Funding | 1020
1014 | 13470402505 | Gonzales Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 821 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1021
1015 | 04470402506 | Loop | Lighting Upgrades | Highway Trans. Fund 822 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 1022
1016 | 04470402507 | Loop | Retrofit Shop Bays For 10 Yard Trucks | Highway Trans. Fund 823 | 100000 | 100000 | mm/dd/yy | 0% | 0% | 0 | 0 | 100000 | Pending Administrative Funding | 1023
1017 | 19470402508 | Linden Maintenance Office | Install Overhead Door Operators & Gate | Highway Trans. Fund 824 | 83000 | 83000 | mm/dd/yy | 0% | 0% | 0 | 0 | 83000 | Pending Administrative Funding | 1024
1018 | 19470402509 | Linden Maintenance Office | Replace VCT Flooring And Paint Interior | Highway Trans. Fund 825 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 1025
1019 | 18470402510 | District Headquarters | Modular Furniture Installation | Highway Trans. Fund 826 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 1026
1020 | 18470402511 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 827 | 21500 | 21500 | mm/dd/yy | 0% | 0% | 0 | 0 | 21500 | Pending Administrative Funding | 1027
1021 | 18470402512 | District Headquarters | Countertops - Restrooms On 4Th Floor | Highway Trans. Fund 828 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1028
1022 | 18470402513 | District Headquarters | Paint Exterior And Interior | Highway Trans. Fund 829 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1029
1023 | 22470402514 | Del Rio Maintenance Office | Relocate Generator From Freer | Highway Trans. Fund 830 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 1030
1024 | 22470402515 | Del Rio Maintenance Office (US 90) | Men's Restroom Renovation | Highway Trans. Fund 831 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1031
1025 | 05470402516 | Morton Maintenance Office | Repaint Exterior, Old Faded Peeling | Highway Trans. Fund 832 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 1032
1026 | 05470402517 | Tulia Maintenance Office | Repaint Exterior, Old Faded Peeling | Highway Trans. Fund 833 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 1033
1027 | 13470402518 | Jackson Cty Maint. | Paint Interior Structure Of Equip Shed | Highway Trans. Fund 834 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1034
1028 | 22470402519 | Cotulla Maintenance Office | Men's Restroom Renovation | Highway Trans. Fund 835 | 24000 | 24000 | mm/dd/yy | 0% | 0% | 0 | 0 | 24000 | Pending Administrative Funding | 1035
1029 | 22470402520 | Cotulla Maintenance Office | Replace Breakroom Flooring | Highway Trans. Fund 836 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1036
1030 | 20470402521 | Jasper Area Engineer & Maintenance Office | Replace AV Electrical Circuit | Highway Trans. Fund 837 | 1500 | 1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 1500 | Pending Administrative Funding | 1037
1031 | 20470402522 | Jasper Area Engineer & Maintenance Office | Clean Fuel Tanks | Highway Trans. Fund 838 | 4000 | 4000 | mm/dd/yy | 0% | 0% | 0 | 0 | 4000 | Pending Administrative Funding | 1038
1032 | 20470402523 | Jasper Area Engineer & Maintenance Office | Interior Lighting | Highway Trans. Fund 839 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1039
1033 | 20470402524 | Jasper Area Engineer & Maintenance Office | Paint Office Interior | Highway Trans. Fund 840 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1040
1034 | 20470402525 | Jasper Area Engineer & Maintenance Office | Remodel Rest Rooms & Wall Repair | Highway Trans. Fund 841 | 54000 | 54000 | mm/dd/yy | 0% | 0% | 0 | 0 | 54000 | Pending Administrative Funding | 1041
1035 | 20470402526 | Jasper Area Engineer & Maintenance Office | Replace Carpet And VCT | Highway Trans. Fund 842 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1042
1036 | 20470402527 | Orange Maintenance Office | Replace Siding And Roofing | Highway Trans. Fund 843 | 65000 | 65000 | mm/dd/yy | 0% | 0% | 0 | 0 | 65000 | Pending Administrative Funding | 1043
1037 | 20470402528 | Orange Maintenance Office | Upgrade Electrical | Highway Trans. Fund 844 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1044
1038 | 12470402529 | Conroe Area Engineer & Maintenance Office | New Carpet/VCT | Highway Trans. Fund 845 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1045
1039 | 12470402530 | Conroe Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 846 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1046
1040 | 12470402531 | Conroe Area Engineer & Maintenance Office | Reconfigure Cubicles (Space Management) | Highway Trans. Fund 847 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1047
1041 | 12470402532 | Conroe Area Engineer & Maintenance Office | Renovate Breakroom | Highway Trans. Fund 848 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1048
1042 | 22470402533 | Laredo Administration | Administration: Nail Down Spanish Tiles; Remove/Replace Broken Spanish Tiles | Highway Trans. Fund 849 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding | 1049
1043 | 22470402534 | Laredo Area Engineer & Maintenance Office | Remove Worn Out Existing VCT Flooring & Replace Ceramic Tile | Highway Trans. Fund 850 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1050
1044 | 22470402535 | Laredo Area Engineer & Maintenance Office (Lilac/Conference room) | Retrofit To Video Teleconference Room | Highway Trans. Fund 851 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1051
1045 | 22470402536 | Laredo Auto Shop | Bat Issues (Clean Up And Resolution) | Highway Trans. Fund 852 | 300000 | 300000 | mm/dd/yy | 0% | 0% | 0 | 0 | 300000 | Pending Administrative Funding | 1052
1046 | 22470402537 | Laredo Auto Shop | Minor Restrooms Renovation | Highway Trans. Fund 853 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1053
1047 | 22470402538 | Laredo Compound facilities | Exterior Painting | Highway Trans. Fund 854 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 1054
1048 | 22470402539 | Laredo District Headquarters | Carpet Replacement | Highway Trans. Fund 855 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 1055
1049 | 22470402540 | Laredo FIN/Safety | Modular Unit (12) | Highway Trans. Fund 856 | 96000 | 96000 | mm/dd/yy | 0% | 0% | 0 | 0 | 96000 | Pending Administrative Funding | 1056
1050 | 15470402541 | Transguide | Proportionate Share Of 1St Floor Renovation | Highway Trans. Fund 857 | 1000000 | 1000000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1000000 | Pending Administrative Funding | 1057
1051 | 10470402542 | District Headquarters | Demo Warehouse Office | Highway Trans. Fund 858 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 1058
1052 | 10470402543 | District Headquarters | Install New Elevator | Highway Trans. Fund 859 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 1059
1053 | 10470402544 | District Headquarters | Reconfigure To Allow For Drivethrough | Highway Trans. Fund 860 | 21500 | 21500 | mm/dd/yy | 0% | 0% | 0 | 0 | 21500 | Pending Administrative Funding | 1060
1054 | 13470402545 | Victoria A.O. | Paint Interior Office | Highway Trans. Fund 861 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1061
1055 | 13470402546 | Victoria A.O. | Sealing Exterior Block Walls | Highway Trans. Fund 862 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1062
1056 | 13470402547 | Victoria Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 863 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1063
1057 | 13470402548 | Victoria Cty Maint. | Replace Wash Rack Canopy | Highway Trans. Fund 864 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 1064
1058 | 16470402549 | District Headquarters | Install Storm Shutters On All Windows And Doors | Highway Trans. Fund 865 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1065
1059 | 16470402550 | District Headquarters | Paint Exterior Walls At Shop - Corpus Christi DHQ | Highway Trans. Fund 866 | 27500 | 27500 | mm/dd/yy | 0% | 0% | 0 | 0 | 27500 | Pending Administrative Funding | 1066
1060 | 24470402551 | District Headquarters | Install LED Lighting In Wall Packs | Highway Trans. Fund 867 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1067
1061 | 24470402552 | District Headquarters | Install Vestabule / Canopy Near Breakroom | Highway Trans. Fund 868 | 36000 | 36000 | mm/dd/yy | 0% | 0% | 0 | 0 | 36000 | Pending Administrative Funding | 1068
1062 | 24470402553 | District Headquarters | Install Vestibule Front And Rear, Lobby Entries | Highway Trans. Fund 869 | 48000 | 48000 | mm/dd/yy | 0% | 0% | 0 | 0 | 48000 | Pending Administrative Funding | 1069
1063 | 24470402554 | District Headquarters | Lab Dock Storage, Install Soffit Filler To Close Off Gap At Top. | Highway Trans. Fund 870 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1070
1064 | 12470402555 | Angleton Area Engineer & Maintenance Office | Replace Insulation (Laboratory) | Highway Trans. Fund 871 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 1071
1065 | 05470402556 | District Headquarters-Division West Building | New VCT Floor | Highway Trans. Fund 872 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 1072
1066 | 15470402557 | Bexar Metro Area Engineer & Maintenance Office | Interior LED Lighting Upgrade | Highway Trans. Fund 873 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 1073
1067 | 15470402558 | Bexar Metro Area Engineer & Maintenance Office | Raise Truck Wash Canopy | Highway Trans. Fund 874 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1074
1068 | 15470402559 | Bexar Metro Area Engineer & Maintenance Office | Retrofit Equipment Bay For Enclosed Climate Control LED Storage | Highway Trans. Fund 875 | 2000 | 2000 | mm/dd/yy | 0% | 0% | 0 | 0 | 2000 | Pending Administrative Funding | 1075
1069 | 09470402560 | Gatesville Area Engineer & Maintenance Office | Upgrade Shop And Office | Highway Trans. Fund 876 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 1076
1070 | 13470402561 | Yoakum A.O. | Level Building & Repair Exterior Cracks In Brick | Highway Trans. Fund 877 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 1077
1071 | 13470402562 | Yoakum Area Engineer & Maintenance Office | Level Building (Area Engineers Bldg) | Highway Trans. Fund 878 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 1078
1072 | 17470402563 | Hearne Area Engineer & Maintenance Office | Install Welding Ventilation Hood | Highway Trans. Fund 879 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 1079
1073 | 17470402564 | Hearne Area Engineer & Maintenance Office | Redo HVAC/Vent/Pipes | Highway Trans. Fund 880 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1080
1074 | 17470402565 | Hearne Area Engineer & Maintenance Office | Redo Lighting In Washbay | Highway Trans. Fund 881 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1081
1075 | 17470402566 | Hearne Area Engineer & Maintenance Office | Replace Ceiling Tiles | Highway Trans. Fund 882 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1082
1076 | 05470402567 | Dimmitt Maintenance Office | Repaint Exterior | Highway Trans. Fund 883 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 1083
1077 | 03470402568 | Gainesville Area Engineer & Maintenance Office | Renovate Building For Storage | Highway Trans. Fund 884 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 1084
1078 | 25470402569 | Shamrock Maintenance Office | Convert Truck Barn To Drive Thru, New Heaters In Truck Barn | Highway Trans. Fund 885 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 1085
1079 | 18470402570 | Denton Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 886 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1086
1080 | 05470402571 | Littlefield Area Engineer & Maintenance Office | New VCT Floor | Highway Trans. Fund 887 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 1087
1081 | 05470402572 | Littlefield Area Engineer & Maintenance Office | Replace Windows AE's Office | Highway Trans. Fund 888 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1088
1082 | 05470402573 | NE Special Crews | Electrical Up-Grade Panel To Switches,Light Plug | Highway Trans. Fund 889 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 1089
1083 | 05470402574 | NE Special Crews | New VCT Floor | Highway Trans. Fund 890 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1090
1084 | 05470402575 | NE Special Crews | Remove In-Ground Hydraulic Floor Lift | Highway Trans. Fund 891 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 1091
1085 | 21470402576 | District Headquarters | Flooring Replacement | Highway Trans. Fund 892 | 7000 | 7000 | mm/dd/yy | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding | 1092
1086 | 15470402577 | Boerne Maintenance Office | Interior Paint | Highway Trans. Fund 893 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 1093
1087 | 38470402578 | TxDOT Flight Services | Building Renovations | Highway Trans. Fund 894 | 430000 | 430000 | mm/dd/yy | 0% | 0% | 0 | 0 | 430000 | Pending Administrative Funding | 1094
1088 | 38470402579 | TxDOT Flight Services | New Epoxy Flooring In Hangars 2,3 And 4 | Highway Trans. Fund 895 | 210000 | 210000 | mm/dd/yy | 0% | 0% | 0 | 0 | 210000 | Pending Administrative Funding | 1095
1089 | 38470402580 | TxDOT Flight Services | Repair Drainage Issues Around Hangars Water Run Off Going Inside | Highway Trans. Fund 896 | 60000 | 60000 | mm/dd/yy | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding | 1096
1090 | 20470402581 | Beaumont Area Engineer & Maintenance Office | Interior Lighting | Highway Trans. Fund 897 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1097
1091 | 20470402582 | Beaumont Area Engineer & Maintenance Office | Repair Heating System | Highway Trans. Fund 898 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 1098
1092 | 16470402583 | District Headquarters | Paint Interior Walls At Vehicle Titles And Registration - Corpus Christi DHQ | Highway Trans. Fund 899 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1099
1093 | 18470402584 | District Headquarters | Flooring Replaced - Remove VCT And Replace With VCT | Highway Trans. Fund 900 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1100
1094 | 18470402585 | District Headquarters | Paint Exterior | Highway Trans. Fund 901 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1101
1095 | 02470402586 | Decatur Area Engineer & Maintenance Office | Replace Flooring At Area Engineer And Maintenance - Decatur Area Engineer And Maintenance | Highway Trans. Fund 902 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1102
1096 | 13470402587 | Fayette Cty Maint. | Interior Renovation (Floors, Ceiling, & Ac Ducts) | Highway Trans. Fund 903 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 1103
1097 | 20470402588 | Anahuac Maintenance Office | Install Roll-Up Door Opener | Highway Trans. Fund 904 | 3000 | 3000 | mm/dd/yy | 0% | 0% | 0 | 0 | 3000 | Pending Administrative Funding | 1104
1098 | 20470402589 | Liberty Area Engineer & Maintenance Office | Abate Floor Tile | Highway Trans. Fund 905 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1105
1099 | 20470402590 | Liberty Area Engineer & Maintenance Office | Interior Lighting | Highway Trans. Fund 906 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1106
1100 | 20470402591 | Liberty Area Engineer & Maintenance Office | Paint Office Interior | Highway Trans. Fund 907 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1107
1101 | 20470402592 | Liberty Area Engineer & Maintenance Office | Replace Carpet And VCT | Highway Trans. Fund 908 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1108
1102 | 20470402593 | Liberty Area Engineer & Maintenance Office | Replace Electrical Panels | Highway Trans. Fund 909 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1109
1103 | 20470402594 | Liberty Area Engineer & Maintenance Office | Rest Room/Shower/Ac/Water Heater | Highway Trans. Fund 910 | 9500 | 9500 | mm/dd/yy | 0% | 0% | 0 | 0 | 9500 | Pending Administrative Funding | 1110
1104 | 17470402595 | Bryan Area Engineer & Maintenance Office | Renovate Maintenance Building | Highway Trans. Fund 911 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 1111
1105 | 17470402596 | Bryan Area Engineer & Maintenance Office | Replace Fuel Canopy - Bryan AEM | Highway Trans. Fund 912 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 1112
1106 | 17470402597 | Bryan Area Engineer & Maintenance Office | Restroom Remodels, Training Building | Highway Trans. Fund 913 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1113
1107 | 25470402598 | Clarendon Maintenance Office | Convert Truck Barn To Drive Thru, New Heaters In Truck Barn | Highway Trans. Fund 914 | 200000 | 200000 | mm/dd/yy | 0% | 0% | 0 | 0 | 200000 | Pending Administrative Funding | 1114
1108 | 24470402599 | El Paso (East) Area Engineer & Maintenance Office | Install New Front Doors (Building ) And Secure The Lobby Area | Highway Trans. Fund 915 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 1115
1109 | 24470402600 | El Paso (East) Area Engineer & Maintenance Office | Modify Interior Doorway, At Stockroom Forklift Access. | Highway Trans. Fund 916 | 5900 | 5900 | mm/dd/yy | 0% | 0% | 0 | 0 | 5900 | Pending Administrative Funding | 1116
1110 | 24470402601 | EL PASO (EAST) AREA Area Engineer & Maintenance Office | Building Renovations | Highway Trans. Fund 917 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding | 1117
1111 | 24470402602 | El Paso (West) Area Engineer & Maintenance Office | Install Truck Lift | Highway Trans. Fund 918 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding | 1118
1112 | 24470402603 | El Paso (West) Area Engineer & Maintenance Office | Larger Restroom In Our Maintenance Section | Highway Trans. Fund 919 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 1119
1113 | 02470402604 | District Headquarters | Emergency Generator At Intelligent Transportation Management Center - Fort Worth DHQ | Highway Trans. Fund 920 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding | 1120
1114 | 22470402605 | Freer | Interior & Exterior Painting & Sheet Metal Painting | Highway Trans. Fund 921 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 1121
1115 | 22470402606 | Freer | Overhead Projector & Electrical | Highway Trans. Fund 922 | 2500 | 2500 | mm/dd/yy | 0% | 0% | 0 | 0 | 2500 | Pending Administrative Funding | 1122
1116 | 38470402607 | CEDAR PARK Research and Technology Center | Interior Renovations | Highway Trans. Fund 923 | 180000 | 180000 | mm/dd/yy | 0% | 0% | 0 | 0 | 180000 | Pending Administrative Funding | 1123
1117 | 10470402608 | South Tyler Area Engineer & Maintenance Office | Repaint Bldg. B | Highway Trans. Fund 924 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1124
1118 | 09470402609 | Hillsboro Area Engineer & Maintenance Office | Upgrade Lab | Highway Trans. Fund 925 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 1125
1119 | 09470402610 | Hillsboro Area Engineer & Maintenance Office | Replace Plumbing | Highway Trans. Fund 926 | 12000 | 12000 | mm/dd/yy | 0% | 0% | 0 | 0 | 12000 | Pending Administrative Funding | 1126
1120 | 13470402611 | Colorado Cty Maint. | Painting Interior Structure Of Equip Shed | Highway Trans. Fund 927 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1127
1121 | 16470402612 | Bee Co. | Install Redundant 2000 Gallon Diesel Tank To Existing Fuel Island | Highway Trans. Fund 928 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 1128
1122 | 18470402613 | Cedar Hill Maintenance Office | Upgrade Electrical | Highway Trans. Fund 929 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 1129
1123 | 13470402614 | Hallettsville Maintenance Office | Replace Tin At Mechanic Shop | Highway Trans. Fund 930 | 7000 | 7000 | mm/dd/yy | 0% | 0% | 0 | 0 | 7000 | Pending Administrative Funding | 1130
1124 | 13470402615 | Lavaca Cty Maint | Replace Tin & Paint Exterior Struct Of Wash Rack | Highway Trans. Fund 931 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1131
1125 | 13470402616 | Lavaca Cty Maint. | Paint Exterior Structure Of Fuel Canopy | Highway Trans. Fund 932 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1132
1126 | 13470402617 | Lavaca Cty Maint. | Repair Sheetrock And Paint Walls | Highway Trans. Fund 933 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 1133
1127 | 19470402618 | District Headquarters | Remodel Inside Of Building | Highway Trans. Fund 934 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 1134
1128 | 19470402619 | District Headquarters | Restroom Upgrades | Highway Trans. Fund 935 | 181000 | 181000 | mm/dd/yy | 0% | 0% | 0 | 0 | 181000 | Pending Administrative Funding | 1135
1129 | 17470402620 | Brenham Area Engineer & Maintenance Office | Enclose Two Bays Of Equipment Shed | Highway Trans. Fund 936 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1136
1130 | 17470402621 | Brenham Area Engineer & Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 937 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1137
1131 | 17470402622 | Brenham Area Engineer & Maintenance Office | Install Electric Door Openers For Roll-Up Doors | Highway Trans. Fund 938 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 1138
1132 | 17470402623 | Brenham Area Engineer & Maintenance Office | Replace Windows On Storage Shed | Highway Trans. Fund 939 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1139
1133 | 08470402624 | Abilene Maintenance Office | Install Double Pane Glass Windows In Store Front Entry Area | Highway Trans. Fund 940 | 4500 | 4500 | mm/dd/yy | 0% | 0% | 0 | 0 | 4500 | Pending Administrative Funding | 1140
1134 | 17470402625 | Fairfield Maintenance Office | Close In Part Of Shed For Work Area | Highway Trans. Fund 941 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 1141
1135 | 22470402626 | La Pryon on HWY 57 | Install Interior Lighting | Highway Trans. Fund 942 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 1142
1136 | 22470402627 | La Pryor Maintenance Office | Renovation Conference Room | Highway Trans. Fund 943 | 150000 | 150000 | mm/dd/yy | 0% | 0% | 0 | 0 | 150000 | Pending Administrative Funding | 1143
1137 | 22470402628 | La Pryor Maintenance Office | Renovate Maintenance Facility | Highway Trans. Fund 944 | 125000 | 125000 | mm/dd/yy | 0% | 0% | 0 | 0 | 125000 | Pending Administrative Funding | 1144
1138 | 22470402629 | La Pryor Maintenance Office | Retrofit Existing Office Space | Highway Trans. Fund 945 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 1145
1139 | 11470402630 | Hemphill Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 946 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1146
1140 | 11470402631 | Hemphill Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 947 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1147
1141 | 11470402632 | Groveton Maintenance Office | Replace Fuel Dispensers | Highway Trans. Fund 948 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1148
1142 | 11470402633 | Groveton Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 949 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1149
1143 | 16470402634 | Kingsville Maintenance Office | Repair Plumbing System At Truck Wash Bay - Kingsville MNT | Highway Trans. Fund 950 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 1150
1144 | 16470402635 | Robstown Maintenance Office | Repair Plumbing System At Truck Wash Bay - Robstown Maintenance | Highway Trans. Fund 951 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 1151
1145 | 22470402636 | Laredo Auto Shop | Bay Wash Repairs | Highway Trans. Fund 952 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 1152
1146 | 18470402637 | Corsicana Area Engineer & Maintenance Office | Floor Tile Removal - Corridors Only (Stain Concrete) | Highway Trans. Fund 953 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1153
1147 | 18470402638 | Corsicana Area Engineer & Maintenance Office | Paint Exterior | Highway Trans. Fund 954 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1154
1148 | 12470402639 | District Headquarters | Install Safety Flooring | Highway Trans. Fund 955 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 1155
1149 | 12470402640 | District Headquarters | Renovate Restrooms (Locker Rooms) | Highway Trans. Fund 956 | 42000 | 42000 | mm/dd/yy | 0% | 0% | 0 | 0 | 42000 | Pending Administrative Funding | 1156
1150 | 12470402641 | District Headquarters | Replace Emergency Exit Signage | Highway Trans. Fund 957 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 1157
1151 | 12470402642 | District Headquarters | Upgrade Lighting (LED) | Highway Trans. Fund 958 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 1158
1152 | 17470402643 | Brenham Area Engineer & Maintenance Office | Add Network Connections To Lab Area | Highway Trans. Fund 959 | 7500 | 7500 | mm/dd/yy | 0% | 0% | 0 | 0 | 7500 | Pending Administrative Funding | 1159
1153 | 17470402644 | Brenham Area Engineer & Maintenance Office | Replace Sidewalk Lab To Area Office | Highway Trans. Fund 960 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding | 1160
1154 | 17470402645 | Hearne Area Engineer & Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 961 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1161
1155 | 17470402646 | Hearne Area Engineer & Maintenance Office | New Fuel Canopy - Hearne AEM | Highway Trans. Fund 962 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 1162
1156 | 17470402647 | Huntsville Area Engineer & Maintenance Office | Improve Lighting In Yard/Shed | Highway Trans. Fund 963 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1163
1157 | 16470402648 | Alice Area Engineer & Maintenance Office | Install Electrical Wiring - Alice AEM | Highway Trans. Fund 964 | 40000 | 40000 | mm/dd/yy | 0% | 0% | 0 | 0 | 40000 | Pending Administrative Funding | 1164
1158 | 16470402649 | Alice Area Engineer & Maintenance Office | Repair Sewer System - Alice AEM | Highway Trans. Fund 965 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1165
1159 | 12470402650 | Humble Area Engineer & Maintenance Office | Renovate Interior | Highway Trans. Fund 966 | 500000 | 500000 | mm/dd/yy | 0% | 0% | 0 | 0 | 500000 | Pending Administrative Funding | 1166
1160 | 22470402651 | Del Rio Maintenance Office | Demo (D) And Install (I) Of 2 Lamp T8 Light Fixture (D-2 & I-6 @ Fueling Station; D-57 & I-45 @ Warehouse; And D-39 & I-31 @ MNT Vehicle | Highway Trans. Fund 967 | 18000 | 18000 | mm/dd/yy | 0% | 0% | 0 | 0 | 18000 | Pending Administrative Funding | 1167
1161 | 11470402652 | District Headquarters | Renovate Interior | Highway Trans. Fund 968 | 8000 | 8000 | mm/dd/yy | 0% | 0% | 0 | 0 | 8000 | Pending Administrative Funding | 1168
1162 | 06470402653 | Ft Stockton Area Engineer & Maintenance Office | Paint Cat-Walk | Highway Trans. Fund 969 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1169
1163 | 15470402654 | West Bexar Maintenance Office | Interior Paint | Highway Trans. Fund 970 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1170
1164 | 15470402655 | West Bexar Maintenance Office | Retrofit Shop Bay To Meeting Room | Highway Trans. Fund 971 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 1171
1165 | 38470402656 | Riverside Annex I RA118 | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 972 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1172
1166 | 38470402657 | Riverside Annex II RA150-200 | EOC Technology Renovation (Electronics) | Highway Trans. Fund 973 | 60000 | 60000 | mm/dd/yy | 0% | 0% | 0 | 0 | 60000 | Pending Administrative Funding | 1173
1167 | 38470402658 | Riverside Annex II RA150-200 | Retrofit Of Existing Exterior Light Fixture | Highway Trans. Fund 974 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 1174
1168 | 03470402659 | Bowie Maintenance Office | Upgrade Electrical | Highway Trans. Fund 975 | 80000 | 80000 | mm/dd/yy | 0% | 0% | 0 | 0 | 80000 | Pending Administrative Funding | 1175
1169 | 16470402660 | Nueces West | Install Storm Shutters On All Windows And Doors | Highway Trans. Fund 976 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 1176
1170 | 11470402661 | Shepherd Maintenance Office | Upgrade Interior Lighting | Highway Trans. Fund 977 | 15000 | 15000 | mm/dd/yy | 0% | 0% | 0 | 0 | 15000 | Pending Administrative Funding | 1177
1171 | 21470402662 | Edcouch Maintenance Office | Bird Net For Truck Wash And Equip. Shed | Highway Trans. Fund 978 | 1000 | 1000 | mm/dd/yy | 0% | 0% | 0 | 0 | 1000 | Pending Administrative Funding | 1178
1172 | 21470402663 | Edcouch Maintenance Office | Repaint Generator | Highway Trans. Fund 979 | 500 | 500 | mm/dd/yy | 0% | 0% | 0 | 0 | 500 | Pending Administrative Funding | 1179
1173 | 21470402664 | Edcouch Maintenance Office | Repair Wall Packs | Highway Trans. Fund 980 | 2500 | 2500 | mm/dd/yy | 0% | 0% | 0 | 0 | 2500 | Pending Administrative Funding | 1180
1174 | 17470402665 | District Headquarters | Add Awning To Shop Building | Highway Trans. Fund 981 | 35000 | 35000 | mm/dd/yy | 0% | 0% | 0 | 0 | 35000 | Pending Administrative Funding | 1181
1175 | 17470402666 | District Headquarters | Administration Bldg Foundation Repair | Highway Trans. Fund 982 | 50000 | 50000 | mm/dd/yy | 0% | 0% | 0 | 0 | 50000 | Pending Administrative Funding | 1182
1176 | 17470402667 | District Headquarters | Awnings Between Buildings W/ Lights | Highway Trans. Fund 983 | 30000 | 30000 | mm/dd/yy | 0% | 0% | 0 | 0 | 30000 | Pending Administrative Funding | 1184
1177 | 17470402669 | District Headquarters | Install A/C System To HQ Warehouse | Highway Trans. Fund 984 | 25000 | 25000 | mm/dd/yy | 0% | 0% | 0 | 0 | 25000 | Pending Administrative Funding | 1185
1178 | 17470402670 | District Headquarters | New Canopy And Lights | Highway Trans. Fund 985 | 12500 | 12500 | mm/dd/yy | 0% | 0% | 0 | 0 | 12500 | Pending Administrative Funding | 1186
1179 | 17470402671 | District Headquarters | New Fuel Canopy | Highway Trans. Fund 986 | 45000 | 45000 | mm/dd/yy | 0% | 0% | 0 | 0 | 45000 | Pending Administrative Funding | 1187
1180 | 17470402672 | District Headquarters | Overhead Crane Shops | Highway Trans. Fund 987 | 75000 | 75000 | mm/dd/yy | 0% | 0% | 0 | 0 | 75000 | Pending Administrative Funding | 1188
1181 | 17470402673 | District Headquarters | Paint Signal Warehouse Walls | Highway Trans. Fund 988 | 10000 | 10000 | mm/dd/yy | 0% | 0% | 0 | 0 | 10000 | Pending Administrative Funding | 1189
1182 | 17470402674 | District Headquarters | Repair Admin Building Water Intrusion | Highway Trans. Fund 989 | 20000 | 20000 | mm/dd/yy | 0% | 0% | 0 | 0 | 20000 | Pending Administrative Funding | 1190
1183 | 17470402675 | District Headquarters | Upgrade Used Oil & Antifreeze Containers | Highway Trans. Fund 990 | 5000 | 5000 | mm/dd/yy | 0% | 0% | 0 | 0 | 5000 | Pending Administrative Funding | 1191
1184 | 21470402676 | Roma Area Engineer & Maintenance Office | Building Finish Out | Highway Trans. Fund 991 | 120000 | 120000 | mm/dd/yy | 0% | 0% | 0 | 0 | 120000 | Pending Administrative Funding | 1192
1185 | 38470402678 | Statewide | Emergency Repairs - Statewide | Highway Trans. Fund 992 | 50866849 | 63338244 | mm/dd/yy | 0% | 0% | 0 | 0 | 63338244 | Pending Administrative Funding
Removed | 38470402968 | Various | Condition Assessment | Highway Trans. Fund 6 | 5000000 | -5000000 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Funded with Highway Operating Funds | 1
Removed | 38470402969 | Various | Condition Assessment Software | Highway Trans. Fund 6 | 1000000 | -1000000 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Funded with Highway Operating Funds | 2
Removed | 06470401497 | Andrews Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 6 | 1500 | -1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Funded with Highway Operating Funds | 12
Removed | 10470401503 | Tyler District Headquarters | Replace Boilers at Administration Office | Highway Trans. Fund 6 | 180000 | -180000 | mm/dd/yy | 0% | 100% | 0 | 0 | 0 | Completed with FY15 Funds | 18
Removed | 06470401515 | McCamey Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 6 | 1500 | -1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Funded with Highway Operating Funds | 30
Removed | 06470401525 | Stanton Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 6 | 1500 | -1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Funded with Highway Operating Funds | 40
Removed | 06470401555 | Kermit Maintenance Office | Install Motion Sensors On Install Automatic Gate | Highway Trans. Fund 6 | 1500 | -1500 | mm/dd/yy | 0% | 0% | 0 | 0 | 0 | Funded with Highway Operating Funds | 70
[5 empty] | 200000000 | 200000000 |  |  |  | 313105 | 0 | 199686895

## TDCJ 9.16
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2016-09-15 | [9 empty] | 2016-09-15
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 4th Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 04215005 | Hughes Unit, Gatesville | Facility Repair: Replace HVAC Unit - Support Operations | Deferred Maintenance Account No. 5166 |  | 57800 | 2016-10-15 | N/A | 2% | 46984 | 2835.5 | 7980.5
2 | 09915001 | Hutchins Unit, Dallas | Facility Repair: Refurbish Air Handler - Support Operations | Deferred Maintenance Account No. 5166 |  | 60818.03 | 2015-11-23 | N/A | 100% | 0 | 60818.03 | 0
3 | 05014007 | Roach Unit, Childress | Roofing: Repair Roof - ISF | Deferred Maintenance Account No. 5166 | 75600 | 75600 | 2016-07-27 | N/A | 100% | 0 | 49064.46 | 26535.54 | Yes
4 | 00512006 | Clemens Unit, Brazoria | Facility Repair: Resurface Floor - Main Building Kitchen | Deferred Maintenance Account No. 5166 | 40400 | 40400 | 2017-03-10 | 100% | 2% | 0 | 15235.52 | 25164.48 | Yes
5 | 10510005 | Murray Unit, Gatesville | Facility Repair: Install Handicap Accessible Shower - Offender Dorms | Deferred Maintenance Account No. 5166 | 37400 | 37400 | 2016-10-15 | 100% | 97% | 0 | 29322.32 | 8077.68 | Yes
6 | 01015016 | Ellis Unit, Huntsville | Safety: Replace Generator - Boiler Room | Deferred Maintenance Account No. 5166 |  | 73500 | 2016-10-17 | 100% | 98% | 1511.55 | 70185.71 | 1802.74
7 | 06913002 | Allred Unit, Iowa Park | Roofing: Resurface Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 88800 | 88800 | 2016-11-15 | 100% | 50% | 0 | 57100.51 | 31699.49 | Yes
8 | 10815003 | Sanchez Unit, El Paso | Infrastructure: Refurbish Lift Station - Front Administration Building | Deferred Maintenance Account No. 5166 |  | 225537 | 2016-08-16 | N/A | 100% | 0 | 225537 | 0 | Yes
9 | 08212003 | Havins Unit, Brownwood | Facility Repair: Install Fiberglass Wall Panels - Multiple Buildings | Deferred Maintenance Account No. 5166 | 47900 | 47900 | 2016-11-23 | 100% | 20% | 30276.45 | 7033.83 | 10589.72 | Yes
10 | 06715022 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Infirmary | Deferred Maintenance Account No. 5166 |  | 119400 | 2017-01-15 | N/A | 2% | 88448.78 | 1759.3 | 29191.92 | Yes
11 | 03615005 | Michael Unit, Tennessee Colony | Safety: Replace Emergency Generator - Lift Station | Deferred Maintenance Account No. 5166 |  | 51000 | 2016-10-15 | 100% | 95% | 0 | 46544.39 | 4455.61
12 | 09413001 | Gurney Unit, Tennessee Colony | Facility Repair: Renovate Maintenance Shop | Deferred Maintenance Account No. 5166 | 46400 | 46400 | 2016-10-23 | 100% | 90% | 108.06 | 28032.69 | 18259.25 | Yes
13 | 06716001 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Support Operations | Deferred Maintenance Account No. 5166 |  | 122200 | 2017-01-15 | N/A | 2% | 60984.758 | 436.49 | 60778.752 | Yes
14 | 08015001 | Sayle Unit, Breckenridge | Facility Repair: Replace Feed Water Tank - Boiler Room | Deferred Maintenance Account No. 5166 |  | 66100 | 2016-11-01 | 100% | 96% | 0 | 59192.03 | 6907.97
15 | 06211002 | Ft. Stockton Unit, Fort Stockton | Facility Repair: Replace Showers - Offender Dorms | Deferred Maintenance Account No. 5166 | 374900 | 374900 | 2016-10-12 | 100% | 48% | 189672.79 | 45235.05 | 139992.16
16 | 01313007 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Repair Shop | Deferred Maintenance Account No. 5166 | 45200 | 59600 | 2016-12-08 | 100% | 5% | 406.3 | 41700.89 | 17492.81 | Yes
17 | 04505002 | Estes Unit, Venus | Security: Install Concrete Footer - Perimeter Fence | Deferred Maintenance Account No. 5166 | 37700 | 28038.02 | 2016-04-05 | N/A | 100% | 0 | 28038.02 | 0
18 | 08915001 | Johnston Unit, Winnsboro | Facility Repair: Replace Steam Boiler - Boiler Room | Deferred Maintenance Account No. 5166 |  | 74655.25 | 2016-07-01 | 100% | 100% | 0 | 74655.25 | 0 | Yes
19 | 08416002 | Halbert Unit, Burnet | Facility Repair: Replace Refrigeration Equipment - Food Service | Deferred Maintenance Account No. 5166 |  | 66400 | 2016-12-23 | N/A | 2% | 56705 | 5881.27 | 3813.73 | Yes
20 | 02215006 | Beto Unit, Tennessee Colony | Facility Repair: Replace Hot Water Storage Tank - Boiler Room | Deferred Maintenance Account No. 5166 |  | 128600 | 2016-11-18 | 100% | 2% | 103580 | 0 | 25020 | Yes
21 | 12913004 | Young Unit, Dickinson | Infrastructure: Replace/Refurbish Cooling Tower - Central Plant | Deferred Maintenance Account No. 5166 |  | 279200 | 2017-05-15 | 100% | 0% | 0 | 0 | 279200
22 | 10014001 | Lychner Unit, Humble | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 |  | 394700 | 2017-02-01 | 100% | 0% | 0 | 0 | 394700
23 | 03015002 | Jester III Unit, Richmond | Facility Repair: Replace Heat Exchangers, Storage Tank & Condensate Pump - Heat Exchanger Room | Deferred Maintenance Account No. 5166 |  | 181800 | 2017-01-01 | 100% | 3% | 107105.68 | 395.46 | 74298.86 | Yes
24 | 07815004 | Segovia Unit, Edinburg | Facility Repair: Replace Water Softener - Multiple Dorms | Deferred Maintenance Account No. 5166 |  | 55900 | 2016-12-15 | 100% | 86% | 0 | 36492.83 | 19407.17
25 | 10414006 | Ware Unit, Colorado City | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 |  | 80100 | 2017-04-15 | 1% | 0% | 0 | 0 | 80100 | Yes
26 | 09215007 | Holliday Unit, Huntsville | Facility Repair: Replace Air Handler & Heater - Offender Housing | Deferred Maintenance Account No. 5166 |  | 246600 | 2017-02-15 | 1% | 0% | 0 | 0 | 246600
27 | 09915002 | Hutchins Unit, Dallas | Facility Repair: Refurbish Air Handler - Kitchen | Deferred Maintenance Account No. 5166 |  | 66200 | 2017-11-15 | N/A | 20% | 62142.85 | 626.68 | 3430.47 | Yes
28 | 01711010 | Ramsey Unit, Rosharon | Security: Replace Locking System | Deferred Maintenance Account No. 5166 | 2073900 | 2073900 | 2016-11-01 | 100% | 51% | 1125753.07 | 821949.89 | 126197.04
29 | 02802006 | Powledge Unit, Palestine | Roofing: Repair/Replace Roof on Metal Fab Factory Building | Deferred Maintenance Account No. 5166 | 1477100 | 1477100 | 2016-10-30 | 100% | 69% | 336396.34 | 1034519.55 | 106184.11 | Yes
30 | 02909007 | Luther Unit, Navasota | Safety: Install Fire Alarm System - Multiple Locations | Deferred Maintenance Account No. 5166 | 1313200 | 1313200 | 2016-11-01 | 100% | 88% | 152033.52 | 1038937.16 | 122229.32 | Yes
31 | 04301001 | Kyle Unit, Kyle | Safety: Repair/Replace Fire Alarm System - Multiple Buildings | Deferred Maintenance Account No. 5166 | 324044.62 | 366473.06 | 2016-12-01 | 100% | 40% | 242471.1 | 111982.74 | 12019.22 | Yes
32 | 04404002 | Bridgeport Unit, Bridgeport | Security: Replace Control System Electric Door Locks & Intercom System | Deferred Maintenance Account No. 5166 | 1616900 | 1616900 | 2016-10-18 | 100% | 82% | 287205.31 | 1189216.49 | 140478.2 | Yes
33 | 03711006 | Clements Unit, Amarillo | Roofing: Replace Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 7461800 | 7461800 | 2017-02-01 | 100% | 18% | 5618002.39 | 1406875.66 | 436921.95
34 | 03608012 | Michael Unit, Tennessee Colony | Security: Replace Door Controls - Multiple Buildings | Deferred Maintenance Account No. 5166 | 5494300 | 5494300 | 2017-04-15 | 100% | 46% | 2638115.07 | 2483248.03 | 372936.9
35 | 01802005 | Stringfellow Unit, Rosharon | Security: Replace Cell Door Locks - Offender Dorm Wing | Deferred Maintenance Account No. 5166 | 839916 | 839916 | 2016-07-06 | 100% | 100% | 23846.23 | 767748.64 | 48321.13 | Yes
36 | 02004006 | Wynne Unit, Huntsville | Facility Repair: Extending Covered Area - Transportation Repair Shop | Deferred Maintenance Account No. 5166 | 484400 | 484400 | 2016-11-10 | 100% | 19% | 178667.25 | 98835.96 | 206896.79 | Yes
37 | 02413007 | Crain Unit, Gatesville | Roofing: Replace Roof - Dorm Building | Deferred Maintenance Account No. 5166 | 107300 | 125800 | 2016-04-26 | 100% | 100% | 3000 | 110931.5 | 11868.5
38 | 03111006 | Hilltop Unit, Gatesville | Infrastructure: Replace Ground Water Storage Tank | Deferred Maintenance Account No. 5166 | 747200 | 747200 | 2016-06-27 | 100% | 100% | 0 | 694783.39 | 52416.61 | Yes
39 | 01410011 | Jester I Unit, Richmond | Infrastructure: Replace Ground Storage Water Tanks #1 & #2 | Deferred Maintenance Account No. 5166 | 461800 | 330800 | 2016-05-31 | 100% | 100% | 0 | 317886.63 | 12913.37 | Yes
40 | 11812001 | Travis Co. Unit, Austin | Infrastructure: Replace Grease Trap - Kitchen | Deferred Maintenance Account No. 5166 | 148700 | 183900 | 2016-08-04 | 100% | 100% | 23100 | 153502.15 | 7297.85 | Yes
41 | 05410010 | Polunsky Unit, Livingston | Security: Install High Mast Lighting - Offender Dorm Building & Perimeter Fence | Deferred Maintenance Account No. 5166 | 121200 | 206500 | 2016-11-07 | 100% | 38% | 120600 | 72200 | 13700 | Yes
42 | 01312013 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Security Operations Building | Deferred Maintenance Account No. 5166 | 156400 | 156400 | 2016-12-01 | 100% | 0% | 75.5 | 1382.3 | 154942.2
43 | 00513004 | Clemens Unit, Brazoria | Roofing: Replace Roof - Main Building | Deferred Maintenance Account No. 5166 | 347200 | 391900 | 2016-06-21 | 100% | 100% | 30 | 337672.33 | 54197.67 | Yes
44 | 04710001 | Robertson Unit, Abilene | Roofing: Replace Roofs - Multiple Buildings | Deferred Maintenance Account No. 5166 | 7891200 | 8321800 | 2018-07-15 | 100% | 6% | 7291868.86 | 540498 | 489433.14
45 | 02911013 | Luther Unit, Navasota | Infrastructure: Replace Ground Storage Tank - Water Plant | Deferred Maintenance Account No. 5166 | 626900 | 626900 | 2016-09-30 | 100% | 98% | 203350.28 | 393786.29 | 29763.43 | Yes
46 | 01113002 | Ferguson Unit, Midway | Infrastructure: Refurbish Elevated Storage Tank - Water Plant | Deferred Maintenance Account No. 5166 | 337800 | 503500 | 2016-08-16 | 100% | 100% | 127258.25 | 343163.75 | 33078 | Yes
47 | 11106003 | Moore Unit, Bonham | Security: Replace Security Control System | Deferred Maintenance Account No. 5166 | 3304198 | 1940598 | 2017-04-01 | 100% | 40% | 1129324.77 | 678770.98 | 132502.25
48 | 03708003 | Clements Unit, Amarillo | Safety: DESIGN ONLY - Repair/Replace Fire Line - Administrative Segregation | Deferred Maintenance Account No. 5166 | 420000 | 420000 | 2017-07-15 | 0% | N/A | 0 | 0 | 420000
49 | 03608011 | Michael Unit, Tennessee Colony | Safety: DESIGN ONLY - Repair/Replace Fire Line - Administrative Segregation | Deferred Maintenance Account No. 5166 | 420000 | 420000 | 2017-03-01 | 0% | N/A | 0 | 0 | 420000
50 | 04911009 | Stiles Unit, Beaumont | Facility Repair: Replace Windows - Offender Housing | Deferred Maintenance Account No. 5166 | 107400 | 107400 | 2016-12-01 | 100% | 0% | 0 | 0 | 107400
51 | 02210005 | Beto Unit, Tennessee Colony | Facility Repair: Replace Flooring - Main Kitchen & Scullery | Deferred Maintenance Account No. 5166 | 407000 | 407000 | 2017-04-01 | 100% | 0% | 0 | 0 | 407000
52 | 01915001 | Scott Unit, Angleton | Infrastructure: Replace Lift Station and Bar Screen - Waste Water Treatment Plant | Deferred Maintenance Account No. 5166 | 1881800 | 1881800 | 2017-09-01 | 100% | 0% | 33601.21 | 58912.79 | 1789286
53 | 02212005 | Beto Unit, Tennessee Colony | Safety: Install Standby Generator & Transfer Switch - Trusty Camp | Deferred Maintenance Account No. 5166 | 110100 | 120600 | 2017-01-01 | 100% | 30% | 78453.38 | 35861.16 | 6285.46
54 | 00512007 | Clemens Unit, Brazoria | Safety: Install Standby Generator - Trusty Camp | Deferred Maintenance Account No. 5166 | 109200 | 109200 | 2016-11-01 | 100% | 6% | 76740.46 | 19331.04 | 13128.5
55 | 01714002 | Ramsey Unit, Rosharon | Safety: Install Standby Generator - Trusty Camp | Deferred Maintenance Account No. 5166 | 106700 | 106700 | 2016-12-01 | 100% | 5% | 80982.64 | 1468.54 | 24248.82
56 | 02215011 | Beto Unit, Tennessee Colony | Facility Repair: Install Electrical to Cells - Infirmary | Deferred Maintenance Account No. 5166 | 19300 | 19300 | 2017-06-01 | 100% | 0% | 0 | 0 | 19300
57 | 01913008 | Scott Unit, Angleton | Facility Repair: Renovate 3 & 4 Pickets | Deferred Maintenance Account No. 5166 | 65700 | 65700 | 2018-09-17 | 100% | 2% | 0 | 0 | 65700 | Yes
58 | 02212017 | Beto Unit, Tennessee Colony | Infrastructure: Replace Hot Water Lines - Main Building | Deferred Maintenance Account No. 5166 | 49600 | 49600 | 2016-12-01 | 100% | 96% | 0 | 45520.66 | 4079.34
59 | 10814001 | Sanchez Unit, El Paso | Infrastructure: DESIGN ONLY - Renovate Elevated Water Storage Tank | Deferred Maintenance Account No. 5166 | 17700 | 17700 | 2016-08-24 | 100% | N/A | 0 | 0 | 17700 | Yes
60 | 03913005 | Hobby Unit, Marlin | Roofing: Replace Roof - Kitchen/Commissary | Deferred Maintenance Account No. 5166 | 153100 | 153100 | 2017-01-15 | 100% | 0% | 0 | 0 | 153100 | Yes
61 | 02012008 | Wynne Unit, Huntsville | Facility Repair: Replace Flooring - Kitchen | Deferred Maintenance Account No. 5166 | 92900 | 92900 | 2017-01-01 | 100% | 1% | 0 | 0 | 92900 | Yes
62 | 03616019 | Michael Unit, Tennessee Colony | Infrastructure: Replace Transformer - Packing Plant | Deferred Maintenance Account No. 5166 |  | 41200 | 2016-05-08 | N/A | 100% | 0 | 39200 | 2000 | Yes
63 | 00609001 | Coffield Unit, Tennessee Colony | Facility Repair: Renovate Commissary Space | Deferred Maintenance Account No. 5166 | 55800 | 55800 | 2017-03-03 | 100% | 3% | 29412.07 | 13714.66 | 12673.27 | Yes
64 | 01713045 | Ramsey Unit, Rosharon | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 35100 | 65100 | 2017-04-27 | 100% | 2% | 49634.88 | 12850.98 | 2614.14 | Yes
65 | 03813007 | Daniel Unit, Snyder | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 162200 | 162200 | 2017-05-01 | 100% | 0% | 0 | 0 | 162200
66 | 04012003 | Lewis Unit, Woodville | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 162200 | 162200 | 2016-12-01 | 97% | 0% | 0 | 0 | 162200
67 | 09199005 | Chasefield Unit, Beeville | Safety: Repair/Replace Fire Alarm - Multiple Buildings | Deferred Maintenance Account No. 5166 | 98900 | 98900 | 2017-05-15 | 13% | 0% | 0 | 0 | 98900 | Yes
68 | 04813002 | McConnell Unit, Beeville | Safety: Replace Intercom System - Medical | Deferred Maintenance Account No. 5166 | 101300 | 101300 | 2017-07-01 | 100% | 1% | 0 | 0 | 101300
69 | 02615001 | Pack Unit, Navasota | Infrastructure: Replace Filtration System - Storage Tank | Deferred Maintenance Account No. 5166 | 1432383 | 3270700 | 2017-04-01 | 100% | 1% | 2885838.03 | 94961.62 | 289900.35 | Yes
70 | 02813001 | Powledge Unit, Palestine | Infrastructure: DESIGN ONLY - Repair Washout - Outfall Line Waste Water Treatment Plant | Deferred Maintenance Account No. 5166 | 4200 | 4200 | 2016-11-25 | 14% | N/A | 0 | 0 | 4200 | Yes
71 | 03312003 | Jester IV Unit, Richmond | Roofing: DESIGN ONLY - Replace Roof - Psychiatric Facility | Deferred Maintenance Account No. 5166 | 443700 | 443700 | 2017-12-01 | 12% | N/A | 319454 | 0 | 124246 | Yes
72 | 03613004 | Michael Unit, Tennessee Colony | Roofing: DESIGN ONLY - Replace Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 858400 | 603600 | 2017-09-15 | 1% | N/A | 470019 | 0 | 133581 | Yes
73 | 01914001 | Scott Unit, Angleton | Facility Repair: DESIGN ONLY - Replace Plumbing - Multiple Cell Blocks | Deferred Maintenance Account No. 5166 | 261000 | 79247 | 2016-11-15 | 45% | N/A | 48491.97 | 25754.89 | 5000.14 | Yes
74 | 01913004 | Scott Unit, Angleton | Facility Repair: DESIGN ONLY - Kitchen Renovation | Deferred Maintenance Account No. 5166 | 530700 | 530700 | 2017-12-01 | 0% | N/A | 0 | 0 | 530700 | Yes
75 | 02702010 | Terrell Unit, Rosharon | Facility Repair: Renovate Exhaust System - Vocational Shop | Deferred Maintenance Account No. 5166 | 164700 | 164700 | 2017-01-15 | 5% | 0% | 0 | 0 | 164700 | Yes
76 | 01912007 | Scott Unit, Angleton | Security: DESIGN ONLY - Replace Locking System - Multiple Wings | Deferred Maintenance Account No. 5166 | 267800 | 267800 | 2016-12-01 | 1% | N/A | 180528.12 | 9281.88 | 77990 | Yes
77 | 01313004 | Huntsville Unit, Huntsville | Facility Repair: DESIGN ONLY - Repair/Replace South Wall - Perimeter | Deferred Maintenance Account No. 5166 | 461600 | 461600 | 2017-02-15 | 0% | N/A | 0 | 0 | 461600 | Yes
78 | 01205010 | Goree Unit, Huntsville | Facility Repair: Renovate Showers - Multiple Buildings | Deferred Maintenance Account No. 5166 | 126900 | 126900 | 2017-06-01 | 100% | 6% | 48532.2 | 45048.13 | 33319.67 | Yes
79 | 01300042 | Huntsville Unit, Huntsville | Safety: DESIGN ONLY - Install Fire Alarm System | Deferred Maintenance Account No. 5166 | 521900 | 521900 | 2017-01-10 | 50% | N/A | 300425.58 | 0 | 221474.42 | Yes
80 | 04813003 | McConnell Unit, Beeville | Infrastructure: DESIGN ONLY - Replace Steam & Condensate Lines - Kitchen/Laundry Building | Deferred Maintenance Account No. 5166 | 164600 | 164600 | 2017-10-01 | 0% | N/A | 0 | 0 | 164600 | Yes
81 | 12107001 | Lindsey Unit, Jacksboro | Infrastructure: DESIGN ONLY - Correct Drainage - Multiple Buildings | Deferred Maintenance Account No. 5166 | 6300 | 6300 | 2016-12-10 | 14% | N/A | 0 | 0 | 6300 | Yes
82 | 10907002 | Lockhart Unit, Lockhart | Safety: Replace Fire Alarm - Multiple Buildings | Deferred Maintenance Account No. 5166 | 118700 | 118700 | 2017-03-16 | 100% | 1% | 0 | 0 | 118700 | Yes
83 | 01000010 | Ellis Unit, Huntsville | Safety: DESIGN ONLY - Install Fire Alarm System - Unit Wide | Deferred Maintenance Account No. 5166 | 378000 | 378000 | 2017-03-01 | 15% | N/A | 305573.21 | 0 | 72426.79 | Yes
84 | 08116009 | Rudd Unit, Brownfield | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 |  | 76400 | 2017-06-19 | N/A | 2% | 1115.6 | 7947.83 | 67336.57 | Yes
85 | 05402015 | Polunsky Unit, Livingston | Roofing: Repair / Replace Roofs - Multiple Buildings | Deferred Maintenance Account No. 5166 |  | 6626655 | 2018-05-23 | 100% | 1% | 6289325.89 | 9277.36 | 328051.75 | Yes
86 | 09216001 | Holliday Unit, Huntsville | Safety: Add Wheelchair Accessibility - Multiple Dorms | Deferred Maintenance Account No. 5166 |  | 45400 | 2017-01-01 | 100% | 3% | 9872.12 | 3938.57 | 31589.31
87 | 04716003 | Robertson Unit, Abilene | Facility Repair: Replace Deaerator - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 149700 | 2017-02-01 | 100% | 3% | 128980.6 | 655.26 | 20064.14 | Yes
88 | 03612001 | Michael Unit, Tennessee Colony | Infrastructure: DESIGN ONLY - Replace Elevated Storage Tank & Storage Tank Well #4 | Deferred Maintenance Account No. 5166 | 4693942 | 30000 | 2016-11-01 | 96% | N/A | 14044.32 | 0 | 15955.68 | Yes
89 | 01608001 | Mt. View Unit, Gatesville | Infrastructure: DESIGN ONLY - Replace Ground Water Storage Tank, Boost Station and Replace Water Lines | Deferred Maintenance Account No. 5166 | 4947317 | 70500 | 2016-08-08 | 100% | N/A | 19837.98 | 45612.46 | 5049.56 | Yes
90 | 00715005 | Darrington Unit, Rosharon | Facility Repair: Replace Chillers - Intake Housing | Deferred Maintenance Account No. 5166 |  | 295700 | 2017-09-01 | 1% | 0% | 0 | 0 | 295700
91 | 09215009 | Holliday Unit, Huntsville | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 |  | 137200 | 2017-07-22 | N/A | 3% | 128022.11 | 8839.37 | 338.52 | Yes
92 | 02212024 | Beto Unit, Tennessee Colony | Infrastructure: Reline Manholes | Deferred Maintenance Account No. 5166 |  | 64700 | 2017-01-01 | 100% | 1% | 0 | 0 | 64700
93 | 10316007 | Lopez Unit, Edinburg | Facility Repair: Replace Air Handler - Administrative Segregation | Deferred Maintenance Account No. 5166 |  | 94500 | 2016-11-22 | N/A | 1% | 90000 | 0 | 4500
94 | 09816005 | Dominguez Unit, San Antonio | Facility Repair: Replace HVAC Unit - Kitchen | Deferred Maintenance Account No. 5166 |  | 89700 | 2017-03-15 | 0% | 0% | 0 | 0 | 89700
95 | 06816007 | Connally Unit, Kenedy | Facility Repair: Replace HVAC Units - Education and Medical | Deferred Maintenance Account No. 5166 |  | 313600 | 2017-01-02 | 5% | 0% | 0 | 0 | 313600
96 | 00716001 | Darrington Unit, Rosharon | Facility Repair: Replace Chillers - Warehouse | Deferred Maintenance Account No. 5166 |  | 101600 | 2017-06-10 | 1% | 0% | 0 | 0 | 101600
97 | 03115003 | Hilltop Unit, Gatesville | Infrastructure: Replace Boilers - Boiler Room | Deferred Maintenance Account No. 5166 |  | 73700 | 2017-02-15 | 100% | 2% | 3549.7 | 44509.55 | 25640.75
98 | 07916001 | Moore Unit, Bonham | Infrastructure: Replace Boilers - Boiler Room | Deferred Maintenance Account No. 5166 |  | 51600 | 2017-03-01 | 100% | 3% | 748.55 | 42784.38 | 8067.07
99 | 01015008 | Ellis Unit, Huntsville | Infrastructure: Replace Service Entrance Switchgear - Back Gate | Deferred Maintenance Account No. 5166 |  | 207900 | 2017-08-01 | 100% | 0% | 0 | 0 | 207900
100 | 07009003 | Neal Unit, Amarillo | Facility Repair: Renovate Mechanical Room and Replace Showers | Deferred Maintenance Account No. 5166 |  | 23756 | 2017-11-01 | 100% | 7% | 0 | 5637.31 | 18118.69 | Yes
101 | 05216006 | Briscoe Unit, Dilley | Facility Repair: Replace Deaerator - Boiler Room | Deferred Maintenance Account No. 5166 |  | 246800 | 2016-11-19 | 100% | 1% | 0 | 0 | 246800 | Yes
102 | 09012004 | Montford Unit, Lubbock | Infrastructure: Install Backflow Preventer | Deferred Maintenance Account No. 5166 |  | 178700 | 2017-01-21 | 100% | 1% | 178700 | 0 | 0 | Yes
103 | 09116022 | Chasefield Unit, Beeville | Facility Repair: Replace Chiller | Deferred Maintenance Account No. 5166 |  | 45000 | 2017-01-12 | N/A | 1% | 0 | 0 | 45000 | Yes
104 | 03216017 | Estelle Unit, Huntsville | Facility Repair: Replace Air Handler - High Security Kitchen Roof | Deferred Maintenance Account No. 5166 |  | 182900 | 2017-09-01 | 1% | 0% | 0 | 0 | 182900 | Yes
105 | 03616021 | Michael Unit, Tennessee Colony | Safety: Replace Emergency Generator - Boiler Room | Deferred Maintenance Account No. 5166 |  | 46200 | 2017-02-03 | 100% | 1% | 0 | 0 | 46200 | Yes
N/A | 10313003 | Lopez Unit, Edinburg | Facility Repair: Replace/Rebuild Walls and Doors - Kitchen | Deferred Maintenance Account No. 5166 | 103700 | 0 | 2017-03-01 | 100% | 25% | 0 | 0 | 0
N/A | 02707005 | Terrell Unit, Rosharon | Infrastructure: Renovate Sewer Line from Food Service | Deferred Maintenance Account No. 5166 | 48700 | 0 | N/A | N/A | N/A | 0 | 0 | 0
N/A | 01313001 | Huntsville Unit, Huntsville | Roofing: DESIGN ONLY - Replace Roof/Repair Walls - Infirmary Building | Deferred Maintenance Account No. 5166 | 153600 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | Yes
|  |  |  | Totals: | 56393900.62 | 58765393.36 |  |  |  | 32020907.778 | 14055123.11 | 12689362.472

## TDCJ 6.16
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2016-06-15 | [9 empty] | 2016-06-15
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 3rd Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 04215005 | Hughes Unit, Gatesville | Facility Repair: Replace HVAC Unit - Support Operations | Deferred Maintenance Account No. 5166 |  | 57800 | 2016-10-15 | N/A | 3% | 44334 | 2835.5 | 10630.5 | Yes
2 | 09915001 | Hutchins Unit, Dallas | Facility Repair: Refurbish Air Handler - Support Operations | Deferred Maintenance Account No. 5166 |  | 60818.03 | 2015-11-23 | N/A | 100% | 0 | 60818.03 | 0 | Yes
3 | 05014007 | Roach Unit, Childress | Roofing: Repair Roof - ISF | Deferred Maintenance Account No. 5166 | 75600 | 75600 | 2016-07-26 | N/A | 3% | 33600 | 24717.01 | 17282.99
4 | 00512006 | Clemens Unit, Brazoria | Facility Repair: Resurface Floor - Main Building Kitchen | Deferred Maintenance Account No. 5166 | 40400 | 40400 | 2016-09-13 | 100% | 3% | 0 | 15235.52 | 25164.48
5 | 10510005 | Murray Unit, Gatesville | Facility Repair: Install Handicap Accessible Shower - Offender Dorms | Deferred Maintenance Account No. 5166 | 37400 | 37400 | 2016-09-15 | 100% | 25% | 0.23 | 27282.26 | 10117.51 | Yes
6 | 01015016 | Ellis Unit, Huntsville | Safety: Replace Generator - Boiler Room | Deferred Maintenance Account No. 5166 |  | 73500 | 2016-10-17 | 100% | 25% | 58042.87 | 12276.59 | 3180.54 | Yes
7 | 06913002 | Allred Unit, Iowa Park | Roofing: Resurface Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 88800 | 88800 | 2016-08-01 | 100% | 4% | 68703.88 | 3636.08 | 16460.04
8 | 10815003 | Sanchez Unit, El Paso | Infrastructure: Refurbish Lift Station - Front Administration Building | Deferred Maintenance Account No. 5166 |  | 236900 | 2016-10-30 | N/A | 30% | 185000 | 0 | 51900 | Yes
9 | 08212003 | Havins Unit, Brownwood | Facility Repair: Install Fiberglass Wall Panels - Multiple Buildings | Deferred Maintenance Account No. 5166 | 47900 | 47900 | 2016-08-19 | 100% | 3% | 30276.45 | 6727.08 | 10896.47
10 | 06715022 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Infirmary | Deferred Maintenance Account No. 5166 |  | 119400 | 2016-08-07 | N/A | 2% | 108914.78 | 1759.3 | 8725.92
11 | 03615005 | Michael Unit, Tennessee Colony | Safety: Replace Emergency Generator - Lift Station | Deferred Maintenance Account No. 5166 |  | 51000 | 2016-10-15 | 100% | 3% | 43906 | 2638.39 | 4455.61 | Yes
12 | 09413001 | Gurney Unit, Tennessee Colony | Facility Repair: Renovate Maintenance Shop | Deferred Maintenance Account No. 5166 | 46400 | 46400 | 2016-07-01 | 100% | 35% | 9153.84 | 18393.35 | 18852.81
13 | 06716001 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Support Operations | Deferred Maintenance Account No. 5166 |  | 122200 | 2016-10-15 | N/A | 2% | 103284.75 | 436.49 | 18478.76 | Yes
14 | 08015001 | Sayle Unit, Breckenridge | Facility Repair: Replace Feed Water Tank - Boiler Room | Deferred Maintenance Account No. 5166 |  | 66100 | 2016-11-01 | 100% | 3% | 55374.43 | 4921.49 | 5804.08 | Yes
15 | 06211002 | Ft. Stockton Unit, Fort Stockton | Facility Repair: Replace Showers - Offender Dorms | Deferred Maintenance Account No. 5166 | 374900 | 374900 | 2016-10-12 | 100% | 2% | 185453 | 27068.29 | 162378.71
16 | 01313007 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Repair Shop | Deferred Maintenance Account No. 5166 | 45200 | 59600 | 2016-07-11 | 100% | 5% | 47293.96 | 797.2 | 11508.84
17 | 04505002 | Estes Unit, Venus | Security: Install Concrete Footer - Perimeter Fence | Deferred Maintenance Account No. 5166 | 37700 | 28038.02 | 2016-04-05 | N/A | 100% | 0 | 28038.02 | 0 | Yes
18 | 08915001 | Johnston Unit, Winnsboro | Facility Repair: Replace Steam Boiler - Boiler Room | Deferred Maintenance Account No. 5166 |  | 83700 | 2016-10-01 | 100% | 5% | 68629.1 | 4843 | 10227.9 | Yes
19 | 08416002 | Halbert Unit, Burnet | Facility Repair: Replace Refrigeration Equipment - Food Service | Deferred Maintenance Account No. 5166 |  | 56400 | 2016-12-23 | N/A | 2% | 46255 | 5881.27 | 4263.73 | Yes
20 | 02215006 | Beto Unit, Tennessee Colony | Facility Repair: Replace Hot Water Storage Tank - Boiler Room | Deferred Maintenance Account No. 5166 |  | 128600 | 2016-09-01 | 100% | 1% | 122400 | 0 | 6200
21 | 12913004 | Young Unit, Dickinson | Infrastructure: Replace/Refurbish Cooling Tower - Central Plant | Deferred Maintenance Account No. 5166 |  | 279200 | 2017-05-15 | 10% | 0% | 0 | 0 | 279200
22 | 10014001 | Lychner Unit, Humble | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 |  | 394700 | 2017-02-01 | 5% | 0% | 0 | 0 | 394700
23 | 03015002 | Jester III Unit, Richmond | Facility Repair: Replace Heat Exchangers, Storage Tank & Condensate Pump - Heat Exchanger Room | Deferred Maintenance Account No. 5166 |  | 181800 | 2016-10-20 | 100% | 3% | 106777 | 0 | 75023
24 | 07815004 | Segovia Unit, Edinburg | Facility Repair: Replace Water Softener - Multiple Dorms | Deferred Maintenance Account No. 5166 |  | 55900 | 2016-12-15 | 100% | 1% | 34328.42 | 1736.08 | 19835.5
25 | 10414006 | Ware Unit, Colorado City | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 |  | 80100 | 2016-09-01 | 1% | 0% | 0 | 0 | 80100
26 | 09215007 | Holliday Unit, Huntsville | Facility Repair: Replace Air Handler & Heater - Offender Housing | Deferred Maintenance Account No. 5166 |  | 246600 | 2017-02-15 | 1% | 0% | 0 | 0 | 246600
27 | 09915002 | Hutchins Unit, Dallas | Facility Repair: Refurbish Air Handler - Kitchen | Deferred Maintenance Account No. 5166 |  | 66200 | 2016-10-28 | N/A | 0% | 0 | 0 | 66200 | Yes
28 | 01711010 | Ramsey Unit, Rosharon | Security: Replace Locking System | Deferred Maintenance Account No. 5166 | 2073900 | 2073900 | 2016-11-01 | 100% | 25% | 1716860.03 | 259523.33 | 97516.64
29 | 02802006 | Powledge Unit, Palestine | Roofing: Repair/Replace Roof on Metal Fab Factory Building | Deferred Maintenance Account No. 5166 | 1477100 | 1477100 | 2016-09-30 | 100% | 40% | 869730.41 | 519751.6 | 87617.99 | Yes
30 | 02909007 | Luther Unit, Navasota | Safety: Install Fire Alarm System - Multiple Locations | Deferred Maintenance Account No. 5166 | 1313200 | 1313200 | 2016-08-01 | 100% | 60% | 506029.24 | 701983.78 | 105186.98
31 | 04301001 | Kyle Unit, Kyle | Safety: Repair/Replace Fire Alarm System - Multiple Buildings | Deferred Maintenance Account No. 5166 | 324044.62 | 324045 | 2016-09-01 | 100% | 15% | 237445.06 | 63958.75 | 22641.19
32 | 04404002 | Bridgeport Unit, Bridgeport | Security: Replace Control System Electric Door Locks & Intercom System | Deferred Maintenance Account No. 5166 | 1616900 | 1616900 | 2016-09-01 | 100% | 65% | 832610.62 | 666960.33 | 117329.05
33 | 03711006 | Clements Unit, Amarillo | Roofing: Replace Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 7461800 | 7461800 | 2017-02-01 | 100% | 6% | 6686282.87 | 399070.28 | 376446.85
34 | 03608012 | Michael Unit, Tennessee Colony | Security: Replace Door Controls - Multiple Buildings | Deferred Maintenance Account No. 5166 | 5494300 | 5494300 | 2017-04-15 | 100% | 40% | 3343352.7 | 1783669.27 | 367278.03
35 | 01802005 | Stringfellow Unit, Rosharon | Security: Replace Cell Door Locks - Offender Dorm Wing | Deferred Maintenance Account No. 5166 | 839916 | 839916 | 2016-09-01 | 100% | 95% | 317709.23 | 452039.39 | 70167.38
36 | 02004006 | Wynne Unit, Huntsville | Facility Repair: Extending Covered Area - Transportation Repair Shop | Deferred Maintenance Account No. 5166 | 484400 | 484400 | 2016-09-10 | 100% | 15% | 211461.03 | 82280.07 | 190658.9
37 | 02413007 | Crain Unit, Gatesville | Roofing: Replace Roof - Dorm Building | Deferred Maintenance Account No. 5166 | 107300 | 125800 | 2016-04-26 | 100% | 99% | 119770 | 0 | 6030 | Yes
38 | 03111006 | Hilltop Unit, Gatesville | Infrastructure: Replace Ground Water Storage Tank | Deferred Maintenance Account No. 5166 | 747200 | 747200 | 2016-08-10 | 100% | 80% | 310110.33 | 400178.57 | 36911.1 | Yes
39 | 01410011 | Jester I Unit, Richmond | Infrastructure: Replace Ground Storage Water Tanks #1 & #2 | Deferred Maintenance Account No. 5166 | 461800 | 330800 | 2016-08-01 | 100% | 95% | 153019 | 153881.95 | 23899.05
40 | 11812001 | Travis Co. Unit, Austin | Infrastructure: Replace Grease Trap - Kitchen | Deferred Maintenance Account No. 5166 | 148700 | 183900 | 2016-07-01 | 100% | 1% | 175077 | 0 | 8823
41 | 05410010 | Polunsky Unit, Livingston | Security: Install High Mast Lighting - Offender Dorm Building & Perimeter Fence | Deferred Maintenance Account No. 5166 | 121200 | 206500 | 2016-10-01 | 100% | 1% | 196600 | 685.82 | 9214.18
42 | 01312013 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Security Operations Building | Deferred Maintenance Account No. 5166 | 156400 | 156400 | 2016-12-01 | 100% | 0% | 75.5 | 1382.3 | 154942.2
43 | 00513004 | Clemens Unit, Brazoria | Roofing: Replace Roof - Main Building | Deferred Maintenance Account No. 5166 | 347200 | 391900 | 2016-12-01 | 100% | 78% | 118135.56 | 225472.05 | 48292.39
44 | 04710001 | Robertson Unit, Abilene | Roofing: Replace Roofs - Multiple Buildings | Deferred Maintenance Account No. 5166 | 7891200 | 8321800 | 2018-07-15 | 100% | 1% | 7817435.11 | 92663.2 | 411701.69
45 | 02911013 | Luther Unit, Navasota | Infrastructure: Replace Ground Storage Tank - Water Plant | Deferred Maintenance Account No. 5166 | 626900 | 626900 | 2016-07-15 | 100% | 35% | 516266 | 90274.82 | 20359.18
46 | 01113002 | Ferguson Unit, Midway | Infrastructure: Refurbish Elevated Storage Tank - Water Plant | Deferred Maintenance Account No. 5166 | 337800 | 503500 | 2016-07-15 | 100% | 20% | 414900 | 61370 | 27230
47 | 11106003 | Moore Unit, Bonham | Security: Replace Security Control System | Deferred Maintenance Account No. 5166 | 3304198 | 1940598 | 2017-04-01 | 100% | 13% | 1700427.84 | 135883.5 | 104286.66
48 | 03708003 | Clements Unit, Amarillo | Safety: Repair/Replace Fire Line - Administrative Segregation | Deferred Maintenance Account No. 5166 | 420000 | 420000 | 2017-07-15 | 100% | 1% | 0 | 0 | 420000
49 | 03608011 | Michael Unit, Tennessee Colony | Safety: Repair/Replace Fire Line - Administrative Segregation | Deferred Maintenance Account No. 5166 | 420000 | 420000 | 2017-03-01 | 100% | 1% | 0 | 0 | 420000
50 | 04911009 | Stiles Unit, Beaumont | Facility Repair: Replace Windows - Offender Housing | Deferred Maintenance Account No. 5166 | 107400 | 107400 | 2016-12-01 | 100% | 0% | 0 | 0 | 107400
51 | 02210005 | Beto Unit, Tennessee Colony | Facility Repair: Replace Flooring - Main Kitchen & Scullery | Deferred Maintenance Account No. 5166 | 407000 | 407000 | 2017-04-01 | 100% | 0% | 0 | 0 | 407000
52 | 01915001 | Scott Unit, Angleton | Infrastructure: Replace Lift Station and Bar Screen - Waste Water Treatment Plant | Deferred Maintenance Account No. 5166 | 1881800 | 1881800 | 2017-09-01 | 100% | 0% | 60603.9 | 31910.1 | 1789286
53 | 02212005 | Beto Unit, Tennessee Colony | Safety: Install Standby Generator & Transfer Switch - Trusty Camp | Deferred Maintenance Account No. 5166 | 110100 | 120600 | 2017-01-01 | 100% | 15% | 81143.38 | 30300.37 | 9156.25 | Yes
54 | 00512007 | Clemens Unit, Brazoria | Safety: Install Standby Generator - Trusty Camp | Deferred Maintenance Account No. 5166 | 109200 | 109200 | 2016-11-01 | 100% | 2% | 95964.26 | 0 | 13235.74
55 | 01714002 | Ramsey Unit, Rosharon | Safety: Install Standby Generator - Trusty Camp | Deferred Maintenance Account No. 5166 | 106700 | 106700 | 2016-12-01 | 100% | 2% | 75389.36 | 0 | 31310.64
56 | 02215011 | Beto Unit, Tennessee Colony | Facility Repair: Install Electrical to Cells - Infirmary | Deferred Maintenance Account No. 5166 | 19300 | 19300 | 2017-06-01 | 100% | 0% | 0 | 0 | 19300
57 | 01913008 | Scott Unit, Angleton | Facility Repair: Renovate 3 & 4 Pickets | Deferred Maintenance Account No. 5166 | 65700 | 65700 | 2017-02-15 | 100% | 0% | 0 | 0 | 65700 | Yes
58 | 02212017 | Beto Unit, Tennessee Colony | Infrastructure: Replace Hot Water Lines - Main Building | Deferred Maintenance Account No. 5166 | 49600 | 49600 | 2016-12-01 | 100% | 3% | 9401 | 14063.89 | 26135.11
59 | 10814001 | Sanchez Unit, El Paso | Infrastructure: DESIGN ONLY - Renovate Elevated Water Storage Tank | Deferred Maintenance Account No. 5166 | 17700 | 17700 | 2016-09-01 | 86% | N/A | 0 | 0 | 17700 | Yes
60 | 03913005 | Hobby Unit, Marlin | Roofing: Replace Roof - Kitchen/Commissary | Deferred Maintenance Account No. 5166 | 153100 | 153100 | 2016-08-01 | 86% | 0% | 0 | 0 | 153100
61 | 02012008 | Wynne Unit, Huntsville | Facility Repair: Replace Flooring - Kitchen | Deferred Maintenance Account No. 5166 | 92900 | 92900 | 2016-10-01 | 100% | 0% | 0 | 0 | 92900
62 | 03616019 | Michael Unit, Tennessee Colony | Infrastructure: Replace Transformer - Packing Plant | Deferred Maintenance Account No. 5166 |  | 41200 | 2016-10-12 | N/A | 0% | 39200 | 0 | 2000 | Yes
63 | 00609001 | Coffield Unit, Tennessee Colony | Facility Repair: Renovate Commissary Space | Deferred Maintenance Account No. 5166 | 55800 | 55800 | 2016-07-01 | 100% | 0% | 0 | 0 | 55800
64 | 01713045 | Ramsey Unit, Rosharon | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 35100 | 35100 | 2016-09-05 | 100% | 2% | 13333.12 | 0 | 21766.88
65 | 03813007 | Daniel Unit, Snyder | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 162200 | 162200 | 2017-05-01 | 98% | 0% | 0 | 0 | 162200
66 | 04012003 | Lewis Unit, Woodville | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 162200 | 162200 | 2016-12-01 | 14% | 0% | 0 | 0 | 162200
67 | 09199005 | Chasefield Unit, Beeville | Safety: Repair/Replace Fire Alarm - Multiple Buildings | Deferred Maintenance Account No. 5166 | 98900 | 98900 | 2016-11-01 | 5% | 0% | 0 | 0 | 98900
68 | 04813002 | McConnell Unit, Beeville | Safety: Replace Intercom System - Medical | Deferred Maintenance Account No. 5166 | 101300 | 101300 | 2017-07-01 | 100% | 0% | 0 | 0 | 101300
69 | 02615001 | Pack Unit, Navasota | Infrastructure: Replace Filtration System - Storage Tank | Deferred Maintenance Account No. 5166 | 1432383 | 2774800 | 2017-04-01 | 100% | 0% | 79492.06 | 71307.59 | 2624000.35 | Yes
70 | 02813001 | Powledge Unit, Palestine | Infrastructure: DESIGN ONLY - Repair Washout - Outfall Line Waste Water Treatment Plant | Deferred Maintenance Account No. 5166 | 4200 | 4200 | 2016-07-01 | 14% | N/A | 0 | 0 | 4200
71 | 01313001 | Huntsville Unit, Huntsville | Roofing: DESIGN ONLY - Replace Roof/Repair Walls - Infirmary Building | Deferred Maintenance Account No. 5166 | 153600 | 153600 | 2016-10-15 | 0% | N/A | 0 | 0 | 153600
72 | 03312003 | Jester IV Unit, Richmond | Roofing: DESIGN ONLY - Replace Roof - Psychiatric Facility | Deferred Maintenance Account No. 5166 | 443700 | 443700 | 2017-12-01 | 1% | N/A | 319454 | 0 | 124246
73 | 03613004 | Michael Unit, Tennessee Colony | Roofing: DESIGN ONLY - Replace Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 858400 | 702300 | 2017-09-15 | 0% | N/A | 0 | 0 | 702300 | Yes
74 | 01914001 | Scott Unit, Angleton | Facility Repair: DESIGN ONLY - Replace Plumbing - Multiple Cell Blocks | Deferred Maintenance Account No. 5166 | 261000 | 79247 | 2016-10-05 | 1% | N/A | 74246.86 | 0 | 5000.14 | Yes
75 | 01913004 | Scott Unit, Angleton | Facility Repair: DESIGN ONLY - Kitchen Renovation | Deferred Maintenance Account No. 5166 | 530700 | 530700 | 2017-12-01 | 0% | N/A | 0 | 0 | 530700
76 | 02702010 | Terrell Unit, Rosharon | Facility Repair: Renovate Exhaust System - Vocational Shop | Deferred Maintenance Account No. 5166 | 164700 | 164700 | 2016-07-01 | 5% | 0% | 0 | 0 | 164700
77 | 01912007 | Scott Unit, Angleton | Security: DESIGN ONLY - Replace Locking System - Multiple Wings | Deferred Maintenance Account No. 5166 | 267800 | 267800 | 2016-12-01 | 1% | N/A | 189810 | 0 | 77990
78 | 01313004 | Huntsville Unit, Huntsville | Facility Repair: DESIGN ONLY - Repair/Replace South Wall - Perimeter | Deferred Maintenance Account No. 5166 | 461600 | 461600 | 2017-02-15 | 0% | N/A | 0 | 0 | 461600
79 | 01205010 | Goree Unit, Huntsville | Facility Repair: Renovate Showers - Multiple Buildings | Deferred Maintenance Account No. 5166 | 126900 | 126900 | 2017-06-01 | 100% | 3% | 50271.18 | 369 | 76259.82 | Yes
80 | 01300042 | Huntsville Unit, Huntsville | Safety: DESIGN ONLY - Install Fire Alarm System | Deferred Maintenance Account No. 5166 | 521900 | 521900 | 2016-10-01 | 14% | N/A | 300425.58 | 0 | 221474.42
81 | 04813003 | McConnell Unit, Beeville | Infrastructure: DESIGN ONLY - Replace Steam & Condensate Lines - Kitchen/Laundry Building | Deferred Maintenance Account No. 5166 | 164600 | 164600 | 2017-10-01 | 0% | N/A | 0 | 0 | 164600
82 | 12107001 | Lindsey Unit, Jacksboro | Infrastructure: DESIGN ONLY - Correct Drainage - Multiple Buildings | Deferred Maintenance Account No. 5166 | 6300 | 6300 | 2016-07-01 | 14% | N/A | 0 | 0 | 6300
83 | 10907002 | Lockhart Unit, Lockhart | Safety: Replace Fire Alarm - Multiple Buildings | Deferred Maintenance Account No. 5166 | 118700 | 118700 | 2016-10-01 | 100% | 0% | 0 | 0 | 118700 | Yes
84 | 01000010 | Ellis Unit, Huntsville | Safety: DESIGN ONLY - Install Fire Alarm System - Unit Wide | Deferred Maintenance Account No. 5166 | 378000 | 378000 | 2016-10-01 | 1% | N/A | 305573.21 | 0 | 72426.79
85 | 05402015 | Polunsky Unit, Livingston | Roofing: Repair / Replace Roofs - Multiple Buildings | Deferred Maintenance Account No. 5166 |  | 6626655 | 2019-09-01 | 100% | 0% | 191172.25 | 896.55 | 6434586.2 | Yes
86 | 09216001 | Holliday Unit, Huntsville | Safety: Add Wheelchair Accessibility - Multiple Dorms | Deferred Maintenance Account No. 5166 |  | 45400 | 2017-01-01 | 100% | 0% | 0 | 0 | 45400
87 | 04716003 | Robertson Unit, Abilene | Facility Repair: Replace Deaerator - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 118200 | 2016-09-01 | 100% | 0% | 0 | 0 | 118200
88 | 03612001 | Michael Unit, Tennessee Colony | Infrastructure: DESIGN ONLY - Replace Elevated Storage Tank & Storage Tank Well #4 | Deferred Maintenance Account No. 5166 | 4693942 | 30000 | 2016-09-01 | 90% | N/A | 14044.32 | 0 | 15955.68 | Yes
89 | 01608001 | Mt. View Unit, Gatesville | Infrastructure: DESIGN ONLY - Replace Ground Water Storage Tank, Boost Station and Replace Water Lines | Deferred Maintenance Account No. 5166 | 4947317 | 70500 | 2016-09-15 | 86% | N/A | 19837.98 | 45612.46 | 5049.56 | Yes
90 | 00715005 | Darrington Unit, Rosharon | Facility Repair: Replace Chillers - Intake Housing | Deferred Maintenance Account No. 5166 |  | 295700 | 2017-09-01 | 0% | 0% | 0 | 0 | 295700 | Yes
91 | 09215009 | Holliday Unit, Huntsville | Facility Repair: Replace Refrigeration Equipment - Kitchen | Deferred Maintenance Account No. 5166 |  | 123200 | 2017-07-22 | N/A | 3% | 108856.5 | 8178.87 | 6164.63 | Yes
92 | 02212024 | Beto Unit, Tennessee Colony | Infrastructure: Reline Manholes | Deferred Maintenance Account No. 5166 |  | 64700 | 2017-01-01 | 100% | 1% | 0 | 0 | 64700 | Yes
93 | 10316007 | Lopez Unit, Edinburg | Facility Repair: Replace Air Handler - Administrative Segregation | Deferred Maintenance Account No. 5166 |  | 94500 | 2016-11-22 | N/A | 0% | 0 | 0 | 94500 | Yes
94 | 09816005 | Dominguez Unit, San Antonio | Facility Repair: Replace HVAC Unit - Kitchen | Deferred Maintenance Account No. 5166 |  | 89700 | 2017-03-15 | 0% | 0% | 0 | 0 | 89700 | Yes
95 | 06816007 | Connally Unit, Kenedy | Facility Repair: Replace HVAC Units - Education and Medical | Deferred Maintenance Account No. 5166 |  | 313600 | 2017-01-02 | 1% | 0% | 0 | 0 | 313600 | Yes
96 | 00716001 | Darrington Unit, Rosharon | Facility Repair: Replace Chillers - Warehouse | Deferred Maintenance Account No. 5166 |  | 101600 | 2017-06-10 | 0% | 0% | 0 | 0 | 101600 | Yes
97 | 03115003 | Hilltop Unit, Gatesville | Infrastructure: Replace Boilers - Boiler Room | Deferred Maintenance Account No. 5166 |  | 73700 | 2017-02-15 | 100% | 1% | 39795 | 0 | 33905 | Yes
98 | 07916001 | Moore Unit, Bonham | Infrastructure: Replace Boilers - Boiler Room | Deferred Maintenance Account No. 5166 |  | 51600 | 2017-03-01 | 100% | 1% | 44998.35 | 0 | 6601.65 | Yes
99 | 01015008 | Ellis Unit, Huntsville | Infrastructure: Replace Service Entrance Switchgear - Back Gate | Deferred Maintenance Account No. 5166 |  | 207900 | 2017-08-01 | 100% | 0% | 0 | 0 | 207900 | Yes
100 | 07009003 | Neal Unit, Amarillo | Facility Repair: Renovate Mechanical Room and Replace Showers | Deferred Maintenance Account No. 5166 |  | 23756 | 2017-11-01 | 100% | 7% | 4645 | 970.33 | 18140.67 | Yes
N/A | 10313003 | Lopez Unit, Edinburg | Facility Repair: Replace/Rebuild Walls and Doors - Kitchen | Deferred Maintenance Account No. 5166 | 103700 | 0 | 2017-03-01 | 100% | 3% | 0 | 0 | 0
N/A | 02707005 | Terrell Unit, Rosharon | Infrastructure: Renovate Sewer Line from Food Service | Deferred Maintenance Account No. 5166 | 48700 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | Yes
N/A | 00616016 | Coffield Unit, Tennessee Colony | Infrastructure: Replace Transformer - Massey Substation | Deferred Maintenance Account No. 5166 | 0 | 0 | N/A | N/A | N/A | 0 | 0 | 0 | Yes
|  |  |  | Totals: | 56393900.62 | 57638273.05 |  |  |  | 29712682.55 | 6544679.12 | 21380911.38

## TDCJ Notes 6.16
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2016-06-15
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Supplemental Information
1 | TIMELINE: (original estimated substantial completion date: 04/15/16; revised: 10/15/16). Project is scheduled for FY16/17 construction.
2 | BUDGET: Project complete. Budget reduced to final expended.
5 | TIMELINE: (original estimated substantial completion date: 5/12/16; revised: 09/15/16). Project is scheduled for FY16/17 construction.
6 | BUDGET: Increased cost of materials. TIMELINE: (original estimated substantial completion date: 04/01/16; revised 10/17/16). Project is scheduled for FY16/17 construction.
8 | TIMELINE: (original estimated substantial completion date: 06/12/16; revised: 10/30/16). Project is scheduled for FY16/17 construction.
11 | TIMELINE: (original estimated substantial completion date: 03/30/16; revised: 10/15/16). Project is scheduled for FY16/17 construction.
13 | TIMELINE: (original estimated substantial completion date: 04/15/16; revised: 10/15/16). Project is scheduled for FY16/17 construction.
14 | TIMELINE: (original estimated substantial completion date: 06/03/16; revised: 11/01/16). Project is scheduled for FY16/17 construction.
17 | BUDGET: Project complete. Budget reduced to final expended. TIMELINE: (original estimated substantial completion date: 08/08/16; actual completion date: 04/05/16).
18 | TIMELINE: (original estimated substantial completion date: 06/01/16; revised: 10/01/16). Project is scheduled for FY16/17 construction.
19 | TIMELINE: (original estimated substantial completion date: 04/13/16; revised: 12/23/16). Project is scheduled for FY16/17 construction.
27 | BUDGET: After assessment it was determined that refurbishment of the air handler rather than replacement would be the best and most cost efficient option. TIMELINE: (original estimated substantial completion date: 03/15/17; revised: 10/28/16). Project is scheduled for FY16/17 construction.
29 | TIMELINE: (original estimated substantial completion date: 06/01/16; revised: 09/30/16). Project is scheduled for FY16/17 construction.
37 | TIMELINE: (original estimated substantial completion date: 08/15/16; actual completion date: 04/26/16). Pending final expenditures to close the project.
38 | TIMELINE: (original estimated substantial completion date: 06/01/16; revised: 08/10/16). Project is scheduled for FY16 construction.
53 | BUDGET: Increased cost of materials.
57 | TIMELINE: (original estimated substantial completion date: 07/01/16; revised: 02/15/17). Project is scheduled for FY16/17 construction.
59 | PROJECT DESCRIPTION: Clarification of project title - Project is design only for the 16/17 biennium. TIMELINE: (original estimated substantial completion date: 5/1/16; revised: 09/01/16). Project is scheduled for FY18/19 construction.
62 | PRIORITIZATION: New project added with priority ranking of 62. BUDGET: Michael Unit - Replace Transformer - Packing Plant.
69 | BUDGET: Construction cost higher than originally anticipated.
73 | TIMELINE: (original estimated substantial completion date: 02/15/17; revised: 09/15/17). Project is scheduled for FY18/19 construction.
74 | BUDGET: Design estimate was lower than originally anticipated. TIMELINE: (original estimated substantial completion date: 06/01/16; revised: 10/05/16). Project is scheduled for FY18/19 construction.
79 | TIMELINE: (original estimated substantial completion date: 10/15/16; revised: 06/01/17). Project is scheduled for FY16/17 construction.
83 | PROJECT DESCRIPTION: Project title change - Project is now design and construction. TIMELINE: (original estimated substantial completion date: 5/1/16; revised: 10/01/16). Project is scheduled for FY16/17 construction.
85 | BUDGET: Lowest qualified bidder was lower than original estimate.
88 | PRIORITIZATION: Project Priority updated from 89 to 88. TIMELINE: (original estimated substantial completion date: 06/01/16; revised: 09/01/16). Project is scheduled for FY18/19 construction.
89 | PRIORITIZATION: Project priority updated from 90 to 89. PROJECT DESCRIPTION: Project title updated to add water lines. TIMELINE: (original estimated substantial completion date: 06/01/16; revised: 09/15/16). Project is scheduled for FY18/19 construction.
90 | PRIORITIZATION: New project added with priority ranking of 90. BUDGET: Darrington Unit: Replace Chillers - Intake Housing.
91 | PRIORITIZATION: New project added with priority ranking of 91. BUDGET: Holliday Unit: Replace Refrigeration Equipment - Kitchen.
92 | PRIORITIZATION: New project added with priority ranking of 92. BUDGET: Beto Unit: Reline Manholes.
93 | PRIORITIZATION: New project added with priority ranking of 93. BUDGET: Lopez Unit: Replace Air Handler - Offender Housing.
94 | PRIORITIZATION: New project added with priority ranking of 94. BUDGET: Dominguez Unit: Replace HVAC Unit - Kitchen.
95 | PRIORITIZATION: New project added with priority ranking of 95. BUDGET: Connally Unit: Replace HVAC Units - Education and Medical.
96 | PRIORITIZATION: New project added with priority ranking of 96. BUDGET: Darrington Unit: Replace Chillers - Warehouse.
97 | PRIORITIZATION: New project added with priority ranking of 97. BUDGET: Hilltop Unit: Replace Boilers - Boiler Room.
98 | PRIORITIZATION: New project added with priority ranking of 98. BUDGET: Moore Unit: Replace Boilers - Boiler Room.
99 | PRIORITIZATION: New project added with priority ranking of 99. BUDGET: Ellis Unit: Replace Service Entrance Switchgear - Back Gate.
100 | PRIORITIZATION: New project added with priority ranking of 100. BUDGET: Neal Unit: Renovate Mechanical Room and Replace Showers.
N/A | PRIORITIZATION: Previous priority ranking of 62. (Terrell Unit) BUDGET: Project cancelled. An on-site evaluation determined that renovating sewer lines would not remedy the problem. Alternative solutions are being discussed.
N/A | PRIORITIZATION: Previous priority ranking of 88. (Coffield Unit) BUDGET: Project cancelled. Substation transferred to electric delivery vendor for repairs.

## TDCJ 3.16
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2016-03-15 | [9 empty] | 2016-03-15
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 2nd Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 04215005 | Hughes Unit, Gatesville | Facility Repair: Replace HVAC Unit - Support Operations | Deferred Maintenance Account No. 5166 |  | 57800 | 2016-04-15 | N/A | 3% | 45284.92 | 1784.53 | 10730.55 | Yes
2 | 09915001 | Hutchins Unit, Dallas | Facility Repair: Refurbish Air Handler - Support Operations | Deferred Maintenance Account No. 5166 |  | 63200 | 2015-11-23 | N/A | 100% | 0 | 60818.03 | 2381.97
3 | 05014007 | Roach Unit, Childress | Roofing: Repair Roof - ISF | Deferred Maintenance Account No. 5166 | 75600 | 75600 | 2016-07-26 | N/A | 2% | 57088.3 | 1998.71 | 16512.99 | Yes
4 | 00512006 | Clemens Unit, Brazoria | Facility Repair: Resurface Floor - Main Building Kitchen | Deferred Maintenance Account No. 5166 | 40400 | 40400 | 2016-09-13 | 100% | 1% | 0 | 15235.52 | 25164.48 | Yes
5 | 10510005 | Murray Unit, Gatesville | Facility Repair: Install Handicap Accessible Shower - Offender Dorms | Deferred Maintenance Account No. 5166 | 37400 | 37400 | 2016-05-12 | 100% | 3% | 15999.88 | 7633.88 | 13766.24 | Yes
6 | 01015016 | Ellis Unit, Huntsville | Safety: Replace Generator - Boiler Room | Deferred Maintenance Account No. 5166 |  | 65100 | 2016-04-01 | 100% | 2% | 59669.5 | 2130.41 | 3300.09 | Yes
7 | 06913002 | Allred Unit, Iowa Park | Roofing: Resurface Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 88800 | 88800 | 2016-08-01 | 100% | 4% | 70803.88 | 2665.26 | 15330.86
8 | 10815003 | Sanchez Unit, El Paso | Infrastructure: Refurbish Lift Station - Front Administration Building | Deferred Maintenance Account No. 5166 |  | 236900 | 2016-06-12 | N/A | 1% | 185000 | 0 | 51900 | Yes
9 | 08212003 | Havins Unit, Brownwood | Facility Repair: Install Fiberglass Wall Panels - Multiple Buildings | Deferred Maintenance Account No. 5166 | 47900 | 47900 | 2016-08-19 | 100% | 3% | 18454.5 | 6727.08 | 22718.42 | Yes
10 | 06715022 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Infirmary | Deferred Maintenance Account No. 5166 |  | 119400 | 2016-08-07 | N/A | 2% | 108914.78 | 1759.3 | 8725.92 | Yes
11 | 03615005 | Michael Unit, Tennessee Colony | Safety: Replace Emergency Generator - Lift Station | Deferred Maintenance Account No. 5166 |  | 51000 | 2016-03-30 | N/A | 3% | 0 | 2638.39 | 48361.61 | Yes
12 | 09413001 | Gurney Unit, Tennessee Colony | Facility Repair: Renovate Maintenance Shop | Deferred Maintenance Account No. 5166 | 46400 | 46400 | 2016-07-01 | 100% | 17% | 26186.84 | 14491.11 | 5722.05 | Yes
13 | 06716001 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Officers' Dining Room | Deferred Maintenance Account No. 5166 |  | 122200 | 2016-04-15 | N/A | 2% | 103284.75 | 436.49 | 18478.76 | Yes
14 | 08015001 | Sayle Unit, Breckenridge | Facility Repair: Replace Feed Water Tank - Boiler Room | Deferred Maintenance Account No. 5166 |  | 66100 | 2016-06-03 | 100% | 3% | 59085.57 | 1030.7 | 5983.73 | Yes
15 | 06211002 | Ft. Stockton Unit, Fort Stockton | Facility Repair: Replace Showers - Offender Dorms | Deferred Maintenance Account No. 5166 | 374900 | 374900 | 2016-10-12 | 100% | 1% | 206128.17 | 6923.87 | 161847.96 | Yes
16 | 01313007 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Repair Shop | Deferred Maintenance Account No. 5166 | 45200 | 59600 | 2016-07-11 | 100% | 2% | 47543.96 | 797.2 | 11258.84 | Yes
17 | 04505002 | Estes Unit, Venus | Security: Install Concrete Footer - Perimeter Fence | Deferred Maintenance Account No. 5166 | 37700 | 37700 | 2016-08-08 | N/A | 75% | 19577.6 | 8631.67 | 9490.73 | Yes
18 | 08915001 | Johnston Unit, Winnsboro | Facility Repair: Replace Steam Boiler - Boiler Room | Deferred Maintenance Account No. 5166 |  | 83700 | 2016-06-01 | 100% | 3% | 75116.84 | 0 | 8583.16 | Yes
19 | 08416002 | Halbert Unit, Burnet | Facility Repair: Replace Refrigeration Equipment - Food Service | Deferred Maintenance Account No. 5166 |  | 56400 | 2016-04-13 | N/A | 1% | 46351.9 | 0 | 10048.1 | Yes
20 | 02215006 | Beto Unit, Tennessee Colony | Facility Repair: Replace Hot Water Storage Tank - Boiler Room | Deferred Maintenance Account No. 5166 |  | 128600 | 2016-09-01 | 100% | 1% | 0 | 0 | 128600 | Yes
21 | 12913004 | Young Unit, Dickinson | Infrastructure: Replace/Refurbish Cooling Tower - Central Plant | Deferred Maintenance Account No. 5166 |  | 279200 | 2017-05-15 | 10% | 0% | 0 | 0 | 279200 | Yes
22 | 10014001 | Lychner Unit, Humble | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 |  | 394700 | 2017-02-01 | 5% | 0% | 0 | 0 | 394700 | Yes
23 | 03015002 | Jester III Unit, Richmond | Facility Repair: Replace Heat Exchangers, Storage Tank & Condensate Pump - Heat Exchanger Room | Deferred Maintenance Account No. 5166 |  | 181800 | 2016-10-20 | 100% | 1% | 173100 | 0 | 8700 | Yes
24 | 07815004 | Segovia Unit, Edinburg | Facility Repair: Replace Water Softener - Multiple Dorms | Deferred Maintenance Account No. 5166 |  | 55900 | 2016-12-15 | 100% | 1% | 48000 | 0 | 7900 | Yes
25 | 10414006 | Ware Unit, Colorado City | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 |  | 80100 | 2016-09-01 | 1% | 0% | 0 | 0 | 80100 | Yes
26 | 09215007 | Holliday Unit, Huntsville | Facility Repair: Replace Air Handler & Heater - Offender Housing | Deferred Maintenance Account No. 5166 |  | 246600 | 2017-02-15 | 1% | 0% | 0 | 0 | 246600 | Yes
27 | 09915002 | Hutchins Unit, Dallas | Facility Repair: Replace Air Handler - Food Service | Deferred Maintenance Account No. 5166 |  | 170500 | 2017-03-15 | 1% | 0% | 0 | 0 | 170500 | Yes
28 | 01711010 | Ramsey Unit, Rosharon | Security: Replace Locking System | Deferred Maintenance Account No. 5166 | 2073900 | 2073900 | 2016-11-01 | 100% | 2% | 1977050.48 | 5979.43 | 90870.09 | Yes
29 | 02802006 | Powledge Unit, Palestine | Roofing: Repair/Replace Roof on Metal Fab Factory Building | Deferred Maintenance Account No. 5166 | 1477100 | 1477100 | 2016-06-01 | 100% | 4% | 1362988.61 | 50664.45 | 63446.94 | Yes
30 | 02909007 | Luther Unit, Navasota | Safety: Install Fire Alarm System - Multiple Locations | Deferred Maintenance Account No. 5166 | 1313200 | 1313200 | 2016-08-01 | 100% | 43% | 818613.78 | 404734.68 | 89851.54 | Yes
31 | 04301001 | Kyle Unit, Kyle | Safety: Repair/Replace Fire Alarm System - Multiple Buildings | Deferred Maintenance Account No. 5166 | 324044.62 | 324045 | 2016-09-01 | 100% | 9% | 303741.62 | 0 | 20303.38 | Yes
32 | 04404002 | Bridgeport Unit, Bridgeport | Security: Replace Control System Electric Door Locks & Intercom System | Deferred Maintenance Account No. 5166 | 1616900 | 1616900 | 2016-09-01 | 100% | 29% | 1184968.99 | 331876.96 | 100054.05 | Yes
33 | 03711006 | Clements Unit, Amarillo | Roofing: Replace Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 7461800 | 7461800 | 2017-02-01 | 100% | 1% | 7054463.45 | 49283.33 | 358053.22 | Yes
34 | 03608012 | Michael Unit, Tennessee Colony | Security: Replace Door Controls - Multiple Buildings | Deferred Maintenance Account No. 5166 | 5494300 | 5494300 | 2017-04-15 | 100% | 18% | 4277511.38 | 896001.79 | 320786.83 | Yes
35 | 01802005 | Stringfellow Unit, Rosharon | Security: Replace Cell Door Locks - Offender Dorm Wing | Deferred Maintenance Account No. 5166 | 839916 | 839916 | 2016-09-01 | 100% | 21% | 787334.33 | 3904.26 | 48677.41 | Yes
36 | 02004006 | Wynne Unit, Huntsville | Facility Repair: Extending Covered Area - Transportation Repair Shop | Deferred Maintenance Account No. 5166 | 484400 | 484400 | 2016-09-10 | 100% | 1% | 213059.23 | 38315.67 | 233025.1 | Yes
37 | 02413007 | Crain Unit, Gatesville | Roofing: Replace Roof - Dorm Building | Deferred Maintenance Account No. 5166 | 107300 | 125800 | 2016-08-15 | 100% | 1% | 119770 | 0 | 6030 | Yes
38 | 03111006 | Hilltop Unit, Gatesville | Infrastructure: Replace Ground Water Storage Tank | Deferred Maintenance Account No. 5166 | 747200 | 747200 | 2016-06-01 | 100% | 5% | 715127.61 | 0 | 32072.39 | Yes
39 | 01410011 | Jester I Unit, Richmond | Infrastructure: Replace Ground Storage Water Tanks #1 & #2 | Deferred Maintenance Account No. 5166 | 461800 | 330800 | 2016-08-01 | 100% | 12% | 306274 | 8289.7 | 16236.3 | Yes
40 | 11812001 | Travis Co. Unit, Austin | Infrastructure: Replace Grease Trap - Kitchen | Deferred Maintenance Account No. 5166 | 148700 | 183900 | 2016-07-01 | 100% | 1% | 175077 | 0 | 8823 | Yes
41 | 05410010 | Polunsky Unit, Livingston | Security: Install High Mast Lighting - Offender Dorm Building & Perimeter Fence | Deferred Maintenance Account No. 5166 | 121200 | 206500 | 2016-10-01 | 100% | 0% | 0 | 0 | 206500 | Yes
42 | 01312013 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Security Operations Building | Deferred Maintenance Account No. 5166 | 156400 | 156400 | 2016-12-01 | 100% | 0% | 0 | 0 | 156400 | Yes
43 | 00513004 | Clemens Unit, Brazoria | Roofing: Replace Roof - Main Building | Deferred Maintenance Account No. 5166 | 347200 | 391900 | 2016-12-01 | 100% | 5% | 367589 | 0 | 24311 | Yes
44 | 04710001 | Robertson Unit, Abilene | Roofing: Replace Roofs - Multiple Buildings | Deferred Maintenance Account No. 5166 | 7891200 | 8321800 | 2018-07-15 | 100% | 1% | 7892819.95 | 21010.46 | 407969.59 | Yes
45 | 02911013 | Luther Unit, Navasota | Infrastructure: Replace Ground Storage Tank - Water Plant | Deferred Maintenance Account No. 5166 | 626900 | 626900 | 2016-07-15 | 100% | 2% | 607562 | 0 | 19338 | Yes
46 | 01113002 | Ferguson Unit, Midway | Infrastructure: Refurbish Elevated Storage Tank - Water Plant | Deferred Maintenance Account No. 5166 | 337800 | 503500 | 2016-07-15 | 100% | 1% | 479500 | 0 | 24000 | Yes
47 | 11106003 | Moore Unit, Bonham | Security: Replace Security Control System | Deferred Maintenance Account No. 5166 | 3304198 | 1940598 | 2017-04-01 | 100% | 1% | 1832650.99 | 10029.76 | 97917.25 | Yes
48 | 03708003 | Clements Unit, Amarillo | Safety: Repair/Replace Fire Line - Administrative Segregation | Deferred Maintenance Account No. 5166 | 420000 | 420000 | 2017-07-15 | 100% | 1% | 0 | 0 | 420000 | Yes
49 | 03608011 | Michael Unit, Tennessee Colony | Safety: Repair/Replace Fire Line - Administrative Segregation | Deferred Maintenance Account No. 5166 | 420000 | 420000 | 2017-03-01 | 100% | 1% | 0 | 0 | 420000 | Yes
50 | 04911009 | Stiles Unit, Beaumont | Facility Repair: Replace Windows - Offender Housing | Deferred Maintenance Account No. 5166 | 107400 | 107400 | 2016-12-01 | 100% | 0% | 0 | 0 | 107400 | Yes
51 | 02210005 | Beto Unit, Tennessee Colony | Facility Repair: Replace Flooring - Main Kitchen & Scullery | Deferred Maintenance Account No. 5166 | 407000 | 407000 | 2017-04-01 | 86% | 0% | 0 | 0 | 407000 | Yes
52 | 01915001 | Scott Unit, Angleton | Infrastructure: Replace Lift Station and Bar Screen - Waste Water Treatment Plant | Deferred Maintenance Account No. 5166 | 1881800 | 1881800 | 2017-09-01 | 80% | 0% | 69801.9 | 22712.1 | 1789286 | Yes
53 | 02212005 | Beto Unit, Tennessee Colony | Safety: Install Standby Generator & Transfer Switch - Trusty Camp | Deferred Maintenance Account No. 5166 | 110100 | 110100 | 2017-01-01 | 100% | 2% | 103747.31 | 0 | 6352.69 | Yes
54 | 00512007 | Clemens Unit, Brazoria | Safety: Install Standby Generator - Trusty Camp | Deferred Maintenance Account No. 5166 | 109200 | 109200 | 2016-11-01 | 100% | 1% | 72332 | 0 | 36868 | Yes
55 | 01714002 | Ramsey Unit, Rosharon | Safety: Install Standby Generator - Trusty Camp | Deferred Maintenance Account No. 5166 | 106700 | 106700 | 2016-12-01 | 100% | 1% | 72332 | 0 | 34368 | Yes
56 | 02215011 | Beto Unit, Tennessee Colony | Facility Repair: Install Electrical to Cells - Infirmary | Deferred Maintenance Account No. 5166 | 19300 | 19300 | 2017-06-01 | 14% | 0% | 0 | 0 | 19300 | Yes
57 | 01913008 | Scott Unit, Angleton | Facility Repair: Renovate 3 & 4 Pickets | Deferred Maintenance Account No. 5166 | 65700 | 65700 | 2016-07-01 | 14% | 0% | 0 | 0 | 65700 | Yes
58 | 02212017 | Beto Unit, Tennessee Colony | Infrastructure: Replace Hot Water Lines - Main Building | Deferred Maintenance Account No. 5166 | 49600 | 49600 | 2016-12-01 | 100% | 2% | 26525.53 | 0 | 23074.47 | Yes
59 | 10814001 | Sanchez Unit, El Paso | Infrastructure: Renovate Elevated Water Storage Tank | Deferred Maintenance Account No. 5166 | 17700 | 17700 | 2016-05-01 | 14% | 0% | 0 | 0 | 17700 | Yes
60 | 03913005 | Hobby Unit, Marlin | Roofing: Replace Roof - Kitchen/Commissary | Deferred Maintenance Account No. 5166 | 153100 | 153100 | 2016-08-01 | 45% | 0% | 0 | 0 | 153100 | Yes
61 | 02012008 | Wynne Unit, Huntsville | Facility Repair: Replace Flooring - Kitchen | Deferred Maintenance Account No. 5166 | 92900 | 92900 | 2016-10-01 | 10% | 0% | 0 | 0 | 92900 | Yes
62 | 02707005 | Terrell Unit, Rosharon | Infrastructure: Renovate Sewer Line from Food Service | Deferred Maintenance Account No. 5166 | 48700 | 48700 | 2016-12-01 | 14% | 0% | 0 | 0 | 48700 | Yes
63 | 00609001 | Coffield Unit, Tennessee Colony | Facility Repair: Renovate Commissary Space | Deferred Maintenance Account No. 5166 | 55800 | 55800 | 2016-07-01 | 14% | 0% | 0 | 0 | 55800 | Yes
64 | 01713045 | Ramsey Unit, Rosharon | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 35100 | 35100 | 2016-09-05 | 100% | 1% | 0 | 0 | 35100 | Yes
65 | 03813007 | Daniel Unit, Snyder | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 162200 | 162200 | 2017-05-01 | 45% | 0% | 0 | 0 | 162200 | Yes
66 | 04012003 | Lewis Unit, Woodville | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 162200 | 162200 | 2016-12-01 | 1% | 0% | 0 | 0 | 162200 | Yes
67 | 09199005 | Chasefield Unit, Beeville | Safety: Repair/Replace Fire Alarm - Multiple Buildings | Deferred Maintenance Account No. 5166 | 98900 | 98900 | 2016-11-01 | 5% | 0% | 0 | 0 | 98900 | Yes
68 | 04813002 | McConnell Unit, Beeville | Safety: Replace Intercom System - Medical | Deferred Maintenance Account No. 5166 | 101300 | 101300 | 2017-07-01 | 5% | 0% | 0 | 0 | 101300 | Yes
69 | 02615001 | Pack Unit, Navasota | Infrastructure: Replace Filtration System - Storage Tank | Deferred Maintenance Account No. 5166 | 1432383 | 1432383 | 2017-04-01 | 50% | 0% | 143340.47 | 7459.18 | 1281583.35 | Yes
70 | 02813001 | Powledge Unit, Palestine | Infrastructure: DESIGN ONLY - Repair Washout - Outfall Line Waste Water Treatment Plant | Deferred Maintenance Account No. 5166 | 4200 | 4200 | 2016-07-01 | 10% | N/A | 0 | 0 | 4200 | Yes
71 | 01313001 | Huntsville Unit, Huntsville | Roofing: DESIGN ONLY - Replace Roof/Repair Walls - Infirmary Building | Deferred Maintenance Account No. 5166 | 153600 | 153600 | 2016-10-15 | 1% | N/A | 0 | 0 | 153600 | Yes
72 | 03312003 | Jester IV Unit, Richmond | Roofing: DESIGN ONLY - Replace Roof - Psychiatric Facility | Deferred Maintenance Account No. 5166 | 443700 | 443700 | 2017-12-01 | 1% | N/A | 0 | 0 | 443700 | Yes
73 | 03613004 | Michael Unit, Tennessee Colony | Roofing: DESIGN ONLY - Replace Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 858400 | 702300 | 2017-02-15 | 1% | N/A | 0 | 0 | 702300 | Yes
74 | 01914001 | Scott Unit, Angleton | Facility Repair: DESIGN ONLY - Replace Plumbing - Multiple Cell Blocks | Deferred Maintenance Account No. 5166 | 261000 | 261000 | 2016-06-01 | 1% | N/A | 0 | 0 | 261000 | Yes
75 | 01913004 | Scott Unit, Angleton | Facility Repair: DESIGN ONLY - Kitchen Renovation | Deferred Maintenance Account No. 5166 | 530700 | 530700 | 2017-12-01 | 0% | N/A | 0 | 0 | 530700 | Yes
76 | 02702010 | Terrell Unit, Rosharon | Facility Repair: Renovate Exhaust System - Vocational Shop | Deferred Maintenance Account No. 5166 | 164700 | 164700 | 2016-07-01 | 5% | 0% | 0 | 0 | 164700 | Yes
77 | 01912007 | Scott Unit, Angleton | Security: DESIGN ONLY - Replace Locking System - Multiple Wings | Deferred Maintenance Account No. 5166 | 267800 | 267800 | 2016-12-01 | 1% | N/A | 0 | 0 | 267800 | Yes
78 | 01313004 | Huntsville Unit, Huntsville | Facility Repair: DESIGN ONLY - Repair/Replace South Wall - Perimeter | Deferred Maintenance Account No. 5166 | 461600 | 461600 | 2017-02-15 | 1% | N/A | 0 | 0 | 461600 | Yes
79 | 01205010 | Goree Unit, Huntsville | Facility Repair: Renovate Showers - Multiple Buildings | Deferred Maintenance Account No. 5166 | 126900 | 126900 | 2016-10-15 | 100% | 1% | 0 | 0 | 126900 | Yes
80 | 01300042 | Huntsville Unit, Huntsville | Safety: DESIGN ONLY - Install Fire Alarm System | Deferred Maintenance Account No. 5166 | 521900 | 521900 | 2016-10-01 | 1% | N/A | 300425.58 | 0 | 221474.42 | Yes
81 | 04813003 | McConnell Unit, Beeville | Infrastructure: DESIGN ONLY - Replace Steam & Condensate Lines - Kitchen/Laundry Building | Deferred Maintenance Account No. 5166 | 164600 | 164600 | 2017-10-01 | 0% | N/A | 0 | 0 | 164600 | Yes
82 | 12107001 | Lindsey Unit, Jacksboro | Infrastructure: DESIGN ONLY - Correct Drainage - Multiple Buildings | Deferred Maintenance Account No. 5166 | 6300 | 6300 | 2016-07-01 | 5% | N/A | 0 | 0 | 6300 | Yes
83 | 10907002 | Lockhart Unit, Lockhart | Safety: DESIGN ONLY - Replace Fire Alarm - Multiple Buildings | Deferred Maintenance Account No. 5166 | 118700 | 118700 | 2016-05-01 | 0% | 0% | 0 | 0 | 118700 | Yes
84 | 01000010 | Ellis Unit, Huntsville | Safety: DESIGN ONLY - Install Fire Alarm System - Unit Wide | Deferred Maintenance Account No. 5166 | 378000 | 378000 | 2016-10-01 | 1% | N/A | 0 | 0 | 378000 | Yes
85 | 05402015 | Polunsky Unit, Livingston | Roofing: Repair / Replace Roofs - Multiple Buildings | Deferred Maintenance Account No. 5166 |  | 7352271 | 2019-09-01 | 100% | 0% | 191172.25 | 0 | 7161098.75 | Yes
86 | 09216001 | Holliday Unit, Huntsville | Safety: Add Wheelchair Accessibility - Multiple Dorms | Deferred Maintenance Account No. 5166 |  | 45400 | 2017-01-01 | 1% | 0% | 0 | 0 | 45400 | Yes
87 | 04716003 | Robertson Unit, Abilene | Facility Repair: Replace Deaerator - Boiler Room | Deferred Maintenance Account No. 5166 | 0 | 118200 | 2016-09-01 | N/A | 0% | 0 | 0 | 118200 | Yes
88 | 00616016 | Coffield Unit, Tennessee Colony | Infrastructure: Replace Transformer - Massey Substation | Deferred Maintenance Account No. 5166 | 0 | 817400 | 2017-01-15 | N/A | 0% | 0 | 0 | 817400 | Yes
89 | 03612001 | Michael Unit, Tennessee Colony | Infrastructure: DESIGN ONLY - Replace Elevated Storage Tank & Storage Tank Well #4 | Deferred Maintenance Account No. 5166 | 4693942 | 30000 | 2016-06-01 | 80% | N/A | 14044.32 | 0 | 15955.68 | Yes
90 | 01608001 | Mt. View Unit, Gatesville | Infrastructure: DESIGN ONLY - Replace Ground Water Storage Tank & Add Boost Station | Deferred Maintenance Account No. 5166 | 4947317 | 70500 | 2016-06-01 | 80% | N/A | 65450.44 | 0 | 5049.56 | Yes
N/A | 10313003 | Lopez Unit, Edinburg | Facility Repair: Replace/Rebuild Walls and Doors - Kitchen | Deferred Maintenance Account No. 5166 | 103700 | 0 | 2017-03-01 | N/A | N/A | 0 | 0 | 0
|  |  |  | Totals: | 56393900.62 | 56685613 |  |  |  | 32900865.61 | 1985963.92 | 21798783.47

## TDCJ 12.15
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2015-12-15 | [9 empty] | 2015-12-15
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 04215005 | Hughes Unit, Gatesville | Facility Repair: Replace HVAC Unit - Support Operations | Deferred Maintenance Account No. 5166 |  | 57800 | 2015-12-02 | N/A | 100% | 46585.22 | 0 | 11214.78 | Yes
2 | 09915001 | Hutchins Unit, Dallas | Facility Repair: Refurbish Air Handler - Support Operations | Deferred Maintenance Account No. 5166 |  | 63200 | 2015-11-23 | N/A | 100% | 60241.99 | 500 | 2458.01 | Yes
3 | 05014007 | Roach Unit, Childress | Roofing: Repair Roof - ISF | Deferred Maintenance Account No. 5166 | 75600 | 75600 | 2016-01-18 | N/A | 1% | 25438.71 | 0 | 50161.29 | Yes
4 | 00512006 | Clemens Unit, Brazoria | Facility Repair: Resurface Floor - Main Building Kitchen | Deferred Maintenance Account No. 5166 | 40400 | 40400 | 2016-06-01 | 100% | 1% | 15235.52 | 0 | 25164.48
5 | 10510005 | Murray Unit, Gatesville | Facility Repair: Install Handicap Accessible Shower - Offender Dorms | Deferred Maintenance Account No. 5166 | 37400 | 37400 | 2016-04-15 | 100% | 2% | 21369.82 | 0 | 16030.18
6 | 01015016 | Ellis Unit, Huntsville | Safety: Replace Generator - Boiler Room | Deferred Maintenance Account No. 5166 |  | 65100 | 2016-02-01 | 100% | 1% | 58500 | 0 | 6600 | Yes
7 | 06913002 | Allred Unit, Iowa Park | Roofing: Resurface Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 88800 | 88800 | 2016-08-01 | 100% | 1% | 24957.95 | 0 | 63842.05
8 | 10815003 | Sanchez Unit, El Paso | Infrastructure: Refurbish Lift Station - Front Administration Building | Deferred Maintenance Account No. 5166 |  | 236900 | 2016-01-21 | N/A | 1% | 185000 | 0 | 51900 | Yes
9 | 08212003 | Havins Unit, Brownwood | Facility Repair: Install Fiberglass Wall Panels - Multiple Buildings | Deferred Maintenance Account No. 5166 | 47900 | 47900 | 2016-04-01 | 100% | 3% | 43153.52 | 0 | 4746.48
10 | 06715022 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Infirmary | Deferred Maintenance Account No. 5166 |  | 119400 | 2016-03-01 | N/A | 1% | 113347.11 | 0 | 6052.89 | Yes
11 | 09413001 | Gurney Unit, Tennessee Colony | Facility Repair: Renovate Maintenance Shop | Deferred Maintenance Account No. 5166 | 46400 | 46400 | 2016-07-01 | 100% | 3% | 40649.36 | 0 | 5750.64
12 | 06716001 | Telford Unit, New Boston | Facility Repair: Replace HVAC Unit - Officers' Dining Room | Deferred Maintenance Account No. 5166 |  | 122200 | 2016-03-09 | N/A | 2% | 103756.72 | 0 | 18443.28 | Yes
13 | 08015001 | Sayle Unit, Breckenridge | Facility Repair: Replace Feed Water Tank - Boiler Room | Deferred Maintenance Account No. 5166 |  | 66100 | 2016-01-27 | 100% | 0% | 0 | 0 | 66100 | Yes
14 | 06211002 | Ft. Stockton Unit, Fort Stockton | Facility Repair: Replace Showers - Offender Dorms | Deferred Maintenance Account No. 5166 | 374900 | 374900 | 2016-04-15 | 100% | 1% | 180813 | 0 | 194087 | Yes
15 | 01313007 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Repair Shop | Deferred Maintenance Account No. 5166 | 45200 | 45200 | 2016-03-01 | 100% | 0% | 0 | 0 | 45200
16 | 04505002 | Estes Unit, Venus | Security: Install Concrete Footer - Perimeter Fence | Deferred Maintenance Account No. 5166 | 37700 | 37700 | 2016-08-08 | N/A | 3% | 26251.21 | 0 | 11448.79 | Yes
17 | 08915001 | Johnston Unit, Winnsboro | Facility Repair: Replace Steam Boiler - Boiler Room | Deferred Maintenance Account No. 5166 |  | 83700 | 2016-06-01 | 100% | 0% | 0 | 0 | 83700 | Yes
18 | 08416002 | Halbert Unit, Burnet | Facility Repair: Replace Refrigeration Equipment - Food Service | Deferred Maintenance Account No. 5166 |  | 56400 | 2016-04-13 | N/A | 0% | 0 | 0 | 56400 | Yes
19 | 02215006 | Beto Unit, Tennessee Colony | Facility Repair: Replace Hot Water Storage Tank - Boiler Room | Deferred Maintenance Account No. 5166 |  | 128600 | 2016-09-01 | 10% | 0% | 0 | 0 | 128600 | Yes
20 | 12913004 | Young Unit, Dickinson | Infrastructure: Replace/Refurbish Cooling Tower - Central Plant | Deferred Maintenance Account No. 5166 |  | 279200 | 2017-05-15 | 5% | 0% | 0 | 0 | 279200 | Yes
21 | 10014001 | Lychner Unit, Humble | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 |  | 394700 | 2017-02-01 | 1% | 0% | 0 | 0 | 394700 | Yes
22 | 03015002 | Jester III Unit, Richmond | Facility Repair: Replace Heat Exchangers, Storage Tank & Condensate Pump - Heat Exchanger Room | Deferred Maintenance Account No. 5166 |  | 181800 | 2016-10-20 | 1% | 0% | 0 | 0 | 181800 | Yes
23 | 07815004 | Segovia Unit, Edinburg | Facility Repair: Replace Water Softener - Multiple Dorms | Deferred Maintenance Account No. 5166 |  | 55900 | 2016-12-15 | 0% | 0% | 0 | 0 | 55900 | Yes
24 | 10414006 | Ware Unit, Colorado City | Facility Repair: Replace HVAC Unit - Medical | Deferred Maintenance Account No. 5166 |  | 80100 | 2016-09-01 | 0% | 0% | 0 | 0 | 80100 | Yes
25 | 09215007 | Holliday Unit, Huntsville | Facility Repair: Replace Air Handler & Heater - Offender Housing | Deferred Maintenance Account No. 5166 |  | 246600 | 2017-02-15 | 1% | 0% | 0 | 0 | 246600 | Yes
26 | 09915002 | Hutchins Unit, Dallas | Facility Repair: Replace Air Handler - Food Service | Deferred Maintenance Account No. 5166 |  | 170500 | 2017-03-15 | 1% | 0% | 0 | 0 | 170500 | Yes
27 | 01711010 | Ramsey Unit, Rosharon | Security: Replace Locking System | Deferred Maintenance Account No. 5166 | 2073900 | 2073900 | 2016-11-01 | 100% | 1% | 1983029.91 | 0 | 90870.09
28 | 02802006 | Powledge Unit, Palestine | Roofing: Repair/Replace Roof on Metal Fab Factory Building | Deferred Maintenance Account No. 5166 | 1477100 | 1477100 | 2016-06-01 | 100% | 1% | 1416319.61 | 0 | 60780.39
29 | 02909007 | Luther Unit, Navasota | Safety: Install Fire Alarm System - Multiple Locations | Deferred Maintenance Account No. 5166 | 1313200 | 1313200 | 2016-08-01 | 100% | 1% | 1243944.21 | 0 | 69255.79
30 | 04301001 | Kyle Unit, Kyle | Safety: Repair/Replace Fire Alarm System - Multiple Buildings | Deferred Maintenance Account No. 5166 | 324044.62 | 324045 | 2016-09-01 | 100% | 1% | 303741.62 | 0 | 20303.38
31 | 04404002 | Bridgeport Unit, Bridgeport | Security: Replace Control System Electric Door Locks & Intercom System | Deferred Maintenance Account No. 5166 | 1616900 | 1616900 | 2016-09-01 | 100% | 3% | 1430505.3 | 98588.15 | 87806.55
32 | 03711006 | Clements Unit, Amarillo | Roofing: Replace Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 7461800 | 7461800 | 2017-02-01 | 100% | 1% | 7106310.45 | 0 | 355489.55
33 | 03608012 | Michael Unit, Tennessee Colony | Security: Replace Door Controls - Multiple Buildings | Deferred Maintenance Account No. 5166 | 5494300 | 5494300 | 2017-04-15 | 100% | 1% | 4896053.06 | 308239.61 | 290007.33
34 | 01802005 | Stringfellow Unit, Rosharon | Security: Replace Cell Door Locks - Offender Dorm Wing | Deferred Maintenance Account No. 5166 | 839916 | 839916 | 2016-09-01 | 100% | 1% | 790843.2 | 0 | 49072.8
35 | 02004006 | Wynne Unit, Huntsville | Facility Repair: Extending Covered Area - Transportation Repair Shop | Deferred Maintenance Account No. 5166 | 484400 | 484400 | 2016-04-15 | 100% | 0% | 0 | 0 | 484400 | Yes
36 | 02413007 | Crain Unit, Gatesville | Roofing: Replace Roof - Dorm Building | Deferred Maintenance Account No. 5166 | 107300 | 107300 | 2016-03-15 | 100% | 0% | 0 | 0 | 107300
37 | 03111006 | Hilltop Unit, Gatesville | Infrastructure: Replace Ground Water Storage Tank | Deferred Maintenance Account No. 5166 | 747200 | 747200 | 2016-04-01 | 100% | 0% | 0 | 0 | 747200
38 | 01410011 | Jester I Unit, Richmond | Infrastructure: Replace Ground Storage Water Tanks #1 & #2 | Deferred Maintenance Account No. 5166 | 461800 | 330800 | 2016-08-01 | 100% | 0% | 0 | 0 | 330800 | Yes
39 | 11812001 | Travis Co. Unit, Austin | Infrastructure: Replace Grease Trap - Kitchen | Deferred Maintenance Account No. 5166 | 148700 | 148700 | 2016-07-01 | 100% | 0% | 0 | 0 | 148700
40 | 05410010 | Polunsky Unit, Livingston | Security: Install High Mast Lighting - Offender Dorm Building & Perimeter Fence | Deferred Maintenance Account No. 5166 | 121200 | 121200 | 2016-04-01 | 100% | 0% | 0 | 0 | 121200
41 | 01312013 | Huntsville Unit, Huntsville | Roofing: Replace Roof - Security Operations Building | Deferred Maintenance Account No. 5166 | 156400 | 156400 | 2016-05-01 | 100% | 0% | 0 | 0 | 156400
42 | 00513004 | Clemens Unit, Brazoria | Roofing: Replace Roof - Main Building | Deferred Maintenance Account No. 5166 | 347200 | 347200 | 2016-12-01 | 100% | 0% | 0 | 0 | 347200
43 | 04710001 | Robertson Unit, Abilene | Roofing: Replace Roofs - Multiple Buildings | Deferred Maintenance Account No. 5166 | 7891200 | 8321800 | 2018-07-15 | 100% | 0% | 161320.89 | 12393.52 | 8148085.59 | Yes
44 | 02911013 | Luther Unit, Navasota | Infrastructure: Replace Ground Storage Tank - Water Plant | Deferred Maintenance Account No. 5166 | 626900 | 626900 | 2016-07-15 | 100% | 0% | 0 | 0 | 626900
45 | 01113002 | Ferguson Unit, Midway | Infrastructure: Refurbish Elevated Storage Tank - Water Plant | Deferred Maintenance Account No. 5166 | 337800 | 503500 | 2016-07-15 | 100% | 0% | 0 | 0 | 503500 | Yes
46 | 11106003 | Moore Unit, Bonham | Security: Replace Security Control System | Deferred Maintenance Account No. 5166 | 3304198 | 1940598 | 2017-04-01 | 100% | 0% | 59159.78 | 3750.97 | 1877687.25 | Yes
47 | 01608001 | Mt. View Unit, Gatesville | Infrastructure: Replace Ground Water Storage Tank & Add Boost Station | Deferred Maintenance Account No. 5166 | 4947317 | 4947317 | 2017-12-01 | 100% | 0% | 0 | 0 | 4947317
48 | 03708003 | Clements Unit, Amarillo | Safety: Repair/Replace Fire Line - Administrative Segregation | Deferred Maintenance Account No. 5166 | 420000 | 420000 | 2016-02-01 | 100% | 0% | 296408.51 | 0 | 123591.49
49 | 03608011 | Michael Unit, Tennessee Colony | Safety: Repair/Replace Fire Line - Administrative Segregation | Deferred Maintenance Account No. 5166 | 420000 | 420000 | 2016-02-01 | 100% | 0% | 0 | 0 | 420000
50 | 04911009 | Stiles Unit, Beaumont | Facility Repair: Replace Windows - Offender Housing | Deferred Maintenance Account No. 5166 | 107400 | 107400 | 2017-10-01 | 100% | 0% | 0 | 0 | 107400 | Yes
51 | 03612001 | Michael Unit, Tennessee Colony | Infrastructure: Replace Elevated Storage Tank & Storage Tank Well #4 | Deferred Maintenance Account No. 5166 | 4693942 | 4693942 | 2017-06-01 | 50% | 0% | 0 | 0 | 4693942
52 | 02210005 | Beto Unit, Tennessee Colony | Facility Repair: Replace Flooring - Main Kitchen & Scullery | Deferred Maintenance Account No. 5166 | 407000 | 407000 | 2017-04-01 | 50% | 0% | 0 | 0 | 407000
53 | 01915001 | Scott Unit, Angleton | Infrastructure: Replace Lift Station and Bar Screen - Waste Water Treatment Plant | Deferred Maintenance Account No. 5166 | 1881800 | 1881800 | 2017-09-01 | 45% | 0% | 0 | 0 | 1881800
54 | 02212005 | Beto Unit, Tennessee Colony | Safety: Install Standby Generator & Transfer Switch - Trusty Camp | Deferred Maintenance Account No. 5166 | 110100 | 110100 | 2017-01-01 | 14% | 0% | 0 | 0 | 110100
55 | 00512007 | Clemens Unit, Brazoria | Safety: Install Standby Generator - Trusty Camp | Deferred Maintenance Account No. 5166 | 109200 | 109200 | 2016-11-01 | 14% | 0% | 0 | 0 | 109200
56 | 01714002 | Ramsey Unit, Rosharon | Safety: Install Standby Generator - Trusty Camp | Deferred Maintenance Account No. 5166 | 106700 | 106700 | 2016-12-01 | 14% | 0% | 0 | 0 | 106700
57 | 02215011 | Beto Unit, Tennessee Colony | Facility Repair: Install Electrical to Cells - Infirmary | Deferred Maintenance Account No. 5166 | 19300 | 19300 | 2016-06-01 | 10% | 0% | 0 | 0 | 19300
58 | 01913008 | Scott Unit, Angleton | Facility Repair: Renovate 3 & 4 Pickets | Deferred Maintenance Account No. 5166 | 65700 | 65700 | 2016-07-01 | 10% | 0% | 0 | 0 | 65700
59 | 02212017 | Beto Unit, Tennessee Colony | Infrastructure: Replace Hot Water Lines - Main Building | Deferred Maintenance Account No. 5166 | 49600 | 49600 | 2016-12-01 | 10% | 0% | 0 | 0 | 49600
60 | 10814001 | Sanchez Unit, El Paso | Infrastructure: Renovate Elevated Water Storage Tank | Deferred Maintenance Account No. 5166 | 17700 | 17700 | 2016-05-01 | 10% | 0% | 0 | 0 | 17700
61 | 03913005 | Hobby Unit, Marlin | Roofing: Replace Roof - Kitchen/Commissary | Deferred Maintenance Account No. 5166 | 153100 | 153100 | 2016-08-01 | 10% | 0% | 0 | 0 | 153100 | Yes
62 | 02012008 | Wynne Unit, Huntsville | Facility Repair: Replace Flooring - Kitchen | Deferred Maintenance Account No. 5166 | 92900 | 92900 | 2016-10-01 | 10% | 0% | 0 | 0 | 92900 | Yes
63 | 02707005 | Terrell Unit, Rosharon | Infrastructure: Renovate Sewer Line from Food Service | Deferred Maintenance Account No. 5166 | 48700 | 48700 | 2016-12-01 | 10% | 0% | 0 | 0 | 48700
64 | 00609001 | Coffield Unit, Tennessee Colony | Facility Repair: Renovate Commissary Space | Deferred Maintenance Account No. 5166 | 55800 | 55800 | 2016-07-01 | 5% | 0% | 0 | 0 | 55800 | Yes
65 | 01713045 | Ramsey Unit, Rosharon | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 35100 | 35100 | 2016-04-15 | 5% | 0% | 0 | 0 | 35100 | Yes
66 | 03813007 | Daniel Unit, Snyder | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 162200 | 162200 | 2017-05-01 | 5% | 0% | 0 | 0 | 162200
67 | 04012003 | Lewis Unit, Woodville | Roofing: Replace Roof - Kitchen | Deferred Maintenance Account No. 5166 | 162200 | 162200 | 2016-12-01 | 1% | 0% | 0 | 0 | 162200
68 | 09199005 | Chasefield Unit, Beeville | Safety: Repair/Replace Fire Alarm - Multiple Buildings | Deferred Maintenance Account No. 5166 | 98900 | 98900 | 2016-11-01 | 1% | 0% | 0 | 0 | 98900
69 | 04813002 | McConnell Unit, Beeville | Safety: Replace Intercom System - Medical | Deferred Maintenance Account No. 5166 | 101300 | 101300 | 2016-07-01 | 0% | 0% | 0 | 0 | 101300
70 | 02615001 | Pack Unit, Navasota | Infrastructure: Replace Filtration System - Storage Tank | Deferred Maintenance Account No. 5166 | 1432383 | 1432383 | 2017-04-01 | 1% | 0% | 0 | 0 | 1432383
71 | 2813001 | Powledge Unit, Palestine | Infrastructure: DESIGN ONLY - Repair Washout - Outfall Line Waste Water Treatment Plant | Deferred Maintenance Account No. 5166 | 4200 | 4200 | 2016-07-01 | 10% | N/A | 0 | 0 | 4200
72 | 01313001 | Huntsville Unit, Huntsville | Roofing: DESIGN ONLY - Replace Roof/Repair Walls - Infirmary Building | Deferred Maintenance Account No. 5166 | 153600 | 153600 | 2016-10-15 | 1% | N/A | 0 | 0 | 153600
73 | 03312003 | Jester IV Unit, Richmond | Roofing: DESIGN ONLY - Replace Roof - Psychiatric Facility | Deferred Maintenance Account No. 5166 | 443700 | 443700 | 2017-12-01 | 1% | N/A | 0 | 0 | 443700
74 | 03613004 | Michael Unit, Tennessee Colony | Roofing: DESIGN ONLY - Replace Roof - Multiple Buildings | Deferred Maintenance Account No. 5166 | 858400 | 702300 | 2017-02-15 | 1% | N/A | 0 | 0 | 702300 | Yes
75 | 01914001 | Scott Unit, Angleton | Facility Repair: DESIGN ONLY - Replace Plumbing - Multiple Cell Blocks | Deferred Maintenance Account No. 5166 | 261000 | 261000 | 2016-06-01 | 1% | N/A | 0 | 0 | 261000
76 | 01913004 | Scott Unit, Angleton | Facility Repair: DESIGN ONLY - Kitchen Renovation | Deferred Maintenance Account No. 5166 | 530700 | 530700 | 2017-03-01 | 1% | N/A | 0 | 0 | 530700
77 | 02702010 | Terrell Unit, Rosharon | Facility Repair: Renovate Exhaust System - Vocational Shop | Deferred Maintenance Account No. 5166 | 164700 | 164700 | 2016-07-01 | 5% | 0% | 0 | 0 | 164700
78 | 01912007 | Scott Unit, Angleton | Security: DESIGN ONLY - Replace Locking System - Multiple Wings | Deferred Maintenance Account No. 5166 | 267800 | 267800 | 2016-12-01 | 1% | N/A | 0 | 0 | 267800
79 | 01313004 | Huntsville Unit, Huntsville | Facility Repair: DESIGN ONLY - Repair/Replace South Wall - Perimeter | Deferred Maintenance Account No. 5166 | 461600 | 461600 | 2016-10-15 | 1% | N/A | 0 | 0 | 461600
80 | 01205010 | Goree Unit, Huntsville | Facility Repair: Renovate Showers - Multiple Buildings | Deferred Maintenance Account No. 5166 | 126900 | 126900 | 2016-10-15 | 1% | 0% | 0 | 0 | 126900
81 | 01300042 | Huntsville Unit, Huntsville | Safety: DESIGN ONLY - Install Fire Alarm System | Deferred Maintenance Account No. 5166 | 521900 | 521900 | 2016-10-01 | 1% | N/A | 0 | 0 | 521900
82 | 04813003 | McConnell Unit, Beeville | Infrastructure: DESIGN ONLY - Replace Steam & Condensate Lines - Kitchen/Laundry Building | Deferred Maintenance Account No. 5166 | 164600 | 164600 | 2016-07-01 | 1% | 0% | 0 | 0 | 164600
83 | 12107001 | Lindsey Unit, Jacksboro | Infrastructure: DESIGN ONLY - Correct Drainage - Multiple Buildings | Deferred Maintenance Account No. 5166 | 6300 | 6300 | 2016-07-01 | 5% | 0% | 0 | 0 | 6300
84 | 10907002 | Lockhart Unit, Lockhart | Safety: Replace Fire Alarm - Multiple Buildings | Deferred Maintenance Account No. 5166 | 118700 | 118700 | 2016-05-01 | N/A | 0% | 0 | 0 | 118700
85 | 01000010 | Ellis Unit, Huntsville | Safety: DESIGN ONLY - Install Fire Alarm System - Unit Wide | Deferred Maintenance Account No. 5166 | 378000 | 378000 | 2016-10-01 | 1% | N/A | 0 | 0 | 378000
N/A | 10313003 | Lopez Unit, Edinburg | Facility Repair: Replace/Rebuild Walls and Doors - Kitchen | Deferred Maintenance Account No. 5166 | 103700 | 0 | 2017-03-01 | N/A | N/A | 0 | 0 |  | Yes
|  |  |  | Totals: | 56393900.62 | 57644001 |  |  |  | 20632936.67 | 423472.25 | 36587592.08

## TDCJ Notes 3.16
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2016-03-15
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Supplemental Information
1 | TIMELINE: (original estimated substantial completion date: 12/02/15; revised: 04/15/16). Project is scheduled for FY16 construction.
3 | TIMELINE: (original estimated substantial completion date: 01/18/16; revised: 07/26/16). Project is scheduled for FY16 construction.
4 | TIMELINE: (original estimated substantial completion date: 06/01/16; revised: 09/13/16). Project is scheduled for FY16/17 construction.
5 | TIMELINE: (original estimated substantial completion date: 04/15/16; revised: 05/12/16). Project is scheduled for FY16 construction.
6 | TIMELINE: (original estimated substantial completion date: 02/01/16; revised: 04/01/16). Project is scheduled for FY16 construction.
8 | TIMELINE: (original estimated substantial completion date: 01/21/16; revised: 06/12/16). Project is scheduled for FY16 construction.
9 | TIMELINE: (original estimated substantial completion date: 04/01/16; revised: 08/19/16). Project is scheduled for FY16 construction.
10 | TIMELINE: (original estimated substantial completion date: 03/01/16; revised: 08/07/16). Project is scheduled for FY16 construction.
11 | PRIORITIZATION: New project added with priority ranking of 11. BUDGET: Michael Unit: Emergency Generator - Lift Station.
12 | PRIORITIZATION: Project priority updated from 11 to 12.
13 | PRIORITIZATION: Project priority updated from 12 to 13. TIMELINE: (original estimated substantial completion date: 03/09/16; revised: 04/15/16). Project is scheduled for FY16 construction.
14 | PRIORITIZATION: Project priority updated from 13 to 14. TIMELINE: (original estimated substantial completion date: 01/27/16; revised: 06/03/16). Project is scheduled for FY16 construction.
15 | PRIORITIZATION: Project priority updated from 14 to 15. TIMELINE: (original estimated substantial completion date: 04/15/16; revised: 10/12/16). Project is scheduled for FY16/17 construction.
16 | PRIORITIZATION: Project priority updated from 15 to 16. BUDGET: Project Budget revised due to increase in construction estimate. TIMELINE: (original estimated substantial completion date: 03/01/16; revised: 07/11/16). Project is scheduled for FY16 construction.
17 | PRIORITIZATION: Project priority updated from 16 to 17.
18 | PRIORITIZATION: Project priority updated from 17 to 18.
19 | PRIORITIZATION: Project priority updated from 18 to 19.
20 | PRIORITIZATION: Project priority updated from 19 to 20.
21 | PRIORITIZATION: Project priority updated from 20 to 21.
22 | PRIORITIZATION: Project priority updated from 21 to 22.
23 | PRIORITIZATION: Project priority updated from 22 to 23.
24 | PRIORITIZATION: Project priority updated from 23 to 24.
25 | PRIORITIZATION: Project priority updated from 24 to 25.
26 | PRIORITIZATION: Project priority updated from 25 to 26.
27 | PRIORITIZATION: Project priority updated from 26 to 27.
28 | PRIORITIZATION: Project priority updated from 27 to 28.
29 | PRIORITIZATION: Project priority updated from 28 to 29.
30 | PRIORITIZATION: Project priority updated from 29 to 30.
31 | PRIORITIZATION: Project priority updated from 30 to 31.
32 | PRIORITIZATION: Project priority updated from 31 to 32.
33 | PRIORITIZATION: Project priority updated from 32 to 33.
34 | PRIORITIZATION: Project priority updated from 33 to 34.
35 | PRIORITIZATION: Project priority updated from 34 to 35.
36 | PRIORITIZATION: Project priority updated from 35 to 36. TIMELINE: (original estimated substantial completion date: 04/15/16; revised: 09/10/16). Project is scheduled for FY16/17 construction.
37 | PRIORITIZATION: Project priority updated from 36 to 37. BUDGET: Lowest qualified bidder was higher than initial estimate. TIMELINE: (original estimated substantial completion date: 03/15/16; revised: 08/15/16). Project is scheduled for FY16 construction.
38 | PRIORITIZATION: Project priority updated from 37 to 38. TIMELINE: (original estimated substantial completion date: 04/01/16; revised: 06/01/16). Project is scheduled for FY16 construction.
39 | PRIORITIZATION: Project priority updated from 38 to 39.
40 | PRIORITIZATION: Project priority updated from 39 to 40. BUDGET: Lowest qualified bidder was higher than initial estimate.
41 | PRIORITIZATION: Project priority updated from 40 to 41. BUDGET: Lowest qualified bidder was higher than initial estimate. TIMELINE: (original estimated substantial completion date: 04/01/16; revised: 10/01/16). Project is scheduled for FY16/17 construction.
42 | PRIORITIZATION: Project priority updated from 41 to 42. TIMELINE: (original estimated substantial completion date: 05/01/16; revised: 12/01/16). Project is scheduled for FY16/17 construction.
43 | PRIORITIZATION: Project priority updated from 42 to 43. BUDGET: Lowest qualified bidder was higher than initial estimate.
44 | PRIORITIZATION: Project priority updated from 43 to 44.
45 | PRIORITIZATION: Project priority updated from 44 to 45.
46 | PRIORITIZATION: Project priority updated from 45 to 46.
47 | PRIORITIZATION: Project priority updated from 46 to 47.
48 | TIMELINE: (original estimated substantial completion date: 02/01/16; revised: 07/15/17). Project is scheduled for FY16/17 construction.
49 | TIMELINE: (original estimated substantial completion date: 02/01/16; revised: 03/01/17). Project is scheduled for FY16/17 construction.
50 | TIMELINE: (original estimated substantial completion date: 10/01/17; revised: 12/01/16). Project is scheduled for FY16/17 construction.
51 | PRIORITIZATION: Project priority updated from 52 to 51.
52 | PRIORITIZATION: Project priority updated from 53 to 52.
53 | PRIORITIZATION: Project priority updated from 54 to 53.
54 | PRIORITIZATION: Project priority updated from 55 to 54.
55 | PRIORITIZATION: Project priority updated from 56 to 55.
56 | PRIORITIZATION: Project priority updated from 57 to 56. TIMELINE: (original estimated substantial completion date: 06/01/16; revised: 06/01/17). Project is scheduled for FY17 construction.
57 | PRIORITIZATION: Project priority updated from 58 to 57.
58 | PRIORITIZATION: Project priority updated from 59 to 58.
59 | PRIORITIZATION: Project priority updated from 60 to 59.
60 | PRIORITIZATION: Project priority updated from 61 to 60.
61 | PRIORITIZATION: Project priority updated from 62 to 61.
62 | PRIORITIZATION: Project priority updated from 63 to 62.
63 | PRIORITIZATION: Project priority updated from 64 to 63.
64 | PRIORITIZATION: Project priority updated from 65 to 64. TIMELINE: (original estimated substantial completion date: 04/15/16; revised: 09/05/16). Project is scheduled for FY16/17 construction.
65 | PRIORITIZATION: Project priority updated from 66 to 65.
66 | PRIORITIZATION: Project priority updated from 67 to 66.
67 | PRIORITIZATION: Project priority updated from 68 to 67.
68 | PRIORITIZATION: Project priority updated from 69 to 68. TIMELINE: (original estimated substantial completion date: 07/01/16; revised: 07/01/17). Project is scheduled for FY17 construction.
69 | PRIORITIZATION: Project priority updated from 70 to 69.
70 | PRIORITIZATION: Project priority updated from 71 to 70.
71 | PRIORITIZATION: Project priority updated from 72 to 71.
72 | PRIORITIZATION: Project priority updated from 73 to 72.
73 | PRIORITIZATION: Project priority updated from 74 to 73.
74 | PRIORITIZATION: Project priority updated from 75 to 74.
75 | PRIORITIZATION: Project priority updated from 76 to 75. TIMELINE: (original estimated substantial completion date: 03/01/17; revised: 12/01/17). Project is scheduled for FY16/17 design.
76 | PRIORITIZATION: Project priority updated from 77 to 76.
77 | PRIORITIZATION: Project priority updated from 78 to 77.
78 | PRIORITIZATION: Project priority updated from 79 to 78. TIMELINE: (original estimated substantial completion date: 10/15/16; revised: 02/15/17). Project is scheduled for FY16/17 design.
79 | PRIORITIZATION: Project priority updated from 80 to 79.
80 | PRIORITIZATION: Project priority updated from 81 to 80.
81 | PRIORITIZATION: Project priority updated from 82 to 81. TIMELINE: (original estimated substantial completion date: 07/01/16; revised: 10/01/17). Project is scheduled for FY16/17 design.
82 | PRIORITIZATION: Project priority updated from 83 to 82.
83 | PRIORITIZATION: Project priority updated from 84 to 83. STATUS: Project changed to design only.
84 | PRIORITIZATION: Project priority updated from 85 to 84.
85 | PRIORITIZATION: New project added with priority ranking of 85. BUDGET: Polunsky Unit: Repair/Replace Roofs - Multiple Buildings
86 | PRIORITIZATION: New project added with priority ranking of 86. BUDGET: Holliday Unit: Add Wheelchair Accessibility - Multiple Dorms
87 | PRIORITIZATION: New project added with priority ranking of 87. BUDGET: Robertson Unit: Replace Deaerator - Boiler Room
88 | PRIORITIZATION: New project added with priority ranking of 88. BUDGET: Coffield Unit: Replace Transformer - Massey Substation
89 | PRIORITIZATION: Project priority updated from 51 to 89. BUDGET: Design behind due to weather. Project budget reduced to design estimate. TIMELINE: (original estimated substantial construction completion date: 06/01/17; revised estimated substantial design completion date: 06/01/16). Project is scheduled for FY18/19 construction.
90 | PRIORITIZATION: Project priority updated from 47 to 90. BUDGET: Additional design for water storage added to original project scope. Project budget reduced to design estimate. TIMELINE: (original estimated substantial construction completion date: 12/01/17; revised estimated substantial design completion date: 06/01/16). Project is scheduled for FY18/19 construction.

## TDCJ Notes 12.15
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2015-12-15
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Supplemental Information
1 | BUDGET: Project to replace broken equipment / infrastructure - Hughes Unit: Replace HVAC Unit - Support Operations
2 | BUDGET: Project to replace broken equipment / infrastructure - Hutchins Unit: Refurbish Air Handler - Support Operations
3 | TIMELINE: (original estimated substantial completion date: 07/01/16; revised: 01/18/16). Construction in progress.
6 | BUDGET: Project to replace broken equipment / infrastructure - Ellis Unit: Replace Generator - Boiler Room
8 | BUDGET: Project to replace broken equipment / infrastructure - Sanchez Unit: Refurbish Lift Station - Front Administration Building
10 | BUDGET: Project to replace broken equipment / infrastructure - Telford Unit: Replace HVAC Unit - Infirmary
12 | BUDGET: Project to replace broken equipment / infrastructure - Telford Unit: Replace HVAC Unit - Officers' Dining Room
13 | BUDGET: Project to replace broken equipment / infrastructure - Sayle Unit: Replace Feed Water Tank - Boiler Room
14 | TIMELINE: (original estimated substantial completion date: 01/01/17; revised: 04/15/16). Project is scheduled for FY16 construction.
16 | TIMELINE: (original estimated substantial completion date: 06/01/17; revised: 08/08/16). Project is scheduled for FY16 construction.
17 | BUDGET: Project to replace broken equipment / infrastructure - Johnston Unit: Replace Steam Boiler - Boiler Room
18 | BUDGET: Project to replace broken equipment / infrastructure - Halbert Unit: Replace Refrigeration Equipment - Food Service
19 | BUDGET: Project to replace broken equipment / infrastructure - Beto Unit: Replace Hot Water Storage Tank - Boiler Room
20 | BUDGET: Project to replace broken equipment / infrastructure - Young Unit: Replace/Refurbish Cooling Tower - Central Plant
21 | BUDGET: Project to replace broken equipment / infrastructure - Lychner Unit: Replace HVAC Unit - Medical
22 | BUDGET: Project to replace broken equipment / infrastructure - Jester III Unit: Replace Heat Exchangers, Storage Tank & Condensate Pump - Heat Exchanger Room
23 | BUDGET: Project to replace broken equipment / infrastructure - Segovia Unit: Replace Water Softener - Multiple Dorms
24 | BUDGET: Project to replace broken equipment / infrastructure - Ware Unit: Replace HVAC Unit - Medical
25 | BUDGET: Project to replace broken equipment / infrastructure - Holliday Unit: Replace Air Handler & Heater - Offender Housing
26 | BUDGET: Project to replace broken equipment / infrastructure - Hutchins Unit: Replace Air Handler - Food Service
35 | TIMELINE: (original estimated substantial completion date: 02/01/17; revised: 04/15/16) Project is scheduled for FY16 construction.
38 | BUDGET: Lowest qualified bidder was lower than initial estimate.
43 | BUDGET: Lowest qualified bidder was higher than initial estimate.
45 | BUDGET: Lowest qualified bidder was higher than initial estimate.
46 | BUDGET: Lowest qualified bidder was lower than initial estimate.
50 | TIMELINE: (original estimated substantial completion date: 06/15/16; revised: 10/01/17). Project is scheduled for FY17 construction.
61 | TIMELINE: (original estimated substantial completion date: 05/01/17; revised: 08/01/16). Project is scheduled for FY16 design and construction.
62 | TIMELINE: (original estimated substantial completion date: 07/01/17; revised: 10/01/16). Project is scheduled for FY16 design and construction.
64 | TIMELINE: (original estimated substantial completion date: 05/01/17; revised: 07/01/16). Project is scheduled for FY16 design and construction.
65 | TIMELINE: (original estimated substantial completion date: 03/01/17; revised: 04/15/16). Project is scheduled for FY16 design and construction.
74 | BUDGET: Project Budget revised due to decrease in design estimate.
N/A | BUDGET - Project completed prior to receiving FY16 funding.

## TPWD 9.16
| Agency: | Texas Parks and Wildlife Department
| Date: | 2016-09-15 | [9 empty] | 2016-09-15
| Prepared by: | Infrastructure Division
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 127490 | Battleship Texas SHP - Structural Repairs 3523 Independence Parkway S LaPorte, Tx,77571 (Harris County) | Balance of work to repair internal structural elements, identified in an October 2012 scope of work, which is necessary to stabilize the ship . Repairs are critical if the ship remains in a wet berth and would be absolutely necessary if ship is ever placed into a dry berth. | 5166 - General Revenue Dedicated | 25000000 | 25000000 | 2018-04-30 | 100% | 0% | 1203535 | 551366.58 | 23245098.42
2 | 116818 | Fort Richardson SHS - Water and Wastewater System Replacement 228 State Park Road 61 Jacksboro, TX 76458 (Jack County) | Planning and design costs to replace the 50-year-old wastewater system, water distribution system and the main lift station with modernized and efficient systems capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 200000 | 216068 | 2018-01-31 | 5% | 0% | 99118.8 | 1239.95 | 115709.25
3 | 116151 | Seminole Canyon SHS - Camp Loop Upgrades US Hwy 90 W Comstock, TX 78837 (Val Verde County) | Planning and design costs to upgrade the Desert Vista Camp Loop's utilities, to include replacement and repairs to the On Site Sewage Facility System, water well, storage tank, pumps, and associated appurtenances, accessible restroom upgrades, and electrical service. | 5166 - General Revenue Dedicated | 1000000 | 375076 | 2019-03-31 | 5% | 0% | 201080.6 | 1685.47 | 172309.93
4 | 126472 | Goliad SHS - Wastewater System Upgrade 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Planning and design costs to replace obsolete clay wastewater lines and systems, lift station, septic tanks, and drain fields with a modernized, efficient system capable of servicing the entire site, which includes the Hacienda, Mission workshop, CCC Restroom, Old River Restroom, park headquarters, group dining hall, camp loop, and residence. | 5166 - General Revenue Dedicated | 225000 | 300214 | 2018-01-31 | 5% | 0% | 0 | 3271.38 | 296942.62
5 | 117535 | Copper Breaks SP - Water Distribution System Replacement 777 Park Road 62 Quanah,79252-7679 (Hardman County) | Planning and design costs to Replace a 50-year-old, leaking water distribution system and chlorination station with a modernized and efficient system capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 533000 | 295954 | 2019-03-31 | 5% | 0% | 148146.96 | 1063.24 | 146743.8
6 | 116471 | Balmorhea SP - CCC Motor Court Renovations, Utility Upgrades and Headquarters Replacement - Planning and Design 9207 H. 17S Toyahvale, TX (Reeves County) | Renovate 18 Civilian Conservation Corps (CCC) motel units at the San Solomon Springs Motel Court, to include repairing termite damaged woodwork; upgrade the water and wastewater utilities and campground electrical utility service from 30 amp to 50 amp; renovate camp loop restrooms. | 5166 - General Revenue Dedicated | 1200000 | 5690000 | 2019-03-31 | 10% | 0% | 3.4106e-13 | 27699.75 | 5662300.25
7 | 117494 | Pedernales Falls SP - Restroom Replacements 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Replace one public restroom complex. Scope of work also includes development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 2000000 | 1226426 | 2019-03-31 | 30% | 0% | 115329 | 9736.29 | 1101360.71
8 | 122865 | Huntsville SP - CCC Boathouse and Lodge Patio Wall Repairs 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Planning and design costs to renovate Civilian Conservation Corps (CCC) boathouse to include restoring the exterior hardwood siding, repairing the roof as well as interior and exterior structural damages, and repairing and stabilizing the Lodge's patio wall. | 5166 - General Revenue Dedicated | 500000 | 574698 | 2019-04-01 | 5% | 0% | 0 | 2611.34 | 572086.66
9 | 116921 | Palo Duro Canyon SP - Headquarters Replacement 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Planning and design costs for site headquarters replacement. Headquarters is currently operating out of an under-sized converted residence and the project would provide an adequately-sized and modern facility to better serve the increasing number of visitors. | 5166 - General Revenue Dedicated | 250000 | 250000 | 2018-01-31 | 5% | 0% | 5.6843e-14 | 15248.16 | 234751.84
10 | 117504 | Garner SP - Water System Upgrades US 83 N Concan, TX 78838 (Uvalde County) | Preliminary engineering costs to upgrade the park's overall water system, including treatment to reduce water hardness, and replace water distribution lines serving several park facilities in order to reduced system maintenance costs. | 5166 - General Revenue Dedicated | 400000 | 148895 | 2018-01-31 | 5% | 0% | 97683 | 2653.07 | 48558.93
11 | 117536 | Fairfield Lake SP - Wastewater Treatment Plant Repairs TX 2570 E Fairfield, TX 75840 (Freestone County) | Replace the mechanical systems at two existing wastewater treatment plants with modernized and efficient systems that are capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 650000 | 1376263 | 2019-03-31 | 10% | 0% | 174540 | 29220.48 | 1172502.52
12 | 117505 | Statewide - Unspecified State Park State Park Region 3 Restroom Replacement Program | Replace three public restroom complexes at Guadalupe State Park camping and day-use areas and one restroom complex at Government Canyon State Natural Area. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 4000000 | 4610057 | 2019-03-31 | 30% | 0% | 307729 | 27742.83 | 4274585.17
13 | 126496 | Tyler SP - Residence Replacements 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Replace two obsolete staff residences with two adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structures, to include utility connections, parking and associated paving. | 5166 - General Revenue Dedicated | 1000000 | 1000000 | 2019-03-31 | 5% | 0% | 52453 | 1868.37 | 945678.63
14 | 124729 | San Jacinto Battleground SHS - Residence Replacements 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Replace two residences and remove from a sensitive archaeological site. | 5166 - General Revenue Dedicated | 830000 | 830000 | 2019-03-31 | 5% | 0% | 52203 | 2255.66 | 775541.34
15 | 127483 | Lake Tawakoni SP - Residence Replacement 10822 FM 2475 Willis Point, TX 75169 (Hunt Van Zandt County) | Replace mobile home residence with an adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structure, to include utility connections, parking and associated paving. | 5166 - General Revenue Dedicated | 480000 | 480000 | 2019-03-31 | 5% | 0% | 34871 | 1774.17 | 443354.83
16 | 7358 | Mission Tejas SHS - Replace Visitor Center 120 State Park Rd. 4 Grapeland, TX 75844 (Houston County) | Replace visitor center that was destroyed by Hurricane Ike. New facility will include offices, assembly area, visitor check-in area, a new entry road and parking lot, utility extensions, and interpretive displays to educate visitors about the El Camino Real Trail. | 5166 - General Revenue Dedicated | 2713100 | 1815090 | 2018-08-31 | 100% | 0% | 1118519.94 | 47790.89 | 648779.17
17 | 117449 | Fort Leaton SHS - Roof Replacement FM 170 E Presidio, TX 79845 (Presidio County) | Replace leaking roof to preserve the historic structure and protect the building and contents from further water damage. | 5166 - General Revenue Dedicated | 413600 | 698591 | 2019-03-31 | 10% | 0% | 90103 | 3374.25 | 605113.75
18 | 117534 | Devil's River SP - Septic System Replacement 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Replace obsolete septic system to serve the lodge and bunkhouse facility at the Del Norte Unit. | 5166 - General Revenue Dedicated | 306800 | 306800 | 2019-03-31 | 5% | 0% | 1.1546e-14 | 1726.2 | 305073.8
19 | 122405 | Perry R Bass Marine Research Station - Hatchery Replacement HC 02, Box 385 FM 3280 Palacios TX 77465 (Matagorda County) | Planning and design costs for replacement of the under-sized and damaged ponds, hatchery buildings, infrastructure, and jetty pump intake. | 5166 - General Revenue Dedicated (SWFS) | 4131500 | 4131500 | 2018-01-31 | 5% | 0% | 0 | 3638.77 | 4127861.23
20 | 127436 | Galveston Island SP - Beachside Redevelopment 14901 FM 3005 Galveston, TX 77554 (Galveston County) | Design costs to redevelop Galveston Island State Park's beachside in accordance with the GISP Redevelopment Master Plan. Construction plans include one restroom, one RV dump station, one boardwalk, multiple tent platforms, 30 multiple use campsites with electrical / water service, three group shelters, and 20 day-use picnic shelters. | 5166 - General Revenue Dedicated | 350000 | 350000 | 2018-01-31 | 10% | 0% | 92594.47 | 7405.53 | 250000
21 | 122888 | Monument Hill/Kreische Brewery SHS - Kreische House and Brewery Renovations 414 State Loop 92 LaGrange, TX 78945 (Fayette County) | Renovate the interior and exterior of the historic Kreische House and Brewery to include water damage repairs and renovation of the cedar shake roof, structural elements, woodwork, floors, windows, stone work, finishes, historic furniture, and water diversion landscaping to protect the structures during flooding. | 5166 - General Revenue Dedicated | 1500000 | 2234003 | 2019-03-31 | 10% | 0% | 0 | 3077.22 | 2230925.78
22 | 125983 | Sea Center Texas - Pond Electrical System Improvements 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Upgrade obsolete electrical service systems at 36 ponds with modern and energy-efficient systems that will improve hatchery operations | 5166 - General Revenue Dedicated (SWFS) | 1027000 | 1027000 | 2019-03-31 | 60% | 0 | 39934.9 | 31847.82 | 955217.28
23 | 127758 | Sea Center Texas - Flounder Building 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Construct new 3000 square foot flounder spawning building. Building will provide additional hatchery floor space for flounder bloodstock and incubation equipment and include a separate room for culture of live feeds. | 5166 - General Revenue Dedicated (SWFS) | 968500 | 968500 | 2018-08-31 | 100% | 0 | 4949.8 | 0 | 963550.2
24 | 114228 | Colorado Bend SP - Water Treatment Plant Replacement 10 miles S of Bend on Gravel Rd Bend, TX 76824 (San Saba County) | Planning and design costs to replace the water treatment plant with a new system to include a storage tank and ground water well. | 5166 - General Revenue Dedicated | 150000 | 121095 | 2018-01-31 | 10% | 0% | 78095 | 1528.55 | 41471.45
25 | 124743 | Dickinson Marine Lab - New Boat Storage Facility 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | Install three metal boat storage buildings (4,960 square foot total) at the south, east and west sides of an existing paved storage area to secure the boats and protect from weather and vandalism. Storage buildings shall include power and lighting. | 5166 - General Revenue Dedicated (SWFS) | 507000 | 507000 | 2018-08-31 | 30% | 0 | 45169 | 2730.18 | 459100.82
26 | 117507 | Garner SP - Dining Halls and Barracks Remodel US 83 N Concan, TX 78838 (Uvalde County) | Planning and design costs to remodel Group Dining Hall at Shady Meadows and Cypress Springs camping areas to include electrical and HVAC system upgrades, kitchen remodels, insulation for walls and ceilings, window and door repairs or replacements, roof and fascia replacement and interior wall and ceiling finish-out. Remodel Cypress Springs Barracks to include new roofs, electrical upgrades, HVAC installation, door and window repairs and replacements, and interior finish upgrades. Renovations will enhance visitors' experiences and increase revenue. | 5166 - General Revenue Dedicated | 325000 | 325000 | 2018-01-31 | 5% | 0% | -1.1369e-13 | 14574.37 | 310425.63
27 | 114243 | Pedernales Falls SP - Water and Wastewater System Upgrades 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Preliminary engineering and design costs to upgrade the obsolete water treatment plant to include four septic fields, drain fields and the water filtration system, in order to save water resources and provide an adequate system capable of saving water resources while better serving park visitors. | 5166 - General Revenue Dedicated | 106000 | 901872 | 2018-01-31 | 10% | 0% | 99031 | 3452.87 | 799388.13
28 | 127260 | Ray Roberts Lake SP - Johnson Branch Unit Compost Toilet Replacements 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Replace seven obsolete compost toilets with modular vault toilets to serve several trail and camping areas and revise any pathways for ADA compliance. | 5166 - General Revenue Dedicated | 834600 | 642000 | 2019-03-31 | 10% | 0% | 0 | 0 | 642000
29 | 127438 | Lake Livingston SP - Marina Area and Fishing Pier Accessibility Upgrades and Repairs 300 State Park Road 65 Livingston, TX 77351 (Polk County) | Planning and design costs to renovate the Marina Area and Fishing Pier to include: repairs to restrooms, courtesy dock, fueling stations, electrical and lighting systems, and the accessible routes between facilities and parking due to soil subsidence. | 5166 - General Revenue Dedicated | 390000 | 266165 | 2018-01-31 | 10% | 0% | 156281.36 | 4201.58 | 105682.06
30 | 114238 | Inks Lake SP - Headquarters Building Replacement - Planning and Design 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Advance planning costs to replace the under-sized headquarters building with one which includes an adequately-sized lobby and registration area and office, as well as additional restrooms, to meet staff and visitor needs. Improve traffic flow around the headquarters site. | 5166 - General Revenue Dedicated | 587500 | 250000 | 2018-01-31 | 5% | 0% | 80580 | 6207.33 | 163212.67
31 | 117359 | McKinney Falls SP - Smith Visitor Center Facility and Exhibit Renovation 5808 McKinney Falls Austin, TX 78744 (Travis County) | Renovate the Smith Visitor Center including upgrading a learning center to serve as an interactive classroom with new interpretive exhibits to educate students and park visitors about the El Camino Real Trail. | 5166 - General Revenue Dedicated | 859800 | 271598 | 2018-08-31 | 100% | 0% | 51491.36 | 15748.77 | 204357.87
32 | 116769 | Bastrop SP - Dam Replacement 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Planning and design costs to replace the breached dam due to the 2015 memorial day flooding. | 5166 - General Revenue Dedicated | 1000000 | 1000000 | 2018-01-31 | 10% | 0% | 57528.7 | 130725.39 | 811745.91
32A | 118102 | Bastrop SP - Shore Stabilization 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Stabilization of shoreline adjacent to Cabins #1 and #12. | 5166 - General Revenue Dedicated | 0 | 1140000 | 2018-01-31 | 100% | 5% | 33102.59 | 139460.75 | 967436.66
33 | 127360 | Goliad SHS - Custodian's Cottage Renovation and Adaptive Reuse to Interpretive Facility 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Renovate the CCC Custodian's Cottage to convert its use from administrative offices to an adequately-sized interpretive facility which will educate visitors about the El Camino Real Trail. Renovations will include restoration of formal gardens and a new parking lot. | 5166 - General Revenue Dedicated | 978400 | 1941710 | 2018-08-31 | 100% | 0% | 722072.24 | 80282.62 | 1139355.14
34 | 126719 | Mustang Island SP - Campground and Day-Use Area Restroom Replacements 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Replace one restroom complex and renovate the day-use restroom with facilities to include replacement of obsolete mechanical systems and damaged structures. Renovations will include shower and restroom accommodations, accessible parking routes, utility upgrades and connections, a new lift station and force main, a temporary shower and restroom facility, and associated site work, in order to meet current and projected visitor demand. | 5166 - General Revenue Dedicated | 2444000 | 1929716 | 2019-03-31 | 10% | 0% | 157748 | 10857.61 | 1761110.39
35 | 126912 | Caddo Lake SP - Water System Upgrade 245 Park Rd 2 Karnack, TX (Harrison county) | Planning and design costs to upgrade domestic water source to treat for excessive amounts of iron in the water and prevent further damage to plumbing fixtures throughout the park. Repairs include new storage tanks, pump systems, gas chlorination system, iron removal filter, refurbished hydro pneumatic tank, electrical improvements, and a pump house. | 5166 - General Revenue Dedicated | 250000 | 250000 | 2018-01-31 | 0% | 0% | 0 | 2547.74 | 247452.26
36 | 117106 | Indian Lodge - Exterior Plaster and HVAC Replacement TX Hwy 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Renovate the historic facility to include exterior plaster repairs and replace obsolete HVAC units with energy-efficient systems. | 5166 - General Revenue Dedicated | 598000 | 1399500 | 2019-03-31 | 10% | 0% | 152460.6 | 3266.72 | 1243772.68
37 | NA | Statewide - Unspecified State Park Boat Ramp Repairs - Statewide | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 1300000 | 0 | 2019-03-31 | 10% | 0% | 0 | 0 | 0
37A | 115356 | Choke Canyon State Park (South Shore Unit) - Boat Ramp 358 Recreation Rd 8 Calliham, TX 78007 (Live Oak County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 290082 | 2019-03-31 | 10% | 0% | 72592 | 741.42 | 216748.58
37B | 115389 | Fort Parker State Park - Boat Ramp 194 Park Rd 28 Mexia, Tx 76667 (Limestone County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 557214 | 2019-03-31 | 10% | 0% | 115190 | 4321.76 | 437702.24
37C | 116036 | Inks Lake State Park - Boat Ramp 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 314175 | 2019-03-31 | 10% | 0% | 92096 | 365.57 | 221713.43
37D | 117036 | Ray Roberts Lake SP - Isle du Bois Unit - Boat Ramp 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 124330 | 2019-03-31 | 10% | 0% | 33118 | 37.09 | 91174.91
38 | 117503 | Inks Lake SP - Multiple Restroom Replacements 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Replace four public restroom complexes. Scope of work also includes development of utilities and parking. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 4000000 | 3933000 | 2019-03-31 | 60% | 0% | 230079.43 | 45921.11 | 3656999.46
39 | 117495 | Albert and Bessie Kronkosky SNA - Public Use Development - Planning and Design 7690 Hwy 46 West Pipe Creek, TX 78063 (Bandera County) | Advance planning costs to develop newly acquired site and install infrastructure, including utilities, parking, roadways, restrooms, toilets, and a fee collection booth at headquarters. Site development would allow public access and would meet public use needs as required by the land use agreement, which would generate revenue and provide significant outdoor opportunities. | 5166 - General Revenue Dedicated | 588000 | 250000 | 2018-01-31 | 10% | 0% | 29642.32 | 40777.55 | 179580.13
40 | 127510 | Stephen F Austin SHS - Wastewater Treatment Plant Equalization Basin Installation 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | (Project on hold due to floods) Install equalization basin at wastewater treatment plant in order to provide adequate pace flow into the plant during peak usage. | 5166 - General Revenue Dedicated | 240400 | 0 | 2018-01-31 | 10% | 0% | 50678.05 | 3958.07 | -54636.12
41 | 122081 | CCA Marine Development Center - Fish America Spawning Building and Ozone Water Purification System Replacement 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | Replace the under-sized, 30-year-old, Fish America spawning building with a new 4,000 square foot spawning building at the same location that will withstand the coastal elements. Building will include staff offices and research space and a new ozone water purification system to replace the existing non-functioning ozone system. | 5166 - General Revenue Dedicated (SWFS) | 1710000 | 1710000 | 2018-01-31 | 10% | 0% | 194863.91 | 2968.09 | 1512168
42 | 115922 | Abilene SP - Swimming Pool and CCC Bathhouse Repairs FM 89, 150 Park Rd 32 Tuscola, TX 79562 (Taylor County) | (Project Postponed) Planning and design costs to repair and renovate the swimming pool and CCC bathhouse. | 5166 - General Revenue Dedicated | 850000 | 0 | 2018-01-31 | 0% | 0% | 0 | 250.39 | -250.39
43 | 114144 | Austin Headquarters Complex - HVAC Control System Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | Replace the existing climate control system at Austin Headquarters Complex with an updated HVAC Management System which is supported by current industry vendors and allows for remote adjustments by the energy performance contractor. | 5166 - General Revenue Dedicated | 478800 | 631120 | 2018-08-31 | 30% | 0% | 35070 | 3266.25 | 592783.75
44 | 114906 | Austin Headquarters Complex - Heating Ventilation Air-Conditioning (HVAC) Units Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | (Project Cancelled) Replace two deteriorating, independent Liebert HVAC units in the Computer Room that houses the server at the TPWD Austin Headquarters Complex. | 5166 - General Revenue Dedicated | 144348 | 0 | 2018-08-31 | 0% | 0% | 0 | 0 | 0
45 | 117417 | Austin Headquarters Complex - Fire Escape and Storage Building 4200 Smith School Road Austin, TX 78744 (Travis County) | Construct a Building D exterior stairway and fire escape as a secondary egress for safety purposes. Build a storage building on Building D rooftop to store tools, equipment, and materials used to service the rooftop equipment. | 5166 - General Revenue Dedicated | 73152 | 65180 | 2019-03-31 | 60% | 0% | 1222 | 3117.17 | 60840.83
46 | TBD | Statewide - Unspecified State Park2015 Flood Damage Repairs | Funding held to address statewide 2015 flood damages. A comprehensive damage assessment has not yet been completed due to high-water levels and site inaccessibility. | 5166 - General Revenue Dedicated | 8058550 | 3942070 | 2018-01-31 | 5% | 0% | 357944.96 | 26508.19 | 3557616.85
47 | 128233 | Stephen F Austin SHS - Water Tank Repairs 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | (Project on hold due to floods) Pressure wash and repaint elevated water tank per TCEQ regulations. | 5166 - General Revenue Dedicated | 300000 | 728067 | 2018-08-31 | 10% | 0% | 41620 | 0 | 686447
48 | 124545 | Huntsville SP - Dam Repair 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Fortify and repair the earthen embankment and spillway. | 5166 - General Revenue Dedicated | 4380000 | 4389000 | 2017-05-30 | 100% | 20% | 3702995.3 | 685869.15 | 135.55
49 | 132907 | Bastrop SP - Group Barracks Complex Renovation 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Renovate the Group Barracks Complex, which includes four dormitory buildings and one group dinning hall. The existing obsolete restroom will be demolished; restroom/shower facilities will be added to each dormitory facility. The renovations include updating of all mechanicals, plumbing, electrical, and site modifications to become code compliant and improve visitor experience. | 5166 - General Revenue Dedicated | 3558000 | 3558000 | 2018-03-31 | 100% | 0% | 7792 | 47715.71 | 3502492.29
50 | 125986 | Port Isabel Lighthouse - Light house repairs; replace corroded metal 421 East Queen Isabella Blvd Port Isabel, TX 78578 (Cameron County) | Repair and/or replace corroded exterior metal components on the Port Isabel Lighthouse at the Watch room and Lantern Levels and repaint lighthouse exterior. | 5166 - General Revenue Dedicated | 279950 | 425962 | 2017-03-31 | 100% | 0% | -1.7764e-14 | 7468.81 | 418493.19
51 | 137824 | Longhorn Caverns - Communications System and Surge Protection 6211 Park Rd 4 So. Burnet, TX 78611 (Burnet County) | Install communication system for the cavern to protect the public in the event of an emergency. | 5166 - General Revenue Dedicated | 170000 | 170000 | 2018-08-31 | 95% | 0% | 19100 | 0 | 150900
52 | 134232 | Hill Country SNA - Replace Well at Group Lodge 10600 Bandera Creed Rd Bandera, TX 78003 (Bandera County) | Install water system at group lodge to provide potable water to guests. | 5166 - General Revenue Dedicated | 365000 | 365000 | 2017-08-31 | 100% | 0% | 0 | 3572.47 | 361427.53
53 | 134239 | Lost Maples SNA - Replace Potable Water Storage Tank 37221 FM 187 Vanderpool, TX 78885 (Bandera County) | Replace deteriorating drinking water storage tank with a new system in order to address a high iron content in the facility's water supply and meet TCEQ regulations. | 5166 - General Revenue Dedicated | 485000 | 485000 | 2017-08-01 | 100% | 0% | 0 | 6910.21 | 478089.79
54 | 137394 | McKinney Falls SP - Smith Visitor's Center Flood Damage Repairs 5808 McKinney Falls Austin, TX 78744 (Travis County) | Repair all interior finishes, associated mechanical, electrical, and plumbing systems damaged by flood waters. Reconstruct the interior restroom to meet TDLR standards. | 5166 - General Revenue Dedicated | 570000 | 983770.69 | 2017-05-31 | 100% | 0% | 2876.64 | 33830.57 | 947063.48
55 | 136423 | Davis Mountains SP - Communications Bldg. Repairs TX HWY 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Replace fire damaged radio house with a permanent facility to maintain park radio communications within the park and region. | 5166 - General Revenue Dedicated | 317000 | 417000 | 2019-03-31 | 30% | 0% | 0 | 0 | 417000
56 | 112741 | Tyler SP - Headquarters Replacement 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Planning and design cost for replacing the headquarters facility with new, adequately-sized ADA-compliant building, road, parking lot, and entrance. | 5166 - General Revenue Dedicated | 3000000 | 1061124 | 2019-03-31 | 5% | 0% | 0 | 1520.57 | 1059603.43
57 | 127872 | Mustang Island SP - Foundation repairs for (2) residences 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Repair two residences' pilings and beams, which are degraded due to rot. | 5166 - General Revenue Dedicated | 225000 | 147114 | 2018-08-31 | 5% | 0% | 0 | 1495.53 | 145618.47
58 | TBD | Mother Neff SP - CCC Rock Tabernacle Repairs and Stabilization 1680 TX 236 HWY Moody, TX 76557 (Coryell County) | (Project Postponed) - Stabilization of 4000 sq. ft. CCC built tabernacle. Work includes structural, wood, and masonry repairs, reroofing, and site construction. | 5166 - General Revenue Dedicated | 350000 | 0 | 2018-08-31 | 100% | 0% | 0 | 0 | 0
59 | TBD | Devil's River SP - New Visitor Check-in Building and Remodel of Existing Lodge. 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Planning and design costs to develop the newly acquired south unit. The development plan includes a small site headquarters building for visitor check-in and the remodeling of the existing lodge to include staff offices and interpretive space. The development plan is still pending TNC approval. | 5166 - General Revenue Dedicated | 150000 | 150000 | 2018-01-31 | 5% | 0% | 0 | 0 | 150000
60 | 126107 | San Jacinto Battleground SHS - Reflection Pool Structural Assessment 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Professional engineering report and assessment for stabilizing and repairing the retaining walls around the reflecting pool. | 5166 - General Revenue Dedicated | 100000 | 100000 | 2018-01-31 | 5% | 0% | 0 | 2662.24 | 97337.76
61 | 124932 | Sea Center Texas - Fence Replacement 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Replace three miles of perimeter fencing in and around the facility with high game fence and an entry fence in order to protect the hatchery from wildlife intrusion. | 5166 - General Revenue Dedicated (SWFS) | 598000 | 598000 | 2019-03-31 | 30% | 0% | 6273 | 3428.91 | 588298.09
62 | 192540 | Buescher State Park - Erosion mitigation and habitat stabilization (Flood Repair) 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Stabilize the soil and mitigate erosion caused by flooding. | 5166 - General Revenue Dedicated | 0 | 754000 | 2017-05-31 | 0% | 95% | 164673.6 | 249929.83 | 339396.57
|  |  |  | Totals: | 91000000 | 90999999.69 |  |  |  | 10624178.53 | 2370518.56 | 78005302.6

## TPWD 6.16
| Agency: | Texas Parks and Wildlife Department
| Date: | 2016-06-15 | [9 empty] | 2016-06-15
| Prepared by: | Infrastructure Division
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 127490 | Battleship Texas SHP - Structural Repairs 3523 Independence Parkway S LaPorte, Tx,77571 (Harris County) | Balance of work to repair internal structural elements, identified in an October 2012 scope of work, which is necessary to stabilize the ship . Repairs are critical if the ship remains in a wet berth and would be absolutely necessary if ship is ever placed into a dry berth. | 5166 - General Revenue Dedicated | 25000000 | 25000000 | 2018-04-30 | 95% | 0% | 1316078.8 | 392103.56 | 23291817.64
2 | 116818 | Fort Richardson SHS - Water and Wastewater System Replacement 228 State Park Road 61 Jacksboro, TX 76458 (Jack County) | Planning and design costs to replace the 50-year-old wastewater system, water distribution system and the main lift station with modernized and efficient systems capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 200000 | 216068 | 2018-01-31 | 5% | 0% | 0 | 201.42 | 215866.58
3 | 116151 | Seminole Canyon SHS - Camp Loop Upgrades US Hwy 90 W Comstock, TX 78837 (Val Verde County) | Planning and design costs to upgrade the Desert Vista Camp Loop's utilities, to include replacement and repairs to the On Site Sewage Facility System, water well, storage tank, pumps, and associated appurtenances, accessible restroom upgrades, and electrical service. | 5166 - General Revenue Dedicated | 1000000 | 375076 | 2019-03-31 | 5% | 0% | 0 | 299.39 | 374776.61 | *
4 | 126472 | Goliad SHS - Wastewater System Upgrade 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Planning and design costs to replace obsolete clay wastewater lines and systems, lift station, septic tanks, and drain fields with a modernized, efficient system capable of servicing the entire site, which includes the Hacienda, Mission workshop, CCC Restroom, Old River Restroom, park headquarters, group dining hall, camp loop, and residence. | 5166 - General Revenue Dedicated | 225000 | 300214 | 2018-01-31 | 5% | 0% | 0 | 2830.43 | 297383.57
5 | 117535 | Copper Breaks SP - Water Distribution System Replacement 777 Park Road 62 Quanah,79252-7679 (Hardman County) | Planning and design costs to Replace a 50-year-old, leaking water distribution system and chlorination station with a modernized and efficient system capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 533000 | 295954 | 2019-03-31 | 5% | 0% | 0 | 327.13 | 295626.87 | *
6 | 116471 | Balmorhea SP - CCC Motor Court Renovations, Utility Upgrades and Headquarters Replacement - Planning and Design 9207 H. 17S Toyahvale, TX (Reeves County) | Renovate 18 Civilian Conservation Corps (CCC) motel units at the San Solomon Springs Motel Court, to include repairing termite damaged woodwork; upgrade the water and wastewater utilities and campground electrical utility service from 30 amp to 50 amp; renovate camp loop restrooms. | 5166 - General Revenue Dedicated | 1200000 | 5690000 | 2019-03-31 | 5% | 0% | 0 | 835.45 | 5689164.55 | *
7 | 117494 | Pedernales Falls SP - Restroom Replacements 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Replace one public restroom complex. Scope of work also includes development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 2000000 | 1226426 | 2019-03-31 | 5% | 0% | 0 | 5587.68 | 1220838.32 | *
8 | 122865 | Huntsville SP - CCC Boathouse and Lodge Patio Wall Repairs 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Planning and design costs to renovate Civilian Conservation Corps (CCC) boathouse to include restoring the exterior hardwood siding, repairing the roof as well as interior and exterior structural damages, and repairing and stabilizing the Lodge's patio wall. | 5166 - General Revenue Dedicated | 500000 | 574698 | 2019-04-01 | 5% | 0% | 0 | 1102.67 | 573595.33 | *
9 | 116921 | Palo Duro Canyon SP - Headquarters Replacement 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Planning and design costs for site headquarters replacement. Headquarters is currently operating out of an under-sized converted residence and the project would provide an adequately-sized and modern facility to better serve the increasing number of visitors. | 5166 - General Revenue Dedicated | 250000 | 250000 | 2018-01-31 | 0% | 0% | 0 | 13708.43 | 236291.57
10 | 117504 | Garner SP - Water System Upgrades US 83 N Concan, TX 78838 (Uvalde County) | Preliminary engineering costs to upgrade the park's overall water system, including treatment to reduce water hardness, and replace water distribution lines serving several park facilities in order to reduced system maintenance costs. | 5166 - General Revenue Dedicated | 400000 | 148895 | 2018-01-31 | 5% | 0% | 0 | 2211.06 | 146683.94 | *
11 | 117536 | Fairfield Lake SP - Wastewater Treatment Plant Repairs TX 2570 E Fairfield, TX 75840 (Freestone County) | Replace the mechanical systems at two existing wastewater treatment plants with modernized and efficient systems that are capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 650000 | 1376263 | 2019-03-31 | 5% | 0% | 0 | 4074.64 | 1372188.36
12 | 7505 | Statewide - Unspecified State Park State Park Region 3 Restroom Replacement Program | Replace three public restroom complexes at Guadalupe State Park camping and day-use areas and one restroom complex at Government Canyon State Natural Area. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 4000000 | 4610057 | 2019-03-31 | 5% | 0% | 0 | 9725.78 | 4600331.22
13 | 126496 | Tyler SP - Residence Replacements 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Replace two obsolete staff residences with two adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structures, to include utility connections, parking and associated paving. | 5166 - General Revenue Dedicated | 1000000 | 1000000 | 2019-03-31 | 0% | 0% | 0 | 725.7 | 999274.3
14 | 124729 | San Jacinto Battleground SHS - Residence Replacements 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Replace two residences and remove from a sensitive archaeological site. | 5166 - General Revenue Dedicated | 830000 | 830000 | 2019-03-31 | 0% | 0% | 0 | 1196.48 | 828803.52
15 | 127483 | Lake Tawakoni SP - Residence Replacement 10822 FM 2475 Willis Point, TX 75169 (Hunt Van Zandt County) | Replace mobile home residence with an adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structure, to include utility connections, parking and associated paving. | 5166 - General Revenue Dedicated | 480000 | 480000 | 2019-03-31 | 0% | 0% | 0 | 956.36 | 479043.64
16 | 7358 | Mission Tejas SHS - Replace Visitor Center 120 State Park Rd. 4 Grapeland, TX 75844 (Houston County) | Replace visitor center that was destroyed by Hurricane Ike. New facility will include offices, assembly area, visitor check-in area, a new entry road and parking lot, utility extensions, and interpretive displays to educate visitors about the El Camino Real Trail. | 5166 - General Revenue Dedicated | 2713100 | 1815090 | 2018-08-31 | 100% | 0% | 226868.5935 | 41241.4335 | 1546979.973
17 | 117449 | Fort Leaton SHS - Roof Replacement FM 170 E Presidio, TX 79845 (Presidio County) | Replace leaking roof to preserve the historic structure and protect the building and contents from further water damage. | 5166 - General Revenue Dedicated | 413600 | 698591 | 2019-03-31 | 5% | 0% | 0 | 1392.34 | 697198.66
18 | 117534 | Devil's River SP - Septic System Replacement 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Replace obsolete septic system to serve the lodge and bunkhouse facility at the Del Norte Unit. | 5166 - General Revenue Dedicated | 306800 | 306800 | 2019-03-31 | 0% | 0% | 0 | 0 | 306800
19 | 122405 | Perry R Bass Marine Research Station - Hatchery Replacement HC 02, Box 385 FM 3280 Palacios TX 77465 (Matagorda County) | Planning and design costs for replacement of the under-sized and damaged ponds, hatchery buildings, infrastructure, and jetty pump intake. | 5166 - General Revenue Dedicated (SWFS) | 4131500 | 4131500 | 2018-01-31 | 5% | 0% | 0 | 1723.2 | 4129776.8
20 | 127436 | Galveston Island SP - Beachside Redevelopment 14901 FM 3005 Galveston, TX 77554 (Galveston County) | Design costs to redevelop Galveston Island State Park's beachside in accordance with the GISP Redevelopment Master Plan. Construction plans include one restroom, one RV dump station, one boardwalk, multiple tent platforms, 30 multiple use campsites with electrical / water service, three group shelters, and 20 day-use picnic shelters. | 5166 - General Revenue Dedicated | 350000 | 350000 | 2018-01-31 | 10% | 0% | 100000 | 0 | 250000
21 | 122888 | Monument Hill/Kreische Brewery SHS - Kreische House and Brewery Renovations 414 State Loop 92 LaGrange, TX 78945 (Fayette County) | Renovate the interior and exterior of the historic Kreische House and Brewery to include water damage repairs and renovation of the cedar shake roof, structural elements, woodwork, floors, windows, stone work, finishes, historic furniture, and water diversion landscaping to protect the structures during flooding. | 5166 - General Revenue Dedicated | 1500000 | 2234003 | 2019-03-31 | 5% | 0% | 0 | 1488.73 | 2232514.27
22 | 125983 | Sea Center Texas - Pond Electrical System Improvements 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Upgrade obsolete electrical service systems at 36 ponds with modern and energy-efficient systems that will improve hatchery operations | 5166 - General Revenue Dedicated (SWFS) | 1027000 | 1027000 | 2019-03-31 | 5% | 0% | 58655 | 5236.97 | 963108.03
23 | 127758 | Sea Center Texas - Flounder Building 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Construct new 3000 square foot flounder spawning building. Building will provide additional hatchery floor space for flounder bloodstock and incubation equipment and include a separate room for culture of live feeds. | 5166 - General Revenue Dedicated (SWFS) | 968500 | 968500 | 2018-08-31 | 95% | 0% | 0 | 0 | 968500 | *
24 | 114228 | Colorado Bend SP - Water Treatment Plant Replacement 10 miles S of Bend on Gravel Rd Bend, TX 76824 (San Saba County) | Planning and design costs to replace the water treatment plant with a new system to include a storage tank and ground water well. | 5166 - General Revenue Dedicated | 150000 | 121095 | 2018-01-31 | 5% | 0% | 0 | 595.33 | 120499.67
25 | 124743 | Dickinson Marine Lab - New Boat Storage Facility 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | Install three metal boat storage buildings (4,960 square foot total) at the south, east and west sides of an existing paved storage area to secure the boats and protect from weather and vandalism. Storage buildings shall include power and lighting. | 5166 - General Revenue Dedicated (SWFS) | 507000 | 507000 | 2018-08-31 | 5% | 0% | 0 | 524.19 | 506475.81 | *
26 | 117507 | Garner SP - Dining Halls and Barracks Remodel US 83 N Concan, TX 78838 (Uvalde County) | Planning and design costs to remodel Group Dining Hall at Shady Meadows and Cypress Springs camping areas to include electrical and HVAC system upgrades, kitchen remodels, insulation for walls and ceilings, window and door repairs or replacements, roof and fascia replacement and interior wall and ceiling finish-out. Remodel Cypress Springs Barracks to include new roofs, electrical upgrades, HVAC installation, door and window repairs and replacements, and interior finish upgrades. Renovations will enhance visitors' experiences and increase revenue. | 5166 - General Revenue Dedicated | 325000 | 325000 | 2018-01-31 | 5% | 0% | 0 | 12897.3 | 312102.7
27 | 114243 | Pedernales Falls SP - Water and Wastewater System Upgrades 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Preliminary engineering and design costs to upgrade the obsolete water treatment plant to include four septic fields, drain fields and the water filtration system, in order to save water resources and provide an adequate system capable of saving water resources while better serving park visitors. | 5166 - General Revenue Dedicated | 106000 | 901872 | 2018-01-31 | 5% | 0% | 0 | 2461.35 | 899410.65 | *
28 | 127260 | Ray Roberts Lake SP - Johnson Branch Unit Compost Toilet Replacements 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Replace seven obsolete compost toilets with modular vault toilets to serve several trail and camping areas and revise any pathways for ADA compliance. | 5166 - General Revenue Dedicated | 834600 | 642000 | 2019-03-31 | 5% | 0% | 0 | 3658.2 | 638341.8
29 | 127438 | Lake Livingston SP - Marina Area and Fishing Pier Accessibility Upgrades and Repairs 300 State Park Road 65 Livingston, TX 77351 (Polk County) | Planning and design costs to renovate the Marina Area and Fishing Pier to include: repairs to restrooms, courtesy dock, fueling stations, electrical and lighting systems, and the accessible routes between facilities and parking due to soil subsidence. | 5166 - General Revenue Dedicated | 390000 | 266165 | 2018-01-31 | 5% | 0% | 0 | 2339.38 | 263825.62
30 | 114238 | Inks Lake SP - Headquarters Building Replacement - Planning and Design 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Advance planning costs to replace the under-sized headquarters building with one which includes an adequately-sized lobby and registration area and office, as well as additional restrooms, to meet staff and visitor needs. Improve traffic flow around the headquarters site. | 5166 - General Revenue Dedicated | 587500 | 250000 | 2018-01-31 | 5% | 0% | 0 | 3175.34 | 246824.66 | *
31 | 117359 | McKinney Falls SP - Smith Visitor Center Facility and Exhibit Renovation 5808 McKinney Falls Austin, TX 78744 (Travis County) | Renovate the Smith Visitor Center including upgrading a learning center to serve as an interactive classroom with new interpretive exhibits to educate students and park visitors about the El Camino Real Trail. | 5166 - General Revenue Dedicated | 859800 | 271598 | 2018-08-31 | 100% | 0% | 35290.6701 | 6415.3341 | 229891.9958
32 | 116769 | Bastrop SP - Dam Replacement 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Planning and design costs to replace the breached dam due to the 2015 memorial day flooding. | 5166 - General Revenue Dedicated | 1000000 | 1000000 | 2018-01-31 | 10% | 0% | 62431.15 | 125765.49 | 811803.36 | *
32A | 118102 | Bastrop SP - Shore Stabilization 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Stabilization of shoreline adjacent to Cabins #1 and #12. | 5166 - General Revenue Dedicated | 0 | 1140000 | 2018-01-31 | 100% | 5% | 114630.89 | 52638.25 | 972730.86 | *
33 | 127360 | Goliad SHS - Custodian's Cottage Renovation and Adaptive Reuse to Interpretive Facility 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Renovate the CCC Custodian's Cottage to convert its use from administrative offices to an adequately-sized interpretive facility which will educate visitors about the El Camino Real Trail. Renovations will include restoration of formal gardens and a new parking lot. | 5166 - General Revenue Dedicated | 978400 | 1941710 | 2018-08-31 | 100% | 0% | 241993.1664 | 43990.8624 | 1655725.9712
34 | 126719 | Mustang Island SP - Campground and Day-Use Area Restroom Replacements 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Replace one restroom complex and renovate the day-use restroom with facilities to include replacement of obsolete mechanical systems and damaged structures. Renovations will include shower and restroom accommodations, accessible parking routes, utility upgrades and connections, a new lift station and force main, a temporary shower and restroom facility, and associated site work, in order to meet current and projected visitor demand. | 5166 - General Revenue Dedicated | 2444000 | 1929716 | 2019-03-31 | 5% | 0% | 0 | 2112.59 | 1927603.41
35 | 126912 | Caddo Lake SP - Water System Upgrade 245 Park Rd 2 Karnack, TX (Harrison county) | Planning and design costs to upgrade domestic water source to treat for excessive amounts of iron in the water and prevent further damage to plumbing fixtures throughout the park. Repairs include new storage tanks, pump systems, gas chlorination system, iron removal filter, refurbished hydro pneumatic tank, electrical improvements, and a pump house. | 5166 - General Revenue Dedicated | 250000 | 250000 | 2018-01-31 | 0% | 0% | 0 | 246.44 | 249753.56
36 | 117106 | Indian Lodge - Exterior Plaster and HVAC Replacement TX Hwy 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Renovate the historic facility to include exterior plaster repairs and replace obsolete HVAC units with energy-efficient systems. | 5166 - General Revenue Dedicated | 598000 | 1399500 | 2019-03-31 | 5% | 0% | 0 | 830.65 | 1398669.35
37 | NA | Statewide - Unspecified State Park Boat Ramp Repairs - Statewide | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 1300000 | 0 | 2019-03-31 | 5% | 0% | 0 | 0 | 0 | *
37A | 115356 | Choke Canyon State Park (South Shore Unit) - Boat Ramp 358 Recreation Rd 8 Calliham, TX 78007 (Live Oak County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 290082 | 2019-03-31 | 5% | 0% | 0 | 667 | 289415 | *
37B | 115389 | Fort Parker State Park - Boat Ramp 194 Park Rd 28 Mexia, Tx 76667 (Limestone County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 557214 | 2019-03-31 | 5% | 0% | 0 | 0 | 557214 | *
37C | 116036 | Inks Lake State Park - Boat Ramp 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 314175 | 2019-03-31 | 5% | 0% | 0 | 0 | 314175 | *
37D | 117036 | Ray Roberts Lake SP - Isle du Bois Unit - Boat Ramp 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 0 | 124330 | 2019-03-31 | 5% | 0% | 0 | 0 | 124330 | *
38 | 117503 | Inks Lake SP - Multiple Restroom Replacements 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Replace four public restroom complexes. Scope of work also includes development of utilities and parking. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 4000000 | 3933000 | 2019-03-31 | 5% | 0% | 262618 | 8162.55 | 3662219.45
39 | 117495 | Albert and Bessie Kronkosky SNA - Public Use Development - Planning and Design 7690 Hwy 46 West Pipe Creek, TX 78063 (Bandera County) | Advance planning costs to develop newly acquired site and install infrastructure, including utilities, parking, roadways, restrooms, toilets, and a fee collection booth at headquarters. Site development would allow public access and would meet public use needs as required by the land use agreement, which would generate revenue and provide significant outdoor opportunities. | 5166 - General Revenue Dedicated | 588000 | 250000 | 2018-01-31 | 5% | 0% | 60523.8 | 2787.49 | 186688.71 | *
40 | 127510 | Stephen F Austin SHS - Wastewater Treatment Plant Equalization Basin Installation 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | (Project on hold due to floods) Install equalization basin at wastewater treatment plant in order to provide adequate pace flow into the plant during peak usage. | 5166 - General Revenue Dedicated | 240400 | 0 | 2018-01-31 | 5% | 0% | 0 | 1458.69 | -1458.69 | *
41 | 122081 | CCA Marine Development Center - Fish America Spawning Building and Ozone Water Purification System Replacement 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | Replace the under-sized, 30-year-old, Fish America spawning building with a new 4,000 square foot spawning building at the same location that will withstand the coastal elements. Building will include staff offices and research space and a new ozone water purification system to replace the existing non-functioning ozone system. | 5166 - General Revenue Dedicated (SWFS) | 1710000 | 1710000 | 2018-01-31 | 5% | 0% | 0 | 1152.78 | 1708847.22 | *
42 | 115922 | Abilene SP - Swimming Pool and CCC Bathhouse Repairs FM 89, 150 Park Rd 32 Tuscola, TX 79562 (Taylor County) | (Project Postponed) Planning and design costs to repair and renovate the swimming pool and CCC bathhouse. | 5166 - General Revenue Dedicated | 850000 | 0 | 2018-01-31 | 0% | 0% | 0 | 49.31 | -49.31 | *
43 | 114144 | Austin Headquarters Complex - HVAC Control System Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | Replace the existing climate control system at Austin Headquarters Complex with an updated HVAC Management System which is supported by current industry vendors and allows for remote adjustments by the energy performance contractor. | 5166 - General Revenue Dedicated | 478800 | 631120 | 2018-08-31 | 5% | 0% | 0 | 0 | 631120
44 | 114906 | Austin Headquarters Complex - Heating Ventilation Air-Conditioning (HVAC) Units Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | (Project Cancelled) Replace two deteriorating, independent Liebert HVAC units in the Computer Room that houses the server at the TPWD Austin Headquarters Complex. | 5166 - General Revenue Dedicated | 144348 | 0 | 2018-08-31 | 0% | 0% | 0 | 1513.61 | -1513.61 | *
45 | 117417 | Austin Headquarters Complex - Fire Escape and Storage Building 4200 Smith School Road Austin, TX 78744 (Travis County) | Construct a Building D exterior stairway and fire escape as a secondary egress for safety purposes. Build a storage building on Building D rooftop to store tools, equipment, and materials used to service the rooftop equipment. | 5166 - General Revenue Dedicated | 73152 | 65180 | 2019-03-31 | 5% | 0% | 3652 | 107.91 | 61420.09
46 | TBD | Statewide - Unspecified State Park2015 Flood Damage Repairs | Funding held to address statewide 2015 flood damages. A comprehensive damage assessment has not yet been completed due to high-water levels and site inaccessibility. | 5166 - General Revenue Dedicated | 8058550 | 4670137 | 2018-01-31 | 5% | 0% | 0 | 0 | 4670137 | *
47 | TBD | Stephen F Austin SHS - Water Tank Repairs 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | (Project on hold due to floods) Pressure wash and repaint elevated water tank per TCEQ regulations. | 5166 - General Revenue Dedicated | 300000 | 0 | 2018-08-31 | 5% | 0% | 0 | 0 | 0
48 | 124545 | Huntsville SP - Dam Repair 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Fortify and repair the earthen embankment and spillway. | 5166 - General Revenue Dedicated | 4380000 | 4389000 | 2017-05-30 | 100% | 5% | 4268639.08 | 119364.71 | 996.21
49 | 132907 | Bastrop SP - Group Barracks Complex Renovation 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Renovate the Group Barracks Complex, which includes four dormitory buildings and one group dinning hall. The existing obsolete restroom will be demolished; restroom/shower facilities will be added to each dormitory facility. The renovations include updating of all mechanicals, plumbing, electrical, and site modifications to become code compliant and improve visitor experience. | 5166 - General Revenue Dedicated | 3558000 | 3558000 | 2018-03-31 | 100% | 0% | 7792 | 44699.06 | 3505508.94
50 | 125986 | Port Isabel Lighthouse - Light house repairs; replace corroded metal 421 East Queen Isabella Blvd Port Isabel, TX 78578 (Cameron County) | Repair and/or replace corroded exterior metal components on the Port Isabel Lighthouse at the Watch room and Lantern Levels and repaint lighthouse exterior. | 5166 - General Revenue Dedicated | 279950 | 425962 | 2017-03-31 | 100% | 0% | 0 | 3253.84 | 422708.16
51 | 137824 | Longhorn Caverns - Communications System and Surge Protection 6211 Park Rd 4 So. Burnet, TX 78611 (Burnet County) | Install communication system for the cavern to protect the public in the event of an emergency. | 5166 - General Revenue Dedicated | 170000 | 170000 | 2018-08-31 | 5% | 0% | 19100 | 0 | 150900
52 | 134232 | Hill Country SNA - Replace Well at Group Lodge 10600 Bandera Creed Rd Bandera, TX 78003 (Bandera County) | Install water system at group lodge to provide potable water to guests. | 5166 - General Revenue Dedicated | 365000 | 365000 | 2017-08-31 | 100% | 0% | 0 | 2373.35 | 362626.65
53 | 134239 | Lost Maples SNA - Replace Potable Water Storage Tank 37221 FM 187 Vanderpool, TX 78885 (Bandera County) | Replace deteriorating drinking water storage tank with a new system in order to address a high iron content in the facility's water supply and meet TCEQ regulations. | 5166 - General Revenue Dedicated | 485000 | 485000 | 2017-08-01 | 100% | 0% | 0 | 2990.02 | 482009.98
54 | 137394 | McKinney Falls SP - Smith Visitor's Center Flood Damage Repairs 5808 McKinney Falls Austin, TX 78744 (Travis County) | Repair all interior finishes, associated mechanical, electrical, and plumbing systems damaged by flood waters. Reconstruct the interior restroom to meet TDLR standards. | 5166 - General Revenue Dedicated | 570000 | 983770.69 | 2017-05-31 | 60% | 0% | 23700 | 6759.99 | 953310.7
55 | 136423 | Davis Mountains SP - Communications Bldg. Repairs TX HWY 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Replace fire damaged radio house with a permanent facility to maintain park radio communications within the park and region. | 5166 - General Revenue Dedicated | 317000 | 417000 | 2019-03-31 | 30% | 0% | 0 | 0 | 417000
56 | 112741 | Tyler SP - Headquarters Replacement 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Planning and design cost for replacing the headquarters facility with new, adequately-sized ADA-compliant building, road, parking lot, and entrance. | 5166 - General Revenue Dedicated | 3000000 | 1061124 | 2019-03-31 | 5% | 0% | 0 | 0 | 1061124 | *
57 | 127872 | Mustang Island SP - Foundation repairs for (2) residences 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Repair two residences' pilings and beams, which are degraded due to rot. | 5166 - General Revenue Dedicated | 225000 | 147114 | 2018-08-31 | 5% | 0% | 0 | 947.87 | 146166.13
58 | TBD | Mother Neff SP - CCC Rock Tabernacle Repairs and Stabilization 1680 TX 236 HWY Moody, TX 76557 (Coryell County) | (Project Postponed) - Stabilization of 4000 sq. ft. CCC built tabernacle. Work includes structural, wood, and masonry repairs, reroofing, and site construction. | 5166 - General Revenue Dedicated | 350000 | 0 | 2018-08-31 | 100% | 0% | 0 | 0 | 0 | *
59 | TBD | Devil's River SP - New Visitor Check-in Building and Remodel of Existing Lodge. 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Planning and design costs to develop the newly acquired south unit. The development plan includes a small site headquarters building for visitor check-in and the remodeling of the existing lodge to include staff offices and interpretive space. The development plan is still pending TNC approval. | 5166 - General Revenue Dedicated | 150000 | 150000 | 2018-01-31 | 0% | 0% | 0 | 0 | 150000
60 | TBD | San Jacinto Battleground SHS - Reflection Pool Structural Assessment 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Professional engineering report and assessment for stabilizing and repairing the retaining walls around the reflecting pool. | 5166 - General Revenue Dedicated | 100000 | 100000 | 2018-01-31 | 5% | 0% | 0 | 71.8 | 99928.2
61 | 124932 | Sea Center Texas - Fence Replacement 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Replace three miles of perimeter fencing in and around the facility with high game fence and an entry fence in order to protect the hatchery from wildlife intrusion. | 5166 - General Revenue Dedicated (SWFS) | 598000 | 598000 | 2019-03-31 | 5% | 0% | 0 | 782.94 | 597217.06 | *
62 | 192540 | Buescher State Park - Erosion mitigation and habitat stabilization (Flood Repair) 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Stabilize the soil and mitigate erosion caused by flooding. | 5166 - General Revenue Dedicated | 0 | 754000 | 2017-05-31 | 0% | 95% | 287153.6 | 249929.83 | 216916.57
|  |  |  | Totals: | 91000000 | 90999999.69 |  |  |  | 7089126.75 | 1191692.31 | 82719180.63

## TPWD Notes 6.16
| Agency: | Texas Parks & Wildlife - 802
| Date: | 2016-06-15
| Prepared by: | Infrastructure Division
Project Priority | Supplemental Information
3 | For FY 16/17 work on this project will only include the planning and design phases. Construction is anticipated to be performed in FY 18/19.
5 | For FY 16/17 work on this project will only include the planning and design phases. Construction is anticipated to be performed in FY 18/19.
6 | Significant change in budget because we plan to encumber a construction contract in FY17. Originally this project was funded for planning and design only.
7 | Scope changed to the replacement of one restroom complex
8 | For FY 16/17 work on this project will only include the planning and design phases. Construction is anticipated to be performed in FY 18/19.
10 | For FY 16/17 the deliverable for this project is a professional engineering assessment. Design to be performed in FY 18/19.
23 | Priority change for Coastal Fisheries Division, Sea Center Flounder Building use to be in line position #61 and is now moved up in to line position #23
25 | Priority change for Coastal Fisheries Division, Dickinson Marine Lab New Boat Storage Facility use to be in line position #41 and is now moved up in to line position #25
27 | For FY 16/17 work on this project will only include a preliminary engineering study and the design phase. Construction is anticipated to be performed in FY 18/19.
30 | For FY 16/17 work on this project will only include advanced planning. Design to be performed in FY 18/19. Construction in FY 20/21.
32 | This project originally included work to replace both the Bastrop Dam and for Shoreline Stabilization along the Lake at Bastrop State Park. The Dam and Shoreline Stabilization has been broken into separate projects. Line 32 now only represents the Dam project.
32A | This project is added to represent the Bastrop SP Shoreline Stabilization project. This project will include both design and construction of the shoreline stabilization in FY 16/17.
37 | This project originally represented the Boat Ramp Repair Program at various State Parks Statewide. The Program has been broken into 4 separate projects according to the work locations listed below in 37A thru 37D. Line 37 is being zeroed-out and redistributed over the 4 subsequent projects established immediately below.
37A | This project is added to represent the Boat Ramp Repairs to be performed at Choke Canyon State Park (Southshore Unit).
37B | This project is added to represent the Boat Ramp Repairs to be performed at Fort Parker State Park.
37C | This project is added to represent the Boat Ramp Repairs to be performed at Inks Lake State Park.
37D | This project is added to represent the Boat Ramp Repairs to be performed at Ray Roberts Lake State Park (Isle de Bois Unit).
39 | For FY 16/17 work on this project will only include advanced planning. Design to be performed in FY 18/19. Construction in FY 20/21.
40 | This project is currently on hold due to the recent flooding. We must reassess the park's priorities and determine how this project's scope of work may be impacted.
41 | Priority change for Coastal Fisheries Division, CCA Marine Development Center New Spawing Building use to be in line position #23 and is now moved up in to line position #41
42 | This project is being postponed for the FY 16/17 biennium. It will be re-evaluated as a possible project in the FY 18/19 biennium.
44 | This project has been cancelled, work is no longer relevant now that servers have been relocated.
46 | Note that flood project funds have been used to set up new projects on Line #32A and #62
47 | This project is currently on hold due to the recent flooding. We must reassess the park's priorities and determine how this project's scope of work may be impacted.
56 | For FY 16/17 work on this project will only include the planning and design phases. Construction is anticipated to be performed in FY 18/19.
58 | This project is being postponed for the FY 16/17 biennium. It will be re-evaluated as a possible project in the FY 18/19 biennium.
61 | Priority change for Coastal Fisheries Division, Sea Center Texas Fence Replacement use to be in line position #25 and is now moved up in to line position #61

## TPWD 3.16
| Agency: | Texas Parks and Wildlife Department
| Date: | 2016-03-15 | [9 empty] | March 15,2016
| Prepared by: | Infrastructure Division
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 127490 | Battleship Texas SHP - Structural Repairs 3523 Independence Parkway S LaPorte, Tx,77571 (Harris County) | Balance of work to repair internal structural elements, identified in an October 2012 scope of work, which is necessary to stabilize the ship . Repairs are critical if the ship remains in a wet berth and would be absolutely necessary if ship is ever placed into a dry berth. | 5166 - General Revenue Dedicated | 25000000 | 25000000 | 2018-04-30 | 25% | 0% | 1703413 | 1484.9 | 23295102.1
2 | 116818 | Fort Richardson SHS - Water and Wastewater System Replacement 228 State Park Road 61 Jacksboro, TX 76458 (Jack County) | Planning and design costs to replace the 50-year-old wastewater system, water distribution system and the main lift station with modernized and efficient systems capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 200000 | 200000 | 2018-01-31 | 0% | 0% | 0 | 0 | 200000
3 | 116151 | Seminole Canyon SHS - Camp Loop Upgrades US Hwy 90 W Comstock, TX 78837 (Val Verde County) | Upgrade the Desert Vista Camp Loop's utilities, to include replacement and repairs to the On Site Sewage Facility System, water well, storage tank, pumps, and associated appurtenances, accessible restroom upgrades, and electrical service. | 5166 - General Revenue Dedicated | 1000000 | 1000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1000000
4 | 126472 | Goliad SHS - Wastewater System Upgrade 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Planning and design costs to replace obsolete clay wastewater lines and systems, lift station, septic tanks, and drain fields with a modernized, efficient system capable of servicing the entire site, which includes the Hacienda, Mission workshop, CCC Restroom, Old River Restroom, park headquarters, group dining hall, camp loop, and residence. | 5166 - General Revenue Dedicated | 225000 | 225000 | 2018-01-31 | 0% | 0% | 0 | 0 | 225000
5 | 117535 | Copper Breaks SP - Water Distribution System Replacement 777 Park Road 62 Quanah,79252-7679 (Hardman County) | Replace a 50-year-old, leaking water distribution system and chlorination station with a modernized and efficient system capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 533000 | 533000 | 2019-03-31 | 0% | 0% | 0 | 0 | 533000
6 | 116471 | Balmorhea SP - CCC Motor Court Renovations, Utility Upgrades and Headquarters Replacement - Planning and Design 9207 H. 17S Toyahvale, TX (Reeves County) | Renovate 18 Civilian Conservation Corps (CCC) motel units at the San Solomon Springs Motel Court, to include repairing termite damaged woodwork; upgrade the water and wastewater utilities and campground electrical utility service from 30 amp to 50 amp; renovate camp loop restrooms. | 5166 - General Revenue Dedicated | 1200000 | 1200000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1200000
7 | 117494 | Pedernales Falls SP - Restroom Replacements 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Replace two public restroom complexes. Scope of work also includes development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 2000000 | 2000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 2000000
8 | 122865 | Huntsville SP - CCC Boathouse and Lodge Patio Wall Repairs 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Renovate Civilian Conservation Corps (CCC) boathouse to include restoring the exterior hardwood siding, repairing the roof as well as interior and exterior structural damages, and repairing and stabilizing the Lodge's patio wall. | 5166 - General Revenue Dedicated | 500000 | 500000 | 2019-04-01 | 0% | 0% | 0 | 0 | 500000
9 | 116921 | Palo Duro Canyon SP - Headquarters Replacement 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Planning and design costs for site headquarters replacement. Headquarters is currently operating out of an under-sized converted residence and the project would provide an adequately-sized and modern facility to better serve the increasing number of visitors. | 5166 - General Revenue Dedicated | 250000 | 250000 | 2018-01-31 | 0% | 0% | 0 | 293.56 | 249706.44
10 | 117504 | Garner SP - Water System Upgrades US 83 N Concan, TX 78838 (Uvalde County) | Planning and design costs to upgrade the park's overall water system, including treatment to reduce water hardness, and replace water distribution lines serving several park facilities in order to reduced system maintenance costs. | 5166 - General Revenue Dedicated | 400000 | 400000 | 2018-01-31 | 0% | 0% | 0 | 0 | 400000
11 | 117536 | Fairfield Lake SP - Wastewater Treatment Plant Repairs TX 2570 E Fairfield, TX 75840 (Freestone County) | Replace the mechanical systems at two existing wastewater treatment plants with modernized and efficient systems that are capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 650000 | 650000 | 2019-03-31 | 0% | 0% | 0 | 0 | 650000
12 | 7505 | Statewide - Unspecified State Park State Park Region 3 Restroom Replacement Program | Replace three public restroom complexes at Guadalupe State Park camping and day-use areas and one restroom complex at Government Canyon State Natural Area. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 4000000 | 4000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 4000000
13 | 126496 | Tyler SP - Residence Replacements 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Replace two obsolete staff residences with two adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structures, to include utility connections, parking and associated paving. | 5166 - General Revenue Dedicated | 1000000 | 1000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1000000
14 | 124729 | San Jacinto Battleground SHS - Residence Replacements 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Replace two residences and remove from a sensitive archaeological site. | 5166 - General Revenue Dedicated | 830000 | 830000 | 2019-03-31 | 0% | 0% | 0 | 0 | 830000
15 | 127483 | Lake Tawakoni SP - Residence Replacement 10822 FM 2475 Willis Point, TX 75169 (Hunt Van Zandt County) | Replace mobile home residence with an adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structure, to include utility connections, parking and associated paving. | 5166 - General Revenue Dedicated | 480000 | 480000 | 2019-03-31 | 0% | 0% | 0 | 0 | 480000
16 | 7358 | Mission Tejas SHS - Replace Visitor Center 120 State Park Rd. 4 Grapeland, TX 75844 (Houston County) | Replace visitor center that was destroyed by Hurricane Ike. New facility will include offices, assembly area, visitor check-in area, a new entry road and parking lot, utility extensions, and interpretive displays to educate visitors about the El Camino Real Trail. | 5166 - General Revenue Dedicated | 2713100 | 2713100 | 2018-08-31 | 90% | 0% | 10795 | 11882.26 | 2713100
17 | 117449 | Fort Leaton SHS - Roof Replacement FM 170 E Presidio, TX 79845 (Presidio County) | Replace leaking roof to preserve the historic structure and protect the building and contents from further water damage. | 5166 - General Revenue Dedicated | 413600 | 413600 | 2019-03-31 | 0% | 0% | 0 | 0 | 413600
18 | 117534 | Devil's River SP - Septic System Replacement 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Replace obsolete septic system to serve the lodge and bunkhouse facility at the Del Norte Unit. | 5166 - General Revenue Dedicated | 306800 | 306800 | 2019-03-31 | 0% | 0% | 0 | 0 | 306800
19 | 122405 | Perry R Bass Marine Research Station - Hatchery Replacement HC 02, Box 385 FM 3280 Palacios TX 77465 (Matagorda County) | Planning and design costs for replacement of the under-sized and damaged ponds, hatchery buildings, infrastructure, and jetty pump intake. | 5166 - General Revenue Dedicated (SWFS) | 4131500 | 4131500 | 2018-01-31 | 5% | 0% | 0 | 0 | 4131500
20 | 7436 | Galveston Island SP - Beachside Redevelopment 14901 FM 3005 Galveston, TX 77554 (Galveston County) | Design costs to redevelop Galveston Island State Park's beachside in accordance with the GISP Redevelopment Master Plan. Construction plans include one restroom, one RV dump station, one boardwalk, multiple tent platforms, 30 multiple use campsites with electrical / water service, three group shelters, and 20 day-use picnic shelters. | 5166 - General Revenue Dedicated | 350000 | 350000 | 2018-01-31 | 5% | 0% | 0 | 0 | 350000
21 | 122888 | Monument Hill/Kreische Brewery SHS - Kreische House and Brewery Renovations 414 State Loop 92 LaGrange, TX 78945 (Fayette County) | Renovate the interior and exterior of the historic Kreische House and Brewery to include water damage repairs and renovation of the cedar shake roof, structural elements, woodwork, floors, windows, stone work, finishes, historic furniture, and water diversion landscaping to protect the structures during flooding. | 5166 - General Revenue Dedicated | 1500000 | 1500000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1500000
22 | 125983 | Sea Center Texas - Pond Electrical System Improvements 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Upgrade obsolete electrical service systems at 36 ponds with modern and energy-efficient systems that will improve hatchery operations | 5166 - General Revenue Dedicated (SWFS) | 1027000 | 1027000 | 2019-03-31 | 5% | 0% | 0 | 0 | 1027000
23 | 122081 | CCA Marine Development Center - Fish America Spawning Building and Ozone Water Purification System Replacement 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | Replace the under-sized, 30-year-old, Fish America spawning building with a new 4,000 square foot spawning building at the same location that will withstand the coastal elements. Building will include staff offices and research space and a new ozone water purification system to replace the existing non-functioning ozone system. | 5166 - General Revenue Dedicated (SWFS) | 1710000 | 1710000 | 2018-01-31 | 5% | 0% | 0 | 0 | 1710000
24 | 114228 | Colorado Bend SP - Water Treatment Plant Replacement 10 miles S of Bend on Gravel Rd Bend, TX 76824 (San Saba County) | Planning and design costs to replace the water treatment plant with a new system to include a storage tank and ground water well. | 5166 - General Revenue Dedicated | 150000 | 150000 | 2018-01-31 | 5% | 0% | 0 | 0 | 150000
25 | 124932 | Sea Center Texas - Fence Replacement 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Replace three miles of perimeter fencing in and around the facility with high game fence and an entry fence in order to protect the hatchery from wildlife intrusion. | 5166 - General Revenue Dedicated (SWFS) | 598000 | 598000 | 2019-03-31 | 5% | 0% | 0 | 0 | 598000
26 | 117507 | Garner SP - Dining Halls and Barracks Remodel US 83 N Concan, TX 78838 (Uvalde County) | Planning and design costs to remodel Group Dining Hall at Shady Meadows and Cypress Springs camping areas to include electrical and HVAC system upgrades, kitchen remodels, insulation for walls and ceilings, window and door repairs or replacements, roof and fascia replacement and interior wall and ceiling finish-out. Remodel Cypress Springs Barracks to include new roofs, electrical upgrades, HVAC installation, door and window repairs and replacements, and interior finish upgrades. Renovations will enhance visitors' experiences and increase revenue. | 5166 - General Revenue Dedicated | 325000 | 325000 | 2018-01-31 | 0% | 0% | 0 | 3214.14 | 321785.86
27 | 114243 | Pedernales Falls SP - Water and Wastewater System Upgrades 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Planning and design costs to upgrade the obsolete water treatment plant to include four septic fields, drain fields and the water filtration system, in order to save water resources and provide an adequate system capable of saving water resources while better serving park visitors. | 5166 - General Revenue Dedicated | 106000 | 106000 | 2018-01-31 | 0% | 0% | 0 | 0 | 106000
28 | 127260 | Ray Roberts Lake SP - Johnson Branch Unit Compost Toilet Replacements 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Replace seven obsolete compost toilets with modular vault toilets to serve several trail and camping areas and revise any pathways for ADA compliance. | 5166 - General Revenue Dedicated | 834600 | 834600 | 2019-03-31 | 5% | 0% | 0 | 0 | 834600
29 | 127438 | Lake Livingston SP - Marina Area and Fishing Pier Accessibility Upgrades and Repairs 300 State Park Road 65 Livingston, TX 77351 (Polk County) | Planning and design costs to renovate the Marina Area and Fishing Pier to include: repairs to restrooms, courtesy dock, fueling stations, electrical and lighting systems, and the accessible routes between facilities and parking due to soil subsidence. | 5166 - General Revenue Dedicated | 390000 | 390000 | 2018-01-31 | 5% | 0% | 0 | 0 | 390000
30 | 114238 | Inks Lake SP - Headquarters Building Replacement - Planning and Design 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Planning and design costs to replace the under-sized headquarters building with one which includes an adequately-sized lobby and registration area and office, as well as additional restrooms, to meet staff and visitor needs. Improve traffic flow around the headquarters site. | 5166 - General Revenue Dedicated | 587500 | 587500 | 2018-01-31 | 0% | 0% | 0 | 0 | 587500
31 | 117359 | McKinney Falls SP - Smith Visitor Center Facility and Exhibit Renovation 5808 McKinney Falls Austin, TX 78744 (Travis County) | Renovate the Smith Visitor Center including upgrading a learning center to serve as an interactive classroom with new interpretive exhibits to educate students and park visitors about the El Camino Real Trail. | 5166 - General Revenue Dedicated | 859800 | 859800 | 2018-08-31 | 90% | 0% | 9545 | 2986.44 | 859800
32 | 116769 | Bastrop SP - Dam Replacement and Shore Stabilization 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Planning and design costs to replace the breached dam due to the 2015 memorial day flooding. | 5166 - General Revenue Dedicated | 1000000 | 1000000 | 2018-01-31 | 10% | 0% | 100278.08 | 84773.14 | 814948.78
33 | 127360 | Goliad SHS - Custodian's Cottage Renovation and Adaptive Reuse to Interpretive Facility 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Renovate the CCC Custodian's Cottage to convert its use from administrative offices to an adequately-sized interpretive facility which will educate visitors about the El Camino Real Trail. Renovations will include restoration of formal gardens and a new parking lot. | 5166 - General Revenue Dedicated | 978400 | 978400 | 2018-08-31 | 90% | 0% | 50103.85 | 7914.24 | 978400
34 | 126719 | Mustang Island SP - Campground and Day-Use Area Restroom Replacements 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Replace the camp loop and day-use restrooms with two modern facilities to include replacement of obsolete mechanical systems and damaged structures. Renovations will include shower and restroom accommodations, accessible parking routes, utility upgrades and connections, a new lift station and force main, a temporary shower and restroom facility, and associated site work, in order to meet current and projected visitor demand. | 5166 - General Revenue Dedicated | 2444000 | 2444000 | 2019-03-31 | 0% | 0% | 0 | 0 | 2444000
35 | 126912 | Caddo Lake SP - Water System Upgrade 245 Park Rd 2 Karnack, TX (Harrison county) | Planning and design costs to upgrade domestic water source to treat for excessive amounts of iron in the water and prevent further damage to plumbing fixtures throughout the park. Repairs include new storage tanks, pump systems, gas chlorination system, iron removal filter, refurbished hydro pneumatic tank, electrical improvements, and a pump house. | 5166 - General Revenue Dedicated | 250000 | 250000 | 2018-01-31 | 0% | 0% | 0 | 0 | 250000
36 | 117106 | Indian Lodge - Exterior Plaster and HVAC Replacement TX Hwy 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Renovate the historic facility to include exterior plaster repairs and replace obsolete HVAC units with energy-efficient systems. | 5166 - General Revenue Dedicated | 598000 | 598000 | 2019-03-31 | 0% | 0% | 0 | 0 | 598000
37 | NA | Statewide - Unspecified State Park Boat Ramp Repairs - Statewide | Repair boat ramps at multiple state park sites which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 1300000 | 1300000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1300000
38 | 117503 | Inks Lake SP - Multiple Restroom Replacements 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Replace four public restroom complexes. Scope of work also includes development of utilities and parking. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 4000000 | 4000000 | 2019-03-31 | 0% | 0% | 0 | 2933.77 | 3997066.23
39 | 117495 | Albert and Bessie Kronkosky SNA - Public Use Development - Planning and Design 7690 Hwy 46 West Pipe Creek, TX 78063 (Bandera County) | Planning and design costs to develop newly acquired site and install infrastructure, including utilities, parking, roadways, restrooms, toilets, and a fee collection booth at headquarters. Site development would allow public access and would meet public use needs as required by the land use agreement, which would generate revenue and provide significant outdoor opportunities. | 5166 - General Revenue Dedicated | 588000 | 588000 | 2018-01-31 | 0% | 0% | 0 | 410.98 | 587589.02
40 | 127510 | Stephen F Austin SHS - Wastewater Treatment Plant Equalization Basin Installation 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Install equalization basin at wastewater treatment plant in order to provide adequate pace flow into the plant during peak usage. | 5166 - General Revenue Dedicated | 240400 | 240400 | 2018-01-31 | 0% | 0% | 0 | 418.3 | 239981.7
41 | 124743 | Dickinson Marine Lab - New Boat Storage Facility 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | Install three metal boat storage buildings (4,960 square foot total) at the south, east and west sides of an existing paved storage area to secure the boats and protect from weather and vandalism. Storage buildings shall include power and lighting. | 5166 - General Revenue Dedicated (SWFS) | 507000 | 507000 | 2018-08-31 | 5% | 0% | 0 | 0 | 507000
42 | 115922 | Abilene SP - Swimming Pool and CCC Bathhouse Repairs FM 89, 150 Park Rd 32 Tuscola, TX 79562 (Taylor County) | Planning and design costs to repair and renovate the swimming pool and CCC bathhouse. | 5166 - General Revenue Dedicated | 850000 | 850000 | 2018-01-31 | 0% | 0% | 0 | 0 | 850000
43 | 114144 | Austin Headquarters Complex - HVAC Control System Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | Replace the existing climate control system at Austin Headquarters Complex with an updated HVAC Management System which is supported by current industry vendors and allows for remote adjustments by the energy performance contractor. | 5166 - General Revenue Dedicated | 478800 | 478800 | 2018-08-31 | 5% | 0% | 0 | 0 | 478800
44 | 114906 | Austin Headquarters Complex - Heating Ventilation Air-Conditioning (HVAC) Units Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | Replace two deteriorating, independent Liebert HVAC units in the Computer Room that houses the server at the TPWD Austin Headquarters Complex. | 5166 - General Revenue Dedicated | 144348 | 144348 | 2018-08-31 | 0% | 0% | 0 | 0 | 144348
45 | 5786 | Austin Headquarters Complex - Fire Escape and Storage Building 4200 Smith School Road Austin, TX 78744 (Travis County) | Construct a Building D exterior stairway and fire escape as a secondary egress for safety purposes. Build a storage building on Building D rooftop to store tools, equipment, and materials used to service the rooftop equipment. | 5166 - General Revenue Dedicated | 73152 | 73152 | 2019-03-31 | 0% | 0% | 0 | 0 | 73152
46 | TBD | Statewide - Unspecified State Park2015 Flood Damage Repairs | Funding held to address statewide 2015 flood damages. A comprehensive damage assessment has not yet been completed due to high-water levels and site inaccessibility. | 5166 - General Revenue Dedicated | 8058550 | 7721550 | 2018-01-31 | 0% | 0% | 0 | 0 | 7721550 | Yes
47 | TBD | Stephen F Austin SHS - Water Tank Repairs 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Pressure wash and repaint elevated water tank per TCEQ regulations. | 5166 - General Revenue Dedicated | 300000 | 300000 | 2018-08-31 | 0% | 0% | 0 | 0 | 300000
48 | 124545 | Huntsville SP - Dam Repair 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Fortify and repair the earthen embankment and spillway. | 5166 - General Revenue Dedicated | 4380000 | 4380000 | 2017-05-30 | 100% | 5% | 3949418.72 | 18366.07 | 412215.21
49 | 132907 | Bastrop SP - Group Barracks Complex Renovation 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Renovate the Group Barracks Complex, which includes four dormitory buildings and one group dinning hall. The existing obsolete restroom will be demolished; restroom/shower facilities will be added to each dormitory facility. The renovations include updating of all mechanicals, plumbing, electrical, and site modifications to become code compliant and improve visitor experience. | 5166 - General Revenue Dedicated | 3558000 | 3558000 | 2018-03-31 | 90% | 0% | 8792 | 39151.3 | 3510056.7
50 | 125986 | Port Isabel Lighthouse - Light house repairs; replace corroded metal 421 East Queen Isabella Blvd Port Isabel, TX 78578 (Cameron County) | Repair and/or replace corroded exterior metal components on the Port Isabel Lighthouse at the Watch room and Lantern Levels and repaint lighthouse exterior. | 5166 - General Revenue Dedicated | 279950 | 279950 | 2017-03-31 | 90% | 0% | 0 | 1602.95 | 278347.05
51 | 137824 | Longhorn Caverns - Communications System and Surge Protection 6211 Park Rd 4 So. Burnet, TX 78611 (Burnet County) | Install communication system for the cavern to protect the public in the event of an emergency. | 5166 - General Revenue Dedicated | 170000 | 170000 | 2018-08-31 | 0% | 0% | 0 | 0 | 170000
52 | 134232 | Hill Country SNA - Replace Well at Group Lodge 10600 Bandera Creed Rd Bandera, TX 78003 (Bandera County) | Install water system at group lodge to provide potable water to guests. | 5166 - General Revenue Dedicated | 365000 | 365000 | 2017-08-31 | 100% | 0% | 0 | 1420.9 | 363579.1
53 | 134239 | Lost Maples SNA - Replace Potable Water Storage Tank 37221 FM 187 Vanderpool, TX 78885 (Bandera County) | Replace deteriorating drinking water storage tank with a new system in order to address a high iron content in the facility's water supply and meet TCEQ regulations. | 5166 - General Revenue Dedicated | 485000 | 485000 | 2017-08-01 | 100% | 0% | 0 | 1094.35 | 483905.65
54 | 137394 | McKinney Falls SP - Smith Visitor's Center Flood Damage Repairs 5808 McKinney Falls Austin, TX 78744 (Travis County) | Repair all interior finishes, associated mechanical, electrical, and plumbing systems damaged by flood waters. Reconstruct the interior restroom to meet TDLR standards. | 5166 - General Revenue Dedicated | 570000 | 570000 | 2017-05-31 | 60% | 0% | 0 | 3397.35 | 566602.65
55 | 136423 | Davis Mountains SP - Communications Bldg. Repairs TX HWY 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Replace fire damaged radio house with a permanent facility to maintain park radio communications within the park and region. | 5166 - General Revenue Dedicated | 317000 | 317000 | 2019-03-31 | 30% | 0% | 0 | 0 | 317000
56 | 112741 | Tyler SP - Headquarters Replacement 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Replace the headquarters facility with new, adequately-sized ADA-compliant building, road, parking lot, and entrance. | 5166 - General Revenue Dedicated | 3000000 | 3000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 3000000
57 | 127872 | Mustang Island SP - Foundation repairs for (2) residences 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Repair two residences' pilings and beams, which are degraded due to rot. | 5166 - General Revenue Dedicated | 225000 | 225000 | 2018-08-31 | 0% | 0% | 0 | 0 | 225000
58 | TBD | Mother Neff SP - CCC Rock Tabernacle Repairs and Stabilization 1680 TX 236 HWY Moody, TX 76557 (Coryell County) | Stabilization of 4000 sq. ft. CCC built tabernacle. Work includes structural, wood, and masonry repairs, reroofing, and site construction. | 5166 - General Revenue Dedicated | 350000 | 350000 | 2018-08-31 | 100% | 0% | 0 | 0 | 350000
59 | TBD | Devil's River SP - New Visitor Check-in Building and Remodel of Existing Lodge. 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Planning and design costs to develop the newly acquired south unit. The development plan includes a small site headquarters building for visitor check-in and the remodeling of the existing lodge to include staff offices and interpretive space. The development plan is still pending TNC approval. | 5166 - General Revenue Dedicated | 150000 | 150000 | 2018-01-31 | 0% | 0% | 0 | 0 | 150000
60 | TBD | San Jacinto Battleground SHS - Reflection Pool Structural Assessment 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Professional engineering report and assessment for stabilizing and repairing the retaining walls around the reflecting pool. | 5166 - General Revenue Dedicated | 100000 | 100000 | 2018-01-31 | 0% | 0% | 0 | 0 | 100000
61 | 127758 | Sea Center Texas - Flounder Building 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Construct new 3000 square foot flounder spawning building. Building will provide additional hatchery floor space for flounder bloodstock and incubation equipment and include a separate room for culture of live feeds. | 5166 - General Revenue Dedicated (SWFS) | 968500 | 968500 | 2018-08-31 | 60% | 0% | 0 | 0 | 968500
62 | 192540 | Buescher State Park - Erosion mitigation and habitiat stabilization (Flood Repair) 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Stabilize the soil and mitigate erosion caused by flooding. | 5166 - General Revenue Dedicated | 0 | 337000 | 2017-05-31 | 0% | 50% | 146653.6 | 190142 | 204 | Yes
|  |  |  | Totals: | 91000000 | 91000000 |  |  |  | 5978999.25 | 371486.65 | 84649514.1

## TPWD 12.15
| Agency: | Texas Parks and Wildlife Department
| Date: | December 15,2015 | [9 empty] | 2015-12-15
| Prepared by: | Infrastructure Division
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 127490 | Battleship Texas SHP - Structural Repairs 3523 Independence Parkway S LaPorte, Tx,77571 (Harris County) | Balance of work to repair internal structural elements, identified in an October 2012 scope of work, which is necessary to stabilize the ship . Repairs are critical if the ship remains in a wet berth and would be absolutely necessary if ship is ever placed into a dry berth. | 5166 - General Revenue Dedicated | 25000000 | 25000000 | 2018-04-30 | 0% | 0% | 0 | 0 | 25000000
2 | 6818 | Fort Richardson SHS - Water and Wastewater System Replacement 228 State Park Road 61 Jacksboro, TX 76458 (Jack County) | Planning and design costs to replace the 50-year-old wastewater system, water distribution system and the main lift station with modernized and efficient systems capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 200000 | 200000 | 2018-01-31 | 0% | 0% | 0 | 0 | 200000
3 | 6151 | Seminole Canyon SHS - Camp Loop Upgrades US Hwy 90 W Comstock, TX 78837 (Val Verde County) | Upgrade the Desert Vista Camp Loop's utilities, to include replacement and repairs to the On Site Sewage Facility System, water well, storage tank, pumps, and associated appurtenances, accessible restroom upgrades, and electrical service. | 5166 - General Revenue Dedicated | 1000000 | 1000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1000000
4 | 6472 | Goliad SHS - Wastewater System Upgrade 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Planning and design costs to replace obsolete clay wastewater lines and systems, lift station, septic tanks, and drain fields with a modernized, efficient system capable of servicing the entire site, which includes the Hacienda, Mission workshop, CCC Restroom, Old River Restroom, park headquarters, group dining hall, camp loop, and residence. | 5166 - General Revenue Dedicated | 225000 | 225000 | 2018-01-31 | 0% | 0% | 0 | 0 | 225000
5 | 7535 | Copper Breaks SP - Water Distribution System Replacement 777 Park Road 62 Quanah,79252-7679 (Hardman County) | Replace a 50-year-old, leaking water distribution system and chlorination station with a modernized and efficient system capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 533000 | 533000 | 2019-03-31 | 0% | 0% | 0 | 0 | 533000
6 | 6471 | Balmorhea SP - CCC Motor Court Renovations, Utility Upgrades and Headquarters Replacement - Planning and Design 9207 H. 17S Toyahvale, TX (Reeves County) | Renovate 18 Civilian Conservation Corps (CCC) motel units at the San Solomon Springs Motel Court, to include repairing termite damaged woodwork; upgrade the water and wastewater utilities and campground electrical utility service from 30 amp to 50 amp; renovate camp loop restrooms. | 5166 - General Revenue Dedicated | 1200000 | 1200000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1200000
7 | 7494 | Pedernales Falls SP - Restroom Replacements 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Replace two public restroom complexes. Scope of work also includes development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 2000000 | 2000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 2000000
8 | 2865 | Huntsville SP - CCC Boathouse and Lodge Patio Wall Repairs 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Renovate Civilian Conservation Corps (CCC) boathouse to include restoring the exterior hardwood siding, repairing the roof as well as interior and exterior structural damages, and repairing and stabilizing the Lodge's patio wall. | 5166 - General Revenue Dedicated | 500000 | 500000 | 2019-04-01 | 0% | 0% | 0 | 0 | 500000
9 | 6921 | Palo Duro Canyon SP - Headquarters Replacement 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Planning and design costs for site headquarters replacement. Headquarters is currently operating out of an under-sized converted residence and the project would provide an adequately-sized and modern facility to better serve the increasing number of visitors. | 5166 - General Revenue Dedicated | 250000 | 250000 | 2018-01-31 | 0% | 0% | 0 | 0 | 250000
10 | 7504 | Garner SP - Water System Upgrades US 83 N Concan, TX 78838 (Uvalde County) | Planning and design costs to upgrade the park's overall water system, including treatment to reduce water hardness, and replace water distribution lines serving several park facilities in order to reduced system maintenance costs. | 5166 - General Revenue Dedicated | 400000 | 400000 | 2018-01-31 | 0% | 0% | 0 | 0 | 400000
11 | 7536 | Fairfield Lake SP - Wastewater Treatment Plant Repairs TX 2570 E Fairfield, TX 75840 (Freestone County) | Replace the mechanical systems at two existing wastewater treatment plants with modernized and efficient systems that are capable of saving water resources while servicing the entire park. | 5166 - General Revenue Dedicated | 650000 | 650000 | 2019-03-31 | 0% | 0% | 0 | 0 | 650000
12 | 7505 | Statewide - Unspecified State Park State Park Region 3 Restroom Replacement Program | Replace three public restroom complexes at Guadalupe State Park camping and day-use areas and one restroom complex at Government Canyon State Natural Area. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 4000000 | 4000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 4000000
13 | 6496 | Tyler SP - Residence Replacements 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Replace two obsolete staff residences with two adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structures, to include utility connections, parking and associated paving. | 5166 - General Revenue Dedicated | 1000000 | 1000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1000000
14 | 4729 | San Jacinto Battleground SHS - Residence Replacements 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Replace two residences and remove from a sensitive archaeological site. | 5166 - General Revenue Dedicated | 830000 | 830000 | 2019-03-31 | 0% | 0% | 0 | 0 | 830000
15 | 7483 | Lake Tawakoni SP - Residence Replacement 10822 FM 2475 Willis Point, TX 75169 (Hunt Van Zandt County) | Replace mobile home residence with an adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structure, to include utility connections, parking and associated paving. | 5166 - General Revenue Dedicated | 480000 | 480000 | 2019-03-31 | 0% | 0% | 0 | 0 | 480000
16 | 7358 | Mission Tejas SHS - Replace Visitor Center 120 State Park Rd. 4 Grapeland, TX 75844 (Houston County) | Replace visitor center that was destroyed by Hurricane Ike. New facility will include offices, assembly area, visitor check-in area, a new entry road and parking lot, utility extensions, and interpretive displays to educate visitors about the El Camino Real Trail. | 5166 - General Revenue Dedicated | 2713100 | 2713100 | 2018-08-31 | 60% | 0% | 0 | 0 | 2713100
17 | 7449 | Fort Leaton SHS - Roof Replacement FM 170 E Presidio, TX 79845 (Presidio County) | Replace leaking roof to preserve the historic structure and protect the building and contents from further water damage. | 5166 - General Revenue Dedicated | 413600 | 413600 | 2019-03-31 | 0% | 0% | 0 | 0 | 413600
18 | 7534 | Devil's River SP - Septic System Replacement 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Replace obsolete septic system to serve the lodge and bunkhouse facility at the Del Norte Unit. | 5166 - General Revenue Dedicated | 306800 | 306800 | 2019-03-31 | 0% | 0% | 0 | 0 | 306800
19 | 2405 | Perry R Bass Marine Research Station - Hatchery Replacement HC 02, Box 385 FM 3280 Palacios TX 77465 (Matagorda County) | Planning and design costs for replacement of the under-sized and damaged ponds, hatchery buildings, infrastructure, and jetty pump intake. | 5166 - General Revenue Dedicated | 4131500 | 4131500 | 2018-01-31 | 0% | 0% | 0 | 0 | 4131500 | Yes
20 | 7436 | Galveston Island SP - Beachside Redevelopment 14901 FM 3005 Galveston, TX 77554 (Galveston County) | Design costs to redevelop Galveston Island State Park's beachside in accordance with the GISP Redevelopment Master Plan. Construction plans include one restroom, one RV dump station, one boardwalk, multiple tent platforms, 30 multiple use campsites with electrical / water service, three group shelters, and 20 day-use picnic shelters. | 5166 - General Revenue Dedicated | 350000 | 350000 | 2018-01-31 | 0% | 0% | 0 | 0 | 350000
21 | 2888 | Monument Hill/Kreische Brewery SHS - Kreische House and Brewery Renovations 414 State Loop 92 LaGrange, TX 78945 (Fayette County) | Renovate the interior and exterior of the historic Kreische House and Brewery to include water damage repairs and renovation of the cedar shake roof, structural elements, woodwork, floors, windows, stone work, finishes, historic furniture, and water diversion landscaping to protect the structures during flooding. | 5166 - General Revenue Dedicated | 1500000 | 1500000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1500000
22 | 5983 | Sea Center Texas - Pond Electrical System Improvements 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Upgrade obsolete electrical service systems at 36 ponds with modern and energy-efficient systems that will improve hatchery operations | 5166 - General Revenue Dedicated | 1027000 | 1027000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1027000 | Yes
23 | 2081 | CCA Marine Development Center - Fish America Spawning Building and Ozone Water Purification System Replacement 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | Replace the under-sized, 30-year-old, Fish America spawning building with a new 4,000 square foot spawning building at the same location that will withstand the coastal elements. Building will include staff offices and research space and a new ozone water purification system to replace the existing non-functioning ozone system. | 5166 - General Revenue Dedicated | 1710000 | 1710000 | 2018-01-31 | 0% | 0% | 0 | 0 | 1710000 | Yes
24 | 4228 | Colorado Bend SP - Water Treatment Plant Replacement 10 miles S of Bend on Gravel Rd Bend, TX 76824 (San Saba County) | Planning and design costs to replace the water treatment plant with a new system to include a storage tank and ground water well. | 5166 - General Revenue Dedicated | 150000 | 150000 | 2018-01-31 | 0% | 0% | 0 | 0 | 150000
25 | 4932 | Sea Center Texas - Fence Replacement 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Replace three miles of perimeter fencing in and around the facility with high game fence and an entry fence in order to protect the hatchery from wildlife intrusion. | 5166 - General Revenue Dedicated | 598000 | 598000 | 2019-03-31 | 0% | 0% | 0 | 0 | 598000 | Yes
26 | 7507 | Garner SP - Dining Halls and Barracks Remodel US 83 N Concan, TX 78838 (Uvalde County) | Planning and design costs to remodel Group Dining Hall at Shady Meadows and Cypress Springs camping areas to include electrical and HVAC system upgrades, kitchen remodels, insulation for walls and ceilings, window and door repairs or replacements, roof and fascia replacement and interior wall and ceiling finish-out. Remodel Cypress Springs Barracks to include new roofs, electrical upgrades, HVAC installation, door and window repairs and replacements, and interior finish upgrades. Renovations will enhance visitors' experiences and increase revenue. | 5166 - General Revenue Dedicated | 325000 | 325000 | 2018-01-31 | 0% | 0% | 0 | 0 | 325000
27 | 4243 | Pedernales Falls SP - Water and Wastewater System Upgrades 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Planning and design costs to upgrade the obsolete water treatment plant to include four septic fields, drain fields and the water filtration system, in order to save water resources and provide an adequate system capable of saving water resources while better serving park visitors. | 5166 - General Revenue Dedicated | 106000 | 106000 | 2018-01-31 | 0% | 0% | 0 | 0 | 106000
28 | 7260 | Ray Roberts Lake SP - Johnson Branch Unit Compost Toilet Replacements 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Replace seven obsolete compost toilets with modular vault toilets to serve several trail and camping areas and revise any pathways for ADA compliance. | 5166 - General Revenue Dedicated | 834600 | 834600 | 2019-03-31 | 0% | 0% | 0 | 0 | 834600
29 | 7438 | Lake Livingston SP - Marina Area and Fishing Pier Accessibility Upgrades and Repairs 300 State Park Road 65 Livingston, TX 77351 (Polk County) | Planning and design costs to renovate the Marina Area and Fishing Pier to include: repairs to restrooms, courtesy dock, fueling stations, electrical and lighting systems, and the accessible routes between facilities and parking due to soil subsidence. | 5166 - General Revenue Dedicated | 390000 | 390000 | 2018-01-31 | 0% | 0% | 0 | 0 | 390000
30 | 4238 | Inks Lake SP - Headquarters Building Replacement - Planning and Design 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Planning and design costs to replace the under-sized headquarters building with one which includes an adequately-sized lobby and registration area and office, as well as additional restrooms, to meet staff and visitor needs. Improve traffic flow around the headquarters site. | 5166 - General Revenue Dedicated | 587500 | 587500 | 2018-01-31 | 0% | 0% | 0 | 0 | 587500
31 | 7359 | McKinney Falls SP - Smith Visitor Center Facility and Exhibit Renovation 5808 McKinney Falls Austin, TX 78744 (Travis County) | Renovate the Smith Visitor Center including upgrading a learning center to serve as an interactive classroom with new interpretive exhibits to educate students and park visitors about the El Camino Real Trail. | 5166 - General Revenue Dedicated | 859800 | 859800 | 2018-08-31 | 60% | 0% | 0 | 0 | 859800
32 | 116769 | Bastrop SP - Dam Replacement and Shore Stabilization 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Planning and design costs to replace the breached dam due to the 2015 memorial day flooding. | 5166 - General Revenue Dedicated | 1000000 | 1000000 | 2018-01-31 | 0% | 0% | 178560.08 | 435.21 | 821004.71
33 | 7360 | Goliad SHS - Custodian's Cottage Renovation and Adaptive Reuse to Interpretive Facility 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Renovate the CCC Custodian's Cottage to convert its use from administrative offices to an adequately-sized interpretive facility which will educate visitors about the El Camino Real Trail. Renovations will include restoration of formal gardens and a new parking lot. | 5166 - General Revenue Dedicated | 978400 | 978400 | 2018-08-31 | 60% | 0% | 0 | 0 | 978400
34 | 6719 | Mustang Island SP - Campground and Day-Use Area Restroom Replacements 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Replace the camp loop and day-use restrooms with two modern facilities to include replacement of obsolete mechanical systems and damaged structures. Renovations will include shower and restroom accommodations, accessible parking routes, utility upgrades and connections, a new lift station and force main, a temporary shower and restroom facility, and associated site work, in order to meet current and projected visitor demand. | 5166 - General Revenue Dedicated | 2444000 | 2444000 | 2019-03-31 | 0% | 0% | 0 | 0 | 2444000
35 | 6912 | Caddo Lake SP - Water System Upgrade 245 Park Rd 2 Karnack, TX (Harrison county) | Planning and design costs to upgrade domestic water source to treat for excessive amounts of iron in the water and prevent further damage to plumbing fixtures throughout the park. Repairs include new storage tanks, pump systems, gas chlorination system, iron removal filter, refurbished hydro pneumatic tank, electrical improvements, and a pump house. | 5166 - General Revenue Dedicated | 250000 | 250000 | 2018-01-31 | 0% | 0% | 0 | 0 | 250000
36 | 7106 | Indian Lodge - Exterior Plaster and HVAC Replacement TX Hwy 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Renovate the historic facility to include exterior plaster repairs and replace obsolete HVAC units with energy-efficient systems. | 5166 - General Revenue Dedicated | 598000 | 598000 | 2019-03-31 | 0% | 0% | 0 | 0 | 598000
37 | NA | Statewide - Unspecified State Park Boat Ramp Repairs - Statewide | Repair boat ramps at multiple state park sites which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | 5166 - General Revenue Dedicated | 1300000 | 1300000 | 2019-03-31 | 0% | 0% | 0 | 0 | 1300000
38 | 7503 | Inks Lake SP - Multiple Restroom Replacements 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Replace four public restroom complexes. Scope of work also includes development of utilities and parking. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | 5166 - General Revenue Dedicated | 4000000 | 4000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 4000000
39 | 7495 | Albert and Bessie Kronkosky SNA - Public Use Development - Planning and Design 7690 Hwy 46 West Pipe Creek, TX 78063 (Bandera County) | Planning and design costs to develop newly acquired site and install infrastructure, including utilities, parking, roadways, restrooms, toilets, and a fee collection booth at headquarters. Site development would allow public access and would meet public use needs as required by the land use agreement, which would generate revenue and provide significant outdoor opportunities. | 5166 - General Revenue Dedicated | 588000 | 588000 | 2018-01-31 | 0% | 0% | 0 | 0 | 588000
40 | 7510 | Stephen F Austin SHS - Wastewater Treatment Plant Equalization Basin Installation 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Install equalization basin at wastewater treatment plant in order to provide adequate pace flow into the plant during peak usage. | 5166 - General Revenue Dedicated | 240400 | 240400 | 2018-01-31 | 0% | 0% | 0 | 0 | 240400
41 | 4743 | Dickinson Marine Lab - New Boat Storage Facility 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | Install three metal boat storage buildings (4,960 square foot total) at the south, east and west sides of an existing paved storage area to secure the boats and protect from weather and vandalism. Storage buildings shall include power and lighting. | 5166 - General Revenue Dedicated | 507000 | 507000 | 2018-08-31 | 0% | 0% | 0 | 0 | 507000 | Yes
42 | 5922 | Abilene SP - Swimming Pool and CCC Bathhouse Repairs FM 89, 150 Park Rd 32 Tuscola, TX 79562 (Taylor County) | Planning and design costs to repair and renovate the swimming pool and CCC bathhouse. | 5166 - General Revenue Dedicated | 850000 | 850000 | 2018-01-31 | 0% | 0% | 0 | 0 | 850000
43 | 4144 | Austin Headquarters Complex - HVAC Control System Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | Replace the existing climate control system at Austin Headquarters Complex with an updated HVAC Management System which is supported by current industry vendors and allows for remote adjustments by the energy performance contractor. | 5166 - General Revenue Dedicated | 478800 | 478800 | 2018-08-31 | 0% | 0% | 0 | 0 | 478800 | Yes
44 | 4906 | Austin Headquarters Complex - Heating Ventilation Air-Conditioning (HVAC) Units Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | Replace two deteriorating, independent Liebert HVAC units in the Computer Room that houses the server at the TPWD Austin Headquarters Complex. | 5166 - General Revenue Dedicated | 144348 | 144348 | 2018-08-31 | 0% | 0% | 0 | 0 | 144348 | Yes
45 | 5786 | Austin Headquarters Complex - Fire Escape and Storage Building 4200 Smith School Road Austin, TX 78744 (Travis County) | Construct a Building D exterior stairway and fire escape as a secondary egress for safety purposes. Build a storage building on Building D rooftop to store tools, equipment, and materials used to service the rooftop equipment. | 5166 - General Revenue Dedicated | 73152 | 73152 | 2019-03-31 | 0% | 0% | 0 | 0 | 73152 | Yes
46 | TBD | Statewide - Unspecified State Park2015 Flood Damage Repairs | Funding held to address statewide 2015 flood damages. A comprehensive damage assessment has not yet been completed due to high-water levels and site inaccessibility. | 5166 - General Revenue Dedicated | 8058550 | 8058550 | 2018-01-31 | 0% | 0% | 0 | 0 | 8058550 | Yes
47 | TBD | Stephen F Austin SHS - Water Tank Repairs 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Pressure wash and repaint elevated water tank per TCEQ regulations. | 5166 - General Revenue Dedicated | 300000 | 300000 | 2018-08-31 | 0% | 0% | 0 | 0 | 300000
48 | 124545 | Huntsville SP - Dam Repair 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Fortify and repair the earthen embankment and spillway. | 5166 - General Revenue Dedicated | 4380000 | 4380000 | 2017-05-30 | 100% | 0% | 3879000 | 2650.68 | 498349.32
49 | 132907 | Bastrop SP - Group Barracks Complex Renovation 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Renovate the Group Barracks Complex, which includes four dormitory buildings and one group dinning hall. The existing obsolete restroom will be demolished; restroom/shower facilities will be added to each dormitory facility. The renovations include updating of all mechanicals, plumbing, electrical, and site modifications to become code compliant and improve visitor experience. | 5166 - General Revenue Dedicated | 3558000 | 3558000 | 2018-03-31 | 90% | 0% | 0 | 2354.49 | 3555645.51
50 | 125986 | Port Isabel Lighthouse - Light house repairs; replace corroded metal 421 East Queen Isabella Blvd Port Isabel, TX 78578 (Cameron County) | Repair and/or replace corroded exterior metal components on the Port Isabel Lighthouse at the Watch room and Lantern Levels and repaint lighthouse exterior. | 5166 - General Revenue Dedicated | 279950 | 279950 | 2017-03-31 | 30% | 0% | 0 | 618.68 | 279331.32
51 | 137824 | Longhorn Caverns - Communications System and Surge Protection 6211 Park Rd 4 So. Burnet, TX 78611 (Burnet County) | Install communication system for the cavern to protect the public in the event of an emergency. | 5166 - General Revenue Dedicated | 170000 | 170000 | 2018-08-31 | 0% | 0% | 0 | 0 | 170000
52 | 134232 | Hill Country SNA - Replace Well at Group Lodge 10600 Bandera Creed Rd Bandera, TX 78003 (Bandera County) | Install water system at group lodge to provide potable water to guests. | 5166 - General Revenue Dedicated | 365000 | 365000 | 2017-08-31 | 90% | 0% | 0 | 0 | 365000
53 | 134239 | Lost Maples SNA - Replace Potable Water Storage Tank 37221 FM 187 Vanderpool, TX 78885 (Bandera County) | Replace deteriorating drinking water storage tank with a new system in order to address a high iron content in the facility's water supply and meet TCEQ regulations. | 5166 - General Revenue Dedicated | 485000 | 485000 | 2017-08-01 | 90% | 0% | 0 | 0 | 485000
54 | 137394 | McKinney Falls SP - Smith Visitor's Center Flood Damage Repairs 5808 McKinney Falls Austin, TX 78744 (Travis County) | Repair all interior finishes, associated mechanical, electrical, and plumbing systems damaged by flood waters. Reconstruct the interior restroom to meet TDLR standards. | 5166 - General Revenue Dedicated | 570000 | 570000 | 2017-05-31 | 30% | 0% | 0 | 128.36 | 569871.64
55 | 136423 | Davis Mountains SP - Communications Bldg. Repairs TX HWY 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Replace fire damaged radio house with a permanent facility to maintain park radio communications within the park and region. | 5166 - General Revenue Dedicated | 317000 | 317000 | 2019-03-31 | 30% | 0% | 0 | 0 | 317000
56 | 112741 | Tyler SP - Headquarters Replacement 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Replace the headquarters facility with new, adequately-sized ADA-compliant building, road, parking lot, and entrance. | 5166 - General Revenue Dedicated | 3000000 | 3000000 | 2019-03-31 | 0% | 0% | 0 | 0 | 3000000
57 | 7872 | Mustang Island SP - Foundation repairs for (2) residences 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Repair two residences' pilings and beams, which are degraded due to rot. | 5166 - General Revenue Dedicated | 225000 | 225000 | 2018-08-31 | 0% | 0% | 0 | 0 | 225000
58 | TBD | Mother Neff SP - CCC Rock Tabernacle Repairs and Stabilization 1680 TX 236 HWY Moody, TX 76557 (Coryell County) | Stabilization of 4000 sq. ft. CCC built tabernacle. Work includes structural, wood, and masonry repairs, reroofing, and site construction. | 5166 - General Revenue Dedicated | 350000 | 350000 | 2018-08-31 | 100% | 0% | 0 | 0 | 350000
59 | TBD | Devil's River SP - New Visitor Check-in Building and Remodel of Existing Lodge. 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Planning and design costs to develop the newly acquired south unit. The development plan includes a small site headquarters building for visitor check-in and the remodeling of the existing lodge to include staff offices and interpretive space. The development plan is still pending TNC approval. | 5166 - General Revenue Dedicated | 150000 | 150000 | 2018-01-31 | 0% | 0% | 0 | 0 | 150000
60 | TBD | San Jacinto Battleground SHS - Reflection Pool Structural Assessment 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Professional engineering report and assessment for stabilizing and repairing the retaining walls around the reflecting pool. | 5166 - General Revenue Dedicated | 100000 | 100000 | 2018-01-31 | 0% | 0% | 0 | 0 | 100000
61 | 127758 | Sea Center Texas - Flounder Building 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Construct new 3000 square foot flounder spawning building. Building will provide additional hatchery floor space for flounder bloodstock and incubation equipment and include a separate room for culture of live feeds. | 5166 - General Revenue Dedicated | 968500 | 968500 | 2018-08-31 | 60% | 0% | 0 | 0 | 968500 | Yes
|  |  |  | Totals: | 91000000 | 91000000 |  |  |  | 4057560.08 | 6187.42 | 86936252.5
0

## TPWD Notes 12.15
| Agency: | Texas Parks and Wildlife Department
| Date: | December 15,2015
| Prepared by: | Infrastructure Division
Project Priority | Supplemental Information
19 | New Project - was not included on the report submitted to the JOC on September 15th because the $91M in Deferred Maintenance is not exclusive to State Parks, but includes $8,942,000 for Coastal Fisheries
22 | New Project - was not included on the report submitted to the JOC on September 15th because the $91M in Deferred Maintenance is not exclusive to State Parks, but includes $8,942,000 for Coastal Fisheries
23 | New Project - was not included on the report submitted to the JOC on September 15th because the $91M in Deferred Maintenance is not exclusive to State Parks, but includes $8,942,000 for Coastal Fisheries
25 | New Project - was not included on the report submitted to the JOC on September 15th because the $91M in Deferred Maintenance is not exclusive to State Parks, but includes $8,942,000 for Coastal Fisheries
41 | New Project - was not included on the report submitted to the JOC on September 15th because the $91M in Deferred Maintenance is not exclusive to State Parks, but includes $8,942,000 for Coastal Fisheries
43 | New Project - was not included on the report submitted to the JOC on September 15th because the $91M in Deferred Maintenance is not exclusive to State Parks, but includes $696,300 for the Austin HQ Complex.
44 | New Project - was not included on the report submitted to the JOC on September 15th because the $91M in Deferred Maintenance is not exclusive to State Parks, but includes $696,300 for the Austin HQ Complex.
45 | New Project - was not included on the report submitted to the JOC on September 15th because the $91M in Deferred Maintenance is not exclusive to State Parks, but includes $696,300 for the Austin HQ Complex.
46 | Estimated Budget was originally submitted as $10M, but only $8,058,550 will be funded by Deferred Maintenance funds.
61 | New Project - was not included on the report submitted to the JOC on September 15th because the $91M in Deferred Maintenance is not exclusive to State Parks, but includes $8,942,000 for Coastal Fisheries
Deleted | The following State Park projects have been removed from this report because they are not funded with Deferred Maintenance Funds: Franklin Mountains Visitor's Center ($3,600,000), Palo Pinto New Park Development (2,678,899), and Fort Boggy Phase 2 ($1,100,000).

## TMD 6.16
| Agency: | Texas Military Department - Agency 401
| Date: | 2016-06-09 | [9 empty] | 2016-06-09
Prepared by:
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 48150090 | Westheimer Readiness Center, 15150 Westheimer Parkway, Houston 77082 | The project will repair 69,029 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 2000000 | 2000000 | 3 QTR FY18 | 100% | 0% | 143347.44 | 16570.44 | 1840082.12 | yes
2 | 48140070 | Pasadina Readiness Center, 2917 San Augustine Avenue, Pasadina 77503 | The project will repair an existing 19,064 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1500000 | 1500000 | 2 QTR FY18 | 100% | 0% | 1472147.44 | 12290.44 | 15562.12 | yes
3 | 48140040 | San Marcos Readiness Center, 201 City Park, San Marcos 78666 | The project will repair an existing 10,776 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1125000 | 1125000 | 2 QTR FY18 | 100% | 0% | 913695.29 | 70898.13 | 140406.58 | yes
4 | 48150110 | Grand Prairie, 1013 Lake Crest Drive, Grand Prairie 75051 | The project will repair 60,943 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 3875000 | 3875000 | 3 QTR FY18 | 100% | 0% | 3774360.04 | 9112.98 | 91526.98 | yes
5 | 48160100 | Fairview Readiness Center, 4601 Fairview Drive, Austin 78731 | The project will repair an existing 50,603 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 1375000 | 1375000 | 3 QTR FY18 | 100% | 0% | 160997.16 | 0 | 1214002.84 | yes
6 | 48130053 | Camp Mabry Readiness Center (Bldg 75), 2200 West 35th Street, Austin, 78703 | The project will repair an existing 72,358 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 4000000 | 4000000 | 4 QTR FY19 | 0% | 0% | 0 | $- | 4000000 | yes
7 | 48150060 | El Paso Hondo Pass Readiness Center, 9100 Gateway North, El Paso 79924 | The project will repair an existing 44,555 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 2875000 | 2875000 | 4 QTR FY19 | 0% | 0% | 0 | $- | 2875000 | yes
8 | 48170090 | Temple Readiness Center, 8502 Airport Road. Temple 76502 | The project will repair an existing 46,058 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 1437500 | 1437500 | 4 QTR FY19 | 0% | 0% | 0 | $- | 1437500 | yes
9 | 48140061 | Denison Readiness Center, 1700 Loy Lake, Denison 75020 | The project will repair an existing 18,541 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1375000 | 1375000 | 4 QTR FY19 | 0% | 0% | 0 | $- | 1375000 | yes
0
0
0
0
|  |  |  | Totals: | 19562500 | 19562500 |  |  |  | 6464547.37 | 108871.99 | 12989080.64

## TMD Notes 6.16
| Agency: | Texas Military Department - Agency 401
| Date: | 2016-06-09
Prepared by:
Project Priority | Supplemental Information
| Total Estimated Project Budget | Federal Share | Federal Share Obligated | Remaining Federal Share | Comments
1 | 8000000 | 6000000 | 491261 | 5508739 | Project is in the Bidding Phase. Bids open 30JUN16.
2 | 3000000 | 1500000 | 1283203.56 | 216796.44 | Construction contract awarded to SMR Corporation. NTP pending.
3 | 2250000 | 1125000 | 931946.16 | 193053.84 | Construction contract awarded to The Barr Company. Construction kick-off is 7JUN16. NTP is 14JUN16
4 | 7750000 | 3875000 | 2280589.3 | 1594410.7 | Construction contract to be awarded to SMR Corporation pending bid review.
5 | 5500000 | 4125000 | 355317.25 | 3769682.75 | Project is in the Bidding Phase. Bids open 16AUG16.
11282682.73

## TMD 9.16
| Agency: | Texas Military Department - Agency 401
| Date: | 2016-09-08 | [9 empty] | 2016-09-08
| Prepared by: | Leslie Gervais
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 4th Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 48150090 | Westheimer Readiness Center, 15150 Westheimer Parkway, Houston 77082 | The project will repair 69,029 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 2000000 | 1252102.44 | 3 QTR FY18 | 100% | 0% | 1109771.8 | 142330.64 | 0 | yes
2 | 48140070 | Pasadina Readiness Center, 2917 San Augustine Avenue, Pasadina 77503 | The project will repair an existing 19,064 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1500000 | 1472147.44 | 2017-07-05 | 100% | 0% | 1373615.4 | 98532.04 | 0 | yes
3 | 48140040 | San Marcos Readiness Center, 201 City Park, San Marcos 78666 | The project will repair an existing 10,776 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1125000 | 923601.69 | 2016-12-21 | 100% | 5% | 841207.26 | 82394.43 | 0 | yes
4 | 48150110 | Grand Prairie, 1013 Lake Crest Drive, Grand Prairie 75051 | The project will repair 60,943 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 3875000 | 3870654.88 | 3 QTR FY18 | 100% | 0% | 3580334.19 | 290320.69 | 0 | yes
5 | 48160100 | Fairview Readiness Center, 4601 Fairview Drive, Austin 78731 | The project will repair an existing 50,603 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 1375000 | 1615540.55 | 3 QTR FY18 | 100% | 0% | 1466547.17 | 148993.38 | 0 | yes
6 | 48130053 | Camp Mabry Readiness Center (Bldg 75), 2200 West 35th Street, Austin, 78703 | The project will repair an existing 72,358 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 4000000 | 4000000 | 4 QTR FY19 | 95% | 0% | 0 | 0 | 4000000 | yes
7 | 48150060 | El Paso Hondo Pass Readiness Center, 9100 Gateway North, El Paso 79924 | The project will repair an existing 44,555 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 2875000 | 3165801 | 4 QTR FY19 | 5% | 0% | 270614.9 | 20186.1 | 2875000 | yes
8 | 48170090 | Temple Readiness Center, 8502 Airport Road. Temple 76502 | The project will repair an existing 46,058 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 1437500 | 1712295 | 4 QTR FY19 | 5% | 0% | 129618.3 | 145176.7 | 1437500 | yes
9 | 48140061 | Denison Readiness Center, 1700 Loy Lake, Denison 75020 | The project will repair an existing 18,541 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1375000 | 1550357 | 4 QTR FY19 | 5% | 0% | 160028.2 | 15328.8 | 1375000 | yes
|  |  |  | Totals: | 19562500 | 19562500 |  |  |  | 8931737.22 | 943262.78 | 9687500

## TMD 3.16
| Agency: | Texas Military Department - Agency 401
| Date: | 2016-03-11 | [9 empty] | 2016-03-11
Prepared by:
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 48150090 | Westheimer Readiness Center, 15150 Westheimer Parkway, Houston 77082 | The project will repair 69,029 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 2000000 | 2000000 | 3 QTR FY18 | 65% | 0% | 135055.62 | 0 | 1864944.38 | yes
2 | 48140070 | Pasadina Readiness Center, 2917 San Augustine Avenue, Pasadina 77503 | The project will repair an existing 19,064 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1500000 | 1500000 | 2 QTR FY18 | 100% | 0% | 97999.03 | 0 | 1402000.97 | yes
3 | 48140040 | San Marcos Readiness Center, 201 City Park, San Marcos 78666 | The project will repair an existing 10,776 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1125000 | 1125000 | 2 QTR FY18 | 100% | 0% | 79539.29 | 22694 | 1022766.71 | yes
4 | 48150110 | Grand Prairie, 1013 Lake Crest Drive, Grand Prairie 75051 | The project will repair 60,943 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 3875000 | 3875000 | 3 QTR FY18 | 100% | 0% | 241645.94 | 0 | 3633354.06 | yes
5 | 48160100 | Fairview Readiness Center, 4601 Fairview Drive, Austin 78731 | The project will repair an existing 50,603 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 1375000 | 1375000 | 3 QTR FY18 | 65% | 0% | 90060.68 | 0 | 1284939.32 | yes
6 | 48130053 | Camp Mabry Readiness Center (Bldg 75), 2200 West 35th Street, Austin, 78703 | The project will repair an existing 72,358 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 4000000 | 4000000 | 4 QTR FY19 | 0% | 0% | 0 | $- | 4000000 | yes
7 | 48150060 | El Paso Hondo Pass Readiness Center, 9100 Gateway North, El Paso 79924 | The project will repair an existing 44,555 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 2875000 | 2875000 | 4 QTR FY19 | 0% | 0% | 0 | $- | 2875000 | yes
8 | 48170090 | Temple Readiness Center, 8502 Airport Road. Temple 76502 | The project will repair an existing 46,058 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 1437500 | 1437500 | 4 QTR FY19 | 0% | 0% | 0 | $- | 1437500 | yes
9 | 48140061 | Denison Readiness Center, 1700 Loy Lake, Denison 75020 | The project will repair an existing 18,541 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1375000 | 1375000 | 4 QTR FY19 | 0% | 0% | 0 | $- | 1375000 | yes
0
0
0
0
|  |  |  | Totals: | 19562500 | 19562500 |  |  |  | 644300.56 | 22694 | 18895505.44

## TMD Notes 3.16
| Agency: | Texas Military Department - Agency 401
| Date: | 2016-03-11
Prepared by:
Project Priority | Supplemental Information
| Total Estimated Project Budget | Federal Share | Federal Share Encumbered | Remaining Federal Share | Comments
1 | 8000000 | 6000000 | 473306 | 5526694
2 | 3000000 | 1500000 | 141629.75 | 1358370.25 | Project is in the Bidding Phase. Bids open 4/28/16.
3 | 2250000 | 1125000 | 101506 | 1023494 | Project is in the Bidding Phase. Bids open 3/24/16.
4 | 7750000 | 3875000 | 353139 | 3521861
5 | 5500000 | 4125000 | 331575 | 3793425 | Project has a change order pending due to an increased scope to address life, safety, code and building access issues on the Navy side of the building. Construction will likely shift to 1 QTR FY17.
6 | 8000000 | 4000000 | 0 | 4000000 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
7 | 5750000 | 2875000 | 0 | 2875000 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
8 | 5750000 | 4312500 | 0 | 4312500 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
9 | 2750000 | 1375000 | 0 | 1375000 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
|  | 29187500 | 1401155.75 | 27786344.25

## TMD 12.15
| Agency: | Texas Military Department - Agency 401
| Date: | 2015-12-15 | [9 empty] | 2015-11-30
| Prepared by: | Tim Anderson, Deputy CFMO
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 48150090 | Westheimer Readiness Center, 15150 Westheimer Parkway, Houston 77082 | The project will repair 69,029 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 2000000 | 2000000 | 3 QTR FY18 | 10% | 0% | 144000 | 0 | 1856000 | yes
2 | 48140070 | Pasadina Readiness Center, 2917 San Augustine Avenue, Pasadina 77503 | The project will repair an existing 19,064 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1500000 | 1500000 | 2 QTR FY18 | 10% | 0% | 108000 | 0 | 1392000 | yes
3 | 48140040 | San Marcos Readiness Center, 201 City Park, San Marcos 78666 | The project will repair an existing 10,776 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1125000 | 1125000 | 2 QTR FY18 | 35% | 0% | 81000 | 0 | 1044000 | yes
4 | 48150110 | Grand Prairie Readiness Center, 1013 Lake Crest Drive, Grand Prairie 75051 | The project will repair 60,943 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 3875000 | 3875000 | 3 QTR FY18 | 10% | 0% | 279000 | 0 | 3596000 | yes
5 | 48160100 | Fairview Readiness Center, 4601 Fairview Drive, Austin 78731 | The project will repair an existing 50,603 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 1375000 | 1375000 | 3 QTR FY18 | 10% | 0% | 99000 | 0 | 1276000 | yes
6 | 48130053 | Camp Mabry Readiness Center (Bldg 75), 2200 West 35th Street, Austin, 78703 | The project will repair an existing 72,358 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 4000000 | 4000000 | 4 QTR FY19 | 0% | 0% | 0 | 0 | 4000000 | yes
7 | 48150060 | El Paso Hondo Pass Readiness Center, 9100 Gateway North, El Paso 79924 | The project will repair an existing 44,555 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 2875000 | 2875000 | 4 QTR FY19 | 0% | 0% | 0 | 0 | 2875000 | yes
8 | 48170090 | Temple Readiness Center, 8502 Airport Road. Temple 76502 | The project will repair an existing 46,058 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 25%, Federal Funds 75% | 1437500 | 1437500 | 4 QTR FY19 | 0% | 0% | 0 | 0 | 1437500 | yes
9 | 48140061 | Denison Readiness Center, 1700 Loy Lake, Denison 75020 | The project will repair an existing 18,541 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | GR 50%, Federal Funds 50% | 1375000 | 1375000 | 4 QTR FY19 | 0% | 0% | 0 | 0 | 1375000 | yes
0
0
0
0
0
|  |  |  | Totals: | 19562500 | 19562500 |  |  |  | 711000 | 0 | 18851500

## TMD Notes 12.15
| Agency: | Texas Military Department - Agency 401
| Date: | 2015-12-15
Prepared by:
Project Priority | Supplemental Information
| Project Name & Location | Total Estimated Project Budget | Estimated Federal Share | Federal Share Encumbered | Remaining Federal Share | Note 1 | Note 2 | Note 3
1 | Westheimer Readiness Center, 15150 Westheimer Parkway, Houston 77082 | 8000000 | 6000000 | 437390 | 5562610 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
2 | Pasadina Readiness Center, 2917 San Augustine Avenue, Pasadina 77503 | 3000000 | 1500000 | 111500 | 1388500 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
3 | San Marcos Readiness Center, 201 City Park, San Marcos 78666 | 2250000 | 1125000 | 81000 | 1044000 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
4 | Grand Prairie Readiness Center, 1013 Lake Crest Drive, Grand Prairie 75051 | 7750000 | 3875000 | 279000 | 3596000 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
5 | Fairview Readiness Center, 4601 Fairview Drive, Austin 78731 | 5500000 | 4125000 | 297000 | 3828000 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
6 | Camp Mabry Readiness Center (Bldg 75), 2200 West 35th Street, Austin, 78703 | 8000000 | 4000000 | 0 | 4000000 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
7 | El Paso Hondo Pass Readiness Center, 9100 Gateway North, El Paso 79924 | 5750000 | 2875000 | 0 | 2875000 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
8 | Temple Readiness Center, 8502 Airport Road. Temple 76502 | 5750000 | 4312500 | 0 | 4312500 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
9 | Denison Readiness Center, 1700 Loy Lake, Denison 75020 | 2750000 | 1375000 | 0 | 1375000 | Project is on schedule | Fed Share for construction pending budget approval | Fed Funding requirement has been communicated to National Guard Bureau as "STAR Campaign"
|  |  |  | 1205890 | 27981610

## Legend
Report Components Legend:
Project Priority | This column represents a sequential numbering of projects in priority order, beginning with "1". If a project needs to be identified among multiple rows because it has several components, continue to use the same project number.
Agency ID | For Agency Use Only: this column is for the recording of internal agency project identification numbers for agency reference purposes.
Project Name and Location | If the project name is different than the facility where the project is being performed, indicate the facility name in parenthesis after the project name. Also, indicate the location of the project following the project name. This location information will include physical address, district and/or region where the project is located.
Project Description | Describe in detail the repairs to be completed.
Source of Funding (MOF) | Indicate the Method of Finance (MOF) used for the project.
Original Estimated Project Budget | Report the estimated project cost as originally estimated and presented during the December 2015 project report submitted to this committee. Amount shall total Article IX appropriated amounts.
Current Estimated Project Budget | Report the estimated project cost as of the current reporting quarter. These amounts are subject to quarterly change.
Estimated Substantial Completion Date | Input estimated project substantial completion date. This shall be reflective of the estimated date when the project or designated portion thereof is sufficiently complete in accordance with the contracted agreement so that the facility can be occupied or utilized for its intended use. This information is subject to quarterly change and is to be reported as of the quarter of the report being submitted.
% Completion | Estimate the percentage completion of the project in the design and construction phases. This information is subject to quarterly change and is to be reported as of the quarter of the report being submitted.
FY 2016-17 Encumbered | Indicate the amount encumbered/obligated on this project within the current biennium (FY 2016-17).
FY 2016-17 Expended | Indicate the amount expended on this project within the current biennium (FY 2016-17).
Remaining Project Balance | The remaining balance after deducting the FY 2016-17 Encumbered and Expended columns from the Current Estimated Project Budget column.
Supplemental Notes | Indicate with a "yes" if supplemental notes are included for this project. On the "Supplemental Notes" worksheet describe in detail any deviations or changes in the project priority, scope, cost or timeline.