## Sheet1
FY 18-19 Report
| Original Estimated Project Budget | Current Estimated Project Budget | FY 2018-19 Encumbered | Percent Encumbered | FY 2018-19 Expended | Percent Expended | Remaining Project Balance | Percent Remaining
December 2017 Quarterly Report
DPS | 12000000 | 12000000 | 143908 | 1.199% | 27191 | 0.2266% | 11828901 | 98.57%
TMD | 11000000 | 9777775 | 1491460 | 15.25% | 0 | 0% | 8286315 | 84.75%
TPWD | 66185665 | 66185665 | 964733 | 1.458% | 820525 | 0% | 64400407 | 97.3%
TDCJ | 41635989 | 41999389 | 2778596 | 6.616% | 845573 | 2.013% | 38375220 | 91.37%
TFC | 90000000 | 90000000 | 0 | 0% | 0 | 0% | 90000000 | 100%
TXDOT | 50000000 | 50000000 | 605000 | 1.21% | 0 | 0% | 49395000 | 98.79%
THC | 6350000 | 6350000 | 721825 | 11.37% | 63355 | 0.9977% | 5564820 | 87.63%
SPB | 4700000 | 4700000 | 9854 | 0.2097% | 0 | 0% | 4690146 | 99.79%
DSHS | 1800000 | 1800000 | 0 | 0% | 0 | 0% | 1800000 | 100%
HHSC- State Hospitals | 80000000 | 79632659 | 970829 | 1.219% | 0 | 0% | 78661830 | 98.78%
HHSC- State Supported Living Centers | 78600000 | 78515321 | 0 | 0% | 0 | 0% | 78515321 | 100%
JJD | 12100000 | 12100000 | 341665 | 2.824% | 0 | 0% | 11758335 | 97.18%
Totals | 454371654 | 453060809 | 8027870 | 1.772% | 1756644 | 0.3877% | 443276295 | 97.84%
October Hearing
DPS | 12000000 | 12000000 | 0 | 0% | 0 | 0% | 12000000 | 100%
TMD | 11000000 | 11000000 | 0 | 0% | 0 | 0% | 11000000 | 100%
TPWD | 66185665 | 66185665 | 0 | 0% | 0 | 0% | 66185665 | 100%
TDCJ | 41635989 | 41635989 | 609388 | 1.464% | 300361 | 0.7214% | 40726240 | 97.81%
TFC | 90000000 | 90000000 | 0 | 0% | 0 | 0% | 90000000 | 100%
TXDOT | 50000000 | 50000000 | 0 | 0% | 0 | 0% | 50000000 | 100%
THC | 6350000 | 6350000 | 1000000 | 15.75% | 0 | 0% | 5350000 | 84.25%
SPB | 4700000 | 4700000 | 9854 | 0.2097% | 0 | 0% | 4690146 | 99.79%
DSHS | 1800000 | 1800000 | 0 | 0% | 0 | 0% | 1800000 | 100%
HHSC- State Hospitals | 79923257 | 79923257 | 0 | 0% | 0 | 0% | 79923257 | 100%
HHSC- State Supported Living Centers | 79862729 | 79862729 | 0 | 0% | 0 | 0% | 79862729 | 100%
JJD | 12100000 | 12100000 | 0 | 0% | 0 | 0% | 12100000 | 100%
Totals | 455557640 | 455557640 | 1619242 | 0.3554% | 300361 | 0.06593% | 453638037 | 99.58%

## DPS
| Agency: | Texas Department of Public Safety - 0405
| Date: | 2017-12-15
| Prepared by: | 85th Legislature - $12M DM Projects
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Current Estimated Project Budget (FY18 2nd Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | Committed | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | ST-TEMP-18-62601 | Statewide DM Staff | Professional staff employed by DPS and/or contractors to administer DM projects | Economic Stabilization Fund (ESF) | 750000 | 750000 | 750000 | NA | NA | NA |  |  |  | 750000 | No
2 | ST-IWMS-18-62930 | Statewide Integrated Workplace Management System | A computerized Integrated Workplace Management system (IWMS) that is web based and can be implemented statewide is needed to track and plan for maintenance of DPS facilities. As funding permits, this will include the implementation of space management, inventory management, lease management, and environmental sustainability integration. | ESF | 1700000 | 1700000 | 1700000 | 2019-08-31 | 90% | 0% | 1700000 |  |  | 1700000 | No
3 | ST-FCA-18-62931 | Statewide Facility Condition Assessment | Statewide Assessment: An updated professional statewide Facility Condition Assessment study is needed to identify current deferred maintenance and capital renewal projects and associated costs. | ESF | 1300000 | 1300000 | 1300000 | 2019-08-31 | 70% | 0% | 1300000 |  |  | 1300000 | No
4 | ST-SEC-18-62933 | Statewide Security Upgrade/Replacements | Replace and upgrade access controls, video surveillance systems, door hardware, exterior doors, replace broken/old cameras, add cameras, and add access control where needed. | ESF | 1000000 | 387000 | 387000 | 2019-08-31 | 0% | 0% |  |  |  | 387000 | No
5 | ST-UST-18-62934 | Statewide Fuel System Removal/Replace | Remove underground storage tanks (UST) and replace with above ground storage tanks (Midland UST bulk fuel Removal/install AST for generator; Remove Plainview UST bulk fuel, Remove Sulphur Springs UST bulk fuel; Remove San Antonio diesel UST, inventory automation of various fuel systems) | ESF | 450000 | 237745 | 237745 | 2019-08-31 | 100% | 0% |  |  |  | 237745 | No
5 | ST-UST-18-62934 | Midland District Office (Reg 4) Fuel System Removal 2405 S. Loop 250 West Midland, Texas 79703 | Midland UST Tank removal and AST installation | ESF |  | 72255 | 72255 | 2018-08-31 | 100% | 0% |  | 72255 |  | 0 | No
5 | ST-UST-18-62934 | Plainview Area Office (Reg 5) Fuel System Removal 1108 South Columbia/Business I-27 Plainview, Texas 79072 | Plainview UST 4,000G Tank removal | ESF |  | 40000 | 40000 | 2018-08-31 | 100% | 0% |  |  |  | 40000 | No
5 | ST-UST-18-62934 | Sulphur Springs Area Office (Reg 1) Fuel System Removal 1528 E. Shannon Road Sulphur Springs, Texas 75482 | Sulphur Springs UST 4,000G Tank and pit water removal | ESF |  | 60000 | 60000 | 2018-08-31 | 100% | 0% |  |  |  | 60000 | No
5 | ST-UST-18-62934 | San Antonio Regional Office (Reg 6) Fuel System Removal 6502 S. New Braunfels Ave. San Antonio, Texas 78223 | San Antonio UST 2,500G Tank removal | ESF |  | 40000 | 40000 | 2018-08-31 | 100% | 0% |  |  |  | 40000 | No
6 | ST-TEST-18-62935 | Statewide Support Project Consultants | Funding for design team, testing, consulting, commissioning, CMT, inspections type of expenditures associated with projects. | ESF | 300000 | 300000 | 300000 | 2019-08-31 | 0% | 0% |  |  |  | 300000 | No
7 | HQ-C-18-62936 | Austin HQ (Building C) HVAC System Replacement 5805 North Lamar Blvd Austin, Texas 78752 | HVAC System including piping, chiller, add DDC, etc. | ESF | 2950000 | 2950000 | 2950000 | 2019-08-31 | 0% | 0% |  |  |  | 2950000 | No
8 | HQ-E-18-62937 | Austin HQ (Building E) Chiller Replacement 5805 North Lamar Blvd Austin, Texas 78752 | Replace chiller | ESF | 275000 | 275000 | 275000 | 2019-08-31 | 0% | 0% |  |  |  | 275000 | No
9 | 2-HHQ-18-62938 | Houston Regional Headquarters (West Road) Crime Lab (Reg 2) Chiller Replacement 12230 West Road Jersey Village, Texas 77065 | Replace second chiller | ESF | 275000 | 340000 | 340000 | 2018-05-31 | 99% | 0% |  |  |  | 340000 | No
10 | 2-HHQ-18-62939 | Houston Regional Headquarters (Reg 2) Chiller Replacement 12230 West Road Jersey Village, Texas 77065 | Replace both chillers | ESF | 375000 | 680000 | 680000 | 2018-08-31 | 0% | 0% |  |  |  | 680000 | No
11 | 5-PLA-18-62940 | Plainview Area Office (Reg 5) Roof Replacement 1108 South Columbia/Business I-27 Plainview, Texas 79072 | Roof Replacement (approx. 2,800 sf - addition) | ESF | 150000 | 150000 | 150000 | 2018-03-01 | 100% | 0% | 55000 |  |  | 150000 | No
12 | 2-VIC-18-62941 | Victoria sub district Office (Reg 6) CID Roof Replacement 8802 North Navarro Victoria, Texas 77904 | Roof Replacement of CID building | ESF | 100000 | 343000 | 65000 | 2018-03-31 | 100% | 0% | 65000 |  |  | 65000 | Yes
13 | HQ-CAM-18-62942 | Austin HQ (Campus) Campus Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Repave deteriorated asphalt with concrete on main drive lanes from Guadalupe to loading dock of Building A. Repair and expand paving at the Director's parking lot (building A) |  | 583000 | 583000 | 583000 | 2019-08-31 | 0% | 0% |  |  |  | 583000 | Yes
14 | HQ-CAM-18-62942 | Austin HQ (Campus) Campus Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Building E & G; Requires specialized EIFS clean, repair, paint, caulk, paint exterior doors |  | 200000 | 200000 | 200000 | 2019-08-31 | 0% | 0% |  |  |  | 200000 | Yes
15 | HQ-CAM-18-62942 | Austin HQ (Campus) Campus Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Building A, B & C Annex; requires specialized repointing of joints, caulking and cleaning of historic limestone surfaces. Pain exterior doors and handrails. |  | 317000 | 317000 | 317000 | 2019-08-31 | 0% | 0% |  |  |  | 317000 | Yes
16 | HQ-CAM-18-62942 | Austin HQ (Campus) Campus Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Buildings D, F4, F5, H, K, L, O, & Q; Requires general caulking, repointing, cleaning and painting of block/metal/wood surfaces. Paint exterior doors and handrails. |  | 125000 | 125000 | 125000 | 2019-08-31 | 0% | 0% |  |  |  | 125000 | Yes
17 | HQ-CAM-18-62942 | Austin HQ (Campus) Campus Upgrade 5805 North Lamar Blvd Austin, Texas 78752 | Repair and expand existing irrigation systems |  | 150000 | 150000 | 150000 | 2018-08-31 | 0% | 0% |  |  |  | 150000 | Yes
18 | ST-CON-18-62932 | Statewide Unexpected DM repairs/Project Contingency | Statewide Unexpected DM repairs/Project Contingency: Emergency deferred maintenance repairs includes all trades listed above and unforeseen emergency building/infrastructure repairs as necessary for prior biennium and current DM projects. | ESF | 1000000 | 821822.5 | 1100840.1 | 2019-08-31 | 0% | 0% |  |  |  | 1100840.1 | No
19 | HQ-ADO-18 | Austin District Office (Reg 6) - Roof Replacement Change Order | Add to address hidden conditions revealed during the roof replacement | ESF |  | 19230 | 19230 | 2017-12-31 | 100% | 0% |  |  |  | 19230 | No
| ST-CON-18-62932 | Laredo Crime Laboratory (Reg 3) 1901 Bob Bullock Loop Laredo, Texas 78043 | Repairs required after an electrical storm for the Laredo Fire Alarm Panel | ESF |  | 8285.4 | 8285.4 | 2018-01-15 | 100% | 75% |  | 8285.4 |  | 0 | No
| ST-CON-18-62932 | Houston Regional Headquarters (West Road) Crime Lab (Reg 2) Chiller Repair 12230 West Road Jersey Village, Texas 77065 | Repairs to crime lab chiller #2. | ESF |  | 4100 | 4100 | 2017-12-08 | 100% | 100% |  |  | 4100 | 0 | No
| ST-CON-18-62932 | Houston Regional Headquarters (West Road) Crime Lab (Reg 2) Boiler Repair 12230 West Road Jersey Village, Texas 77065 | Repairs to the Houston crime lab boiler | ESF |  | 4732 | 4732 | 2018-01-02 | 100% | 5% |  | 4732 |  | 0 | No
| ST-CON-18-62932 | Houston Regional Headquarters (West Road) (Reg 2) Boiler Replacement 12230 West Road Jersey Village, Texas 77065 | Replace boiler | ESF |  | 35000 | 35000 | 2018-01-31 | 100% | 5% |  | 35000 |  | 0 | No
| ST-CON-18-62932 | Decatur Area Office (Reg 1) HVAC Repairs 2000 S. Trinity St Decatur, Texas 76234 | Replace HVAC | ESF |  | 10079 | 10079 | 2017-10-05 | 100% | 100% |  |  | 10079 | 0 | No
| ST-CON-18-62932 | Corpus Christi Crime Lab (Reg 3) RTU Coil Replacement 1922 S. Padre Island Drive Corpus Christi, Texas 78416 | Repairs to RTU 1 and 2 | ESF |  | 18653 | 18653 | 2018-01-31 | 100% | 0% |  | 18653 |  | 0 | No
| ST-CON-18-62932 | San Antonio Regional HQ (Reg 6) ATG Repair 6502 South New Braunfels Ave San Antonio, Texas 78223 | ATG repairs and upgrades to the leak detection system | ESF |  | 20000 | 20000 | 2018-03-31 | 100% | 0% | 20000 |  |  | 20000 | No
| ST-CON-18-62932 | Odessa Area Office (Reg 4) Repair Natural Gas Line 1910 IH-20 West Odessa, Texas 79762 | Repair main Natural Gas line from meter to building | ESF |  | 6000 | 4982.4 | 2017-12-15 | 100% | 95% |  | 4982.4 |  | 0 | No
| ST-CON-18-62932 | Babcock Area Office (Reg 6) Roof Repair 1258 Babcock Rd San Antonio, TX 78228 | Repair roof | ESF |  | 2500 | 2500 | 2017-10-06 | 100% | 100% |  |  | 2500 | 0 | No
| ST-CON-18-62932 | Childress District Office (Reg 6) Roof Repair 1700 Ave. F Northwest Childress, Texas 79201 | Repair leak in main office roof | ESF |  | 4000 | 4000 | 2017-10-20 | 100% | 100% |  |  | 4000 | 0 | No
| ST-CON-18-62932 | Weslaco Regional Office (Reg 3) RTU Coil Replacement 2525 N. International Blvd Weslaco, TX 78596 | Coil Replacement for RTUs 5,8 & 9 | ESF |  | 39086 | 39086 | 2018-03-31 | 100% | 0% | 39086 |  |  | 39086 | No
| ST-CON-18-62932 | San Antonio Regional HQ (Reg 6) Roof Repair 6502 South New Braunfels Ave San Antonio, Texas 78223 | Roof Repair on portable building | ESF |  | 3400 | 3400 | 2017-11-03 | 100% | 100% |  |  | 3400 | 0 | No
| ST-CON-18-62932 | Austin HQ (Building B) HVAC Repair 5805 North Lamar Blvd Austin, Texas 78752 | Replaced compressor for HVAC controls serving Building B. | ESF |  | 3112.1 | 3112.1 | 2017-10-02 | 100% | 100% |  |  | 3112.1 | 0 | No
|  |  |  | Totals: | 12000000 | 12000000 | 12000000 |  |  |  |  | 143907.8 | 27191.1 | 11828901.1
Note on H21: tw08469: 12/4/17 using index 26901 for Victoria H. Harvey. Moved $278K to contingency per WAM.

## DPS Supp.
| Agency: | Texas Department of Public Safety - 0405
| Date: | 2017-12-15
| Prepared by: | Tavia Wendlandt
Project Priority | Supplemental Information
12 | 85th Leg - FEMA expected to reimburse for damage incurred due to Hurricane Harvey. Reduced line item by $278,000 and moved to contingency.
13-17 | 85th Leg - First quarter reflected one comprehensive project for HQ campus upgrades. We updated the report to show the primary components of the planned campus upgrade. Priority #13, the paving project, will be overseen by TFC.
104 | 84th Leg - Project scope was absorbed by an ongoing remodel project and DM funding was not utilized.
106 (Cont) | 84th Leg - Rider 40 appropriations ($17.7M) - project savings of $761,148 will offset contingency negative balance of $638,957 for a positive remaining balance of $121,571
160 | 84th Leg - New priority DM project proposed utilizing the $200M bond funding to upgrade vacated crime laboratory space to help relieve overcrowding at the Headquarters complex. This is an approved bond project with TPFA. Recieved email from LBB approving the project. Original proposed DM projects have been moved to a separate tab within the spreadsheet as they have become a lower agency priority compared to Building B. If there are any savings from the approved DM projects, then we will begin to work on these currently unfunded DM projects.
Waiting for LBB approval of funding to begin project; Excerpt from letter to LBB: “Per Article IX Sec. 14.03 (h) (3) Limitation on Expenditures – Capital Budget, the Department of Public Safety requests to transfer appropriations from a capital budget item to a non-capital budget item. Capital budget authority of $21, 000,000 is included in Article V, Rider 2 b. (2) Deferred Maintenance for deferred maintenance projects at the Department of Public Safety, however additional appropriations of $21,000,000 were not provided. This situation results in a $21,000,000 reduction to our Agency’s operations which cause undue hardship on the Agency’s programs. The Department requests a transfer of $11,139,565 in fiscal year 2016 and $9,860,435 in fiscal year 2017 from a capital budget item to a non-capital budget item.”

## TMD
| Agency: | Texas Military Department - Agency 401
| Date: | 2017-12-19 | [9 empty] | 2017-12-19
Prepared by:
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 48120206 | Camp Mabry Admin Offices 2200 W 35th St Bldg 1 Austin, 78730 | The project will repair 22,702 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 2500000 | 1943202 | 3 QTR FY19 | 0% | 0% | 422701 | 0 | 1520501 | yes
2 | 48190030 | Weslaco Readiness Center 1100 Vo-Tech Drive Weslaco 78596 | The project will repair an existing 76,069 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 2500000 | 2361135 | 4 QTR FY19 | 0% | 0% | 488047 | 0 | 1873088 | yes
3 | 48140040 | Terrell Readiness Center Lions Club Parkway Hwy 80 West Terrell 75160 | The project will repair an existing 22,138 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 1500000 | 1383650 | 3 QTR FY20 | 0% | 0% | 142414 | 0 | 1241236 | yes
4 | 48180020 | Fort Worth Shoreview Readiness Center 8111 Shoreview Dr Fort Worth 76108 | The project will repair 59,027 sf of Readiness Center space to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 2000000 | 1809489 | 4 QTR FY20 | 0% | 0% | 221267 | 0 | 1588222 | yes
5 | 48190020 | Fort Worth Cobb Park Readiness Center 2101 Cobb Park Dr Fort Worth 76105 | The project will repair an existing 34,549 sf Readiness Center to include compliance with ADA, ATFP, and current building code. General facility repairs to include: interior surfaces, mechanical and electrical systems, restrooms, and kitchen. | General Revenue 50%, Federal Funds 50% | 2500000 | 2280299 | 4 QTR FY20 | 0% | 0% | 217031 | 0 | 2063268 | yes
|  |  |  | Totals: | 11000000 | 9777775 |  |  |  | 1491460 | 0 | 8286315

## TMD Supp.
| Agency: | Texas Military Department - Agency 401
| Date: | 2017-12-19 | [5 empty] | 2017-12-19
Prepared by:
Supplemental Information
Project Priority | Project Name & Location | Total Estimated Project Budget | Federal Share | Federal Share Encumbered / Estimated | Federal Share Expended | Remaining Federal Share | Comments
1 | Camp Mabry Admin Offices 2200 W 35th St Bldg 1 Austin, 78730 | 5000000 | 1945027 | 0 | 0 | 1945027 | Project in Design
2 | Weslaco Readiness Center 1100 Vo-Tech Drive Weslaco 78596 | 5000000 | 2333600 | 0 | 0 | 2333600 | Project in Design
3 | Terrell Readiness Center Lions Club Parkway Hwy 80 West Terrell 75160 | 3000000 | 1363600 | 0 | 0 | 1363600 | Project in Design
4 | Fort Worth Shoreview Readiness Center 8111 Shoreview Dr Fort Worth 76108 | 4000000 | 1795600 | 0 | 0 | 1795600 | Project in Design
5 | Fort Worth Cobb Park Readiness Center 2101 Cobb Park Dr Fort Worth 76105 | 5000000 | 2288600 | 0 | 0 | 2288600 | Project in Design
| Totals: | 22000000 | 9726427 | 0 | 0 | 9726427

## TPWD
| Agency: | Texas Parks and Wildlife Department
| Date: | 2017-12-13 | [9 empty] | 2017-12-13
| Prepared by: | Infrastructure Division
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 127490 | Battleship Texas SHP - Structural Repairs 3523 Independence Parkway S LaPorte, TX,77571 (Harris County) | Construction administration and Balance of work to repair internal structural elements, identified in an October 2012 scope of work, which is necessary to stabilize the ship . Repairs are critical if the ship remains in a wet berth and would be absolutely necessary if ship is ever placed into a dry berth. | General Revenue - (SGST) | 1200000 | 1962000 | 2020-08-24 12:00 | 100% | 30% | 500 | 1774.93 | 1959725.07
2 | 116818 | Fort Richardson SHS - Water and Wastewater System Replacement 228 State Park Road 61 Jacksboro, TX 76458 (Jack County) | Construction costs Planning and design costs to replace the 50-year-old wastewater system, water distribution system and the main lift station with modernized and efficient systems capable of saving water resources while servicing the entire park. | General Revenue - (SGST) | 35000 | 1105000 | 2019-04-16 17:00 | 60% | 0% | 0 | 132.03 | 1104867.97 | *
3 | 116151 | Seminole Canyon SHS - Camp Loop Upgrades US Hwy 90 W Comstock, TX 78837 (Val Verde County) | Construction costs Planning and design costs to upgrade the Desert Vista Camp Loop's utilities, to include replacement and repairs to the On Site Sewage Facility System, water well, storage tank, pumps, and associated appurtenances, accessible restroom upgrades, and electrical service. | General Revenue - (SGST) | 71904.6225 | 1465000 | 2019-09-10 17:00 | 60% | 11% | 0 | 1164.53 | 1463835.47 | *
4 | 126472 | Goliad SHS - Wastewater System Upgrade 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Construction costs Planning and design costs to replace obsolete clay wastewater lines and systems, lift station, septic tanks, and drain fields with a modernized, efficient system capable of servicing the entire site, which includes the Hacienda, Mission workshop, CCC Restroom, Old River Restroom, park headquarters, group dining hall, camp loop, and residence. | General Revenue - (SGST) | 50000 | 1351000 | 2018-02-14 17:00 | 60% | 0% | 0 | 0 | 1351000 | *
5 | 117535 | Copper Breaks SP - Water Distribution System Replacement 777 Park Road 62 Quanah,79252-7679 (Hardman County) | Replace a 50-year-old, leaking water distribution system and chlorination station with a modernized and efficient system capable of saving water resources while servicing the entire park. | General Revenue - (SGST) | 57245.7375 | 57245.7375 | 2018-03-16 17:00 | 100% | 37% | -5.3291e-15 | 1313.71 | 55932.0275
6 | 116471 | Balmorhea SP - CCC Motor Court Renovations, Utility Upgrades and Headquarters Replacement - Planning and Design 9207 H. 17S Toyahvale, TX (Reeves County) | Renovate 18 Civilian Conservation Corps (CCC) motel units at the San Solomon Springs Motel Court, to include repairing termite damaged woodwork; upgrade the water and wastewater utilities and campground electrical utility service from 30 amp to 50 amp; renovate camp loop restrooms. | General Revenue - (SGST) | 809623.8885 | 809623.8885 | 2019-03-28 17:00 | 100% | 13% | 3.69 | 4246.1 | 805374.0985
7 | 117494 | Pedernales Falls SP - Restroom Replacements 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Replace one public restroom complex. Scope of work also includes development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | General Revenue - (SGST) | 180000 | 150000 | 2018-07-16 17:00 | 100% | 32% | 0 | 1322.48 | 148677.52
8 | 122865 | Huntsville SP - CCC Boathouse and Lodge Patio Wall Repairs 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Planning and design costs to renovate Civilian Conservation Corps (CCC) boathouse to include restoring the exterior hardwood siding, repairing the roof as well as interior and exterior structural damages, and repairing and stabilizing the Lodge's patio wall. | General Revenue - (SGST) | 23410.128 | 23410.128 | 2021-04-13 17:00 | 60% | 0% | 0 | 0 | 23410.128
9 | 116921 | Palo Duro Canyon SP - Headquarters Replacement 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Planning costs for site headquarters replacement. Headquarters is currently operating out of an under-sized converted residence and the project would provide an adequately-sized and modern facility to better serve the increasing number of visitors. | General Revenue - (SGST) | 25803.384 | 40000 | 2020-02-21 17:00 | 30% | 0% | 0 | 444.09 | 39555.91
10 | 117504 | Garner SP - Water System Upgrades US 83 N Concan, TX 78838 (Uvalde County) | Construction costs Planning and design costs to upgrade the park's overall water system, including treatment to reduce water hardness, and replace water distribution lines serving several park facilities in order to reduced system maintenance costs. | General Revenue - (SGST) | 500000 | 1250000 | 2020-01-06 | 30% | 0% | 0 | 184.85 | 1249815.15 | *
11 | 117536 | Fairfield Lake SP - Wastewater Treatment Plant Repairs TX 2570 E Fairfield, TX 75840 (Freestone County) | Replace the mechanical systems at two existing wastewater treatment plants with modernized and efficient systems that are capable of saving water resources while servicing the entire park. | General Revenue - (SGST) | 75782.466 | 175000 | 2018-06-08 17:00 | 100% | 50% | 7902.8 | 772.45 | 166324.75
12 | 117505 | Statewide - Unspecified State Park State Park Region 3 Restroom Replacement Program | Replace three public restroom complexes at Guadalupe State Park camping and day-use areas and one restroom complex at Government Canyon State Natural Area. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | General Revenue - (SGST) | 500891.085 | 320000 | 2019-01-28 17:00 | 100% | 9% | 0 | 3629.07 | 316370.93
13 | 126496 | Tyler SP - Residence Replacements 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Replace two obsolete staff residences with two adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structures, to include utility connections, parking and associated paving. | General Revenue - (SGST) | 126919.248 | 160000 | 2019-01-16 17:00 | 100% | 0% | 0 | 0 | 160000
NEW - 14 | 124729 | San Jacinto Battleground SHS - Replace Residence 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Planning and design costs to replace two residences and remove from a sensitive archaeological site. (Project on Hold) | General Revenue - (SGST) | 0 | 220 | N/A | 100% | 0% | 0 | 0 | 220 | *
15 | 127483 | Lake Tawakoni SP - Residence Replacement 10822 FM 2475 Willis Point, TX 75169 (Hunt Van Zandt County) | Replace mobile home residence with an adequately-sized, durable, 1,800 square feet, three bedroom / two bath, energy-efficient structure, to include utility connections, parking and associated paving. | General Revenue - (SGST) | 65290.767 | 68000 | 2019-01-16 17:00 | 100% | 5% | 0 | 355.16 | 67644.84
16 | 127358 | Mission Tejas SHS - Replace Visitor Center 120 State Park Rd. 4 Grapeland, TX 75844 (Houston County) | Replace visitor center that was destroyed by Hurricane Ike. New facility will include offices, assembly area, visitor check-in area, a new entry road and parking lot, utility extensions, and interpretive displays to educate visitors about the El Camino Real Trail. | General Revenue - (SGST) | 224828.6985 | 40000 | 2018-01-12 | 100% | 79% | 0 | 0 | 40000
17 | 117449 | Fort Leaton SHS - Roof Replacement FM 170 E Presidio, TX 79845 (Presidio County) | Replace leaking roof to preserve the historic structure and protect the building and contents from further water damage. | General Revenue - (SGST) | 93705.801 | 40000 | 2018-01-12 | 100% | 74% | 0 | 1772.27 | 38227.73
18 | 117534 | Devil's River SP - Septic System Replacement 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Replace multiple obsolete septic systems to meet TCEQ requirements. | General Revenue - (SGST) | 50000 | 55000 | 2018-02-26 17:00 | 100% | 42% | 14645 | 1480.06 | 38874.94
19 | 122888 | Monument Hill/Kreische Brewery SHS - Kreische House and Brewery Renovations 414 State Loop 92 LaGrange, TX 78945 (Fayette County) | Planning and design costs to renovate the interior and exterior of the historic Kreische House and Brewery to include water damage repairs and renovation of the cedar shake roof, structural elements, woodwork, floors, windows, stone work, finishes, historic furniture, and water diversion landscaping to protect the structures during flooding. Project also includes the cost to construct the roof. | General Revenue - (SGST) | 60000 | 434000 | 2018-11-30 | 10% | 0% | 0 | 1269.44 | 432730.56 | *
20 | 114228 | Colorado Bend SP - Water Treatment Plant Replacement 10 miles S of Bend on Gravel Rd Bend, TX 76824 (San Saba County) | Construction costs Planning and design costs to replace the water treatment plant with a new system to include a storage tank and ground water well. | General Revenue - (SGST) | 25000 | 580101 | 2020-07-22 17:00 | 30% | 0% | 0 | 0 | 580101 | *
21 | 114243 | Pedernales Falls SP - Water and Wastewater System Upgrades 2585 Park Road 6026 Johnson City, TX 78636 (Blanco County) | Planning and design costs to upgrade the obsolete water treatment plant to include four septic fields, drain fields and the water filtration system, in order to save water resources and provide an adequate system capable of saving water resources while better serving park visitors. | General Revenue - (SGST) | 153638.9715 | 153639 | 2020-04-30 17:00 | 60% | 0% | 0 | 15457.04 | 138181.96
22 | 117260 | Ray Roberts Lake SP - Johnson Branch Unit Compost Toilet Replacements 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Replace seven obsolete compost toilets with modular vault toilets to serve several trail and camping areas and revise any pathways for ADA compliance. | General Revenue - (SGST) | 73704.4065 | 60000 | 2018-05-22 17:00 | 100% | 33% | 0 | 992.83 | 59007.17
23 | 127438 | Lake Livingston SP - Marina Area and Fishing Pier Accessibility Upgrades and Repairs 300 State Park Road 65 Livingston, TX 77351 (Polk County) | Planning and design costs to renovate the Marina Area and Fishing Pier to include: repairs to restrooms, courtesy dock, fueling stations, electrical and lighting systems, and the accessible routes between facilities and parking due to soil subsidence. | General Revenue - (SGST) | 25000 | 25000 | 2019-05-02 17:00 | 60% | 0% | 0 | 88.4 | 24911.6
24 | 114238 | Inks Lake SP - Headquarters Building Replacement - Planning and Design 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Planning and design costs to replace the under-sized headquarters building with one which includes an adequately-sized lobby and registration area and office, as well as additional restrooms, to meet staff and visitor needs. Improve traffic flow around the headquarters site. | General Revenue - (SGST) | 68405.427 | 70000 | 2020-06-29 17:00 | 10% | 0% | 0 | 55.82 | 69944.18
25 | 117359 | McKinney Falls SP - Smith Visitor Center Facility and Exhibit Renovation 5808 McKinney Falls Austin, TX 78744 (Travis County) | Renovate the Smith Visitor Center including upgrading a learning center to serve as an interactive classroom with new interpretive exhibits to educate students and park visitors about the El Camino Real Trail. | General Revenue - (SGST) | 50000 | 150000 | 2018-02-25 | 100% | 0% | 0 | 0 | 150000
26 | 118102 | Bastrop SP - Shore Stabilization 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Stabilization of shoreline adjacent to Cabins #1 and #12. | General Revenue - (SGST) | 57765.0675 | 57765.0675 | 2018-01-11 17:00 | 100% | 73% | 0 | 385.16 | 57379.9075
27 | 127360 | Goliad SHS - Custodian's Cottage Renovation and Adaptive Reuse to Interpretive Facility 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | Renovate the CCC Custodian's Cottage to convert its use from administrative offices to an adequately-sized interpretive facility which will educate visitors about the El Camino Real Trail. Renovations will include restoration of formal gardens and a new parking lot. | General Revenue - (SGST) | 325000 | 100000 | 2018-01-11 | 100% | 70% | 0 | 0 | 100000
28 | 126719 | Mustang Island SP - Campground and Day-Use Area Restroom Replacements 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | Replace two obsolete restrooms with one large restroom complex. The scope of work includes a new forty-four fixture count restroom facility, five new host sites, all associated site work, utilities, parking, and the hazmat removal and demolition of the existing restroom. | General Revenue - (SGST) | 396567.447 | 220000 | 2018-10-10 17:00 | 100% | 13% | 0 | 386.02 | 219613.98
29 | 126912 | Caddo Lake SP - Water System Upgrade 245 Park Rd 2 Karnack, TX (Harrison county) | Planning and design costs to upgrade domestic water source to treat for excessive amounts of iron in the water and prevent further damage to plumbing fixtures throughout the park. Repairs include new storage tanks, pump systems, gas chlorination system, iron removal filter, refurbished hydro pneumatic tank, electrical improvements, and a pump house. | General Revenue - (SGST) | 25000 | 25000 | 2018-08-03 | 95% | 0% | 0 | 0 | 25000
30 | 117106 | Indian Lodge - Exterior Plaster and HVAC Replacement TX Hwy 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Renovate the historic facility to include exterior plaster repairs and replace obsolete HVAC units with energy-efficient systems. | General Revenue - (SGST) | 224748.543 | 224748.543 | 2018-11-28 17:00 | 100% | 17% | 0 | 2396.66 | 222351.883
31 | 115356 | Choke Canyon State Park (South Shore Unit) - Boat Ramp 358 Recreation Rd 8 Calliham, TX 78007 (Live Oak County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | General Revenue - (SGST) | 52419.699 | 30000 | 2018-03-02 17:00 | 100% | 30% | 8138.08 | 612.9 | 21249.02
32 | 115389 | Fort Parker State Park - Boat Ramp 194 Park Rd 28 Mexia, Tx 76667 (Limestone County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | General Revenue - (SGST) | 130000 | 70000 | 2018-03-26 17:00 | 100% | 63% | 30695.47 | 2743.4 | 36561.13
NEW - 33 | 116036 | Inks Lake State Park - Boat Ramp 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. (Project on Hold), TPWD did not receive a qualified construction bid in FY17 so funds for the project were lost due to lack of UB authority. | General Revenue - (SGST) | 0 | 108900 | 2018-04-08 17:00 | 100% | 0% | 0 | 0 | 108900 | *
34 | 117036 | Ray Roberts Lake SP - Isle du Bois Unit - Boat Ramp 100 PW 4137 Pilot Point 765258-8944 (Denton County) | Repair boat ramp which may include accessibility upgrades, courtesy docks, piers and renovation of existing facilities. | General Revenue - (SGST) | 25000 | 30000 | 2018-03-09 17:00 | 100% | 46% | 0 | 2.16 | 29997.84
35 | 117503 | Inks Lake SP - Multiple Restroom Replacements 3630 Pk Rd 4 W Burnet, TX 78611 (Burnett County) | Replace four public restroom complexes. Scope of work also includes development of utilities and parking. Sanitary complexes to include showers and development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | General Revenue - (SGST) | 327367.1595 | 492000 | 2019-02-11 17:00 | 100% | 21% | -7.1054e-15 | 3064.65 | 488935.35
36 | 117495 | Albert and Bessie Kronkosky SNA - Public Use Development - Planning and Design 7690 Hwy 46 West Pipe Creek, TX 78063 (Bandera County) | Advance planning costs to develop newly acquired site and install infrastructure, including utilities, parking, roadways, restrooms, toilets, and a fee collection booth at headquarters. Site development would allow public access and would meet public use needs as required by the land use agreement, which would generate revenue and provide significant outdoor opportunities. | General Revenue - (SGST) | 25000 | 100000 | 2021-10-12 17:00 | 10% | 0% | 0 | 0 | 100000
37 | 127510 | Stephen F Austin SHS - Wastewater Treatment Plant Equalization Basin Installation 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Construction costs Planning and design costs to install equalization basin at wastewater treatment plant in order to provide adequate pace flow into the plant during peak usage. | General Revenue - (SGST) | 25000 | 385000 | 2018-09-11 17:00 | 60% | 0% | 0 | 234.22 | 384765.78 | *
38 | 118450 | Buescher SP - Boundary Fence Replacement - Fire Recovery 100 Park Road 1E Smithville, TX 78957-0075 (Bastrop County) | Replace approximately 7.5 miles of boundary fence around Buescher State Park and along Park Road 1-C, a majority of which sustained significant damage or was totally destroyed in a wildfire that began mid October 2015. | General Revenue - (SGST) | 150000 | 183000 | 2018-09-26 17:00 | 100% | 35% | 0 | 263.14 | 182736.86
39 | 118414 | Lake Whitney SP - Camp Loop Restroom - Flood Recovery 433 FM 1244 Whitney, TX 76692 (Hill County) | Restore Restroom #5 at Area E's interior finishes and critical structural components prior to re-opening the facility which was damaged in the 2016 Flood. | General Revenue - (SGST) | 49072.647 | 81000 | 2018-05-09 17:00 | 100% | 32% | 750 | 1459.43 | 78790.57
40 | 137395 | McKinney Falls SP - Restroom #4 Upper Falls North - Flood Recovery 5808 McKinney Falls Pkwy Austin, TX 78744 (Travis County) | Repair interior and exterior finishes damaged by the flood. Work will also address major mechanical, electrical and plumbing systems needed to restore full function of the restroom facility. | General Revenue - (SGST) | 25000 | 10000 | 2017-11-15 17:00 | 100% | 89% | 0 | 0 | 10000
41 | 128233 | Stephen F Austin SHS - Water Tank Repairs 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | Pressure wash and repaint elevated water tank per TCEQ regulations. | General Revenue - (SGST) | 70000 | 70000 | 2018-03-20 17:00 | 100% | 54% | 0 | 1227.97 | 68772.03
42 | 124545 | Huntsville SP - Dam Repair 565 Park Road 40 W Huntsville, TX 77342-0508 (Walker County) | Fortify and repair the earthen embankment and spillway. | General Revenue - (SGST) | 236087.121 | 180000 | 2017-12-13 10:00 | 100% | 99% | 0 | 0 | 180000
43 | 132907 | Bastrop SP - Group Barracks Complex Renovation 100 Park road 1 A Bastrop, TX 78602 (Bastrop County) | Renovate the Group Barracks Complex, which includes four dormitory buildings and one group dinning hall. The existing obsolete restroom will be demolished; restroom/shower facilities will be added to each dormitory facility. The renovations include updating of all mechanicals, plumbing, electrical, and site modifications to become code compliant and improve visitor experience. | General Revenue - (SGST) | 452827.5105 | 388000 | 2018-09-21 17:00 | 100% | 28% | 0 | 0 | 388000
44 | 125986 | Port Isabel Lighthouse - Light house repairs; replace corroded metal 421 East Queen Isabella Blvd Port Isabel, TX 78578 (Cameron County) | Repair and/or replace corroded exterior metal components on the Port Isabel Lighthouse at the Watch room and Lantern Levels and repaint lighthouse exterior. | General Revenue - (SGST) | 50000 | 50000 | 2018-01-12 17:00 | 100% | 92% | 0 | 0 | 50000
45 | 137824 | Longhorn Caverns - Communications System and Surge Protection 6211 Park Rd 4 So. Burnet, TX 78611 (Burnet County) | Install communication system for the cavern to protect the public in the event of an emergency. | General Revenue - (SGST) | 20400 | 15000 | 2017-12-08 17:00 | 100% | 80% | 0 | 0 | 15000
46 | 134232 | Hill Country SNA - Replace Well at Group Lodge 10600 Bandera Creed Rd Bandera, TX 78003 (Bandera County) | Install water system at group lodge to provide potable water to guests. | General Revenue - (SGST) | 63367.2375 | 36000 | 2018-08-22 12:00 | 100% | 41% | 0 | 0 | 36000
47 | 134239 | Lost Maples SNA - Replace Potable Water Storage Tank 37221 FM 187 Vanderpool, TX 78885 (Bandera County) | Replace deteriorating drinking water storage tank with a new system in order to address a high iron content in the facility's water supply and meet TCEQ regulations. | General Revenue - (SGST) | 97679.52 | 130000 | 2018-05-15 17:00 | 100% | 39% | 0 | 74.57 | 129925.43
48 | 137394 | McKinney Falls SP - Smith Visitor's Center Flood Damage Repairs 5808 McKinney Falls Austin, TX 78744 (Travis County) | Repair all interior finishes, associated mechanical, electrical, and plumbing systems damaged by flood waters. Reconstruct the interior restroom to meet TDLR standards. | General Revenue - (SGST) | 125000 | 125000 | 2017-12-26 17:00 | 100% | 55% | 0 | 0 | 125000
49 | 136423 | Davis Mountains SP - Communications Bldg. Repairs TX HWY 118 N, Park Rd 3 Fort Davis, TX 79734 (Jeff Davis County) | Replace fire damaged radio house with a permanent facility to maintain park radio communications within the park and region. | General Revenue - (SGST) | 317000 | 400000 | 2019-03-28 17:00 | 30% | 0% | 0 | 0 | 400000
50 | 112741 | Tyler SP - Headquarters Replacement 789 Park Rd 16 Tyler, TX 75706-9141 (Smith County) | Planning and design cost for replacing the headquarters facility with new, adequately-sized ADA-compliant building, road, parking lot, and entrance. | General Revenue - (SGST) | 68673.9555 | 45000 | 2020-01-02 12:00 | 30% | 0% | 0 | 0 | 45000
51 | 118540 | Devil's River SP - New Visitor Check-in Building and Remodel of Existing Lodge. 101 N. Sweeten Street Rocksprings, TX 78880 (Edward County) | Planning and design costs to develop the newly acquired south unit. | General Revenue - (SGST) | 250000 | 250000 | 2020-12-14 17:00 | 10% | 0% | 0 | 22237.55 | 227762.45
52 | 126107 | San Jacinto Battleground SHS - Reflection Pool Structural Assessment 3523 Independence Parkway S LaPorte, TX 77571 (Harris County) | Professional engineering report and assessment for stabilizing and repairing the retaining walls around the reflecting pool. | General Revenue - (SGST) | 10000 | 15000 | 2018-07-20 | 60% | 0% | 0 | 12.88 | 14987.12
53 | 115897 | Palo Duro Canyon SP - Repairs to Juniper Camp Loop 13 Miles E of Canyon at end of Hwy 217 Canyon, TX 79015 (Randall County) | Repairs to existing facilities and address storm water drainage issues around the buildings. | General Revenue - (SGST) | 15000 | 15000 | 2017-10-13 16:54 | 100% | 100% | 0 | 0 | 15000
54 | 115900 | Caddo Lake SP - Restroom Replacement 245 Park Rd 2 Karnack, TX (Harrison county) | Replace one public restroom complex. Scope of work also includes development of utilities and parking. Structures will be site-built and designed to meet all accessibility, building code, and public health requirements. Building materials to be vandal resistant and assist in facility clean up and longevity. | General Revenue - (SGST) | 150000 | 150000 | 2018-06-28 17:00 | 100% | 15% | 4521.17 | 677.01 | 144801.82
55 | 117585 | Statewide - Unspecified Radio Tower Assessments | Perform repairs on the 35 remotely-located, active TPWD radio tower sites, towers, and building structures supporting the radio equipment. Repairs will maintain Federal Communications Commission compliance and will meet obligations to maintain the towers and sites as part of lease agreements. | General Revenue - (SGST) | 77399 | 100000 | 2018-10-31 17:00 | 100% | 40% | 0 | 0 | 100000
56 | 128106 | Palmetto SP - Group Camp Area Erosion Control 78 Park Road 11 South Gonzales, TX 78629 (Gonzalez County) | Planning and assessment needed to prepare a Preliminary Engineering Report (PER) of riverbank erosion and stabilization recommendations and final repairs below the Group Camp Area. Planning and Design will be funded with 18/19 funds. | General Revenue - (SGST) | 25000 | 25000 | 2018-09-01 | 10% | 0% | 0 | 0 | 25000
57 | 128197 | Galveston Island SP - Repair Historical Residences 14901 FM 3005 Galveston, TX 77554 (Galveston County) | Repairs and upgrades to the historic Stewart House and Ranch House. | General Revenue - (SGST) | 11625 | 11625 | 2018-01-09 17:00 | 100% | 50% | 0 | 0 | 11625
58 | 132416 | Hill Country SNA - Water System Replacement and Distribution 10600 Bandera Creed Rd Bandera, TX 78003 (Bandera County) | Replace existing water facilities with a new water distribution network. Add a water treatment system to the main existing well, creating a Public Water System. | General Revenue - (SGST) | 30000 | 0 | 2018-08-22 17:00 | 100% | 34% | 0 | 0 | 0
59 | 134236 | Garner SP - Wastewater Treatment Plant Replacement US 83 N Concan, TX 78838 (Uvalde County) | Replace the undersized, leaking wastewater treatment plant with a modernized and efficient system. | General Revenue - (SGST) | 25000 | 25000 | 2017-05-30 17:00 | 100% | 100% | 0 | 0 | 25000
60 | 137357 | Balmorhea SP - Repair Motel Roofs and Replace Laundry Facility 9207 H. 17S Toyahvale, TX (Reeves County) | Replace the CCC motel building's damaged clay tile roof, and repair critical structural, mechanical, electrical and plumbing systems concealed in the attic space. | General Revenue - (SGST) | 250000 | 0 | 2019-04-05 17:00 | 100% | 13% | 0 | 0 | 0
NEW - 61 | TBD | Bastrop SP - CCC Pool Repairs 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | Planning, Design and Repairs to the CCC Pool water treatment, pumping and distribution system. Project will assess overall leaks within the pool's aging pumping/piping system to include the overall pool liner structure as necessary. | General Revenue - (SGST) | 0 | 822405 | TBD | 0% | 0% | 0 | 0 | 822405 | *
NEW - 62 | TBD | Wyler Aerial Tramway - Facility Upgrades 1700 McKinley Drive, El Paso, TX 79931 (El Paso County) | Replace obsolete FINCOR unit, cabin controls and PLC controller. Tramway's original controls are past their intended service and recommended for replacement by the annual inspection. | General Revenue - (SGST) | 0 | 250000 | TBD | 0% | 0% | 0 | 0 | 250000 | *
NEW - 63 | 118517 | Lake Arrowhead SP - Wastewater Collection and Treatment System Repairs 229 Park Road 63, Wichita Falls, TX 76310 (Clay County) | Repairs to the Wastewater treatment plant and collection system; including full TCEQ Certifications and permitting of the plant. | General Revenue - (SGST) | 0 | 1250000 | 2020-02-28 17:00 | 10% | 0% | 0 | 0 | 1250000 | *
NEW - 64 | PPID 7451 | Big Bend Ranch SP - Building Renovations HCR 67 Box 33 Marfa, TX 79843 (Brewster and Presidio County) | Planning and Design costs to renovate interior, exterior and utilities for the Big House and Superintendent's Residence. | General Revenue - (SGST) | 0 | 182000 | TBD | 0% | 0% | 0 | 0 | 182000 | *
65 | 116769 | Bastrop SP - Dam Replacement and Road Repairs 100 Park Road 1 A Bastrop, TX 78602 (Bastrop County) | 2015 and 2016 Weather Related (State Parks) - Replace the breached dam and repair roads due to the 2015 memorial day flooding. | General Revenue - (SGST) | 6274215 | 6274215 | 2020-08-26 17:00 | 60% | 0% | 0 | 0 | 6274215
66 | 128269 | Cedar Hill SP - Facility Repairs - Flood Recovery 1570 FM 1382 Cedar Hill, TX 75104 (Dallas County) | 2015 and 2016 Weather Related (State Parks) - Repair the Day Use Swim Beach, replacement of multiple restrooms, a pavilion and overall shoreline reinforcement which were damaged by the multiple flooding events in 2015 and 2016. | General Revenue - (SGST) | 17031700 | 15586180 | 2019-10-10 17:00 | 60% | 0% | 0 | 44.44 | 15586135.56
67 | 128301 | Lake Somerville SP - Birch Creek Unit - Facility Repairs - Flood Recovery 14222 Park Road 57 Somerville, TX 77879-9713 (Burleson County) | 2015 and 2016 Weather Related (State Parks) - Construction costs to repair facilities in the Birch Creek Unit day use area. Planning and Design of Repairs to the Cedar Elm camping area, the Old Hickory and Bucktail bridge(s) which were damaged by multiple flooding events in 2015 and 2016. | General Revenue - (SGST) | 2481400 | 855000 | 2020-03-11 17:00 | 30% | 0% | 0 | 0 | 855000 | *
68 | 128322 | Lake Somerville SP - Nails Creek Unit - Facility Repairs - Flood Recovery 6280 FM 180 Ledbetter, TX 78946-9512 (Lee County) | 2015 and 2016 Weather Related (State Parks) - Construction costs to restore public access facilities (Fish Cleaning Stations) in the day use area. Planning and Design of repairs to the Cedar Creek camping area, and the Boat Ramp camping area which were damaged by the multiple flooding events in 2015 and 2016. | General Revenue - (SGST) | 1632000 | 175000 | 2020-03-27 17:00 | 30% | 0% | 0 | 17.45 | 174982.55 | *
69 | 128323 | Lake Somerville SP - Trailway - Bridge Repairs- Flood Recovery 14222 Park Road 57 Somerville, TX 77879-9713 (Burleson County) | 2015 and 2016 Weather Related (State Parks) - Planning and Design of repairs to multiple bridges, culverts, and access ways along the Somerville Trailway that were damaged by multiple flooding events in 2015 and 2016. (On Hold) | General Revenue - (SGST) | 157950 | 10000 | 2019-03-20 17:00 | 60% | 0% | 0 | 0 | 10000 | *
70 | 118477 | Lake Whitney SP - Erosion Repairs - Flood Recovery 433 FM 1244 Whitney, TX 76692 (Hill County) | 2015 and 2016 Weather Related (State Parks) - Planning and Design of erosion damage, a boat ramp, and address soil stabilization that resulted from the multiple 2016 flood events. | General Revenue - (SGST) | 1660500 | 60000 | 2021-03-01 17:00 | 30% | 0% | 0 | 11.29 | 59988.71 | *
71 | 118476 | Lake Whitney SP - Facilities Repairs - Flood Recovery 433 FM 1244 Whitney, TX 76692 (Hill County) | 2015 and 2016 Weather Related (State Parks) - Planning and Design to Repair of limited facilities (restroom #3, restroom #4, and several shade shelter replacements) at key areas damaged during multiple 2016 flood events. Planning and design for the remainder of the impacted areas that include the Towash shelter loop, day use area, the group camp & dinning hall, and all shade shelters. | General Revenue - (SGST) | 4286250 | 60000 | 2021-05-18 17:00 | 30% | 29% | 25636.59 | 1085.38 | 33278.03 | *
72 | TBD | Mother Neff SP - Restroom and CCC Rock Tabernacle Repairs and Stabilization 1680 TX 236 HWY Moody, TX 76557 (Coryell County) | 2015 and 2016 Weather Related (State Parks) - Replace day use restroom with a new CXT and stabilization of 4000 sq. ft. CCC built tabernacle. Work includes structural, wood, and masonry repairs, reroofing, and site construction. (On Hold) | General Revenue - (SGST) | 977000 | 0 | N/A | 100% | 0% | 0 | 0 | 0 | *
73 | 128302 | Ray Roberts Lake SP - Complex Wide- Site Repairs - Flood Recovery 100 PW 4137 Pilot Point, TX 76258-8944 (Denton County) | 2015 and 2016 Weather Related (State Parks) - Repair concrete walks, shoreline stabilization, playground areas, and the green belt trail which was damaged during the multiple flooding events in 2015 and 2016. | General Revenue - (SGST) | 8729250 | 3456000 | 2019-05-16 09:36 | 60% | 0% | 25908.4 | 434.74 | 3429656.86 | *
74 | TBD | Statewide - Unspecified State Park Flood Recovery | 2015 and 2016 Weather Related (State Parks)- Hazardous tree removal from the multiple flooding events in 2015 and 2016. | General Revenue - (SGST) | 300000 | 300000 | TBD | 0% | 0% | 0 | 0 | 300000
75 | 128406 | Stephen F Austin SHS - Facility Repairs - Flood Recovery 3 miles E of Sealy on IH 10 San Felipe, TX 77473-0125 (Austin County) | 2015 and 2016 Weather Related (State Parks) - Repair mini cabin(s), screen shelter(s), group dining hall(s), staff residence, the Bullinger Creek bunkhouse, the Nature Center, and multiple restrooms that were damaged during the 2016 flood. | General Revenue - (SGST) | 4164700 | 4090000 | 2019-08-04 17:00 | 30% | 0% | 0 | 2753.58 | 4087246.42
76 | TBD | Statewide - Unspecified State Park Harvey Recovery | HARVEY - Emergency funding reserved and redirected to address state park 2017 Harvey damages. Now that comprehensive damage assessments have been completed, individual projects (by site) are now set up. | General Revenue - (SGST) | 813600 | 813600 | TBD | 0% | 0% | 0 | 0 | 813600 | *
NEW - 77 | TBD | Brazos Bend SP - Facility Repairs - Harvey Damage Recovery | HARVEY - Planning and Design to repair levee | General Revenue - (SGST) | 0 | 1163767 | TBD | 0% | 0% | 0 | 0 | 1163767 | *
NEW - 78 | 118686 | Buescher SP - CCC Dam Spillway Restoration - Harvey Recovery 100 Park Road 1E, Smithville, TX 78957 | HARVEY - Planning and Design/Interim repairs to the CCC Dam Spillway damaged during the 2017 hurricane event. Significant erosion occurred on downstream slope of the Dam spillway threatening the Safety of the Dam. Project will assess damages, prepare construction documents and repair the damaged structure to meet TCEQ regulations. | General Revenue - (SGST) | 0 | 1250000 | TBD | 5% | 6.427% | 74234.98 | 1255.38 | 1174509.64 | *
NEW - 79 | TBD | Goliad SP - Facility Repairs - Harvey Damage Recovery 108 Park Rd Goliad, TX 77963-3206 (Goliad County) | HARVEY - Repair/renovate maintenance building | General Revenue - (SGST) | 0 | 300000 | TBD | 5% | 0% | 0 | 0 | 300000 | *
NEW - 80 | TBD | Goose Island SP - Facility Repairs - Harvey Recover 202 S Palmetto St., Rockport, TX 78382 (Aransas County) | HARVEY - Construction costs to repair all Park Operational facilities, utility systems, Wooded Area Camping Loop, CCC Recreation Hall, Boat Ramp, Beach Side Camping facilities, Fishing pier, Wildlife viewing overlook, Day-use area, Beach Camping area/boardwalk, and the Big Tree area. Project will prepare construction documents and repair damaged structures to include mold remediation and replacement of damaged interior finishes. | General Revenue - (SGST) | 0 | 1803500 | TBD | 5% | 6.682% | 0 | 112962.75 | 1690537.25 | *
NEW - 81 | 128684 | Goose Island SP - Facility Repairs - Harvey Recovery 202 S Palmetto St., Rockport, TX 78382 (Aransas County) | HARVEY - Roofing repairs to multiple facilities (Park HQ, Maintenance Shop, and Restrooms) throughout the park damaged during the 2017 hurricane event. Project addressed immediate facility preservation to the building exterior needed to prevent additional water intrusion damage to interior finishes. | General Revenue - (SGST) | 0 | 180000 | TBD | 5% | 63% | 0 | 112962.75 | 67037.25 | *
NEW - 82 | 128679 | Goose Island SP - Facility Repairs - Harvey Recovery 202 S Palmetto St., Rockport, TX 78382 (Aransas County) | HARVEY - Repair residence roof damaged during the 2017 hurricane event. Project addressed immediate facility preservation to the building exterior necessary to prevent additional water intrusion damage including minimal interior finishes. | General Revenue - (SGST) | 0 | 50000 | TBD | 5% | 94% | 6192 | 40601.71 | 3206.29 | *
NEW - 83 | TBD | Mustang Island SP - Facility Repairs - Harvey Recovery 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | HARVEY - Construction costs to repair all Park Operational facilities (Headquarters, Residences and Maintenance yard), site utility systems, RV Camping Loop, Day-use and Beach area services. Project will prepare construction documents and repair damaged structures to include mold remediation and replacement of damaged interior finishes. | General Revenue - (SGST) | 0 | 920000 | TBD | 5% | 0% | 0 | 0 | 920000 | *
NEW - 84 | 128702 | Mustang Island SP - Facility Repairs - Harvey Recovery 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | HARVEY - Repairs to both park residences interior finishes damaged during the 2017 hurricane event. Project will assess damages, prepare construction documents and repair damaged to interior finishes. | General Revenue - (SGST) | 0 | 60000 | 2018-04-05 17:00 | 5% | 3.274% | 1892 | 10 | 58098 | *
NEW - 85 | 128677 | Mustang Island SP - Facility Repairs - Harvey Recovery 17047 State Hwy 36 Port Aransas, TX 78373 (Nueces County) | HARVEY - Roofing repairs to both Residences damaged during the 2017 hurricane event. Project addressed immediate facility preservation to the building exterior necessary to prevent additional water intrusion damage to interior finishes. | General Revenue - (SGST) | 0 | 115000 | TBD | 5% | 95% | 29919.45 | 78300.49 | 6780.06 | *
NEW - 86 | 128676 | Rockport Regional Office - Facility Repairs - Harvey Recovery 715 Hwy 35 S, Rockport, TX 78382 (Aransas County) | HARVEY - Repairs to the Headquarters facility damaged during the 2017 hurricane event. Project will assess overall building damage, prepare construction documents and repair all interior damages including mold remediation and replacement of interior finishes. Project includes replacement of an adjacent support office building and associated utility connections. All phases - Planning & Design and Construction - will be funded with 18/19 funds consisting of actual construction activities to include all cost associated with the Bidding, Construction and Project Closeout phases. | General Revenue - (SGST) | 0 | 1400000 | TBD | 5% | 9.259% | 24172.51 | 94472.65 | 1281354.84 | *
NEW - 87 | 128693 | Sheldon Lake SP - Facility Repairs - Harvey Recovery 14320 Garrett Road, Houston, TX 77049 (Harris County) | HARVEY - Repairs to facilities damaged during the 2017 hurricane event. Construction costs to repair the Park Headquarters, Residence, Acorn Annex and Wellhead. Project will perform interior repairs to include mold remediation and replacement of damaged interior finishes. Construction - will be funded with 18/19 funds. | General Revenue - (SGST) | 0 | 193000 | 2018-04-04 17:00 | 5% | 67% | 120107.65 | 7838.11 | 65054.24 | *
NEW - 88 | 118692 | Statewide Radio Towers - Facility Repairs - Harvey Recovery | HARVEY - Emergency repairs to two radio towers damaged during the 2017 hurricane event. Project assessed towers and equipment damages providing immediate repairs necessary to restore life safety communications. | General Revenue - (SGST) | 0 | 150000 | 2018-04-03 17:00 | 5% | 89% | 115216.54 | 17632.1 | 17151.36 | *
NEW - 89 | 190062 | Stephen F. Austin SP - Facility Repairs - Harvey Recovery San Felipe, TX 77473 (Austin County) | HARVEY - State Park Managed Harvey Repairs | General Revenue - (SGST) | 0 | 4500 | TBD | 5% | 100% | 0 | 4242.69 | 257.31 | *
NEW - 90 | 128683 | Stephen F. Austin SP - Facility Repairs - Harvey Recovery San Felipe, TX 77473 (Austin County) | HARVEY - Repairs to the Park Headquarters and Maintenance complex damaged during the 2017 hurricane event. Project addressed immediate facility preservation to the building exteriors necessary to prevent additional water intrusion damage including minimal interior finishes. Overall restoration is incorporated into the prior Weather Related event. | General Revenue - (SGST) | 0 | 97000 | TBD | 5% | 98% | 46716.31 | 48352.38 | 1931.31 | *
NEW - 91 | 128695 | Village Creek SP - Facility Repairs - Harvey Recovery 8854 Park Road 74, Lumberton, TX 77657 (Hardin County) | HARVEY - Repairs to the Cabin, Pavilion, and Pedestrian bridge damaged during the 2017 hurricane event. Project will assess damages, provide a structural Preliminary Engineering Report for the Cabin, prepare construction documents and repair damaged structures. | General Revenue - (SGST) | 0 | 680000 | 2018-04-04 17:00 | 5% | 8.192% | 6099 | 45389.09 | 628511.91 | *
92 | 114144 | Austin Headquarters Complex - HVAC Control System Replacement 4200 Smith School Road Austin, TX 78744 (Travis County) | Replace the existing climate control system at Austin Headquarters Complex with an updated HVAC Management System which is supported by current industry vendors and allows for remote adjustments by the energy performance contractor. | General Revenue - (SGST) | 41338.35 | 25000 | 2017-12-06 17:00 | 100% | 86% | 0 | 1823.51 | 23176.49
93 | 118669 | Austin Headquarters Complex - Multiple HVAC System Upgrades 4200 Smith School Road Austin, TX 78744 (Travis County) | Planning and design costs to upgrade and/or replace aging HVAC system(s) at the Austin HQ facilities. | General Revenue - (SGST) | 29507.25 | 40000 | 2019-07-22 17:00 | 30% | 0% | 0 | 0 | 40000
94 | 117417 | Austin Headquarters Complex - Construct Building D Roof Access 4200 Smith School Road Austin, TX 78744 (Travis County) | Construct a Building D exterior stairway and fire escape as a secondary egress for safety purposes. Build a storage building on Building D rooftop to store tools, equipment, and materials used to service the rooftop equipment. | General Revenue - (SGST) | 0 | 120 | 2017-07-26 17:00 | 100% | 100% | 0 | 86.08 | 33.92
95 | TBD | Austin Headquarters Complex - Unspecified Emergency Repairs 4200 Smith School Road Austin, TX 78744 (Travis County) | Funding reserved to address Austin Headquarter Complex emergency repairs. | General Revenue Dedicated - (Fund9) | 300000 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | *
96 | TBD | Statewide - Unspecified Fund9 Division Flood Recovery | 2015 and 2016 Weather Related (Fund 9) - Various WMA repairs resulting from the 2015 and 2016 floods included roads, fencing, and lake dams at Guadalupe Delta WMA, Kerr WMA, Gus Engeling WMA, and Fawcett WMA. | General Revenue Dedicated - (Fund9) | 677100 | 0 | TBD | 0% | 0% | 0 | 0 | 0 | *
97 | 127570 | Brownsville Field Station - Replace Storage Building 95 Fish Hatchery Road, Brownsville, TX 78520 (Cameron County) | Construct building addition to the Main Boat and Truck storage facility to increase secure storage capacity from five to twelve vehicles. | General Revenue Dedicated - (SWFS) | 150000 | 150000 | 2018-12-14 17:00 | 100% | 5% | 0 | 44.21 | 149955.79
98 | 122081 | CCA Marine Development Center - Fish America Spawning Building and Ozone Water Purification System Replacement 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | Replace the under-sized, 30-year-old, Fish America spawning building with a new 4,000 square foot spawning building at the same location that will withstand the coastal elements. Building will include staff offices and research space and a new ozone water purification system to replace the existing non-functioning ozone system. | General Revenue Dedicated - (Fund9) | 395000 | 75000 | 2019-08-08 17:00 | 100% | 5% | 0 | 512.88 | 74487.12
99 | 128535 | CCA Marine Development Center - Repairs to Ponds 1-10 Harvest Kettles 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | Repair damaged concrete harvest kettles at Ponds 1-10. These ten ponds are original to the site and are in a stage of decay. Repairs would include structural concrete work and efforts to minimize existing pond leaks. | General Revenue Dedicated - (SWFS) | 20000 | 20000 | 2018-04-05 17:00 | 100% | 46% | 0 | 10.21 | 19989.79
100 | 124743 | Dickinson Marine Lab - New Boat Storage Facility 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | Install three metal boat storage buildings (4,960 square foot total) at the south, east and west sides of an existing paved storage area to secure the boats and protect from weather and vandalism. Storage buildings shall include power and lighting. | General Revenue Dedicated - (Fund9) | 72000 | 40000 | 2018-05-25 17:00 | 100% | 17% | 0 | 1025.64 | 38974.36
101 | 125873 | Dickinson Marine Lab - Roof Replacement 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | Replace deteriorated office building roof. | General Revenue Dedicated - (Fund9) | 61000 | 112000 | 2018-09-19 17:00 | 100% | 12% | 1.7764e-15 | 24.15 | 111975.85
102 | 122405 | Perry R Bass Marine Research Station - Hatchery Replacement HC 02, Box 385 FM 3280 Palacios TX 77465 (Matagorda County) | Planning and Design for the renovation and/or replacement of facility buildings, utilities, ponds and infrastructure. In addition to the new hatchery design, project includes the planning and design for a new Seawater Intake System to feed the site's fish rearing ponds. | General Revenue Dedicated - (Fund9) | 325000 | 100000 | 2022-05-20 17:00 | 10% | 0% | 0 | 861.91 | 99138.09
103 | 128533 | Perry R Bass Marine Research Station - Replace Residences HC 02, Box 385 FM 3280 Palacios TX 77465 (Matagorda County) | Construction administration to complete (2) residence replacements. | General Revenue Dedicated - (Fund9) | 55000 | 60000 | 2018-03-16 17:00 | 100% | 27% | 0 | 0 | 60000
104 | 127861 | Rockport Annex - Boat Maintenance Shop Repairs 824 S Fuqua St, Rockport, TX 78382 (Aransas County) | Renovate existing and install new wall panels and repair roof leaks. | General Revenue Dedicated - (SWFS) | 30000 | 30000 | 2018-06-26 17:00 | 100% | 20% | 0 | 144.94 | 29855.06
105 | 124932 | Sea Center Texas - Fence Replacement 300 Medical Drive Lake Jackson, TX 77566 (Brazoria County) | Replace three miles of perimeter fencing in and around the facility with high game fence and an entry fence in order to protect the hatchery from wildlife and human intrusion. | General Revenue Dedicated - (Fund9) | 75000 | 57000 | 2018-08-03 12:00 | 100% | 17% | 0 | 426.84 | 56573.16
106 | 127758 | Sea Center Texas - Flounder Building 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Construct new 3000 square foot flounder spawning building. Building will provide additional hatchery floor space for flounder bloodstock and incubation equipment and include a separate room for culture of live feeds. | General Revenue Dedicated - (Fund9) | 150000 | 120000 | 2018-09-18 17:00 | 100% | 35% | 0 | 0 | 120000
107 | 125983 | Sea Center Texas - Pond Electrical System Improvements 300 Medical Drive Lake Jackson, Texas 77566 (Brazoria County) | Upgrade obsolete electrical service systems at 36 ponds with modern and energy-efficient systems that will improve hatchery operations | General Revenue Dedicated - (Fund9) | 28000 | 5000 | 2017-10-17 17:00 | 100% | 100% | 0 | 711.15 | 4288.85
NEW - 108 | 128687 | CCA Marine Development Center - Facility Repairs - Harvey Recovery 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | HARVEY - Repairs to facilities damaged during the 2017 hurricane event. Project will replace damaged roofing at the Bass Bldg. and Shop bldg. | General Revenue Dedicated - (Fund9) | 0 | 282868 | TBD | 0% | 9.497% | 3.69 | 24531.27 | 258333.04 | *
NEW - 109 | 190072 | CCA Marine Development Center - Facility Repairs - Harvey Recovery 4300 Waldron Road Corpus Christi, TX 78418 (Nueces County) | HARVEY - Coastal Fisheries Managed Repairs to facilities damaged during the 2017 hurricane event. | General Revenue Dedicated - (Fund9) | 0 | 3359 | TBD | 0% | 100% | 0 | 3359.38 | -0.38 | *
NEW - 110 | 190073 | Dickenson Marine Lab - Facility Repairs - Harvey Recovery 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | HARVEY - Coastal Fisheries Managed Repairs to facilities damaged during the 2017 hurricane event. | General Revenue Dedicated - (Fund9) | 0 | 27500 | TBD | 0% | 100% | 0 | 27500 | 0 | *
NEW - 111 | 128696 | Dickinson Marine Lab - Facility Repairs - Harvey Recovery 1502 FM 517 E. Dickinson, TX 77539 (Galveston County) | HARVEY - Repairs to facilities damaged during the 2017 hurricane event. Scope of work includes mold remediation and interior demolition and repairs at the warehouse and office building. | General Revenue Dedicated - (Fund9) | 0 | 718837 | TBD | 0% | 3.686% | 22176.33 | 3375.02 | 693285.65 | *
NEW - 112 | 190074 | Rockport Annex - Facility Repairs - Harvey Recovery 824 S Fuqua St, Rockport, TX 78382 (Aransas County) | HARVEY - Coastal Fisheries Managed Repairs to facilities damaged during the 2017 hurricane event. | General Revenue Dedicated - (Fund9) | 0 | 19300 | TBD | 0% | 297.4% | 11449 | 2995 | 4856 | *
NEW - 113 | 128685 | Rockport Boat Maintenance Shop - Facility Repairs - Harvey Recovery Rockport, TX 78382 (Aransas County) | HARVEY -Repairs to facilities damaged during the 2017 hurricane event. Project will repair damage structures. | General Revenue Dedicated - (Fund9) | 0 | 401167 | TBD | 0% | 54.69% | 53535.68 | 88289.56 | 259341.76 | *
NEW - 114 | 190075 | Rockport Harbor Building - Facility Repairs - Harvey Recovery 824 S Fuqua St, Rockport, TX 78382 (Aransas County) | HARVEY - Coastal Fisheries Managed Repairs to facilities damaged during the 2017 hurricane event. | General Revenue Dedicated - (Fund9) | 0 | 2795 | TBD | 0% | 100% | 0 | 2795 | 0 | *
NEW - 115 | 190070 | Matagorda Island WMA - Facility Repairs - Harvey Recovery Port O'Connor, TX 77982 (Calhoun County) | HARVEY - Cost to temporarily shore up building that was damaged during Harvey. | General Revenue Dedicated - (Fund9) | 0 | 11490 | TBD | 0% | 100% | 0 | 11490 | 0 | *
NEW - 116 | 128694 | JD Murphree WMA - Facility Repairs - Harvey Recovery Park Road 10, Port Arthur, TX 77640 (Jefferson County) | HARVEY - Repairs to the Main Office, Biologist Office and Bunkhouse at the WMA damaged during the 2017 hurricane event. Project includes treating internal water/mold damage and the overall restoration of their interior finishes. | General Revenue Dedicated - (Fund9) | 0 | 223950 | TBD | 0% | 82.11% | 96188.12 | 4784.49 | 122977.39 | *
NEW - 117 | 128697 | Guadalupe Delta WMA - Facility Repairs - Harvey Recovery Bay City, TX 77414 (Calhoun/Refugio/Victoria Counties) | HARVEY - Repairs to the Bunkhouse at the WMA damaged during the 2017 hurricane event. | General Revenue Dedicated - (Fund9) | 0 | 29364 | TBD | 0% | 297.4% | 19165.73 | 2809.03 | 7389.24 | *
118 | 126484 | The Tyler Nature Center - Regional Office Replacement 11942 FM 848, Tyler, TX 75707 (Smith County) | Construction for phase 1 of the multi-regional complex. The current office complex supports business operations for 5 agency divisions and the existing facilities inadequately support business operations. Phase 1 will address the agency staff currently office in the 1950's Quail Hatchery Building. | General Revenue Dedicated - (Fund9) | 1539000 | 1387470 | 2020-10-19 | 0% | 0% | 0 | 0 | 1387470
119 | 123377 | AE Wood Fish Hatchery - Incubation System 507 Staples Rd, San Marcos, TX 78666 (Hays County) | Renovate portions of the hatchery process systems including tanks, troughs, distribution piping, and valving and System Control and Data Acquisition (SCADA) system. | General Revenue Dedicated - (FWFS) | 125000 | 250000 | 2018-12-05 | 100% | 33% | 205803 | 1894.45 | 42302.55
NEW - 120 | TBD | AE Wood Fish Hatchery - HVAC Replacements 507 Staples Rd, San Marcos, TX 78666 (Hays County) | Design and construction to replace the HVAC system at the Lab Building. | General Revenue Dedicated - (FWFS) | 0 | 350000 | TBD | 0% | 0% | 0 | 0 | 350000 | *
121 | 128562 | AE Wood Fish Hatchery - Rivers Studies Building 507 Staples Rd, San Marcos, TX 78666 (Hays County) | Design and construction for site work, site utilities, building foundation and landscaping and the installation of a new modular office for the Rivers Studies staff | General Revenue Dedicated - (FWFS) | 75000 | 250000 | 2020-01-31 | 0% | 0% | 0 | 0 | 250000
122 | 128632 | Dundee Fish Hatchery - Ozone System 16824 FM1180, Electra, TX 76360 (Archer County) | Construction of an ozone disinfection system to control toxic golden algae present in the water source. In order to sustain hatchery operation during intermittent or persistent drought conditions, the project would also design and construct a system to collect the effluent from the six hatchery discharge points and pump it back to Lake Diversion to minimize the water lost from the reservoir as a result of hatchery operations. | General Revenue Dedicated - (FWFS) | 4180000 | 1960000 | 2020-08-10 | 60% | 0% | 0 | 0 | 1960000 | *
NEW - 123 | TBD | Dundee Fish Hatchery - Pump Repairs 16824 FM1180, Electra, TX 76360 (Archer County) | Project will develop a Preliminary Engineering Report with follow on Planning and Design of an effluent water pump back system that will collect wastewater from fish rearing ponds and pump it back into Lake Diversion. Additional Construction cost may be required at the end of 19 into 20/21. | General Revenue Dedicated - (FWFS) | 0 | 1688000 | TBD | 0% | 0% | 0 | 0 | 1688000 | *
124 | 128314 | East Texas Fish Hatchery - Chemical Storage Unit 900 County Road 218, Brookeland, TX 75931 (Jasper County) | Construct concrete slab and install modular storage unit | General Revenue Dedicated - (FWFS) | 25000 | 0 | 2020-12-31 | 100% | 0% | 0 | 0 | 0
NEW - 125 | TBD | East Texas Fish Hatchery - Replace/Repair Pumps 900 County Road 218, Brookeland, TX 75931 (Jasper County) | Replace damaged pump drive shafts on Vertical Turbine Pumps; the existing drive shafts will be machined and kept as shelf stock for future repairs. | General Revenue Dedicated - (FWFS) | 0 | 160000 | TBD | 0% | 0% | 0 | 0 | 160000 | *
NEW - 126 | 127144 | Mathis Office - Design Office Replacement 9892 FM 3377, Mathis, TX 78368 (San Patricio County) | Plan and Design efforts for an Inland Fisheries Field Office replacement. The new building will include offices and a vehicle/equipment shop. | General Revenue Dedicated - (FWFS) | 0 | 100000 | TBD | 0% | 0% | 0 | 0 | 100000 | *
127 | 127550 | Possum Kingdom Fish Hatchery - Hatchery Pond Renovation and Expansion 401 Red Bluff Rd, Graford, TX 76449 (Palo Pinto County) | Plan and Design of modern harvest kettles. Improvements will provide staff with greater efficiencies in harvesting fish and assist in reducing stress on fish during harvest. (Project On Hold) | General Revenue Dedicated - (FWFS) | 500000 | 0 | 2018-03-05 | 100% | 0% | 0 | 0 | 0
128 | 118667 | Possum Kingdom Fish Hatchery - Ozone Chiller Replacement 401 Red Bluff Rd, Graford, TX 76449 (Palo Pinto County) | Replace the existing failing ozone system chiller unit. The system circulates chilled water used to cool ozonation equipment. | General Revenue Dedicated - (FWFS) | 10000 | 10000 | 2018-04-27 | 100% | 10% | 0 | 97.21 | 9902.79
129 | 117303 | Statewide - Inland Fisheries - Upgrade SCADA System | Upgrades to hatchery Supervisory Control and Data Acquisition (SCADA) systems for three (3) sites including A.E. Wood Fish Hatchery, Possum Kingdom Fish Hatchery and East Texas Fish Hatchery. | General Revenue Dedicated - (FWFS) | 30000 | 12000 | 2018-12-05 | 100% | 60% | 0 | 0 | 12000
130 | 116446 | Texas Freshwater Fisheries Center - Construct Effluent Re-Use System 5550 FM2495, Athens, TX 75752 (Henderson County) | Construct water infrastructure improvements. | General Revenue Dedicated - (FWFS) | 25000 | 80000 | 2018-02-08 | 100% | 100% | 0 | -166.3 | 80166.3
131 | 128235 | Texas Freshwater Fisheries Center - Replace Ozone Tower 5550 FM2495, Athens, TX 75752 (Henderson County) | Replace portions of the ozone injection system including the ozone contact columns and affected distribution piping and valving | General Revenue Dedicated - (FWFS) | 30000 | 15000 | 2018-11-12 | 100% | 68% | 13160.16 | 499.08 | 1340.76
NEW - 132 | 126484 | The Tyler Nature Center - Regional Office Replacement 11942 FM 848, Tyler, TX 75707 (Smith County) | Temporary office space needed for Inland Fisheries staff located in the Quail Building. | General Revenue Dedicated - (FWFS) | 0 | 125000 | 2020-10-19 | 10% | 0% | 0 | 0 | 125000 | *
|  |  |  | Totals: | 66185665.1385 | 66185665.3645 |  |  |  | 964733.35 | 820524.67 | 64400407.3445

## TDCJ
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2017-12-15 | [9 empty] | 2017-12-15
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 03017005 | Jester III Unit, Richmond | Facility Repair: Convert TCI Factory to Sheltered Beds | Economic Stabilization Fund No. 0599 | 437400 | 437400 | 2018-01-01 | 100% | 95% | 5331.85 | 324531.7 | 107536.45 | Yes
2 | 06717005 | Telford Unit, New Boston | Facility Repair: Convert TCI Factory to Sheltered Beds | Economic Stabilization Fund No. 0599 | 877300 | 877300 | 2018-01-12 | 100% | 65% | 88772.83 | 468741.35 | 319785.82 | Yes
3 | 12917002 | Young Unit, Dickinson | Facility Repair: Convert Surgical Suites to Sheltered Beds | Economic Stabilization Fund No. 0599 | 139700 | 139700 | 2018-01-01 | 100% | 99% | 1255.94 | 49585.1 | 88858.96 | Yes
4 | 10013001 | Lychner Unit, Humble | Security: Replace Intercom System | Economic Stabilization Fund No. 0599 | 134000 | 134000 | 2019-01-31 | 86% | 0% | 0 | 0 | 134000
5 | 09115026 | Chasefield Unit, Beeville | Roofing: Replace Roof - Maintenance Building | Economic Stabilization Fund No. 0599 | 1000000 | 1000000 | 2019-05-15 | 1% | 0% | 0 | 0 | 1000000
6 | 02214021 | Beto Unit, Tennessee Colony | Facility Repair: Renovate Vault & Replace Refrigeration System - Icehouse | Economic Stabilization Fund No. 0599 | 1000000 | 1000000 | 2018-12-02 | 86% | 0% | 0 | 0 | 1000000
7 | 01215009 | Goree Unit, Huntsville | Facility Repair: Construct Enclosure - Intake Processing | Economic Stabilization Fund No. 0599 | 98900 | 98900 | 2018-04-20 | 100% | 1% | 31060.66 | 0 | 67839.34
8 | 01313001 | Huntsville Unit, Huntsville | Roofing: Replace Roof and Repair North Wall - Infirmary Building | Economic Stabilization Fund No. 0599 | 153600 | 153600 | 2018-12-31 | 100% | 0% | 69.63 | 593.56 | 152936.81
9 | 04317001 | Kyle Unit, Kyle | Facility Repair: Replace Ceiling - Main Hallway & Kitchen | Economic Stabilization Fund No. 0599 | 52500 | 52500 | 2018-06-21 | 1% | 0% | 0 | 0 | 52500
10 | 02710004 | Terrell Unit, Rosharon | Infrastructure: Replace Concrete Drive / Back Gate | Economic Stabilization Fund No. 0599 | 1600280 | 1680380 | 2019-06-28 | 100% | 5% | 1600280 | 914.37 | 79185.63 | Yes
11 | 07015010 | Neal Unit, Amarillo | Roofing: Replace Roof - Beef Processing Plant | Economic Stabilization Fund No. 0599 | 3015000 | 3015000 | 2020-01-30 | 86% | 0% | 0 | 0 | 3015000
12 | 01017017 | Ellis Unit, Huntsville | Facility Repair: Install Water Conservation System - Multiple Locations | Economic Stabilization Fund No. 0599 | 2709000 | 2709000 | 2018-12-30 | 100% | 0% | 0 | 0 | 2709000
13 | 06115001 | Cotulla Unit, Cotulla | Facility Repair: Replace Shower - Multiple Locations | Economic Stabilization Fund No. 0599 | 900000 | 900000 | 2019-01-30 | 1% | 0% | 0 | 0 | 900000
14 | 06313004 | Duncan Unit, Diboll | Facility Repair: Replace Shower Stalls - Unit Wide | Economic Stabilization Fund No. 0599 | 140000 | 140000 | 2018-04-18 | 100% | 0% | 1025 | 0 | 138975
15 | 03612001 | Michael Unit, Tennessee Colony | Infrastructure: Construct Elevated Storage Tank & Replace Ground Storage Tank | Economic Stabilization Fund No. 0599 | 6249400 | 6249400 | 2019-12-30 | 81% | 0% | 0 | 0 | 6249400
16 | 01608001 | Mt. View Unit, Gatesville | Infrastructure: Replace Water Lines - Distribution System & Replace Ground Water Storage | Economic Stabilization Fund No. 0599 | 5651409 | 5651409 | 2019-12-15 | 81% | 0% | 0 | 0 | 5651409
17 | 03708003 | Clements Unit, Amarillo | Safety: Repair/Replace Fire Line - Administrative Segregation | Economic Stabilization Fund No. 0599 | 474100 | 474100 | 2018-02-21 | 86% | 0% | 0 | 0 | 474100
18 | 00613017 | Coffield Unit, Tennessee Colony | Facility Repair: Replace Flooring - Kitchen | Economic Stabilization Fund No. 0599 | 140000 | 140000 | 2018-07-17 | 100% | 0% | 0 | 0 | 140000
19 | 00615025 | Coffield Unit, Tennessee Colony | Facility Repair: Install Showers - Multiple Locations | Economic Stabilization Fund No. 0599 | 1000000 | 1000000 | 2018-11-10 | 100% | 0% | 0 | 0 | 1000000
20 | 12107001 | Lindsey Unit, Jacksboro | Infrastructure: Correct Drainage Problems - Multiple Buildings | Economic Stabilization Fund No. 0599 | 435000 | 435000 | 2018-06-11 | 100% | 0% | 0 | 0 | 435000
21 | 03312003 | Jester IV, Richmond | Roofing: Replace Roof - Psychiatric Facility | Economic Stabilization Fund No. 0599 | 2000000 | 2000000 | 2019-07-15 | 86% | 0% | 0 | 0 | 2000000
22 | 02217005 | Beto Unit, Tennessee Colony | Infrastructure: Install Transformer - Substation | Economic Stabilization Fund No. 0599 | 1571400 | 1721080 | 2018-12-02 | 0% | 0% | 0 | 0 | 1721080 | Yes
22 | 02217005 | Beto Unit, Tennessee Colony | Infrastructure: Install Transformer - Substation | Sale of Land Proceeds Account No. 0543 |  | 124520 | 2018-12-02 | 0% | 0% | 0 | 0 | 124520 | Yes
23 | 01717008 | Ramsey Unit, Rosharon | Roofing: Replace Roof - Main Building | Economic Stabilization Fund No. 0599 | 60900 | 60900 | 2018-05-05 | 100% | 0% | 737.4 | 0 | 60162.6
24 | 04813003 | McConnell Unit, Beeville | Infrastructure: Replace Steam & Condensate Lines | Economic Stabilization Fund No. 0599 | 687700 | 687700 | 2018-02-10 | 100% | 0% | 0 | 0 | 687700
25 | 03115010 | Hilltop Unit, Gatesville | Roofing: Replace Roof - Medical Department | Economic Stabilization Fund No. 0599 | 245600 | 245600 | 2018-11-02 | 100% | 0% | 663.35 | 0 | 244936.65 | Yes
26 | 03217006 | Estelle Unit, Huntsville | Facility Repair: Install Water Conservation System - Multiple Locations | Economic Stabilization Fund No. 0599 | 2596600 | 2596600 | 2018-12-30 | 100% | 0% | 0 | 0 | 2596600
27 | 04816012 | McConnell Unit, Beeville | Security: Replace Cell Doors - Multiple Locations | Economic Stabilization Fund No. 0599 | 350200 | 350200 | 2018-12-28 | N/A | 1% | 333350.4 | 0 | 16849.6 | Yes
28 | 01616002 | Mt. View Unit, Gatesville | Security: Replace Cell Doors - Administrative Segregation | Economic Stabilization Fund No. 0599 | 59300 | 59300 | 2018-01-15 | N/A | 1% | 56388 | 0 | 2912
29 | 05416004 | Polunsky Unit, Livingston | Security: Replace Cell Doors - Multiple Locations | Economic Stabilization Fund No. 0599 | 327400 | 336500 | 2018-03-01 | N/A | 1% | 336423 | 0 | 77 | Yes
30 | 02812001 | Powledge Unit, Palestine | Infrastructure: Repair Washout - Outfall Line - Wastewater Treatment Plant | Economic Stabilization Fund No. 0599 | 205800 | 205800 | 2018-06-16 | 100% | 2% | 40931.35 | 0 | 164868.65
31 | 03613004 | Michael Unit, Tennessee Colony | Roofing: Replace Roof - Multiple Buildings | Economic Stabilization Fund No. 0599 | 6500000 | 6500000 | 2020-01-15 | 81% | 0% | 0 | 0 | 6500000
32 | 03608011 | Michael Unit, Tennessee Colony | Safety: Repair/Replace Fire Line - Administrative Segregation | Economic Stabilization Fund No. 0599 | 474100 | 474100 | 2018-01-26 | 98% | 0% | 0 | 0 | 474100
33 | 01017018 | Ellis Unit, Huntsville | Infrastructure: Install Water Wells | Economic Stabilization Fund No. 0599 | 299000 | 299000 | 2018-01-12 | N/A | 3% | 282306.64 | 1207.36 | 15486
34 | 03615011 | Michael Unit, Tennessee Colony | Infrastructure: Replace Water Line - Between Well & Ground Storage | Economic Stabilization Fund No. 0599 | 50400 | 50400 | 2018-04-13 | 100% | 0% | 0 | 0 | 50400
|  |  |  | Totals: | 41635989 | 41999389 |  |  |  | 2778596.05 | 845573.44 | 38375219.51

## TFC
| Agency: | Texas Facilities Commission (303)
| Date: | 2017-12-15 | [9 empty] | 2017-12-15
| Prepared by: | John Raff, P.E.
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2016-17 Encumbered | FY 2016-17 Expended | Remaining Project Balance | Supp. Notes
1 | 303 | DROC | Replace deteriorated cooling water loop and pumps supplying cooling water to data center. | GR Funds | 2000000 | 2000000 | 2022-12-31 | 0% | 0% | 0 | 0 | 0 | No
2 | 303 | State Bldg/Air Handler Unit Replacements and DM Renovations at Various Buildings, Austin TX Insurance Annex (INX) William P. Clements (WPC) Robert E. Johnson (REJ) Price Daniel Sr. (PDB) Supreme Court Bldg (SCB) Tom C. Clark (TCC) | Renovation/Replacement of air handling units, outside air handling units, air distribution system and control; exterior cladding waterproofing repairs; emergency power and cooling connections and life safety systems. | GR Funds | 39000000 | 39000000 | 2022-12-31 | 0% | 0% | 0 | 0 | 0 | No
3 | 303 | DSHS/ Air Handler Unit Replacements and DM Renovations at Various Buildings, Austin TX DSHS Bldg. G (DHG) DSHS Building K (DHK) ? DSHS Tower Bldg. (DHT) DSHS Records Bldg. (DHR) Robert D Moreton (RDM) DSHS Building F (DHF) DSHS Service Building ( DHSB) Dr. Robert Bernstein Bldg. (RBB) | Renovation/Replacement of air handling units, outside air handling units, air distribution system and control; Structural/cladding/waterproofing repairs; and life safety systems. | GR Funds | 19500000 | 19500000 | 2022-12-31 | 0% | 0% | 0 | 0 | 0 | No
4 | 303 | Dr. Bob Glaze Laboratory Services (DBGL), Austin TX | Repair/Replace Mechanical systems and enhancement to indoor air quality; Replace/Repair of electrical and plumbing systems; Life safety and fire protection systems; repairs of exterior envelope; repair/replace roof. | GR Funds | 10000000 | 10000000 | 2022-12-31 | 0% | 0% | 0 | 0 | 0 | No
5 | 303 | El Paso (ELP) El Paso TX | Roof Replacement; Repair/Replace mechanical systems; structural/waterproofing repairs; Repair/Install Vestibule. | GR Funds | 1000000 | 1000000 | 2022-12-31 | 0% | 0% | 0 | 0 | 0 | No
6 | 303 | Stephen F. Austin, Austin TX William B. Travis, Austin, TX | Repair outside air handling units, Fire separations, lightning protection, plumbing and associated Accessibility. | GR Funds | 5850000 | 5850000 | 2022-12-31 | 0% | 0% | 0 | 0 | 0 | No
7 | 303 | Various Parking Garage Elevators Austin TX | Repair/replacement of elevators. | GR Funds | 2200000 | 2200000 | 2022-12-31 | 0% | 0% | 0 | 0 | 0 | No
8 | 303 | State Parking Garages Austin TX | Repairs to life safety and fire protection systems; repairs to electrical systems; sitework, building envelope, expansion joints and structural systems. | GR Funds | 5150000 | 5150000 | 2022-12-31 | 0% | 0% | 0 | 0 | 0 | No
9 | 303 | P35 Austin, TX | Repair/Replace Cooling tower; distribution system and associated controls | GR Funds | 2300000 | 2300000 | 2022-12-31 | 0% | 0% | 0 | 0 | 0 | No
10 | 303 | Program-wide Priority 1 Repairs | Priority IA and IB deferred maintenance deficiencies that have become an immediate need (I) and impact health and life safety of the building occupants (A) or threaten the continuity of operations for critical governemnt operations (B). These needs have advanced to an immediate stage since the proposed appropriation request developed in August of 2016 or may present as an immediate need through he course of the implementation of the 2018-19 deferred maintenance funding strategies. The list of funding strategies provided for the 2018-19 deferred maintenance appropriation request is provided as an exhibit for reference to qualify initiatives in this project. | GR Funds | 3000000 | 3000000 | 2019-12-31 | 0% | 0% | 0 | 0 | 0 | No
11 | 303
12 | 303
13 | 303
14 | 303
15 | 303
16 | 303
17 | 303
18 | 303
TBD | 303
TBD | 303
TBD | 303
TBD | 303
TBD | 303
TBD | 303
|  |  |  | Totals: | 90000000 | 90000000 |  |  |  | 0 | 0 | 90000000

## TxDOT
[8 empty] | 2668 | Texas Department of Transportation #601 |  | AY18/19 PROJECTS PLANNED | [8 empty] | Version: Final
[8 empty] | Date: | 2017-12-05
Priority Audit Trail | [7 empty] | Prepared by: | Diana Miller, Facilities Business Operations Manager - Support Services Division
[8 empty] | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q1 AY18) | Estimated Substantial Completion Date | % Design Completion | % Construction Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Comment
FY18 Q1 JOC Priority | FY18 Q2 JOC Priority | FY18 Q3 JOC Priority | FY18 Q4 JOC Priority | FY19 Q5 JOC Priority | FY19 Q6 JOC Priority | FY19 Q7 JOC Priority | FY19 Q8 JOC Priority
E1 | [7 empty] | 13470418179 | Building Renovation-Victoria | Capital Repairs | Highway Trans. Fund 6 | 1600000 | 1600000 | 2019-09-27 | 0% | 0% | 0 | 0 | 1600000
E2 | [7 empty] | 19470418181 | Building Renovation-Atlanta DHQ | Capital Repairs | Highway Trans. Fund 6 | 660000 | 660000 | 2018-07-03 | 0% | 0% | 0 | 0 | 660000
E3 | [7 empty] | 25470418060 | Building Renovation-Dickens | Capital Repairs | Highway Trans. Fund 6 | 360000 | 360000 | 2019-03-06 | 0% | 0% | 0 | 0 | 360000
E4 | [7 empty] | 24470418084 | CCURE Security Upgrades (including perimeter fencing)-DHQ | Safety/Security | Highway Trans. Fund 6 | 450000 | 450000 | 2019-02-13 | 0% | 0% | 0 | 0 | 450000
E5 | [7 empty] | 17470418059 | CCURE Security Upgrades (including perimeter fencing)-DHQ | Safety/Security | Highway Trans. Fund 6 | 350000 | 350000 | 2020-05-13 | 0% | 0% | 0 | 0 | 350000
E6 | [7 empty] | 16470418185 | CCURE Security Upgrades - Perimeter Fencing | Safety/Security | Highway Trans. Fund 6 | 297000 | 297000 | 2018-05-10 | 100% | 0% | 297000 | 0 | 0
E7 | [7 empty] | 09470418186 | Waco Roofing | Roofing | Highway Trans. Fund 6 | 308000 | 308000 | 2019-02-13 | 100% | 0% | 308000 | 0 | 0
1 | [7 empty] | 18470418063 | CCURE Security Upgrades (including perimeter fencing)-Corsciana | Safety/Security | Highway Trans. Fund 6 | 116667 | 116667 | 2019-01-16 | 0% | 0% | 0 | 0 | 116667
1.1 | [7 empty] | 18470418064 | CCURE Security Upgrades (including perimeter fencing)-Dallas (North) | Safety/Security | Highway Trans. Fund 6 | 116667 | 116667 | 2019-01-16 | 0% | 0% | 0 | 0 | 116667
1.2 | [7 empty] | 18470418065 | CCURE Security Upgrades (including perimeter fencing)-Dallas (Southwest) | Safety/Security | Highway Trans. Fund 6 | 116667 | 116667 | 2019-01-16 | 0% | 0% | 0 | 0 | 116667
1.3 | [7 empty] | 18470418066 | CCURE Security Upgrades (including perimeter fencing)-Denton | Safety/Security | Highway Trans. Fund 6 | 116667 | 116667 | 2019-01-16 | 0% | 0% | 0 | 0 | 116667
1.4 | [7 empty] | 18470418067 | CCURE Security Upgrades (including perimeter fencing)-McKinney | Safety/Security | Highway Trans. Fund 6 | 116667 | 116667 | 2019-01-16 | 0% | 0% | 0 | 0 | 116667
1.5 | [7 empty] | 18470418068 | CCURE Security Upgrades (including perimeter fencing)-Hutchins | Safety/Security | Highway Trans. Fund 6 | 116667 | 116667 | 2019-01-16 | 0% | 0% | 0 | 0 | 116667
4 | [7 empty] | 22470418109 | Roof Replacement-DHQ | Roofing | Highway Trans. Fund 6 | 360000 | 360000 | 2019-05-05 | 0% | 0% | 0 | 0 | 360000
4.1 | [7 empty] | 22470418110 | Roof Replacement-DHQ | Roofing | Highway Trans. Fund 6 | 240000 | 240000 | 2019-05-05 | 0% | 0% | 0 | 0 | 240000
4.2 | [7 empty] | 22470418111 | Roof Replacement-DHQ | Roofing | Highway Trans. Fund 6 | 120000 | 120000 | 2019-05-05 | 0% | 0% | 0 | 0 | 120000
6 | [7 empty] | 18470418061 | CCURE Security Upgrades (including perimeter fencing)-Rockwall | Safety/Security | Highway Trans. Fund 6 | 200000 | 200000 | 2019-01-16 | 0% | 0% | 0 | 0 | 200000
6.1 | [7 empty] | 18470418062 | CCURE Security Upgrades (including perimeter fencing)-Waxahachie | Safety/Security | Highway Trans. Fund 6 | 200000 | 200000 | 2019-01-16 | 0% | 0% | 0 | 0 | 200000
7 | [7 empty] | 02470418085 | CCURE Security Upgrades (including perimeter fencing)-Decatur | Safety/Security | Highway Trans. Fund 6 | 107520 | 107520 | 2019-04-18 | 0% | 0% | 0 | 0 | 107520
7.1 | [7 empty] | 02470418086 | CCURE Security Upgrades (including perimeter fencing)-Uless | Safety/Security | Highway Trans. Fund 6 | 107520 | 107520 | 2019-04-18 | 0% | 0% | 0 | 0 | 107520
7.2 | [7 empty] | 02470418087 | CCURE Security Upgrades (including perimeter fencing)-Keene | Safety/Security | Highway Trans. Fund 6 | 107520 | 107520 | 2019-04-18 | 0% | 0% | 0 | 0 | 107520
7.3 | [7 empty] | 02470418088 | CCURE Security Upgrades (including perimeter fencing)-Stephenville | Safety/Security | Highway Trans. Fund 6 | 107520 | 107520 | 2019-04-18 | 0% | 0% | 0 | 0 | 107520
7.4 | [7 empty] | 02470418089 | CCURE Security Upgrades (including perimeter fencing)-Weatherford | Safety/Security | Highway Trans. Fund 6 | 107520 | 107520 | 2019-04-18 | 0% | 0% | 0 | 0 | 107520
17 | [7 empty] | 22470418112 | Construct Concrete Flume with Detention Pond-DHQ | Site Work | Highway Trans. Fund 6 | 180000 | 180000 | 2018-12-01 | 0% | 0% | 0 | 0 | 180000
18 | [7 empty] | 12470418098 | CCURE Security Upgrades (including perimeter fencing)-Conroe | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-18 | 0% | 0% | 0 | 0 | 134400
18.1 | [7 empty] | 12470418099 | CCURE Security Upgrades (including perimeter fencing)-Houston (Northeast) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-18 | 0% | 0% | 0 | 0 | 134400
18.2 | [7 empty] | 12470418100 | CCURE Security Upgrades (including perimeter fencing)-Houston (Northwest) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-18 | 0% | 0% | 0 | 0 | 134400
18.3 | [7 empty] | 12470418101 | CCURE Security Upgrades (including perimeter fencing)-Houston (South) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-18 | 0% | 0% | 0 | 0 | 134400
18.4 | [7 empty] | 12470418102 | CCURE Security Upgrades (including perimeter fencing)-Humble | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-18 | 0% | 0% | 0 | 0 | 134400
18.5 | [7 empty] | 12470418103 | CCURE Security Upgrades (including perimeter fencing)-Lamarque | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-18 | 0% | 0% | 0 | 0 | 134400
18.6 | [7 empty] | 12470418104 | CCURE Security Upgrades (including perimeter fencing)-Rosenberg | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-03-18 | 0% | 0% | 0 | 0 | 134400
19 | [7 empty] | 02470418090 | CCURE Security Upgrades (including perimeter fencing)-Gordon | Safety/Security | Highway Trans. Fund 6 | 138240 | 138240 | 2019-04-18 | 0% | 0% | 0 | 0 | 138240
19.1 | [7 empty] | 02470418091 | CCURE Security Upgrades (including perimeter fencing)-Jacksboro | Safety/Security | Highway Trans. Fund 6 | 138240 | 138240 | 2019-04-18 | 0% | 0% | 0 | 0 | 138240
19.2 | [7 empty] | 02470418092 | CCURE Security Upgrades (including perimeter fencing)-Mineral Wells | Safety/Security | Highway Trans. Fund 6 | 138240 | 138240 | 2019-04-18 | 0% | 0% | 0 | 0 | 138240
19.3 | [7 empty] | 02470418093 | CCURE Security Upgrades (including perimeter fencing)-Saginaw | Safety/Security | Highway Trans. Fund 6 | 138240 | 138240 | 2019-04-18 | 0% | 0% | 0 | 0 | 138240
19.4 | [7 empty] | 02470418094 | CCURE Security Upgrades (including perimeter fencing)-Special Crews (Southeast) | Safety/Security | Highway Trans. Fund 6 | 138240 | 138240 | 2019-04-18 | 0% | 0% | 0 | 0 | 138240
30 | [7 empty] | 22470418113 | Parking Lot Expansion (Northeast)-DHQ | Site Work | Highway Trans. Fund 6 | 120000 | 120000 | 2018-12-01 | 0% | 0% | 0 | 0 | 120000
33 | [7 empty] | 24470418069 | CCURE Security Upgrades (including perimeter fencing)-Alpine | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-02-13 | 0% | 0% | 0 | 0 | 134400
33.1 | [7 empty] | 24470418070 | CCURE Security Upgrades (including perimeter fencing)-El Paso (East) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-18 | 0% | 0% | 0 | 0 | 134400
33.2 | [7 empty] | 24470418071 | CCURE Security Upgrades (including perimeter fencing)-El Paso (West) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-18 | 0% | 0% | 0 | 0 | 134400
35 | [7 empty] | 17470418049 | CCURE Security Upgrades (including perimeter fencing)-Brenham | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-05-13 | 0% | 0% | 0 | 0 | 100800
35.1 | [7 empty] | 17470418050 | CCURE Security Upgrades (including perimeter fencing)-Bryan | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-05-13 | 0% | 0% | 0 | 0 | 100800
35.2 | [7 empty] | 17470418051 | CCURE Security Upgrades (including perimeter fencing)-Hearne | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-05-13 | 0% | 0% | 0 | 0 | 100800
35.3 | [7 empty] | 17470418052 | CCURE Security Upgrades (including perimeter fencing)-Huntsville | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-05-13 | 0% | 0% | 0 | 0 | 100800
38 | [7 empty] | 05470418117 | CCURE Security Upgrades (including perimeter fencing)-Brownfield | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-05-18 | 0% | 0% | 0 | 0 | 134400
38.1 | [7 empty] | 05470418118 | CCURE Security Upgrades (including perimeter fencing)-Littlefield | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-04-20 | 0% | 0% | 0 | 0 | 134400
38.2 | [7 empty] | 05470418119 | CCURE Security Upgrades (including perimeter fencing)-Plainview | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-04-20 | 0% | 0% | 0 | 0 | 134400
38.3 | [7 empty] | 05470418120 | CCURE Security Upgrades (including perimeter fencing)-Post RDC | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2020-05-18 | 0% | 0% | 0 | 0 | 134400
39 | [7 empty] | 22470418114 | Building Renovation-Comstock | Capital Repairs | Highway Trans. Fund 6 | 420000 | 420000 | 2019-03-10 | 0% | 0% | 0 | 0 | 420000
43 | [7 empty] | 02470418095 | Construct Box Culvert (Drainage Improvements)-DHQ | Site Work | Highway Trans. Fund 6 | 1200000 | 1200000 | 2019-04-07 | 0% | 0% | 0 | 0 | 1200000
43.1 | [7 empty] | 02470418096 | Parking Lot Resurface-DHQ | Site Work | Highway Trans. Fund 6 | 240000 | 240000 | 2019-04-07 | 0% | 0% | 0 | 0 | 240000
50 | [7 empty] | 12470418105 | Building Renovation-Houston NW | Capital Repairs | Highway Trans. Fund 6 | 3000000 | 3441429.3333 | 2019-03-04 | 0% | 0% | 0 | 0 | 3441429.3333
54 | [7 empty] | 24470418072 | CCURE Security Upgrades (including perimeter fencing)-Canutillo | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-04-18 | 0% | 0% | 0 | 0 | 109964
54.1 | [7 empty] | 24470418073 | CCURE Security Upgrades (including perimeter fencing)-Dell City | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-04-18 | 0% | 0% | 0 | 0 | 109964
54.2 | [7 empty] | 24470418074 | CCURE Security Upgrades (including perimeter fencing)-Fort Davis | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-02-13 | 0% | 0% | 0 | 0 | 109964
54.3 | [7 empty] | 24470418075 | CCURE Security Upgrades (including perimeter fencing)-Fort Hancock | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-04-18 | 0% | 0% | 0 | 0 | 109964
54.4 | [7 empty] | 24470418076 | CCURE Security Upgrades (including perimeter fencing)-Marathon | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-02-13 | 0% | 0% | 0 | 0 | 109964
54.5 | [7 empty] | 24470418077 | CCURE Security Upgrades (including perimeter fencing)-Marfa | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-02-13 | 0% | 0% | 0 | 0 | 109964
54.6 | [7 empty] | 24470418078 | CCURE Security Upgrades (including perimeter fencing)-Pine Springs | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-04-18 | 0% | 0% | 0 | 0 | 109964
54.7 | [7 empty] | 24470418079 | CCURE Security Upgrades (including perimeter fencing)-Presidio | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-02-13 | 0% | 0% | 0 | 0 | 109964
54.8 | [7 empty] | 24470418080 | CCURE Security Upgrades (including perimeter fencing)-Sierra Blanca | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-04-18 | 0% | 0% | 0 | 0 | 109964
54.9 | [7 empty] | 24470418081 | CCURE Security Upgrades (including perimeter fencing)-Terlingua | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-02-13 | 0% | 0% | 0 | 0 | 109964
54.95 | [7 empty] | 24470418082 | CCURE Security Upgrades (including perimeter fencing)-Van Horn | Safety/Security | Highway Trans. Fund 6 | 109964 | 109964 | 2019-02-13 | 0% | 0% | 0 | 0 | 109964
56 | [7 empty] | 14470418034 | CCURE Security Upgrades (including perimeter fencing)-Austin (East) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
56.1 | [7 empty] | 14470418035 | CCURE Security Upgrades (including perimeter fencing)-Austin (Northwest) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
56.2 | [7 empty] | 14470418036 | CCURE Security Upgrades (including perimeter fencing)-Austin (West/Southwest) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
56.3 | [7 empty] | 14470418037 | CCURE Security Upgrades (including perimeter fencing)-Fredericksburg | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
56.4 | [7 empty] | 14470418038 | CCURE Security Upgrades (including perimeter fencing)-Johnson City | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
56.5 | [7 empty] | 14470418039 | CCURE Security Upgrades (including perimeter fencing)-Llano | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
56.6 | [7 empty] | 14470418040 | CCURE Security Upgrades (including perimeter fencing)-Lockhart | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
56.7 | [7 empty] | 14470418041 | CCURE Security Upgrades (including perimeter fencing)-Mason | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
56.8 | [7 empty] | 14470418042 | CCURE Security Upgrades (including perimeter fencing)-San Marcos | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
56.9 | [7 empty] | 14470418043 | CCURE Security Upgrades (including perimeter fencing)-Taylor | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
58 | [7 empty] | 17470418053 | CCURE Security Upgrades (including perimeter fencing)-Buffalo | Safety/Security | Highway Trans. Fund 6 | 156800 | 156800 | 2020-05-13 | 0% | 0% | 0 | 0 | 156800
58.1 | [7 empty] | 17470418054 | CCURE Security Upgrades (including perimeter fencing)-Caldwell | Safety/Security | Highway Trans. Fund 6 | 156800 | 156800 | 2020-05-13 | 0% | 0% | 0 | 0 | 156800
58.2 | [7 empty] | 17470418055 | CCURE Security Upgrades (including perimeter fencing)-Cameron | Safety/Security | Highway Trans. Fund 6 | 156800 | 156800 | 2020-05-13 | 0% | 0% | 0 | 0 | 156800
58.3 | [7 empty] | 17470418056 | CCURE Security Upgrades (including perimeter fencing)-Fairfield | Safety/Security | Highway Trans. Fund 6 | 156800 | 156800 | 2020-05-13 | 0% | 0% | 0 | 0 | 156800
58.4 | [7 empty] | 17470418057 | CCURE Security Upgrades (including perimeter fencing)-Madisonville | Safety/Security | Highway Trans. Fund 6 | 156800 | 156800 | 2020-05-13 | 0% | 0% | 0 | 0 | 156800
58.5 | [7 empty] | 17470418058 | CCURE Security Upgrades (including perimeter fencing)-Navasota | Safety/Security | Highway Trans. Fund 6 | 156800 | 156800 | 2020-05-13 | 0% | 0% | 0 | 0 | 156800
60 | [7 empty] | 05470418121 | CCURE Security Upgrades (including perimeter fencing)-Bovina | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-20 | 0% | 0% | 0 | 0 | 155100
60.05 | [7 empty] | 05470418122 | CCURE Security Upgrades (including perimeter fencing)-Dimmitt | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-20 | 0% | 0% | 0 | 0 | 155100
60.1 | [7 empty] | 05470418123 | CCURE Security Upgrades (including perimeter fencing)-Floydada | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-20 | 0% | 0% | 0 | 0 | 155100
60.15 | [7 empty] | 05470418124 | CCURE Security Upgrades (including perimeter fencing)-Lamesa | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-18 | 0% | 0% | 0 | 0 | 155100
60.2 | [7 empty] | 05470418125 | CCURE Security Upgrades (including perimeter fencing)-Levelland | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-18 | 0% | 0% | 0 | 0 | 155100
60.25 | [7 empty] | 05470418126 | CCURE Security Upgrades (including perimeter fencing)-Lubbock (Northeast) | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-18 | 0% | 0% | 0 | 0 | 155100
60.3 | [7 empty] | 05470418127 | CCURE Security Upgrades (including perimeter fencing)-Morton | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-20 | 0% | 0% | 0 | 0 | 155100
60.35 | [7 empty] | 05470418128 | CCURE Security Upgrades (including perimeter fencing)-Muleshoe | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-20 | 0% | 0% | 0 | 0 | 155100
60.4 | [7 empty] | 05470418129 | CCURE Security Upgrades (including perimeter fencing)-Plains | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-18 | 0% | 0% | 0 | 0 | 155100
60.45 | [7 empty] | 05470418130 | CCURE Security Upgrades (including perimeter fencing)-Ralls | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-18 | 0% | 0% | 0 | 0 | 155100
60.5 | [7 empty] | 05470418131 | CCURE Security Upgrades (including perimeter fencing)-Seminole | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-18 | 0% | 0% | 0 | 0 | 155100
60.55 | [7 empty] | 05470418132 | CCURE Security Upgrades (including perimeter fencing)-Tahoka | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-05-18 | 0% | 0% | 0 | 0 | 155100
60.6 | [7 empty] | 05470418133 | CCURE Security Upgrades (including perimeter fencing)-Tulia | Safety/Security | Highway Trans. Fund 6 | 155100 | 155100 | 2020-04-20 | 0% | 0% | 0 | 0 | 155100
65 | [7 empty] | 12470418106 | Building Demolition-Houston NW | Site Work | Highway Trans. Fund 6 | 240000 | 240000 | 2019-03-04 | 0% | 0% | 0 | 0 | 240000
69 | [7 empty] | 07470418153 | Installation of Above-Ground Fuel Tank-Big Lake | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-03-31 | 0% | 0% | 0 | 0 | 420000
76 | [7 empty] | 15470418158 | Laboratory Building Renovation-DHQ | Capital Repairs | Highway Trans. Fund 6 | 2640000 | 2640000 | 2019-03-31 | 0% | 0% | 0 | 0 | 2640000
79 | [7 empty] | 12470418107 | Replacement of Generator (Campus-wide)-Houston NW | HVAC | Highway Trans. Fund 6 | 360000 | 360000 | 2019-03-03 | 0% | 0% | 0 | 0 | 360000
80 | [7 empty] | 21470418141 | CCURE Security Upgrades (including perimeter fencing)-Hebbronville | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-12 | 0% | 0% | 0 | 0 | 100800
80.1 | [7 empty] | 21470418142 | CCURE Security Upgrades (including perimeter fencing)-Pharr | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-12 | 0% | 0% | 0 | 0 | 100800
80.2 | [7 empty] | 21470418143 | CCURE Security Upgrades (including perimeter fencing)-Rio Grande City | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-12 | 0% | 0% | 0 | 0 | 100800
80.3 | [7 empty] | 21470418144 | CCURE Security Upgrades (including perimeter fencing)-San Benito | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-12 | 0% | 0% | 0 | 0 | 100800
82 | [7 empty] | 07470418154 | Installation of Above-Ground Fuel Tank-San Angelo | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-03-31 | 0% | 0% | 0 | 0 | 420000
84 | [7 empty] | 04470418002 | CCURE Security Upgrades (including perimeter fencing)-Amarillo (East) | Safety/Security | Highway Trans. Fund 6 | 112000 | 112000 | 2019-10-03 | 0% | 0% | 0 | 0 | 112000
84.1 | [7 empty] | 04470418003 | CCURE Security Upgrades (including perimeter fencing)-Canyon | Safety/Security | Highway Trans. Fund 6 | 112000 | 112000 | 2019-10-03 | 0% | 0% | 0 | 0 | 112000
84.2 | [7 empty] | 04470418004 | CCURE Security Upgrades (including perimeter fencing)-Dumas | Safety/Security | Highway Trans. Fund 6 | 112000 | 112000 | 2019-10-30 | 0% | 0% | 0 | 0 | 112000
84.3 | [7 empty] | 04470418005 | CCURE Security Upgrades (including perimeter fencing)-Pampa | Safety/Security | Highway Trans. Fund 6 | 112000 | 112000 | 2019-10-30 | 0% | 0% | 0 | 0 | 112000
87 | [7 empty] | 09470418168 | Well Improvements and Waterline Replacement-Marlin | Capital Repairs | Highway Trans. Fund 6 | 180000 | 180000 | TBD | 0% | 0% | 0 | 0 | 180000
92 | [7 empty] | 13470418177 | Building Renovation-DHQ | Capital Repairs | Highway Trans. Fund 6 | 1800000 | 1800000 | 2019-06-09 | 0% | 0% | 0 | 0 | 1800000
100 | [7 empty] | 15470418159 | Building Renovation-Transguide | Capital Repairs | Highway Trans. Fund 6 | 1680000 | 1680000 | 2019-03-29 | 0% | 0% | 0 | 0 | 1680000
102 | [7 empty] | 24470418083 | Building Renovation-DHQ | Capital Repairs | Highway Trans. Fund 6 | 270000 | 270000 | 2019-02-19 | 0% | 0% | 0 | 0 | 270000
103 | [7 empty] | 21470418145 | CCURE Security Upgrades (including perimeter fencing)-Brownsville | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-02-12 | 0% | 0% | 0 | 0 | 172800
103.1 | [7 empty] | 21470418146 | CCURE Security Upgrades (including perimeter fencing)-Edcouch | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-02-12 | 0% | 0% | 0 | 0 | 172800
103.2 | [7 empty] | 21470418147 | CCURE Security Upgrades (including perimeter fencing)-Falfurrias | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-02-12 | 0% | 0% | 0 | 0 | 172800
103.3 | [7 empty] | 21470418148 | CCURE Security Upgrades (including perimeter fencing)-Mission | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-02-12 | 0% | 0% | 0 | 0 | 172800
103.4 | [7 empty] | 21470418149 | CCURE Security Upgrades (including perimeter fencing)-Raymondville | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-02-12 | 0% | 0% | 0 | 0 | 172800
103.5 | [7 empty] | 21470418150 | CCURE Security Upgrades (including perimeter fencing)-Santa Isidro | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-02-12 | 0% | 0% | 0 | 0 | 172800
103.6 | [7 empty] | 21470418151 | CCURE Security Upgrades (including perimeter fencing)-Zapata | Safety/Security | Highway Trans. Fund 6 | 172800 | 172800 | 2020-02-12 | 0% | 0% | 0 | 0 | 172800
106 | [7 empty] | 07470418155 | Installation of Above-Ground Fuel Tank-DHQ | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-03-31 | 0% | 0% | 0 | 0 | 420000
107 | [7 empty] | 04470418006 | CCURE Security Upgrades (including perimeter fencing)-Amarillo | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-03 | 0% | 0% | 0 | 0 | 120000
107.05 | [7 empty] | 04470418007 | CCURE Security Upgrades (including perimeter fencing)-Borger | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-30 | 0% | 0% | 0 | 0 | 120000
107.1 | [7 empty] | 04470418008 | CCURE Security Upgrades (including perimeter fencing)-Canadian | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-30 | 0% | 0% | 0 | 0 | 120000
107.15 | [7 empty] | 04470418009 | CCURE Security Upgrades (including perimeter fencing)-Channing | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-03 | 0% | 0% | 0 | 0 | 120000
107.2 | [7 empty] | 04470418010 | CCURE Security Upgrades (including perimeter fencing)-Claude | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-03 | 0% | 0% | 0 | 0 | 120000
107.25 | [7 empty] | 04470418011 | CCURE Security Upgrades (including perimeter fencing)-Dalhart | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-30 | 0% | 0% | 0 | 0 | 120000
107.3 | [7 empty] | 04470418012 | CCURE Security Upgrades (including perimeter fencing)-Darrouzett | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-30 | 0% | 0% | 0 | 0 | 120000
107.35 | [7 empty] | 04470418013 | CCURE Security Upgrades (including perimeter fencing)-Groom | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-03 | 0% | 0% | 0 | 0 | 120000
107.4 | [7 empty] | 04470418014 | CCURE Security Upgrades (including perimeter fencing)-Groover | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-30 | 0% | 0% | 0 | 0 | 120000
107.45 | [7 empty] | 04470418015 | CCURE Security Upgrades (including perimeter fencing)-Hereford | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-03 | 0% | 0% | 0 | 0 | 120000
107.5 | [7 empty] | 04470418016 | CCURE Security Upgrades (including perimeter fencing)-Panhandle | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-03 | 0% | 0% | 0 | 0 | 120000
107.55 | [7 empty] | 04470418017 | CCURE Security Upgrades (including perimeter fencing)-Perrington | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-30 | 0% | 0% | 0 | 0 | 120000
107.6 | [7 empty] | 04470418018 | CCURE Security Upgrades (including perimeter fencing)-Stratford | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-30 | 0% | 0% | 0 | 0 | 120000
107.65 | [7 empty] | 04470418019 | CCURE Security Upgrades (including perimeter fencing)-Vega | Safety/Security | Highway Trans. Fund 6 | 120000 | 120000 | 2019-10-03 | 0% | 0% | 0 | 0 | 120000
108 | [7 empty] | 11470418135 | CCURE Security Upgrades (including perimeter fencing)-Center | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-05-13 | 0% | 0% | 0 | 0 | 156801
108.1 | [7 empty] | 11470418136 | CCURE Security Upgrades (including perimeter fencing)-Crockett | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-05-13 | 0% | 0% | 0 | 0 | 156801
108.2 | [7 empty] | 11470418137 | CCURE Security Upgrades (including perimeter fencing)-Groveton | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-05-13 | 0% | 0% | 0 | 0 | 156801
108.3 | [7 empty] | 11470418138 | CCURE Security Upgrades (including perimeter fencing)-Hemphill | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-05-13 | 0% | 0% | 0 | 0 | 156801
108.4 | [7 empty] | 11470418139 | CCURE Security Upgrades (including perimeter fencing)-Lufkin | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-05-13 | 0% | 0% | 0 | 0 | 156801
108.5 | [7 empty] | 11470418140 | CCURE Security Upgrades (including perimeter fencing)-Sheperd | Safety/Security | Highway Trans. Fund 6 | 156801 | 156801 | 2020-05-13 | 0% | 0% | 0 | 0 | 156801
110 | [7 empty] | 19470418020 | CCURE Security Upgrades (including perimeter fencing)-Gilmer | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-24 | 0% | 0% | 0 | 0 | 100800
110.1 | [7 empty] | 19470418021 | CCURE Security Upgrades (including perimeter fencing)-Marshall | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-24 | 0% | 0% | 0 | 0 | 100800
110.2 | [7 empty] | 19470418022 | CCURE Security Upgrades (including perimeter fencing)-Mount Pleasant | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-24 | 0% | 0% | 0 | 0 | 100800
110.3 | [7 empty] | 19470418023 | CCURE Security Upgrades (including perimeter fencing)-Texarkana | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2020-02-24 | 0% | 0% | 0 | 0 | 100800
113 | [7 empty] | 22470418115 | Building Renovation-La Pryor | Capital Repairs | Highway Trans. Fund 6 | 600000 | 600000 | 2019-03-09 | 0% | 0% | 0 | 0 | 600000
120 | [7 empty] | 13470418178 | Building Renovation-DHQ | Capital Repairs | Highway Trans. Fund 6 | 1920000 | 1920000 | 2019-06-09 | 0% | 0% | 0 | 0 | 1920000
121 | [7 empty] | 05470418134 | Building Renovation-Plains | Capital Repairs | Highway Trans. Fund 6 | 1080000 | 1080000 | 2019-05-26 | 0% | 0% | 0 | 0 | 1080000
123 | [7 empty] | 12470418108 | Installation of Above-Ground Fuel Tank-Houston NW | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-03-04 | 0% | 0% | 0 | 0 | 420000
133 | [7 empty] | 07470418156 | Installation of Above-Ground Fuel Tank-Junction | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-03-31 | 0% | 0% | 0 | 0 | 420000
134 | [7 empty] | 13470418180 | Generator Replacement-DHQ | Safety/Security | Highway Trans. Fund 6 | 720000 | 720000 | 2019-06-09 | 0% | 0% | 0 | 0 | 720000
139 | [7 empty] | 03470418173 | CCURE Security Upgrades (including perimeter fencing)-Gainsville | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2019-03-05 | 0% | 0% | 0 | 0 | 100800
139.1 | [7 empty] | 03470418174 | CCURE Security Upgrades (including perimeter fencing)-Graham | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2019-03-05 | 0% | 0% | 0 | 0 | 100800
139.2 | [7 empty] | 03470418175 | CCURE Security Upgrades (including perimeter fencing)-Vernon | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2019-03-05 | 0% | 0% | 0 | 0 | 100800
139.3 | [7 empty] | 03470418176 | CCURE Security Upgrades (including perimeter fencing)-Wichita Falls | Safety/Security | Highway Trans. Fund 6 | 100800 | 100800 | 2019-03-05 | 0% | 0% | 0 | 0 | 100800
140 | [7 empty] | 19470418024 | CCURE Security Upgrades (including perimeter fencing)-Carthage | Safety/Security | Highway Trans. Fund 6 | 161280 | 161280 | 2020-02-24 | 0% | 0% | 0 | 0 | 161280
140.1 | [7 empty] | 19470418025 | CCURE Security Upgrades (including perimeter fencing)-Daingerfield | Safety/Security | Highway Trans. Fund 6 | 161280 | 161280 | 2020-02-24 | 0% | 0% | 0 | 0 | 161280
140.2 | [7 empty] | 19470418026 | CCURE Security Upgrades (including perimeter fencing)-Jefferson | Safety/Security | Highway Trans. Fund 6 | 161280 | 161280 | 2020-02-24 | 0% | 0% | 0 | 0 | 161280
140.3 | [7 empty] | 19470418027 | CCURE Security Upgrades (including perimeter fencing)-Linden | Safety/Security | Highway Trans. Fund 6 | 161280 | 161280 | 2020-02-24 | 0% | 0% | 0 | 0 | 161280
140.4 | [7 empty] | 19470418028 | CCURE Security Upgrades (including perimeter fencing)-New Boston | Safety/Security | Highway Trans. Fund 6 | 161280 | 161280 | 2020-02-24 | 0% | 0% | 0 | 0 | 161280
142 | [7 empty] | 02470418097 | Building Renovation-DHQ | Capital Repairs | Highway Trans. Fund 6 | 3600000 | 4041429.3333 | 2019-05-26 | 0% | 0% | 0 | 0 | 4041429.3333
143 | [7 empty] | 14470418044 | Drainage Improvements-San Marcos | Site Work | Highway Trans. Fund 6 | 60000 | 60000 | 2018-12-27 | 0% | 0% | 0 | 0 | 60000
147 | [7 empty] | 21470418152 | Building Renovation-DHQ | Capital Repairs | Highway Trans. Fund 6 | 3360000 | 3801429.3333 | 2019-04-10 | 0% | 0% | 0 | 0 | 3801429.3333
148 | [7 empty] | 22470418116 | Building Renovation-Brackettville | Capital Repairs | Highway Trans. Fund 6 | 300000 | 300000 | 2019-03-11 | 0% | 0% | 0 | 0 | 300000
158 | [7 empty] | 07470418157 | Installation of Above-Ground Fuel Tank-Menard | Site Work | Highway Trans. Fund 6 | 420000 | 420000 | 2019-03-31 | 0% | 0% | 0 | 0 | 420000
195 | [7 empty] | 14470418182 | Roof Replacement-South Travis MNT | Roofing | Highway Trans. Fund 6 | 350000 | 350000 | 2018-12-01 | 0% | 0% | 0 | 0 | 350000
282 | [7 empty] | 14470418029 | CCURE Security Upgrades (including perimeter fencing)-Austin (North) | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
282.1 | [7 empty] | 14470418030 | CCURE Security Upgrades (including perimeter fencing)-Austin | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
282.2 | [7 empty] | 14470418031 | CCURE Security Upgrades (including perimeter fencing)-Bastrop | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
282.3 | [7 empty] | 14470418032 | CCURE Security Upgrades (including perimeter fencing)-Burnett | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
282.4 | [7 empty] | 14470418033 | CCURE Security Upgrades (including perimeter fencing)-Georgetown | Safety/Security | Highway Trans. Fund 6 | 134400 | 134400 | 2019-04-29 | 0% | 0% | 0 | 0 | 134400
U1 | [8 empty] | Statewide Unspecified Repairs | Safety/Security | Highway Trans. Fund 6 | 1324288 | 1324288 | TBD | 0% | 0% | 0 | 0 | 1324288
PROJECTS LISTED ABOVE CURRENTLY FUNDED $50M | [11 empty] | 50000000 | 50000000 |  |  |  | 605000 | 0 | 49395000
Note on A7: Diana Miller: Projects in Priority Order based on TxDOT 10Year Master Plan

## TxDOT 18-19 New Construction
[8 empty] | 2668 | Texas Department of Transportation #601 |  | AY18/19 RADIO TOWER PROJECTS PLANNED | [8 empty] | Version: Final
[8 empty] | Date: | 2017-12-05
Priority Audit Trail | [7 empty] | Prepared by: | Diana Miller, Facilities Business Operations Manager - Support Services Division
[8 empty] | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for Q1 AY18) | Estimated Substantial Completion Date | % Design Completion | % Construction Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Comment
FY18 Q1 JOC Priority | FY18 Q2 JOC Priority | FY18 Q3 JOC Priority | FY18 Q4 JOC Priority | FY19 Q5 JOC Priority | FY19 Q6 JOC Priority | FY19 Q7 JOC Priority | FY19 Q8 JOC Priority
ERT 1 | [7 empty] | 20470418604 | Radio Tower Replacement of 400 - Beaumont | New Construction | Highway Trans. Fund 6 | 502788 | 502788 | 2018-03-05 | 100% | 0% | 502788 | 0 | 0
442 | [7 empty] | 03470418613 | Radio Tower Replacement of 175' - Wichita Falls | New Construction | Highway Trans. Fund 6 | 250000 | 250000 | 2018-08-24 | 0% | 0% | 0 | 0 | 250000
461 | [7 empty] | 03470418614 | Radio Tower Replacement of 175' - Wichita Falls | New Construction | Highway Trans. Fund 6 | 250000 | 250000 | 2018-08-24 | 0% | 0% | 0 | 0 | 250000
504 | [7 empty] | 25470418612 | Radio Tower Replacement of 175' - Childress | New Construction | Highway Trans. Fund 6 | 250000 | 250000 | 2018-10-25 | 0% | 0% | 0 | 0 | 250000
615 | [7 empty] | 14470418602 | Radio Tower Replacement of 350' - Austin | New Construction | Highway Trans. Fund 6 | 450000 | 450000 | 2018-04-30 | 0% | 0% | 0 | 0 | 450000
630 | [7 empty] | 14470418601 | Radio Tower Replacement of 350' - Austin | New Construction | Highway Trans. Fund 6 | 450000 | 450000 | 2018-09-14 | 0% | 0% | 0 | 0 | 450000
648 | [7 empty] | 14470418603 | Radio Tower Replacement of 350' - Austin | New Construction | Highway Trans. Fund 6 | 450000 | 450000 | 2018-05-17 | 0% | 0% | 0 | 0 | 450000
700 | [7 empty] | 21470418607 | Radio Tower Replacement of 300' - Pharr | New Construction | Highway Trans. Fund 6 | 400000 | 400000 | 2018-08-02 | 0% | 0% | 0 | 0 | 400000
705 | [7 empty] | 23470418605 | Radio Tower Replacement of 175' - Brownwood | New Construction | Highway Trans. Fund 6 | 250000 | 250000 | 2018-04-26 | 0% | 0% | 0 | 0 | 250000
706 | [7 empty] | 19470418610 | Radio Tower Replacement of 175' - Atlanta | New Construction | Highway Trans. Fund 6 | 250000 | 250000 | 2018-07-26 | 0% | 0% | 0 | 0 | 250000
712 | [7 empty] | 04470418615 | Radio Tower Replacement of 175' - Amarillo | New Construction | Highway Trans. Fund 6 | 250000 | 250000 | 2018-06-28 | 0% | 0% | 0 | 0 | 250000
713 | [7 empty] | 19470418611 | Radio Tower Replacement of 175' - Atlanta | New Construction | Highway Trans. Fund 6 | 250000 | 250000 | 2018-07-26 | 0% | 0% | 0 | 0 | 250000
719 | [7 empty] | 04470418609 | Radio Tower Replacement of 350' - Amarillo | New Construction | Highway Trans. Fund 6 | 450000 | 450000 | 2018-06-28 | 0% | 0% | 0 | 0 | 450000
732 | [7 empty] | 17470418606 | Radio Tower Replacement of 300' - Bryan | New Construction | Highway Trans. Fund 6 | 400000 | 400000 | 2018-06-28 | 0% | 0% | 0 | 0 | 400000
743 | [7 empty] | 07470418608 | Radio Tower Replacement of 300' - San Angelo | New Construction | Highway Trans. Fund 6 | 400000 | 400000 | 2018-05-25 | 0% | 0% | 0 | 0 | 400000
U2 | [8 empty] | Unanticipated Emergency Tower Replacement | New Construction | Highway Trans. Fund 6 | 747212 | 747212 | TBD | 0% | 0% | 0 | 0 | 747212
[12 empty] | 6000000 | 6000000 |  |  |  | 502788 | 0 | 5497212
1NC | [7 empty] | 38470418001 | AHQ Consolidation Design | New Construction | Highway Trans. Fund 6 | 30000000 | 30000000 | TBD | 0% | 0% | 0 | 0 | 30000000
Note on A7: Diana Miller: Projects in Priority Order based on TxDOT 10Year Master Plan
Note on C7: Diana Miller: Now Ordering based on Start Sheet Dates

## THC
| Agency: | Texas Historical Commission (808)
| Date: | 2017-12-12
| Prepared by: | Corey Crawford
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 808-18-0450 | Mission Dolores State Historic Site, San Augustine, San Augustine County, Texas | Renovate the museum and laboratory buildings and construct a maintenance building to provide an improved educational experience to visitors. | Economic Stabilization Fund (Fund 0599) | 1425000 | 1425000 | 2019-08-31 | 0% | 0% | 13852 | 0 | 1411148 | Yes
2 | 808-17-0452 | San Felipe de Austin State Historic Site, San Felipe, Austin County, Texas | Construct a new museum, exhibits and maintenance building to provide an improved educational experience to visitors. | Economic Stabilization Fund (Fund 0599) & General Revenue - Sporting Goods Sales Tax (Fund 0001) | 2000000 | 2000000 |  |  |  | 704279.09 | 0 | 1295720.91 | Yes
3 | 808-18-0449 | National Museum of the Pacific War, Fredericksburg, Gillespie County, Texas | Renovate the interior of the Admiral Nimitz Hotel to enhance efficiency and improve the visitor experience. | Economic Stabilization Fund (Fund 0599) | 2000000 | 2000000 | 2019-08-31 | 0% | 0% | 0 | 0 | 2000000 | Yes
4 | 808-18-X1B55 | Roof Repairs - State Historic Sites (Statewide) | FY 18: Conduct necessary roof repairs at various sites in order to safeguard the buildings and their contents. | Economic Stabilization Fund (Fund 0599) | 102000 | 102000 | 2018-08-31 | 0% | 0% | 0 | 0 | 102000 | Yes
5 | 808-18-X2G41 | Interior Renovations - State Historic Sites (Statewide) | FY 18: Conduct renovations to various buildings in order to enhance function and interpretation | Economic Stabilization Fund (Fund 0599) | 73000 | 73000 | 2018-08-31 | 0% | 0% | 0 | 0 | 73000 | Yes
6 | 808-18-STAFF | Mission Dolores State Historic Site, San Augustine, San Augustine County, Texas | Mission Dolores State Historic Site - Staffing (two years) | Economic Stabilization Fund (Fund 0599) | 575000 | 575000 | 2019-08-31 |  |  | 3693.96 | 63355.44 | 507950.6 | Yes
7 | 808-19-X1B56 | Roof Repairs - State Historic Sites (Statewide) | FY 19: Conduct necessary roof repairs at various sites in order to safeguard the buildings and their contents. | Economic Stabilization Fund (Fund 0599) | 102000 | 102000 | 2019-08-31 | 0% | 0% | 0 | 0 | 102000 | Yes
8 | 808-19-X2G42 | Interior Renovations - State Historic Sites (Statewide) | FY 19: Conduct renovations to various buildings in order to enhance function and interpretation | Economic Stabilization Fund (Fund 0599) | 73000 | 73000 | 2019-08-31 | 0% | 0% | 0 | 0 | 73000 | Yes
|  |  |  | Totals: | 6350000 | 6350000 |  |  |  | 721825.05 | 63355.44 | 5564819.51

## THC Supp.
| Agency: | Texas Historical Commission (808)
| Date: | 2017-09-26
| Prepared by: | Corey Crawford
Project Priority | Supplemental Information
1, 6 | Texas Historical Commission Rider 26 requires THC to not spend less than $1,425,000 on Deferred Maintenance projects at the Mission Dolores State Historic Site. The remaining $575,000 is intended for staffing at the site for FYs 2018-2019. RFP is currently in development. THC Rider 2 splits the capital funding evenly $712,500 in each year of the biennium.
2 | This is a continuation of the new Construction project for which appropriations were made by the 83rd and 84th Legislatures. This is funded with $750,000 of Economic Stabilization Funds (Fund 0599) and $1,250,000 of GR - Sporting Goods Sales Tax (Fund 0001). THC Rider 26 requires not less than $2,000,000 be spent on the San Felipe de Austin State Historic Site. THC Rider 2 splits the capital funding evenly $1,000,000 in each year of the biennium.
3 | THC Rider 26 requires not less than $2,000,000 be spent on the National Museum of the Pacific War. RFP is currently in development. THC Rider 2 splits the capital funding evenly $1,000,000 in each year of the biennium.
4, 7 | THC Rider 26 requires not less than $350,000 be spent on the deferred maintenance projects at State Historic Sites. THC Rider 2 splits the capital funding evenly $175,000 in each year of the biennium. There are multiple sites with roof replacement needs.
5, 8 | THC Rider 26 requires not less than $350,000 be spent on the deferred maintenance projects at State Historic Sites. THC Rider 2 splits the capital funding evenly $175,000 in each year of the biennium. There are multiple sites with interior renovation needs.

## SPB
| Agency: | STATE PRESERVATION BOARD (809)
| Date: | 2017-12-15
| Prepared by: | BOB CASH, CYNTHIA PROVINE
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | CRP18001 | Capitol Elevator Modernization/Upgrade Phase 1 | Modernizaion of all Capitol and Extension Elevators. Project is in the design / RFQ phase. RFQ to be issued in the next month. Delayed due to Special Session | FUND 0001 | 1250000 | 1250000 | 2019 | 0% | 0% | 0 | 0 | 1250000 | NO
2 | CRP18017 | Capitol Elevator Modernization/Upgrade Phase 2 | Modernizaion of all Capitol and Extension Elevators. Project is in the design / RFQ phase. RFQ to be issued in the next month. Delayed due to Special Session | FUND 0001 | 1250000 | 1250000 | 2019 | 0% | 0% | 0 | 0 | 1250000 | NO
3 | CRP18015 | HVAC Automation System Upgrade Capitol Extension | RFP for materials being crafted, expect issue of RFP in the next 3 months - Delayed due ot Special Session | FUND 0001 | 2200000 | 2200000 | 2018-06-01 | 1% | 1% | 9854 | 0 | 2190146 | NO
0
0
0
0
0
0
0
0
0
0
0
|  |  |  | Totals: | 4700000 | 4700000 |  |  |  | 9854 | 0 | 4690146

## DSHS
| Agency: | Department of State Health Services - 537
| Date: | 2017-12-15
| Prepared by: | Charles Rotan
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 53700 | 18-401-TCD | To renovate support buildings at Texas Center for Infectious Disease | Economic Stabilization Fund- ESF (other) | 1400000 | 1400000 | Spring 2019 | 0% | 0% | 0 | 0 | 1400000 | Health and Human Services manages and implements the TCID capital projects. Contract execution expected Summer 2018.
| 53700 | Perchloric Fume Hood Replacement | To replace a specialty chemical fume hood system in the DSHS Laboratory that is used with acids. | General Revenue | 400000 | 400000 | 2019-08-31 | 100% | 0% | 0 | 0 | 400000 | Texas Facilities Commission Contract # 12-047-6032. All funding obligated to TFC before the end of the FY 2016-2017 biennium.
0
0
|  |  | Totals: |  | 1800000 | 1800000 |  |  |  | 0 | 0 | 1800000

## HHSC-State Hopitals
| Agency: | HHSC 529 State Hospitals
| Date: | 2017-12-13
| Prepared by: | HHSC State-Operated Facilities Division - Facilities Support Services
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 2nd Qtr.) |  | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 16-012-KSH | Kerrville State Hospital | HVAC & Chiller Replacement | ESF (other) | 80100 | 1123815 |  | TBD | 75% | 0% | 537978 |  | 585837
1 | 16-018-RSH | Rusk State Hospital | Fire Escape & Wall Replacement | ESF (other) | 1502187 | 1564326 |  | TBD | 75% | 0% |  |  | 1564326
1 | 17-006-WCY | Waco Center for Youth | Security Fence Installation | ESF (other) | 200000 | 371564 |  | TBD | 75% | 0% |  |  | 371564
1 | 18-001-ASH | Austin State Hospital | Anti-Ligature & Hardware | ESF (other) | 2432595.69 | 2432596 |  | TBD | 0% | 0% |  |  | 2432596
1 | 18-002-BSH | Big Spring State Hospital | Roof Repairs & Replacement | ESF (other) | 655961.25 | 655961 |  | TBD | 0% | 0% |  |  | 655961
1 | 18-003-BSH | Big Spring State Hospital | Sanitary Sewer Repair | ESF (other) | 5515938.75 | 5515939 |  | TBD | 0% | 0% |  |  | 5515939
1 | 18-004-BSH | Big Spring State Hospital | Electrical Upgrades | ESF (other) | 3081366.75 | 3081367 |  | TBD | 0% | 0% |  |  | 3081367
1 | 18-005-BSH | Big Spring State Hospital | Anti-Ligature & Exterior Stair Repairs | ESF (other) | 4810165.5 | 4810166 |  | TBD | 0% | 0% |  |  | 4810166
1 | 18-006-EPC | El Paso Psychiatric Center | HVAC Control Replacement | ESF (other) | 572985.23 | 572985.23 |  | TBD | 0% | 0% |  |  | 572985.23
1 | 18-007-KSH | Kerrville State Hospital | Chiller & Boiler Replacements | ESF (other) | 3225984.3 | 3225984.3 |  | TBD | 0% | 0% |  |  | 3225984.3
1 | 18-008-KSH | Kerrville State Hospital | Security Fence | ESF (other) | 1260000 | 1260000 |  | TBD | 0% | 0% |  |  | 1260000
1 | 18-009-KSH | Kerrville State Hospital | Roof Repairs & Replacement | ESF (other) | 3434026.05 | 3434026.05 |  | TBD | 0% | 0% |  |  | 3434026.05
1 | 18-010-VSH | North Texas State Hospital, Vernon | Utility Upgrades | ESF (other) | 3132141.6 | 3132141.6 |  | TBD | 0% | 0% |  |  | 3132141.6
1 | 18-011-VSH | North Texas State Hospital, Vernon | Roofing Replacements | ESF (other) | 2462341.35 | 2462341.35 |  | TBD | 0% | 0% |  |  | 2462341.35
1 | 18-012-VSH | North Texas State Hospital, Vernon | Water Tank Repairs | ESF (other) | 590110.5 | 590110.5 |  | TBD | 0% | 0% | 332953 |  | 257157.5
1 | 18-013-VSH | North Texas State Hospital, Vernon | Anti-Ligature & Kitchen Expansion | ESF (other) | 3456716.55 | 3456716.55 |  | TBD | 0% | 0% |  |  | 3456716.55
1 | 18-014-WFH | North Texas State Hospital, Wichita Falls | Building Renovations | ESF (other) | 5107200 | 5107200 |  | TBD | 0% | 0% |  |  | 5107200
1 | 18-015-WFH | North Texas State Hospital, Wichita Falls | Emergency Generator | ESF (other) | 268800 | 268800 |  | TBD | 0% | 0% |  |  | 268800
1 | 18-016-WFH | North Texas State Hospital, Wichita Falls | Roof Replacements | ESF (other) | 2100000 | 2100000 |  | TBD | 0% | 0% |  |  | 2100000
1 | 18-017-RSC | Rio Grande State Center, Harlingen | Building Renovations | ESF (other) | 2784091.8 | 2784091.8 |  | TBD | 0% | 0% |  |  | 2784091.8
1 | 18-018-RSC | Rio Grande State Center, Harlingen | Sewer Repair | ESF (other) | 400590.75 | 400590.75 |  | TBD | 0% | 0% |  |  | 400590.75
1 | 18-019-RSH | Rusk State Hospital | Anti-ligature & Hardware Upgrade | ESF (other) | 5681688.6 | 5681688.6 |  | TBD | 0% | 0% |  |  | 5681688.6
1 | 18-020-RSH | Rusk State Hospital | Emergency Generators | ESF (other) | 800625 | 800625 |  | TBD | 0% | 0% |  |  | 800625
1 | 18-021-RSH | Rusk State Hospital | Building Renovations | ESF (other) | 3990000 | 3990000 |  | TBD | 0% | 0% |  |  | 3990000
1 | 18-022-SAH | San Antonio State Hospital | Fire Sprinkler, Alarm System & Smoke Partitions | ESF (other) | 2327495.1 | 2327495.1 |  | TBD | 0% | 0% |  |  | 2327495.1
1 | 18-023-TSH | Terrell State Hospital | Anti-Ligature Renovations | ESF (other) | 5640640.43 | 5640640.43 |  |  | 0% | 0% |  |  | 5640640.43
1 | 18-024-TSH | Terrell State Hospital | EMS Upgrades & HVAC Replacements | ESF (other) | 2824185 | 2824185 |  | TBD | 0% | 0% |  |  | 2824185
1 | 18-025-TSH | Terrell State Hospital | Roof Replacements | ESF (other) | 2100000 | 2100000 |  | TBD | 0% | 0% |  |  | 2100000
1 | 18-026-WCY | Waco Center for Youth | Replace Fire Alarm System. | ESF (other) | 712358.33 | 712358.85 |  | TBD | 0% | 0% |  |  | 712358.85
1 | 18-027-WCY | Waco Center for Youth | Anti-Ligature & Emergency Generator | ESF (other) | 581670.33 | 581670.6 |  | TBD | 0% | 0% |  |  | 581670.6
1 | 18-028-SH | Various Hospitals | System Wide CSI Remediation | ESF (other) | 5228854 | 3070785 |  | TBD | 0% | 0% | 99897.59 |  | 2970887.41
1 | 18-029-SH | Various Hospitals | System Wide Anti Ligature Remediation | ESF (other) | 3039179.7975 | 3520883 |  | TBD | 0% | 0% |  |  | 3520883
1 | 18-030-RSH | Rusk State Hospital | Boiler and Canopy Replacement | ESF (other) | 0 | 31605 |  | TBD | 0% | 0% |  |  | 31605
1 | 18-031-ASH | Austin State Hospital | Main Switch Gear Replacement | ESF (other) | 0 | 39444 |  | TBD | 0% | 0% |  |  | 39444
|  |  |  | Totals: | 79999999.6575 | 79632658.71 |  |  |  |  | 970828.59 | 0 | 78661830.12
GO Bond | 16-032-WCY | Waco Center for Youth | Gym Floor and Ceiling Replacements | ESF (other) | 0 | 13592 | TBD | 0% | 0% | 0% | 0 | 0 | 13592 | Projects labeled GO Bonds are older projects that are currently being funded by FY 2018 ESF appropriations, while HHSC seeks approval to transfer DADS and DSHS GO Bonds from previous biennia to HHSC for use on these projects. Once the transfer is approved by the LBB and completed, the ESF appropriations will be redirected for FY 18-19 projects listed above. The transfer is needed due HHSC Rider 122 and the authority of HHSC to spend unexpended DADS and DSHS funds.
GO Bond | 17-019-RSH | Rusk State Hospital | Condensing Rack Replacement | ESF (other) | 0 | 82017 | TBD | 0% | 0% | 0% | 54558 | 0 | 27459
GO Bond | 16-007-BSH | Big Spring State Hospital | Electrical Systems Upgrade and Replacement | ESF (other) | 0 | 863 | TBD | 0% | 0% | 0% | 0 | 0 | 863
GO Bond | 16-011-EPC | El Paso Psychiatric Center | Shower Repair | ESF (other) | 0 | 270869 | TBD | 0% | 0% | 0% | 0 | 0 | 270869
|  |  |  | Totals: | 0 | 367341 |  |  |  |  | 54558 | 0 | 312783
|  |  |  | Grand Totals: | 79999999.6575 | 79999999.71 |  |  |  |  | 1025386.59 | 0 | 78974613.12

## HHSC-SH New Construction
| Agency: | HHSC 529 State-Operated Facilities Division - State Hospitals
| Date: | 2017-12-14
| Prepared by: | HHSC State-Operated Facilities Division - Facilities Support Services
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 18-201-RSH | Rusk State Hospital | New 100-bed maximum secuity unit | ESF (other) | 91500000 | 91500000 | TBD | 0% | 0% | 0 | 0 | 91500000
1 | 18-202-KSH | Kerrville State Hospital | Renovation of buildings to create 70-bed maximum security unit | ESF (other) | 30500000 | 30500000 | TBD | 0% | 0% |  |  | 30500000
1 | 18-203-HCPC | UTHealth Continuum of Care, Houston | Expansion of Harris County Psychiatric Center | ESF (other) | 125000000 | 125000000 | TBD | 0% | 0% |  |  | 125000000
1 | 18-204-ASH | Austin State Hospital | Programming and design for replacement of hospital | ESF (other) | 15500000 | 15500000 | TBD | 0% | 0% |  |  | 15500000
1 | 18-205-SAH | San Antonio State Hospital | Programming and design for replacement of hospital | ESF (other) | 14500000 | 14500000 | TBD | 0% | 0% |  |  | 14500000
1 | 18-206-SAH | San Antonio State Hospital | Renovation of 40-bed unit. | ESF (other) | 11500000 | 11500000 | TBD | 0% | 0% |  |  | 11500000
1 | 19-210-HBH | Waco | Purchase of a medical-surgical hospital and additional evaluation for conversion into a psychiatric hospital | ESF (other) | 2000000 | 2000000 | TBD | 0% | 0% |  |  | 2000000
|  |  |  | Totals: | 290500000 | 290500000 |  |  |  | 0 | 0 | 290500000

## HHSC-SSLC
| Agency: | HHSC 529 State Supported Living Centers
| Date: | 2017-12-15
| Prepared by: | HHSC State-Operated Facilities Division - Facilities Support Services
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget (for 1st Qtr.) | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 18-101-ABL | Abilene SSLC | Exterior Renovations, Roofing & Masterlock | ESF (other) | 4575102 | 4575102 | TBD | 0% | 0% | 0 | 0 | 4575102
1 | 18-102-ABL | Abilene SSLC | Deaerator Tank Replacement (Cancelled) | ESF (other) | 94436 | 0 | TBD | 0% | 0% | 0 | 0 | 0
1 | 18-103-ABL | Abilene SSLC | HVAC System Replacement | ESF (other) | 488927.25 | 488927.25 | TBD | 0% | 0% | 0 | 0 | 488927.25
1 | 18-104-ABL | Abilene SSLC | Walk-in Coolers/Freezer Replacement | ESF (other) | 209699.7 | 209699.7 | TBD | 100% | 0% | 0 | 0 | 209699.7
1 | 18-105-ABL | Abilene SSLC | Steam Heating Replacement | ESF (other) | 1108191 | 1108191 | TBD | 0% | 0% | 0 | 0 | 1108191
1 | 18-106-AUL | Austin SSLC | Water Drainage | ESF (other) | 637767.69 | 637767.69 | TBD | 0% | 0% | 0 | 0 | 637767.69
1 | 18-107-AUL | Austin SSLC | Windows Replacement | ESF (other) | 7370171.42 | 7370171.42 | TBD | 0% | 0% | 0 | 0 | 7370171.42
1 | 18-108-AUL | Austin SSLC | Water Lines Replacement, HVAC Repair & Generator | ESF (other) | 1843079.7 | 1843079.7 | TBD | 0% | 0% | 0 | 0 | 1843079.7
1 | 18-109-AUL | Austin SSLC | Roof Repair and Replacement. | ESF (other) | 439531.93 | 439531.93 | TBD | 0% | 0% | 0 | 0 | 439531.93
1 | 18-110-BLC | Brenham SSLC | Building Renovations & Sanitary Sewer Replacement | ESF (other) | 8004522.35 | 8004522.35 | TBD | 0% | 0% | 0 | 0 | 8004522.35
1 | 18-111-BLC | Brenham SSLC | Water Distribution & Water Tank Repairs | ESF (other) | 410447.87 | 410447.87 | TBD | 0% | 0% | 0 | 0 | 410447.87
1 | 18-112-BLC | Brenham SSLC | Roof Repair and Replacement | ESF (other) | 684809.72 | 684809.72 | TBD | 0% | 0% | 0 | 0 | 684809.72
1 | 18-113-CLC | Corpus Christi SSLC | HVAC, Generator & Masterlock Replacement | ESF (other) | 1938369.3 | 1938369.3 | TBD | 0% | 0% | 0 | 0 | 1938369.3
1 | 18-114-CLC | Corpus Christi SSLC | Walkway Improvements | ESF (other) | 693300.3 | 757992 | TBD | 0% | 0% | 0 | 0 | 757992
1 | 18-115-DLC | Denton SSLC | Utility Upgrades | ESF (other) | 8279550.72 | 8279550 | TBD | 0% | 0% | 0 | 0 | 8279550
1 | 18-116-DLC | Denton SSLC | Roof Replacements | ESF (other) | 2036160 | 2036160 | TBD | 0% | 0% | 0 | 0 | 2036160
1 | 18-117-ELC | El Paso SSLC | Electrical Distribution & Switchgear | ESF (other) | 339897.05 | 339897.05 | TBD | 0% | 0% | 0 | 0 | 339897.05
1 | 18-118-ELC | El Paso SSLC | Building & Patio Renovations | ESF (other) | 2414869.58 | 2414869.58 | TBD | 0% | 0% | 0 | 0 | 2414869.58
1 | 18-119-LBL | Lubbock SSLC | HVAC & Plumbing & Ceiling Replacement | ESF (other) | 8888758.2 | 8888758.2 | TBD | 0% | 0% | 0 | 0 | 8888758.2
1 | 18-120-LFL | Lufkin SSLC | Bathroom Renovations | ESF (other) | 2216025 | 2216025 | TBD | 0% | 0% | 0 | 0 | 2216025
1 | 18-121-LFL | Lufkin SSLC | Fuel Tank Installation | ESF (other) | 614775 | 614775 | TBD | 0% | 0% | 0 | 0 | 614775
1 | 18-122-LFL | Lufkin SSLC | Roof Repairs and Replacements | ESF (other) | 601125 | 601125 | TBD | 0% | 0% | 0 | 0 | 601125
1 | 18-123-MLC | Mexia SSLC | Water System & Emergency Generator | ESF (other) | 3503004.88 | 3503004.88 | TBD | 0% | 0% | 0 | 0 | 3503004.88
1 | 18-124-MLC | Mexia SSLC | Bathroom & Walkway Renovations | ESF (other) | 3916470.9 | 3916470.9 | TBD | 0% | 0% | 0 | 0 | 3916470.9
1 | 18-125-RLC | Richmond SSLC | Window Replacement | ESF (other) | 908302.08 | 908302.08 | TBD | 0% | 0% | 0 | 0 | 908302.08
1 | 18-126-RLC | Richmond SSLC | Sanitary Sewer Replacement | ESF (other) | 2588906.41 | 2588906.41 | TBD | 0% | 0% | 0 | 0 | 2588906.41
1 | 18-127-SGL | San Angelo SSLC | Cooling Tower & Chiller Replacement | ESF (other) | 796524.77 | 796524.77 | TBD | 0% | 0% | 0 | 0 | 796524.77
1 | 18-128-RLC | Richmond SSLC | Roof Repairs and Replacements | ESF (other) | 5176133.55 | 4845469.26 | TBD | 0% | 0% | 0 | 0 | 4845469.26
1 | 18-129-SGL | San Angelo SSLC | Bathroom Renovations | ESF (other) | 2924250 | 2924250 | TBD | 0% | 0% | 0 | 0 | 2924250
1 | 18-130-SGL | San Angelo SSLC | Roof Repairs and Replacements | ESF (other) | 1010609.25 | 1010609.25 | TBD | 0% | 0% | 0 | 0 | 1010609.25
1 | 18-131-SGL | San Angelo SSLC | Emergency Generators & Mechanical System Upgrade | ESF (other) | 1640730 | 1640730 | TBD | 0% | 0% | 0 | 0 | 1640730
1 | 18-132-SAL | San Antonio SSLC | Exterior Renovations & Generator Installation | ESF (other) | 637838.25 | 637838.25 | TBD | 0% | 0% | 0 | 0 | 637838.25
1 | 18-133-SAL | San Antonio SSLC | Sanitary Sewer Replacement | ESF (other) | 1607713 | 1607713.8 | TBD | 0% | 0% | 0 | 0 | 1607713.8
1 | 18-134-SGL | San Angelo SSLC | Chiller Controls | ESF (other) | 0 | 73920 | TBD | 100% | 0% | 0 | 0 | 73920
1 | 18-135-DLC | Denton SSLC | Guardhouse Installation | ESF (other) | 0 | 201810 | TBD | 0% | 0% | 0 | 0 | 201810
|  |  | Totals: |  | 78599999.87 | 78515321.36 |  |  |  | 0 | 0 | 78515321.36
GO Bond | 16-051-LSS | Various SSLCs | Medical Gas System Replacement | ESF (other) | 0 | 119.26 | TBD | 0% | 0% | 0 | 0 | 119.26 | Projects labeled GO Bonds are older projects that are currently being funded by FY 2018 ESF appropriations, while HHSC seeks approval to transfer DADS and DSHS GO Bonds from previous biennia to HHSC for use on these projects. Once the transfer is approved by the LBB and completed, the ESF appropriations will be redirected for FY 18-19 projects listed above. The transfer is needed due HHSC Rider 122 and the authority of HHSC to spend unexpended DADS and DSHS funds.
GO Bond | 16-064-ABS | Abilene SSLC | MEP and Life Saftey Code Renovations | ESF (other) | 0 | 476.58 | TBD | 0% | 0% | 0 | 0 | 476.58
GO Bond | 14-054-LFS | Lufkin SSLC | Life Safety and ADA Renovations Project Increase Request | ESF (other) | 0 | 32309.49 | TBD | 0% | 0% | 0 | 0 | 32309.49
GO Bond | 16-052-LFS | Lufkin SSLC | Emergency Generator and Electrical System Replacement | ESF (other) | 0 | 8460.41 | TBD | 0% | 0% | 0 | 0 | 8460.41
GO Bond | 17-018-LFS | Lufkin SSLC | Grease Trap Relocation | ESF (other) | 0 | 43313 | TBD | 100% | 0% | 41250 | 0 | 2063
|  |  | Totals: |  | 0 | 84678.74 |  |  |  | 41250 | 0 | 43428.74
|  |  | Grand Total: |  | 78599999.87 | 78600000.1 |  |  |  | 41250 | 0 | 78558750.1

## JJD
| Agency: | Texas Juvenile Justice Department - 644
| Date: | 2017-12-19 | [9 empty] | 2017-12-19
| Prepared by: | Steven Vargas - Director of Construction
Project Priority | Agency ID | Project Name & Location | Project Description | Source of Funding (MOF) | Original Estimated Project Budget | Current Estimated Project Budget | Estimated Substantial Completion Date | % Design Completion | % Const. Completion | FY 2018-19 Encumbered | FY 2018-19 Expended | Remaining Project Balance | Supp. Notes
1 | 644 | High Voltage Loop - Giddings | Replace major high voltage conduit and wire around the campus in order to bring to current code and support existing transformers. Reconfigure MDP panels and conductors up to the transformers. | ESF | 1483131 | 1483131 | 2018-11-30 | 0% | 0% | 89596.15 | 0 | 1393534.85
2 | 644 | Gym Roof Repair - Giddings | Hurricane Harvey storm damaged a portion of the roof at the gym. Replace roof with new roofing materials. | ESF | 115345 | 115345 | 2018-11-30 | 15% | 0% | 8000 | 0 | 107345
3 | 644 | Pool HVAC Install - Giddings | Install an HVAC system & room finish-out in the newly infilled pool in order to make this space habitabal for staff. | ESF | 122013 | 122013 | 2018-12-31 | 10% | 0% | 12799 | 0 | 109214
4 | 644 | Replace HVAC Units - Brownwood | Replace the HVAC units & associated appurtenances in the building inside the secured area with similarly size units. | ESF | 1195113 | 1195113 | 2018-12-31 | 15% | 0% | 55333.7 | 0 | 1139779.3
5 | 644 | Side 2 Drop Ceiling Tiles Reinforcement - McLennan | Youth have been accessing above the drop ceiling in the octogonal hallways & damaging infrastructure. This project will install plywood over the tiles in all dorms. | ESF | 402689 | 402689 | 2019-01-31 | 10% | 0% | 0 | 0 | 402689 | Will replace one pod of one dorm tiles with in-house personnel to ascertain effectiveness of materials. Pending outcome, TJJD will fund the rest of the side II dorm tile replacements with contractor.
6 | 644 | Replace HVAC Units - McLennan | Replace the HVAC units & associated appurtenances in the building inside the secured area with similarly size units. | ESF | 2136636 | 2136636 | 2019-01-31 | 10% | 0% | 113456 | 0 | 2023180
7 | 644 | Convert Wooden Doors to Metal Doors - Evins | Doors must be changed from wood to metal in order to fortify walkways & due to fire code. | ESF | 76533 | 76533 | 2019-02-28 | 0% | 0% | 0 | 0 | 76533
8 | 644 | HVAC Upgrades to Dorms, Admin, Gym - Gainesville | Replace the HVAC units in the dorms, administration, and gym buildings with similarly sized units. | ESF | 358851 | 358851 | 2019-02-28 | 10% | 0% | 50979.7 | 0 | 307871.3
9 | 644 | Backup Generators - Gainesville | Finish outfitting the entire campus so that all buildings have backup generators in case of a power outage. | ESF | 157046 | 157046 | 2019-02-28 | 0% | 0% | 0 | 0 | 157046
10 | 644 | Drainage Improvements Front of Campus - Giddings | During heavy rain events, the front area of campus is prone to flash flooding. This project will resize the infrastructure to accommodate these events. | ESF | 409186 | 409186 | 2019-11-30 | 0% | 0% | 0 | 0 | 409186
11 | 644 | Structural Repair at Maintenance Office & Auto Shop - Gainesville | Recent foundational settling has caused the buildings to develop major cracks in the structure. This project will mitigate and repair the building. | ESF | 577436 | 577436 | 2019-11-30 | 0% | 0% | 0 | 0 | 577436
12 | 644 | Vocational Shop Retaining Wall - Gainesville | The loading dock has separated from the building. Repairs are needed with a retaining wall in order to address the issue. | ESF | 185641 | 185641 | 2019-11-30 | 0% | 0% | 0 | 0 | 185641
13 | 644 | Roof Panels @ Storage Structre - Giddings | The old greenhouse is currently being used as storage for the Maintenance Dept. Over time the roof panels have deteriorated and this project will provide for a new roof. | ESF | 62950 | 62950 | 2019-11-30 | 0% | 0% | 0 | 0 | 62950
14 | 644 | Access Road to Lake - Giddings | Current ingress/egress to campus lake overflow is over bare field. This project will provide for an access road for Maintenance to traverse. | ESF | 307732 | 307732 | 2019-12-31 | 0% | 0% | 0 | 0 | 307732
15 | 644 | Replace Fire Alarm System - Giddings | The fire alarm systems across campus have reached the end of their useful lives and parts are hard to get. This project will replace and update. | ESF | 583718 | 583718 | 2019-12-31 | 0% | 0% | 0 | 0 | 583718
16 | 644 | Replace Landline - Giddings | The original landline network is old and unreliable. Numerous outages have occurred and a total replacement would be necessary. | ESF | 98474 | 98474 | 2019-12-31 | 0% | 0% | 0 | 0 | 98474
17 | 644 | Replace Gym Floor - Brownwood | The gym floor is original and full of hazards to youth playing on it. Replacement is warranted to prevent falls and trips. | ESF | 160020 | 160020 | 2019-12-31 | 10% | 0% | 11500 | 0 | 148520
18 | 644 | HVAC Duct Cleaning - McLennan | None of the ductwork on campus has ever been cleaned since the campus opened. Cleaning would improve the air quality in the buildings. | ESF | 148313 | 148313 | 2020-01-31 | 0% | 0% | 0 | 0 | 148313
19 | 644 | Campuswide Drainage Improvments - McLennan | Improved erosion control and storm water management upgrades are needed campuswide. | ESF | 1496373 | 1496373 | 2020-01-31 | 0% | 0% | 0 | 0 | 1496373
20 | 644 | Roof Replacement Dorms 1/2 & Infirmary - Evins | These roofs have leaking problems and are suseptable to storm damage. | ESF | 243329 | 243329 | 2020-01-31 | 0% | 0% | 0 | 0 | 243329
21 | 644 | Sidewalk Improvements Campuswide - Gainesville | Sidewalks have cracked and separated over time throughout campus and repairs are needed to prevent trip hazards. | ESF | 190113 | 190113 | 2020-02-29 | 0% | 0% | 0 | 0 | 190113
22 | 644 | Campuswide Drainage Improvments - Gainesville | Improved erosion control and storm water management upgrades are needed campuswide. | ESF | 1105403 | 1105403 | 2020-02-29 | 0% | 0% | 0 | 0 | 1105403
23 | 644 | Unanticipated Critical Maintenance Life/Safety | This project will address any unanticipated, critical maintenance issues arising over the coming two years. | ESF | 483955 | 483955 | 2020-02-29 | 0% | 0% | 0 | 0 | 483955
|  |  |  | Totals: | 12100000 | 12100000 |  |  |  | 341664.55 | 0 | 11758335.45

## TPWD Supp.
| Agency: | Texas Parks & Wildlife
| Date: | 2017-12-13
| Prepared by: | Infrastructure Division
Project Priority | Supplemental Information
1 - 64 | Grouping of State Parks Deferred Maintenance Projects
2 | Fort Richardson W and WW - Re-prioritizing project to be funded for construction in FY18/19, no longer just a design project.
3 | Seminole Canyon SHS Utilities - Re-prioritizing project to be funded for construction in FY18/19, no longer just a design project.
4 | Goliad WW - Re-prioritizing project to be funded for construction in FY18/19, no longer just a design project.
10 | Garner Water - Re-prioritizing project to be funded for construction in FY18/19, no longer just a design project.
14 | San Jacinto Residence - FY16/17 deferred maintenance project that was placed on hold due to archeology issues. This project has been added back to the FY18/19 list due to some nominal administration costs that had to be paid after 8/31/17.
19 | Monument Hill/Kreische Renovations - Re-prioritizing funding for roof replacement in FY18/19, note the rest of the design for this facility (which is underway now) is for deferred maintenance repairs that include much more than just the roof.
20 | Colorado Bend WTP - Re-prioritizing project to be funded for construction in FY18/19, no longer just a design project.
33 | Inks Lake Boat Ramp - FY16/17 deferred maintenance project that did not obtain a qualified bid last biennium. This project is being added back to FY18/19 list to try and award construction once again. Note this project is eligible for a 75% federal grant match so the construction costs you see on this report is only 25% of the state funds required to do the project. We feel this is a great opportunity for the state, otherwise, the state would have to find more than $400,000 to do this project without the aid of the federal grant.
37 | Stephen F Austin Water Tank - Re-prioritizing project to be funded for construction in FY18/19, no longer just a design project.
61 - 64 | New priority projects resulting from deferred maintenance failures and facility closures.
65 - 75 | Grouping of 2015 and 2016 State Park Weather Related Program
67 -69 | Lake Somerville projects reduced in scope and/or on hold in FY18/19, re-prioritizing funds to Harvey related impacts and higher priority deferred maintenance projects.
70 - 71 | Lake Whitney to be a planning and design effort only in FY18/19, re-prioritizing construction funds to Harvey related impacts and other higher priority deferred maintenance projects.
72 | Mother Neff project on hold due to Harvey impacts and other higher priority deferred maintenance needs.
73 | Ray Roberts budget greatly reduced from original estimate due to further design refinement, scope of work for construction in FY18/19 has not been changed.
76 - 91 | Grouping of HARVEY State Park Program
76 - 91 | New projects resulting from Superstorm Harvey. To date, we are redirecting $9.1M of SGST to new emergency projects that were not originally budgeted for.
92 - 95 | Grouping of Austin HQ Projects
95 | Austin HQ funding has been removed due to unexpected Harvey impacts. This means there is no capital construction funding for Austin HQ in FY18/19.
96 -118 | Grouping of Fund 9 Coastal Fisheries and Wildlife Program
96 | 2015 and 2016 Fund9 funds have been redirected to higher priority Hurricane Harvey needs
108-117 | New projects resulting from Superstorm Harvey. To date, we are redirecting $1.7M of Fund9 to new emergency projects that were not originally budgeted for.
119 - 132 | Grouping of Fund 9 Inland Fisheries Program
120, 123, 125, 126, 132 | New Inland Fishery priority projects for FY18/19

## TDCJ Supp
| Agency: | Texas Department of Criminal Justice - 696
| Date: | 2017-12-15
| Prepared by: | Jerry McGinty, Chief Financial Officer
Project Priority | Supplemental Information
1 | TIMELINE: (original estimated substantial completion date: 9/22/17; revised: 1/1/18).
2 | TIMELINE: (original estimated substantial completion date: 9/22/17; revised: 1/12/18).
3 | TIMELINE: (original estimated substantial completion date: 9/22/17; revised: 1/1/18).
10 | BUDGET: Lowest qualified bidder higher than original estimate.
22 | BUDGET: Increased to include design.
25 | TIMELINE: (original estimated substantial completion date: 3/13/18; revised: 11/2/18).
27 | TIMELINE: (original estimated substantial completion date: 3/15/18; revised: 12/28/18).
29 | BUDGET: Material cost higher than original estimate.